## AL6
Release To Service | RAG Status | CLE Due Review | Lead | Lead Safety | IT&E | OT&E | Safety Statement | SQEP Panel Date | Link to previous CLE | Progress Notes | Draft/in progress awaiting Signature | Date to TAA | Link to signed RTS/CLE
RTS AL6 31 Oct 17 - Date To TAA 10 Oct 17- Date to RTSA 17 Oct 17
MSS (GECO 11) update (Sep 17)
Crewman Seat 3-Point Harness
Wiper Blades/Repellant solution
Troop Seat Lap Straps
Knee pad, Gotec RDL4
Fast Roping Adaptor (reduce Kg limit – needs AF)
Flares
CLE
CLE 033 - VAMP 27, Rear Crew Usage |  | 2017-10-01
TC ???? Noise and vibration

## AL 7
Release To Service | RAG Status | CLE Due Review | Lead | Lead Safety | IT&E | OT&E | Safety Statement | SQEP Panel Date | Link to previous CLE | Progress Notes | Draft/in progress awaiting Signature | Date to TAA | Link to signed RTS/CLE
RTS AL7 30 Apr 18 - Date To TAA 17 Apr 18
Airborne Sniping
Sky Guardian 200D (RWR) – Will be addressed by DAS Obsolescence Project and will include CMWS Gen 3 and ALE74 Power PC.
Abseil bolster bracket – strength testing
Remove legacy AEA (Q3) DF
AeroMed Equipment (Gazelle cleared)
From BTR Burn Down Chart
CLE

## AL 8
Release To Service | RAG Status | CLE Due Review | Lead | Lead Safety | IT&E | OT&E | Safety Statement | SQEP Panel Date | Link to previous CLE | Progress Notes | Draft/in progress awaiting Signature | Date to TAA | Link to signed RTS/CLE
RTS AL8 30 Oct 18 - Date To TAA 10 Oct 18
Seat Stowage Straps
Crash Resistant Tie Down Rings
Hella Anti-Col Light
Load Pole Stowage FF
Cockpit CB Guard
C-CBRN Casualty Protection Equipment
P-STASS
GPMG Perch
CLE