## 1.0 Prelims
GROUNDWORKS AND SERVICE INFRASTRUCTURE BUILDERS WORKS PACKAGE
FLEETWOOD FIRE FIGHTING CENTRE
BLACKPOOL AND THE FYLDE COLLEGE
Ref | Item | Quantity | Rate | Total
1.00 | PRELIMINARIES
Location of Works
1.01 | The site is located at the Fleetwood Fire Fighting Centre, Enterprise Way, Fleetwood, FY7 8RY
Local Authority
1.02 | The Local Authority is Wyre Council, Civic Centre, Breck Road, Poulton-le-Fylde, FY6 7PU
Employer
1.03 | The Employer is Blackpool and The Fylde College, Ashfield Road, Bispham, Blackpool, FY2 0HB
Contract Administrator
1.04 | The term 'Contract Administrator' shall mean Leeming Associates, 8-10 Preston Old Road, Freckleton, Preston PR4 1PD. Tel: 01772 632556 Email: office@leemingassociates.com
Quantity Surveyor
1.05 | The term 'Quantity Surveyor' shall mean Leeming Associates
CDM Principal Designer
1.06 | The term 'CDM Principal Designer' shall mean Leeming Associates.
Drawings
1.07 | The following tender drawings form part of the tender documents:- See Leeming Associates 2642.C drawing register and JRB Environmental Design drawing register 014.104B.
Description of Works
1.08 | The works comprise of the creation of a new vehicle entrance and hardstanding areas and builders works associated with the service infrastructure works for the new extension of the Fire Fighting Centre.
Visit the Site
1.09 | Contractors are advised to visit the site and ascertain for themselves the exact nature of the proposed works and any difficulties inherent therein.
Nature of the Works/Access
1.10 | Contractor vehicular access is through the south entrance via Enterprise Way.
EMPLOYERS REQUIREMENTS
Confinement on Site
1.11 | The Contractor shall confine his employees, suppliers or subcontractors materials, plant equipment and huts within the site boundaries and to the approval of the Contract Administrator.
Maintenance of Works
1.12 | The Contractor shall include for making good all damage and disturbance to the public and private roads and footways, kerbs and the like to the entire satisfaction of the local authority, public or private owners.
Police Regulations
1.13 | The Contractor shall include for complying with all Police Regulations or instructions and the Road Traffic Act in relation to; a) parking; b) keeping roads and footpaths clean, free from mud etc and clear of all obstructions caused by materials and plant; and c) conveyance of plant and materials to and from the site.
Nuisance Generally
1.14 | The Contractor shall prevent smoke, dust, fumes, spillage, pollution of waterways/drains and other harmful activities. No bonfires will be allowed.
1.15 | Comply with any reasonable requests from the public and adjoining owners.
1.16 | Keep noise down to as low a level as can be practically attained. Avoid the use of excessively noisy tools (e.g. percussion tools) or restrict their use to agreed times. Use mufflers and acoustic enclosures when necessary.
1.17 | Ban the use of radios, cassettes etc and comply with BS 5228 - 'Noise Control on Construction Sites'.
1.18 | Prevent any form of shock or vibration being transmitted to other buildings.
Workmanship
1.19 | The Works shall be carried out in a sound and workmanlike manner in accordance with current Codes of Practice and to the satisfaction of the Contract Administrator.
1.20 | The Contractor shall employ upon the works only skilled workmen and the Contract Administrator may require the removal of any person who in his opinion is incompetent or negligent in his duties
Materials
1.21 | All materials shall be the best of their respective kinds, confirming where possible to the current British Standards. They shall be handled, stored and fixed strictly in accordance with the manufacturer's instructions.
1.22 | Materials shall be properly stored and protected on site. Damaged items shall be replaced at the Contractor's expense.
Samples
1.23 | Samples of materials proposed to be used in the Works shall be submitted as and when instructed. Approved samples will be selected therefrom and be retained on site in order that material used in the works may be compared therewith.
1.24 | The Contractor shall include for taking all precautions in safeguarding the Works, materials and plant against damage and theft and shall include for the provision of temporary fencing and lighting as considered necessary.
1.25 | The Contractor shall provide tarpaulins and all necessary coverings and take adequate precautions to keep the works free from damage by frost, wind, rain or snow during the progress of the works and clear away on completion.
1.26 | The Contractor shall allow for protecting all work in this Contract and make good any damage and leave in good condition on completion.
Existing Services
1.27 | The Contractor shall locate and identify all live services and temporarily divert and/or protect as necessary.
Signboard
1.28 | A signboard will not be required.
Building Regulations
1.29 | The Contractor shall notify the Local Council or the appointed Approved Inspector of the commencement of the works and at each relevant stage of the works in order for them to inspect the works. The Contractor shall be responsible for obtaining the Building Regulation Completion Certificate on completion of the works.
Progress Chart and Drawings
1.30 | The Contractor shall submit a standard programme and progress chart to the Contract Administrator for approval within three days of the date of acceptance of his tender and keep up-to-date during the contract works.
Site Meetings
1.31 | The Contractor may use the site facilities for regular site meetings.
Removing Rubbish and Cleaning
1.32 | The Contractor shall clear away all rubbish and debris as it accumulates and shall clean down the building immediately before giving up possession including windows, external brickwork, paving's and the like to the satisfaction of the Contract Administrator.
1.33 | The Contractor shall allow removing all waste and the likes out of the areas of works. The corridors and stair areas must be protected at all times.
Handover
1.34 | Prior to handover the Contractor shall make arrangements and agree dates for inspections in respect of making good any defects.
1.35 | All information in respect of maintenance and operation manuals and the complete Health and Safety File shall be available prior to handover.
1.36 | The Contractor shall provide notification of the proposed handover date at least seven days prior to the proposed handover. Upon receipt of such notification the Contract Administrator and the Contractor will inspect the Works and produce a 'snagging list' of defective works. All such snagging works must be completed prior to handover of the works.
CONTRACTOR'S GENERAL COST ITEMS
Management and Staff
1.37 | The Contractor shall include for all on and off site management costs and charges including the designation of a site foreman for the full period of the contract who should be able to be contacted by telephone at all times during the working period.
Temporary Accommodation
1.38 | The Contractor shall provide any temporary accommodation he may require for the execution of the Works, including paying any fees, charges, rates etc in connection therewith. The Contractor shall allow for the removal and any necessary reinstatement on completion.
Light and Power
1.39 | The Contractor shall obtain and pay for all power and lighting supplies for his own and his subcontractors use.
Temporary Hoarding / Fencing
1.40 | The Contractor shall provide temporary fencing, lighting and the like as may be necessary to protect the area of works for satisfying the requirements of any Local or other Authority and the requirements of the CDM Regulations regarding security of the site works.
Water
1.41 | The Contractor shall obtain and pay for all water supplied for his own and his subcontractors use.
General Scaffolding
1.42 | The Contractor shall provide all necessary scaffolding, staging and the like to undertake the works including all necessary adaptions and removal on completion.
Plant
1.43 | The Contractor shall provide all necessary plant, tools, vehicles and the like to undertake the works.
Safety, Health and Welfare
1.44 | The Contractor shall comply with all current statutes, Regulations and Agreements relating to the Building Industry in respect of Safety, Health and Welfare.
1.45 | The Contractor shall comply with all the Construction (Design and Management) Regulations 2007 and shall take on the duties of Principal Contractor and update and add to the Health and Safety File during the works.
1.46 | The Contractor's attention is brought to the Pre-Construction Information which is included within the documentation.
Protection
1.47 | The Contractor shall provide all necessary protection to all external and internal floor and wall finishes for the duration of the contract.
Skips
1.48 | The Contractor shall provide all necessary skips required to complete the scope of works. All skips must be securely ringed with heras fencing at all times. Any skips located close to the any buildings (within 6 meters) MUST be lockable and the Contractor to ensure these skips are locked when not in use.
CONTRACT PARTICULARS
1.49 | The form of contract will be the JCT Agreement for Minor Building Works 2011 Edition - MW 2011
1.50 | The following insertions or amendments will be made to the Contract:-
Recital (5th) CDM Regulations - the project is not notifiable
Article 7 - Applies
Recital (7th) and Schedule 3 - Supplementary provisions do not apply
Clause 1.1 CDM Planning Period - 2 weeks ending on Date for Commencement of Work
Clause 2.2 - Commencement - date to be agreed Completion - date to be agreed
Clause 2.8 - Damages for non-completion £100.00/week or part thereof
Clause 4, 11 & Schedule 2 - To be deleted
Clause 5.3.2 - Insurance cover to be not less than £5,000,000
Clause 5.4B - Insurance of the works and existing structures by Employer in joint names
Clause 7.2 - Adjudicator to be The Royal Institution of Chartered Surveyors
0
To Collection/Tender Summary: £ |  |  |  | 0

## 2.0 Schedule of Works
GROUNDWORKS AND SERVICE INFRASTRUCTURE BUILDERS WORKS PACKAGE
FLEETWOOD FIRE FIGHTING CENTRE
BLACKPOOL AND THE FYLDE COLLEGE
Ref | Item | Quantity |  | Rate | Total
2.00 | SCHEDULE OF WORKS
The Contractor must allow to site check all dimensions. Areas and dimensions in this schedule are indicative.
1.0 | Generally
1.1 | Works shown on Leeming Associates drawing 2642(C).201C and TRP Consulting drawing 6748/E500/S2. | Item
1.2 | Removal of existing and provision of new fencing and gates to be undertaken by others outside this contract. Contractor to include for liaising with Fencing Contractor to coordinate works to maintain site security and Programme of Works. | Item
1.3 | Contractor to refer to the Ground Investigation Report and Engineers Initial Review as part of the Tender Documents. | Item
2.0 | Groundworks
2.1 | Break out and remove existing road kerbs, including concrete bed and haunch | 18 | m
2.2 | Break out and remove existing concrete hardstanding area (assume 200mm thick reinforced concrete slab) and remove from site | 82 | m2
2.3 | Excavate oversite to reduce levels (average 450mm deep) and remove from site | 37 | m3
2.4 | Ditto but average 600mm deep. | 278 | m3
2.5 | Level and compact surfaces of excavation and lay Terram 1000 geotextile sheet | 525 | m2
2.6 | Provide and lay 300mm thick capping layer of stone (6F2) | 158 | m3
2.7 | Provide and lay 150mm thick MOT Type 1 sub base | 525 | m2
2.8 | Level and compact surfaces of stone sub base and lay 1200mm gauge polythene membrane | 525 | m2
2.9 | Provide and lay 200mm thick Grade C40 air entrained concrete slab reinforced with 1 layer A252 mesh to top (50mm cover) | 525 | m2
2.10 | Allow for brushed finish to concrete surface | 525 | m2
2.11 | Allow for all necessary formwork as required to edges of new slab | Item
2.12 | Form joint details as indicated on Engineers drawings including all necessary saw cuts, drilling, joint fillers, steel bars, resin anchors, sleeves and the like:-
| a) Typical sawn joint detail | 73 | m
| b) Formed tied joint | 83 | m
| c) Joint to existing slab | 52 | m
2.13 | Disc cut perimeter and break out area of assumed 150mm thick reinforced concrete slab to existing entrance. Provide and lay new reinforced concrete slab, DPM, sub base, capping layer and Terram (as elsewhere). | 13 | m2
2.14 | Provide and lay 150mm wide PCC dished channel (Charcon or similar approved) including all necessary cutting, excavation, concrete bed haunching | 18 | m
2.15 | Extra for splay cutting / angle details | 3 | No
2.16 | Provide and install road gully, including excavation, concrete bed and surround, and cast iron heavy duty grating | 3 | No
2.17 | Excavate for and lay new 150mm drain connections from new gullies to existing drainage including stone bed and surround and backfilling (3No branches) PROVISIONAL | 24 | m
2.18 | Allow Provisional Sum for excavating to locate existing drains in 3No locations and connecting new branch pipework from road gullies | PROV SUM |  |  | 1500
2.19 | Works to former entrance PROVISIONAL :-
| a) Disc cut and carefully break out approx. 1.00m wide strip of existing concrete hardstanding | 12 | m
| b) Provide and lay 125 x 254mm pre-cast concrete road kerbs including concrete bed and haunching | 12 | m
| c) Include for additional stone fill and laying concrete slab 1.00m wide to form raise threshold | 12 | m
3.0 | M&E Builders Works
3.1 | Saw cut and remove 700mm wide section of existing 150mm thick concrete slab. Form new infill slab detail as Engineers drawing, comprising 600mm long, H10 diameter bars at 600mm centres, drilled and resin anchored into existing slab, 30 x 5mm saw joint and Parseal sealant and reinforced concrete slab (as elsewhere). | 140 | m
3.2 | Undertake M & E Builders works as indicated on JRB environmental Design Ltd drawing number 014.104.B generally to comprise:-
a) Installation of underground service ducts including excavation, removal, earthwork support, 100mm sand bed and 350mm cover, selected earth / stone controlled backfill, ductwork (including bends, fittings and the like) and marker tapes (NB works to concrete slab measured above):-
| i. 300mm wide trench including 1No 150mm duct | 2 | m
| ii. 400mm wide trench including 2No 150mm ducts | 10 | m
| iii. 600mm wide trench including 3No 150mm ducts | 32 | m
| iv. 700mm wide trench including 4No 150mm ducts | 136 | m
| v. 900mm wide trench including 5No 150mm ducts | 28 | m
| vi. 1200mm wide trench including 9No 150mm ducts | 33 | m
| vii. 1400mm wide trench including 12No 150mm ducts | 28 | m
| b) 1200 x 1200mm masonry draw pits including bases and covers | 9 | No
| c) Access chambers with lighting pole mounts | 7 | No
| d) Installation of 6m high CCTV column including concrete base | 1 | Item
| e) Incoming 63mm MDPE water service | 1 | Item
| f) Foundation / slab for switch room | PROV SUM |  |  | 3000
| g) Provision and installation of a new 3000 x 2000 x 2000mm high GRP lockable switch room complete with backboard to rear wall | 1 | No
| h) Testing and commissioning | 1 | Item
| i) Provision of 'as fitted' drawings and manuals | 1 | Item
| j) Line of sight pole / mast for link to Bispham Campus | PROV SUM |  |  | 3000
| k) Other items not listed above but shown on drawings. | Item
3.3 | Allow Provisional Sum for 100mm duct to link Elliott Modular Building with the new Support Accommodation (for fibre / copper link) | PROV SUM |  |  | 3000
4.0 | Contaminated Material
4.1 | Allow extra over cost for removal of contaminated material from site to licensed tip. (PROVISIONAL) | 526 | m3
To Collection/Tender Summary: £

## 3.0 Daywork
GROUNDWORKS AND SERVICE INFRASTRUCTURE BUILDERS WORKS PACKAGE
FLEETWOOD FIRE FIGHTING CENTRE
BLACKPOOL AND THE FYLDE COLLEGE
Ref | Item | Quantity |  | Rate | Total
3.00 | DAYWORK SCHEDULE
Where at all possible additional works will be valued on a measured fair valuation or pro rata basis. Only where these alternatives are not possible will work be valued on a daywork basis.
The Contractor is to insert here his all in daywork rate per hour for the following trades:-
| A. Labourer | - | £ |  | per hour
| B. Electrical | - | £ |  | per hour
| C. Plumber | - | £ |  | per hour
| D. Joiner | - | £ |  | per hour
The Contractor is to insert here his % additions to the net cost of:-
| A. Materials | - | Cost + |  | %
| B. Plant | - | Cost + |  | %
0
To Collection/Tender Summary: £

## 4.0 Collection
GROUNDWORKS AND SERVICE INFRASTRUCTURE BUILDERS WORKS PACKAGE
FLEETWOOD FIRE FIGHTING CENTRE
BLACKPOOL AND THE FYLDE COLLEGE
|  | Total | Current Valuation
4.00 | COLLECTION / TENDER SUMMARY |  |  | 0
4.01 | Preliminaries |  |  | 0
0
4.02 | Schedule of Works
4.03 | Dayworks
4.03 | Contingency - Allow Provisional Sum for unforeseen works | 10000
#VALUE!
0
0
0
0
Total (excluding VAT) to Form of Tender:- |  | 10000 |  | #VALUE!