## Cover Sheet
Risk Management Plan
Contract Ref: |  | THIS IS THE MOST IMPORTANT TOOL IN DELIVERING YOUR CONTRACT. THIS HELPS YOU DOCUMENT & MANAGE COMMERCIAL & SUSTAINABILITY RISKS, ISSUES AND ALSO POTENTIAL OPPORTUNTIES THROUGHOUT THE LIFE OF YOUR CONTRACT.
Contract Name:
Type of contract:
Don’t get hung up looking for risks that aren’t there – low cost contracts may only have a few small risks.
EA Category:
http://intranet.ea.gov/tools/applications/9124.aspx
Estimated Contract Value:
THIS FORMS PART OF YOUR PLAN, YOU SHOULD USE YOUR PROFESSIONAL JUDGEMENT AND PREVIOUS EXPERIENCE TO IDENTIFY COMMERCIAL RISKS. IF YOUR REQUIREMENT FALLS INTO A MED/HIGH RISK CATEGORY YOU SHOULD CONTACT YOUR LOCAL PROCUREMENT DEPARTMENT WHO WILL ADVISE YOU ON THE BEST WAY FORWARD.
Overall Risk:
Date completed:
Please ensure your risk management plan is embedded in your procurement plan
IT IS RECOMMENDED THAT YOU USE THIS TEMPLATE, HOWEVER AS A MINIMUM YOU SHOULD DOCUMENT THE SPECIFIC RISKS. NOTE THAT IF YOUR REQUIREMENT IS A CALL OFF FROM A FRAMEWORK, MANY RISKS SHOULD HAVE BEEN ADDRESSED AT FRAMEWORK LEVEL AND YOU SHOULD REFER TO THE FRAMEWORK SPECIFIC GUIDANCE.
Below is a table of when stages of the procurement process occur to guide you with the Risk Management Plan
For sustainability risks please consult the flow chart for further information on what you need to consider
Before | Planning
Planning and Specification
Risk Assessment
During | Dealing with Suppliers
Request for Quotation and costs
Evaluating and clarification
After | Awarding the Contract
Managing the Contract
Extensions and Variation
Ending the Contract and Disposal
Note on B5: The reference code is assigned to the project
Note on B16: High/Medium/Low
Note on C16: If the overall risk is high, please contact procurement and attach this document

## RISKS
PROCUREMENT PLAN - RISK MANAGEMENT PLAN
Some examples have been provided below: This is for guidance purposes and your risks must be specific to your requirement: use the suggestions as a prompt for you own contract and remove those that do not apply
Commerical/Sustainability/Information risk, issue or opportunity (taking a life cycle approach) | Proposed action (please detail) | Probability of Occurrence 1-5 | Severity of Impact 1-5 | Total Risk/Opportunity Score (1-25) | Stage of procurement process (please specify) | Responsible person and role | Proposed date for completion | Completed action (i.e. what was actually done) (please detail) | Date completed
Tight project timescales to turn the project around. Suppliers are not given enough time to respond to request for quotations so cannot submit quality bids. Not enough time is allocated for evaluating the bids. | Improve forecasting, planning and consultation with users. Engage with suppliers early where possible to flag up the requirement. Produce timetable to ensure that there is enough time to respond to the request for quotation. Arrange a date with your evaluators well in advance for the evaluation and allow time for follow up clarifications. | 3 | 4 | 12 | Procurement plan to detail attainable timescales. RFQ to allow enough time for suppliers to respond | Project Managers | w/c 14th November | e.g. Suppliers given 3 weeks to respond .
Scope is not well defined and therefore starts to slip once the project is up and running. This can result in increased cost and project timescales. | Clearly define scope in the request for quotation. Provide previous project report for background and context. Monitor performance of the supplier and agree outputs and timescales. Any changes to scope need to be flagged up early and agreed in writing between the Project Manager and the supplier before work can proceed. Check FSOD approvals wont need to change if scope and cost changes. | 2 | 4 | 8 | Scope must be agreed before going out with the RFQ and RFQ must clearly define scope. Contract management is key to managing this risk | Project Managers | ongoing | scope has been drafted and reviewed by several technical leads.
Intellectual property/Data ownership is not clearly identified and recorded - lose ownership or access rights and cannot use the outputs in the way the project intended. Could be tied to that supplier for future work. | Consider information owned by partners and incumbent suppliers, associated approvals / licences required for access / use, and costs associated with these. Also consider the use of our logo by suppliers and follow the corporate affairs procedure for this. Consult Legal and IP team when appropriate | 1 | 1 | 1 |  | Project Managers | 31.10.22
Weak specification means the supplier does not fully understand the deliverables/outcomes and any timescales or constraints. This can result in a sub standard bid, lacking in information and priced incorrectly. | Clear outcomes and constraints. Follow the draft specification. Attach any information they require to understand the requirement and respond to it. Consider having a telecon with suppliers to explain the requirements if very complicated. | 2 | 4 | 8 |  | Project Managers | 14.10.22
Evaluation process is not robust enough. This could result in an incorrect award and potential complaints of bad practice from suppliers that did not get awarded the work. | Ensure that request for quotation explains how the bids will be evaluated. Only evaluate on the information provided as part of the bid and not prior knowledge. Ask all suppliers for further information if necessary. Award to the provider that is ranked no 1 for combined cost and quality. Maintain, audit and review evaluation procedures | 2 | 3 | 6 |  | Project Managers | 04.11.22 | Have several inviduals invovled in the evaluation assessment. Apply fair weightings.
The consultants who secure the project have limited capacity | Ensure that we maintain regular contact with the consultants with progress updates. This will includean update on risks/issues which can cover capacity issues and help prioritise the work. Ensure that the RfQ includes consultants explaining how they will maintain continuity of service. | 2 | 2 | 4 | Contract Management | Contract Manager | 31.10.22
Unable to get consultants who wish to do the work | We will make an effort to contact relevant consultants to inform them of the project aswell as the project going on contracts finder. | 3 | 3 | 9 |  |  | 04.11.22
Bids from consultants come in over budget | Clearly mark budget restrictions in procurement plan. Scope of work unlikely to generate bids over budget anyway, but we will talk to consultants to identify opportunities to reduce costs where we can. | 1 | 2 | 2 |  |  | 04.11.22
0
0
Date of completion:
© Environment Agency 2012 Version Control - V1 October 2012
Note on C6: What are you going to do to mitgate the risk?
Note on D6: How likely is it that this would happen? One being least likely, 5 being very likely 1 2 3 4 5
Note on E6: How much would this impact the contract? 1 being very low impact, 5 being very high 1 2 3 4 5
Note on F6: The probability multiplied by the impact to show a final score. High scores showing high risk will highlight red Medium scores will highlight yellow Low risk will highlight green
Note on G6: When in the preparation or lifetime of the contract will this risk be mitigated?
Note on H6: It is preferable to name the responsible person. Also list their role.

## Sheet1
EA Govt led Pan Government | 1
National Contract | 2
National Framework - Call Off | 3
National One Off | 4
Pan Government National Call Off | 5
Pan Government Regional Call Off
Regional Contract
Regional Framework Call Off
Regional One Off
Single Tender / Direct Award