## 4 Year Project Plan
Mandarin Excellence Programme Project Plan
Calendar Year | 2021 | [16 empty] | 2022 | [64 empty] | 2023 | [51 empty] | 2024 | [51 empty] | 2025
Academic Year | 2021/22 | [51 empty] | 2022/23 | [51 empty] | 2023/24 | [51 empty] | 2024/25
Quarter | Q2 |  |  |  | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
Year Commencing April 2021 | time axis 2021-09-06 to 2025-08-25
Programme Implementation & Exit
Liaising with participating schools | bar: 2021-09-06 to 2021-09-27
Project planning | bar: 2021-09-06 to 2021-10-18
Budget planning | bar: 2021-09-06 to 2021-09-13
Meetings with DFE | bar: 2021-09-06
Contract preparation | bar: 2021-09-13
Grant preparation | bar: 2021-09-20 to 2021-09-27
Implementing Exit Plan | bar: 2025-06-30 to 2025-08-25
Programme Delivery (Learning in Schools)
School Liaison (Supporting Hub & Spoke Model)
Supporting for introducing and/or maintain Mandarin in schools
Compiling case studies of best practice | bar: 2021-10-04 to 2021-10-25; 2022-10-03 to 2022-10-24; 2023-10-02 to 2023-10-23; 2024-09-30 to 2024-10-21
Quality assurance of resources hosted for MEP | bar: 2022-01-03 to 2022-01-24; 2022-08-01 to 2022-08-22; 2023-01-02 to 2023-01-23; 2023-07-31 to 2023-08-21; 2024-01-01 to 2024-01-22; 2024-07-29 to 2024-08-19; 2024-12-30 to 2025-01-20; 2025-07-28 to 2025-08-18
School recruitment | bar: 2022-02-28 to 2022-05-09; 2023-02-27 to 2023-05-08; 2024-02-26 to 2024-05-06; 2025-02-24 to 2025-05-05
Stimulating demand for Mandarin | bar: 2022-01-03 to 2022-02-21; 2023-01-02 to 2023-02-20; 2024-01-01 to 2024-02-19; 2024-12-30 to 2025-02-17
University Engagement & Awareness Raising | bar: 2022-01-03 to 2022-03-28; 2023-01-02 to 2023-03-27; 2024-01-01 to 2024-03-25; 2024-12-30 to 2025-03-24
Headteacher Meeting | bar: 2021-10-04; 2022-02-14; 2022-06-27; 2022-10-03; 2023-02-13; 2023-06-26; 2023-10-02; 2024-02-12; 2024-06-24; 2024-09-30; 2025-02-10; 2025-06-23
Teacher Meetings (support & equiping current MEP schools) | bar: 2021-09-27; 2022-02-07; 2022-06-20; 2022-09-26; 2023-02-06; 2023-06-19; 2023-09-25; 2024-02-05; 2024-06-17; 2024-09-23; 2025-02-03; 2025-06-16
Schools visits (supporting & equiping current MEP schools)
Y8 UK Intensive learning course organisation | bar: 2022-02-21 to 2022-04-04; 2023-02-20 to 2023-04-03; 2024-02-19 to 2024-04-01; 2025-02-17 to 2025-03-31
Y8 UK Intensive Learning content planning | bar: 2022-03-28 to 2022-05-09; 2023-03-27 to 2023-05-08; 2024-03-25 to 2024-05-06; 2025-03-24 to 2025-05-05
Y8 UK Intensive Learning content writing | bar: 2022-05-02 to 2022-06-13; 2023-05-01 to 2023-06-12; 2024-04-29 to 2024-06-10; 2025-04-28 to 2025-06-09
Y8 UK Intensive Learning content delivery | bar: 2022-07-04 to 2022-07-11; 2023-07-03 to 2023-07-10; 2024-07-01 to 2024-07-08; 2025-06-30 to 2025-07-07
Developing methods for teaching characters | bar: 2022-04-04 to 2022-06-27; 2023-04-03 to 2023-06-26; 2024-04-01 to 2024-06-24; 2025-03-31 to 2025-06-23
Hurdle Test Setting | bar: 2022-02-14 to 2022-03-14; 2023-02-13 to 2023-03-13; 2024-02-12 to 2024-03-11; 2025-02-10 to 2025-03-10
Hurdle Test Training | bar: 2022-03-28 to 2022-04-04; 2023-03-27 to 2023-04-03; 2024-03-25 to 2024-04-01; 2025-03-24 to 2025-03-31
Hurdle Test Moderation | bar: 2022-05-30 to 2022-07-04; 2023-05-29 to 2023-07-03; 2024-05-27 to 2024-07-01; 2025-05-26 to 2025-06-30
Hurdle Test Monitoring and Mark Sheet Collation | bar: 2022-05-30 to 2022-07-11; 2023-05-29 to 2023-07-10; 2024-05-27 to 2024-07-08; 2025-05-26 to 2025-07-07
Training for hub school teachers (preparation) | bar: 2021-09-20; 2022-01-31; 2022-06-13; 2022-09-19; 2023-01-30; 2023-06-12; 2023-09-18; 2024-01-29; 2024-06-10; 2024-09-16; 2025-01-27; 2025-06-09
Training for hub school teachers (3 national event(s)) | bar: 2021-09-27; 2022-02-07; 2022-06-20; 2022-09-26; 2023-02-06; 2023-06-19; 2023-09-25; 2024-02-05; 2024-06-17; 2024-09-23; 2025-02-03; 2025-06-16
Marketing & Communcications
Communications strategy update and annual planning | bar: 2021-09-06 to 2021-09-13; 2022-07-11 to 2022-08-08; 2022-08-22 to 2022-09-12; 2023-07-24 to 2023-08-07; 2023-08-21 to 2023-09-11; 2024-07-22 to 2024-08-05; 2024-08-19 to 2024-09-09
Sign off and approval from DfE | bar: 2021-09-27; 2022-08-15; 2023-08-14; 2024-08-12
Schools comms pack creation and disseminaton | bar: 2021-10-04 to 2021-10-18; 2022-09-19 to 2022-10-03; 2023-09-18 to 2023-10-02; 2024-09-16 to 2024-09-30
Support to stimulate demand and school recruitment | bar: 2022-01-03 to 2022-05-09; 2023-01-02 to 2023-05-08; 2024-01-01 to 2024-05-06; 2024-12-30 to 2025-05-05
Schools communication activity - ambassadors events, HT events | bar: 2021-10-04 to 2021-12-13; 2022-01-03 to 2022-03-28; 2022-04-18 to 2022-07-25; 2022-10-03 to 2022-12-12; 2023-01-02 to 2023-03-27; 2023-04-17 to 2023-07-24; 2023-10-02 to 2023-12-11; 2024-01-01 to 2024-03-25; 2024-04-15 to 2024-07-22; 2024-09-30 to 2024-12-09; 2024-12-30 to 2025-03-24; 2025-04-14 to 2025-07-21
External communications activity | bar: 2021-10-04 to 2021-10-11; 2021-11-01 to 2021-11-22; 2022-02-14 to 2022-03-07; 2022-06-27 to 2022-07-18; 2022-10-03 to 2022-10-10; 2022-10-31 to 2022-11-21; 2023-02-13 to 2023-03-06; 2023-06-26 to 2023-07-17; 2023-10-02 to 2023-10-09; 2023-10-30 to 2023-11-20; 2024-02-12 to 2024-03-04; 2024-06-24 to 2024-07-15; 2024-09-30 to 2024-10-07; 2024-10-28 to 2024-11-18; 2025-02-10 to 2025-03-03; 2025-06-23 to 2025-07-14
Annual programme evaluation result reporting | bar: 2022-09-12 to 2022-09-19; 2023-09-11 to 2023-09-18; 2024-09-09 to 2024-09-16; 2025-08-18 to 2025-08-25
Reporting to programme board | bar: 2021-12-06; 2022-02-28; 2022-05-23; 2022-08-15; 2022-12-05; 2023-02-27; 2023-05-22; 2023-08-14; 2023-12-04; 2024-02-26; 2024-05-20; 2024-08-12; 2024-12-02; 2025-02-24; 2025-05-19; 2025-08-11
End year comms evaluation and reporting | bar: 2022-07-25 to 2022-08-15; 2023-07-24 to 2023-08-14; 2024-07-22 to 2024-08-12; 2025-07-21 to 2025-08-11
Annual China stakeholder thank you letter from Minister | bar: 2022-07-25; 2023-07-24; 2024-07-22; 2025-07-21
Programme Delivery (Intensive Learning China)
China stakeholder management/identification of host universities | bar: 2021-09-06 to 2021-12-27; 2022-08-08 to 2022-12-26; 2023-08-07 to 2023-12-25; 2024-08-05 to 2024-12-23; 2025-08-04 to 2025-08-25
Risk assessment of local host venues | bar: 2022-01-03 to 2022-01-31; 2023-01-02 to 2023-01-30; 2024-01-01 to 2024-01-29; 2024-12-30 to 2025-01-27
Intensive Learning Teacher Training (Planning) | bar: 2022-02-28 to 2022-03-28; 2023-02-27 to 2023-03-27; 2024-02-26 to 2024-03-25; 2025-02-24 to 2025-03-24
Intensive Learning Teacher Training (Delivery) | bar: 2022-04-18 to 2022-04-25; 2023-04-17 to 2023-04-24; 2024-04-15 to 2024-04-22; 2025-04-14 to 2025-04-21
Programme Development | bar: 2022-02-07 to 2022-05-30; 2023-02-06 to 2023-05-29; 2024-02-05 to 2024-05-27; 2025-02-03 to 2025-05-26
Flight Bookings & Management | bar: 2021-12-06 to 2022-06-27; 2022-12-05 to 2023-06-26; 2023-12-04 to 2024-06-24; 2024-12-02 to 2025-06-23
Student data capture and data sharing | bar: 2022-03-07 to 2022-03-28; 2023-03-06 to 2023-03-27; 2024-03-04 to 2024-03-25; 2025-03-03 to 2025-03-24
Pre Departure School Coordination (Contract & Information sharing) | bar: 2022-05-02 to 2022-05-30; 2023-05-01 to 2023-05-29; 2024-04-29 to 2024-05-27; 2025-04-28 to 2025-05-26
Pre Departure Meeting Preparation | bar: 2022-05-30; 2023-05-29; 2024-05-27; 2025-05-26
Intensive Study Support in China | bar: 2022-07-04 to 2022-07-11; 2023-07-03 to 2023-07-10; 2024-07-01 to 2024-07-08; 2025-06-30 to 2025-07-07
China in country evaluation | bar: 2022-07-18 to 2022-08-01; 2023-07-17 to 2023-07-31; 2024-07-15 to 2024-07-29; 2025-07-14 to 2025-07-28
Annual reporting to programme board | bar: 2022-08-15; 2023-08-14; 2024-08-12; 2025-08-11
Programme Delivery (Intensive Learning Non-China)
China stakeholder management/identification of host universities | bar: 2021-09-06 to 2021-12-27; 2022-08-08 to 2022-12-26; 2023-08-07 to 2023-12-25; 2024-08-05 to 2024-12-23; 2025-08-04 to 2025-08-25
Risk assessment of digital platforms and delivery | bar: 2022-01-03 to 2022-01-31; 2023-01-02 to 2023-01-30; 2024-01-01 to 2024-01-29; 2024-12-30 to 2025-01-27
Programme Development - curriculum and content | bar: 2022-02-07 to 2022-06-27; 2023-02-06 to 2023-06-26; 2024-02-05 to 2024-06-24; 2025-02-03 to 2025-06-23
Intensive Learning Teacher Training (Planning) | bar: 2022-02-28 to 2022-03-28; 2023-02-27 to 2023-03-27; 2024-02-26 to 2024-03-25; 2025-02-24 to 2025-03-24
Intensive Learning Teacher Training (Delivery) | bar: 2022-04-18 to 2022-04-25; 2023-04-17 to 2023-04-24; 2024-04-15 to 2024-04-22; 2025-04-14 to 2025-04-21
China and UK School/University Briefings and Coordination | bar: 2022-05-02 to 2022-05-30; 2023-05-01 to 2023-05-29; 2024-04-29 to 2024-05-27; 2025-04-28 to 2025-05-26
Intensive Study Support in China | bar: 2022-07-04 to 2022-07-11; 2023-07-03 to 2023-07-10; 2024-07-01 to 2024-07-08; 2025-06-30 to 2025-07-07
China in country evaluation | bar: 2022-07-18 to 2022-08-01; 2023-07-17 to 2023-07-31; 2024-07-15 to 2024-07-29; 2025-07-14 to 2025-07-28
Annual reporting to programme board | bar: 2022-08-15; 2023-08-14; 2024-08-12; 2025-08-11
Developing Teaching Capacity
Implementing national programme to support Mandarin teachers | bar: 2021-10-11 to 2021-11-01; 2022-10-10 to 2022-10-31; 2023-10-09 to 2023-10-30; 2024-10-07 to 2024-10-28
MEP Teacher Training | bar: 2021-09-27; 2022-02-07; 2022-06-20; 2022-09-26; 2023-02-06; 2023-06-19; 2023-09-25; 2024-02-05; 2024-06-17; 2024-09-23; 2025-02-03; 2025-06-16
Supporting to find PGCE placements | bar: 2022-03-07 to 2022-07-04; 2023-03-06 to 2023-07-03; 2024-03-04 to 2024-07-01; 2025-03-03 to 2025-06-30
Sharing best practice for NQTs | bar: 2021-10-04 to 2021-10-25; 2022-10-03 to 2022-10-24; 2023-10-02 to 2023-10-23; 2024-09-30 to 2024-10-21
Annual Conference (MEP Strand) | bar: 2022-06-06 to 2022-06-13; 2023-06-05 to 2023-06-12; 2024-06-03 to 2024-06-10; 2025-06-02 to 2025-06-09
Removing Barriers
Resource development | bar: 2022-07-18 to 2022-08-29; 2023-07-17 to 2023-08-28; 2024-07-15 to 2024-08-26
Resource management & admin | bar: 2022-08-15 to 2022-08-29; 2023-08-14 to 2023-08-28; 2024-08-12 to 2024-08-26
Support for teachers using resources | bar: 2021-10-04 to 2021-10-25; 2022-10-03 to 2022-10-24; 2023-10-02 to 2023-10-23; 2024-09-30 to 2024-10-21
Online community management | bar: 2021-10-04 to 2021-10-25; 2022-01-17 to 2022-01-24; 2022-10-03 to 2022-10-24; 2023-01-16 to 2023-01-23; 2023-10-02 to 2023-10-23; 2024-01-15 to 2024-01-22; 2024-09-30 to 2024-10-21; 2025-01-13 to 2025-01-20
Project management
Project Planning | bar: 2021-10-04; 2022-01-03; 2022-04-04; 2022-07-04; 2022-08-29; 2022-10-03; 2023-01-02; 2023-04-03; 2023-07-03; 2023-08-28; 2023-10-02; 2024-01-01; 2024-04-01; 2024-07-01; 2024-08-26; 2024-09-30; 2024-12-30; 2025-03-31; 2025-06-30
Risk & Issue Management | bar: 2021-10-11; 2021-11-08; 2021-12-06; 2022-01-03; 2022-01-31; 2022-02-28; 2022-03-28; 2022-04-25; 2022-05-23; 2022-06-20; 2022-07-18; 2022-08-15; 2022-10-10; 2022-11-07; 2022-12-05; 2023-01-02; 2023-01-30; 2023-02-27; 2023-03-27; 2023-04-24; 2023-05-22; 2023-06-19; 2023-07-17; 2023-08-14; 2023-10-09; 2023-11-06; 2023-12-04; 2024-01-01; 2024-01-29; 2024-02-26; 2024-03-25; 2024-04-22; 2024-05-20; 2024-06-17; 2024-07-15; 2024-08-12; 2024-10-07; 2024-11-04; 2024-12-02; 2024-12-30; 2025-01-27; 2025-02-24; 2025-03-24; 2025-04-21; 2025-05-19; 2025-06-16; 2025-07-14; 2025-08-11
Reporting (Monthly Quarterly, Annually / KPI reports) | bar: 2021-10-11; 2021-11-08; 2021-12-06; 2022-01-03; 2022-01-31; 2022-02-28; 2022-03-28; 2022-04-25; 2022-05-23; 2022-06-20; 2022-07-18; 2022-08-15; 2022-10-10; 2022-11-07; 2022-12-05; 2023-01-02; 2023-01-30; 2023-02-27; 2023-03-27; 2023-04-24; 2023-05-22; 2023-06-19; 2023-07-17; 2023-08-14; 2023-10-09; 2023-11-06; 2023-12-04; 2024-01-01; 2024-01-29; 2024-02-26; 2024-03-25; 2024-04-22; 2024-05-20; 2024-06-17; 2024-07-15; 2024-08-12; 2024-10-07; 2024-11-04; 2024-12-02; 2024-12-30; 2025-01-27; 2025-02-24; 2025-03-24; 2025-04-21; 2025-05-19; 2025-06-16; 2025-07-14; 2025-08-11
UPN Data Management & Reporting | bar: 2021-12-06 to 2021-12-27; 2022-06-13 to 2022-08-08; 2022-12-05 to 2022-12-26; 2023-06-12 to 2023-08-07; 2023-12-04 to 2023-12-25; 2024-06-10 to 2024-08-05; 2024-12-02 to 2024-12-23; 2025-06-09 to 2025-08-04
Grant management
Managing the allocation of funds (£20k funds) | bar: 2021-10-04 to 2021-10-25; 2022-10-03 to 2022-10-24; 2023-10-02 to 2023-10-23; 2024-09-30 to 2024-10-21
Managing the allocation of additonal funds (intensive study) | bar: 2022-06-06 to 2022-06-27; 2023-06-05 to 2023-06-26; 2024-06-03 to 2024-06-24; 2025-06-02 to 2025-06-23
Managing the allocation of additonal funds (continued participation) | bar: 2022-01-03 to 2022-01-24; 2022-03-07 to 2022-03-28; 2023-01-02 to 2023-01-23; 2023-03-06 to 2023-03-27; 2024-01-01 to 2024-01-22; 2024-03-04 to 2024-03-25; 2024-12-30 to 2025-01-20; 2025-03-03 to 2025-03-24
Supply Chain management
Supply Chain Contract Management | bar: 2021-09-06 to 2021-09-27; 2022-09-05 to 2022-09-26; 2023-09-04 to 2023-09-25; 2024-09-02 to 2024-09-23
Independent Evaluation
Coordinating agreement for methodology | bar: 2021-10-04 to 2021-10-11; 2022-10-03 to 2022-10-10; 2023-10-02 to 2023-10-09; 2024-09-30 to 2024-10-07
Quality Assurance (proof reading final reports) | bar: 2022-07-25 to 2022-08-08; 2023-07-24 to 2023-08-07; 2024-07-22 to 2024-08-05; 2025-07-21 to 2025-08-04
Sub-contractor Management | bar: 2021-09-06; 2021-10-04 to 2021-10-11; 2022-03-28; 2022-09-05; 2022-10-03 to 2022-10-10; 2023-03-27; 2023-09-04; 2023-10-02 to 2023-10-09; 2024-03-25; 2024-09-02; 2024-09-30 to 2024-10-07; 2025-03-24
Costs & Value for Money
Financial Reporting | bar: 2021-10-11; 2021-11-08; 2021-12-06; 2022-01-03; 2022-01-31; 2022-02-28; 2022-03-28; 2022-04-25; 2022-05-23; 2022-06-20; 2022-07-18; 2022-08-15; 2022-10-10; 2022-11-07; 2022-12-05; 2023-01-02; 2023-01-30; 2023-02-27; 2023-03-27; 2023-04-24; 2023-05-22; 2023-06-19; 2023-07-17; 2023-08-14; 2023-10-09; 2023-11-06; 2023-12-04; 2024-01-01; 2024-01-29; 2024-02-26; 2024-03-25; 2024-04-22; 2024-05-20; 2024-06-17; 2024-07-15; 2024-08-12; 2024-10-07; 2024-11-04; 2024-12-02; 2024-12-30; 2025-01-27; 2025-02-24; 2025-03-24; 2025-04-21; 2025-05-19; 2025-06-16; 2025-07-14; 2025-08-25
Programme Governance
Expert Panel Involvement | bar: 2021-11-15; 2022-08-08; 2022-11-14; 2023-08-07; 2023-11-13; 2024-08-05; 2024-11-11; 2025-08-04
Monthly Contract Meetings | bar: 2021-10-11; 2021-11-08; 2022-01-03; 2022-01-31; 2022-03-28; 2022-04-25; 2022-06-20; 2022-07-18; 2022-10-10; 2022-11-07; 2023-01-02; 2023-01-30; 2023-03-27; 2023-04-24; 2023-06-19; 2023-07-17; 2023-10-09; 2023-11-06; 2024-01-01; 2024-01-29; 2024-03-25; 2024-04-22; 2024-06-17; 2024-07-15; 2024-10-07; 2024-11-04; 2024-12-30; 2025-01-27; 2025-03-24; 2025-04-21; 2025-06-16; 2025-07-14; 2025-08-25
Quarterly delivery meetings | bar: 2021-12-06; 2022-02-28; 2022-05-23; 2022-08-15; 2022-12-05; 2023-02-27; 2023-05-22; 2023-08-14; 2023-12-04; 2024-02-26; 2024-05-20; 2024-08-12; 2024-12-02; 2025-02-24; 2025-05-19; 2025-08-25