## Notes
Note: All off-island works are scoped as concept works, with a low level of detail and estimated material volumes. Actual volumes of sand, rock and other materials to be used will depend on final designs. Full design and material estimates are available for most of the St Mary's works on Porthloo, Porth Mellon and Porth Hellick. The material quantities and design styles are noted here. Potentially only a limited number of the measures will be installed, because there is a constrained budget for the project. The budget is estimated to be sufficient for about three-quarters of all the works identified here. Alternative methods are acceptable and encouraged, particularly where the alternative reduces costs but achieves the same functional outcome. Aesthetic considerations may prevent alternative methods being adopted for the tendering process. The construction contracts will be 'build' only. Full designs and specifications will be undertaken by Council of the Isles of Scilly once the outcome of this Open Engagement process is known. Council of the Isles of Scilly will also obtain all licences and Planning Permission required. Actual works tendered and the form of the tender(s) (number, packaging, etc.) will depend in part on the responses received under this Open Engagement process.

## St Mary's - Porthloo
Specification
1 | Porthloo beach
1A | Rock armour revetment
Length | 110 | m | Overall aim
Crest height | 6.7 | m AOD (adjacent dune height) | Protect, strengthen & tie into existing embankment with 2 m3 per linear metre rock armour with geotextile & 1-4 mm granite gravel, mixed with full reuse of existing materials & retrofit 1 m3 per metre rock armour ‘toe’ to recently formalised defence at southern end
Toe depth (max) | 0.53 | m AOD
Crest width (min) | 4.5 | m
Toe width | 3 | m
Overall width | 17.13 | m
Slope | 1:2 to 1:1.5 in centre; 1:3 at each end
Rock weight | 1 to 3 tonnes
Rock composition | Cornish granite
Geotextile | GeoFabric HPS12 or equivalent underlying
1B | Retaining wall
Length | 30 | m
Style | Pre-cast concrete L-unit
Base | 500 | mm mass concrete
Crest height | 6.75 | m AOD
Facing | greenheart timber

## St Mary's - Porth Mellon
Specification
2 | Porth Mellon beach
2A | Rock armour revetment
Length | 40 | m
Crest height | 6.19 | m AOD | Overall aim
Toe depth (max) | 0.5 | m AOD | Reinforce bank at the south western end by creating a rock armour revetment (to 6.2 m ODN & foundation of 0.5 m) where the road is currently at risk of being undermined. Complement with measures to assist dune recovery, beach access and repoint & repair 25m section of stone sea wall at NE end of beach.
Crest width (min) | 3 | m
Toe width | 3 | m
Overall width | 14.95 | m
Slope | 1:2 to 1:1.5 in centre; 1:3 at each end
Rock weight | 1 to 3 tonnes
Rock composition | Cornish granite
Crest tie-in | To vegetated bank along Telegraph Road
Margin tie-in | Site-won rock positioned at SE end to tie revetment into existing rock cliff
Other notes | Small-scale vegetation clearance required to facilitate construction
Geotextile | GeoFabric HPS12 or equivalent underlying

## St Mary's - Porth Hellick
Specification
3 | Porth Hellick
3A | Raising dune section |  | comments
Length | 75 | m | approximately from diagram
Crest height | 5 | m AOD |  | Overall aim
Toe depth (max) | 0.5 | m AOD |  | Recharge, regenerate, strengthen, heighten & improved the mobility of 150 m of most damaged dune and its shingle back. This by adding crushed granite into dune with biomatting and varied planting plus transposing. Complement with improved, controlled access measures to protect the heightened dune, stop inward inundation and impacts and enable the dune to build its natural strength and 'walk backwards' with flexible resilience.
Crest width (min) | 1 | m
Min overall width | 8.24 | m
Max overall width | 11.59 | m
Volume required | 276 | m3 | may be an underestimate if more sand has eroded since 2017
Slope | 1:6
Grain size | 1 to 5 | mm
Sand composition | Cornish or Devon granite, matching colour and rock type at Porth Hellick
Margin tie-in | Site-won rock positioned at SE end to tie revetment into existing rock cliff
Other notes | Small-scale vegetation clearance required to facilitate construction
Geotextile | Overlaid on renourished sand – coir matting (Salix coconet 800 or similar), pegged at 3x 500 mm long Salix T-pegs per 1 m2
Overseeding | 50 mm of topsoil laid over matting, seeded with grass mix
Vegetated | Fascicularia bicolor on new section of dune and in 5 other low points
Length of vegetation | 40 | m
Width of vegetation | 4 | m
3B | New vehicle access ramp
Length | 22 | m
Crest height | 5 | m
Crest width | 1 | m
Width | 3.7 | m | (note, 3.6 m width would be exactly 9 widths of capping Dycel 150 blocks – probably preferable)
Slope | 1:6 increasing to 1:3 at toe (buried below beach level)
Concrete: | 2x cast reinforced concrete edge beams 22 m x 500 mm x 500 mm [NB, one 500 x 500 mm beam is about 15 tonnes]; plus 2x 500x500 mm anchor beams RC20/25 with stainless bar in for anchor loops
Materials | 2 layers of Strataweb 200 polyethylene cellular grid (3 layers at ramp crest) [NB 200 refers to depth in mm]
Infill material | 1 to 5 | mm crushed Cornish granite
Overlay material | Ekotex 30 geotextile layer (or similar)
Overlay blocks | Dycel 150 concrete blocks threaded together with stainless steel cable
Overlay block infill | Soil, seeded with grass mix

## Off-islands
Option | Island | Site | Protecting | Aim | Issue | Joint | Activity
1B | Bryher | Great Popplestone | Freshwater supply | Prevent saline intrusion by preventing overtopping waves | N end of bay sand dunes 2 m too low | 5B | Recharge & restore 90 m of dune inclusive of repositioning 50 m3 of in-situ existing 'rock armour'.
1B | Bryher | Great Popplestone | Freshwater supply | Prevent saline intrusion by preventing overtopping waves | N end of bay sand dunes 2 m too low | 5B | Create earth bund around freshwater well location
2B | Bryher | Great Porth north of Great Carn | Main road | Prevent overtopping waves damaging/blocking road | Dune crest 1 m below rest of beach frontage | 3B 4B | Beach recharge & formalised slipway
2B | Bryher | Great Porth north of Great Carn | Main road | Prevent overtopping waves damaging/blocking road | Dune crest 1 m below rest of beach frontage | 3B 4B | 80 m linear of dune restoration and negotiated changes to access and vehicular routes to enable the dune to recover and recess.
3B | Bryher | Great Porth south of Great Carn | Main road | Prevent overtopping waves damaging/blocking road | Low section of dune | 4B 2B | 20 m of damaged dune restoration with recharge
4B | Bryher | Green Bay | The Green | Prevent overtopping waves | Low section of dune | 3B 2B | 100 m of 'dune' restoration and nourishment with 0.5 m3 per linear m to raise dune height by 250 mm
5B | Bryher | Stinking Porth | Freshwater supply | Prevent saline intrusion by preventing overtopping waves | Low section of dune | 1B | Reduce overtop & breach risk at 20 m southern section with 20 m3 of localised dune restoration
6B | Bryher | Kitchen Porth | Vulnerable properties | Prevent inundation | Low section of bank |  | Raise front edge and across 75 mm of informal pathway by 500 mm to provide protective embankment between dune area and properties
7B | Bryher | Quay beach | Quay access | Prevent erosion of road and quay | Eroded corners | 4B | Rock revetment protection works on Quay Beach
1M | St Martin's | Campsite frontage | Freshwater supply | Prevent overtopping | Low section of dune |  | Fence off the 25 % most damaged, weakest sections front and rear over 100 m to give them the chance to recover
2M | St Martin's | Higher Town frontage | Freshwater supply | Prevent overtopping | Low section of dune |  | Sensitively restore 200 m of dune with in-situ materials, supplemented with planting and transposing to protect the most damaged & compromised 25% of dunes, reroute the important coastal path
1A | St Agnes | Porth Killier | Seawall stability | Prevent erosion and reduce overtopping risk | Seawall erosion |  | Reduce scouring of toe/foundation of 10 m section of retaining sea wall by protecting it with 1.5 m3 of rock armour per linear metre
2A | St Agnes | Porth Killier | Main road | Prevent erosion and reduce overtopping risk | Ram erosion |  | Halt ram erosion & overtopping risk at a 5 m section to immediate SE of sea wall by installing localised 2.5 m high rock armour revetment
3A | St Agnes | Porth Killier | Groundwater recharge area | Reduce overtopping risk | Low section of rock armour | 4A | Add 20 m3 of rock armour to existing to raise height and address overtopping risk on NW side of Porth Killier
4A | St Agnes | Porth Coose Periglis | Groundwater recharge area | Reduce overtopping risk | Low sections of dune | 3A | Restore 500 m of dunes, locally recharging 125 m of it with imported granite ‘crush’. Naturally & flexibly strengthen, raise and protect low sections with biomatting & by planting and establishing with varied palette of costal dune flora. Achieve a consistent profile 750 mm above the current low points.
5A | St Agnes | Periglis | Slipway | Repair slipway | Slipway in poor repair |  | Repair Periglis Slipway (6 m3 concrete) & enhance rock armour at quay & tie-in with beach entrance
6A | St Agnes | Whole island | Stock stores | Maintenance | Breaches caused by erosion |  | Breach repair & tie-in stock & provisioning supply/resource & store/maintain for up to 25 years, 75 tonnes of rock armour and 100 tonnes of crushed gravel in 1 m3 big bags, Reserve local availability of plant & capacity to responsively plug & repair dune breaches (x2) & localised rock armour measures to responsively address erosion, including along neighbouring Troytown frontage, utilising supplied and maintained stocks).