| Contract Management Guidance – Template #10 CHANGE CONTROL FORM- Extensions – v. 5 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contract Name: | Provision of Audit Services for Defence Academy Academic Provider |  | Contract Ref. No. | CCS Reference: CCCC16A39 MoD Contract Reference: CCCC16A39 (Variation Ref: CCCC16A39-01) |
|  |  | CLIENT CHANGE NOTICE (CCN) |  |  |
| CCN 1 REDACTED TEXT CCN Reference: Initiated by: Date CCN Raised by relevant party: Source of change: 26th June 2017 Ministry of Defence : |  |  |  |  |
| STAGE 1 – CLIENT |  |  |  |  |
| Summary of proposals/ requirements : | This is a retrospective variation to the Contract between the Crown Commercial Service, acting as Managing Agent on behalf of the Ministry of Defence and Grant Thornton UK LLP. The Terms and Conditions of the Contract apply but with the following amendments: - Variation to the Contract End Date - The original Contract period was 9th November 2016 until 7th February 2017. The intention of the Authority is to vary the Contract end date by four months, to 6th June 2017. - Uplift in Value of an additional £48,000.00 (Exc. VAT), increasing total Contract value from £97,200.00 (Exc. VAT) to £145,200.00 (Exc. VAT). Please refer to Annex 1 for revised deliverables. |  |  |  |
| Proposed payment: | In line with the existing terms and conditions of Contract. |  |  |  |
| Required delivery date, with rationale: | In line with the existing terms and conditions of Contract and the new proposed end date of 6th June 2017. |  |  |  |
| 4th August 2017 REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (Customer organisation representative): Signature Print Name & Position Date 2nd August 2017 REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (CCS representative) Signature Print Name & Position Date |  |  |  |  |
| STAGE 2 – SUPPLIER |  |  |  |  |
| Comments/ caveats on requested change: |  |  |  |  |
| ABORTIVE COSTS : |  |  |  |  |
| Anticipated period from CCN being authorised by client to start of related provision |  |  |  |  |
| Grant Thornton UK LLP confirms that the costs identified above are the agreed figures that will be payable on CCN implementation |  |  |  |  |
| REDACTED TEXT Signed (Supplier Representative): REDACTED TEXT Print Name & Position: 10/08/2017 Date: |  |  |  |  |
| STAGE 3 – CLARIFICATIONS |  |  |  |  |
| Clarification/ queries to to supplier regarding Date: their proposals: Supplier response Date: |  |  |  |  |
| STAGE 4 - CUSTOMER CCN SIGN-OFF TO PROCEED TO IMPLEMENTATION |  |  |  |  |
| Variation Withdrawn |  |  |  |  |
| By signing below, unless CCN is withdrawn, the Ministry of Defence agrees to pay Grant Thornton UK LLP the costs detailed in Stage 1, by deadlines agreed with the supplier, or as defined in the contract. |  |  |  |  |
| REDACTED TEXT 16th August 2017 Signed (Customer Representative): REDACTED TEXT Date Print Name & Position Signature Change authorised to proceed to implementation (CCS): REDACTED TEXT 11th August 2017 REDACTED TEXT Date Print Name & Position Signature |  |  |  |  |
| STAGE 5 - CCN COMPLETION SIGN-OFF |  |  |  |  |
| I confirm that the provision required under the CCN commenced in accordance with the customer requirements and supplier proposals in this CCN. |  |  |  |  |
| Date provision required under the CCN commenced: Date Signed by Customer: Signed (Customer representative): Print Name & Position |  |  |  |  |