| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of a Customer Satisfaction Measurement and Reporting Solution (The Contract) |  |  |
| Contract Reference: | CCCC22A16 | Contract Change Number: | 1 |
| Date CCN issued: | 16/01/2025 | Date Change Effective from: | 16/01/2025 |
| Between: Crown Commercial Service (The Customer) and KPMG LLP (The Supplier) - The Contract is varied as follows: - The existing contract between Crown Commercial Service and KPMG LLP will be varied with a time extension, cost increase and change of scope. - The Current contract is due to end 29th August 2025. The new Contract expiry date shall be 31st January 2026. - The change of scope includes: - The need for the services to be used by all areas of CCS in the delivery of CCS’s business plan objectives, and - The support of a delivery partner to design and embed these services. - The key deliverables / milestones are detailed as below REDACTED TEXT under FOIA Section 43 Commercial Interest - The Contract is varied with an uplift of £1,245,083.00. The New contract value is now £3,735,250 excluding VAT. (£4,482,300.00 including VAT as per PPN 10/21) The remaining value to be invoiced shall be invoiced in 4 equal instalments upon completion of each milestone. Completion will be agreed between CCS contract owner (REDACTED TEXT under FOIA Section 40 Personal Information) and KPMG in writing (via email). - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. Change authorised to proceed by: (Customer’s representative): 16/01/2025 Signature Print Name and Job Title Date |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. 16/01/2025 Authorised for and on behalf of the Supplier: Signature Print Name and Job Title Date |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. 16/01/2025 Authorised for and on behalf of the Customer: Signature Print Name and Job Title Date |  |  |  |