Warrant for the Provision of Technical Support Services to

The Office for Nuclear Regulation (ONR)

| Contractor | AMEC FOSTER WHEELER |
| --- | --- |
| Project Title | Provision of Support on Operating Chemistry Choices for the GDA of UK ABWR |
| ONR Project No. | ONR244 |

1	WHEREAS

1.1	This Warrant will be subject to the terms of this Agreement and the 	overarching Terms and Conditions of Framework Agreement, referenced 	1.11.4.2266 for the provision of Technical Support Services to the Office for 	Nuclear Regulation.

1.2	The Contractor was successful as a result of a competitive tendering 	exercise under tender reference ONR/T2623 to deliver the above services 	under Lot 9 of the Framework Agreement.

2	PROGRAMME OF WORK

2.1	The Programme of Work to be carried out will comprise the complete schedule of services, as described in the Contractor’s proposal detailed at Annex 1.

3	DURATION

3.1	The Services shall be deemed to have commenced on 09 February 2015 and shall be completed by 31 July 2015.

4	CONTRACT MANAGEMENT

4.1	The ONR Contract Manager who will be responsible for liaison and certifying completion of the provision and overall management of the Services is :

Name

Contact Tel No.

e-mail

4.2	The Technical Support Contract Manager who will be responsible for liaison and certifying completion of the provision and overall management of the Services is :

Name

Contact Tel No.

e-mail

5	REPORTING REQUIREMENTS

5.1	The reporting requirements applicable relating to the delivery of the Services are described in Annex 2.

5.2	Draft and Final Reports should be submitted by e-mail to onr.research@onr.gsi.gov.uk

6	MAXIMUM COST

  - 6.1	The total cost for providing the service will be £18,294.25 exclusive of VAT. Any additional costs will be agreed in advance with the ONR Contract Manager and be subject to clause 8 Variation to Warrant.

7	INVOICING

7.1	Invoices shall be submitted to ONR in accordance with the following Invoice 	Schedule:

Date of Invoice                     	Amount to be invoiced

| 10 March 2015 | £6,000.00 |
| --- | --- |
| 10 May 2015 | £6,000.00 |
| 10 July 2015 | £6,294.25 |

7.2	Any variation to the Invoice Schedule shall be agreed with the ONR Project 	Manager and a revised Invoice Schedule provided.

7.3	An original invoice should be raised and submitted to Shared Services at the following address:

SSCL Accounts Payable Team

Room 6124

Tomlinson House

Norcross

Blackpool

FY5 3TA

Failure to include the Purchase Order Number will delay payment.

7.4	Payment will be made subject to Clause C2.2 of Schedule B, Terms & Conditions of the Framework Agreement.

7.5	A copy invoice, accompanied by any appropriate Progress Reports, in the format detailed at Annex 2 should be submitted by e-mail to : onr.research@onr.gsi.gov.uk

Failure to provide such a report may result in a delay to the payment, or rejection of 	the invoice.

8	VARIATION TO WARRANT

8.1	Except where expressly stated in this Warrant, no change, amendment or modification shall be effective unless in writing and signed by the duly authorised representatives of both parties.

8.2	Any agreed changes to the Warrant or Annex 1 Programme of Work will be in the form of a Warrant Amendment, which will be raised and issued by the HSE Commercial Services, on behalf of the Office for Nuclear Regulation (ONR).

SIGNATORIES

In Witness Whereof this WARRANT TO THE FRAMEWORK AGREEMENT has been agreed :

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |

Duly authorised to sign on behalf of AMEC FOSTER WHEELER

305 Bridgewater Place, Birchwood Park, Warrington, WA3 6XF

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |

Duly authorised to sign on behalf of the OFFICE FOR NUCLEAR REGULATION

Building 4, Redgrave Court, Merton Road, Bootle, Merseyside L20 7HS

Annex 1

PROGRAMME OF WORK

The Contractor shall undertake the Programme of Work titled Provision of Support on Operating Chemistry Choices for GDA of UK ABWR, dated 19 November 2014 and referenced Lot9/T2623?19.11.2014, a copy of which is embedded within this Annex 1.

Annex 2

PROJECT PROGRESS REPORT

Within the Project Progress Report, Contractors should seek to provide HSE with an assurance about the status of the project in terms of progress towards delivering the required work to the agreed quality, within agreed timescales and cost.

Where you cannot provide this assurance, you should clearly detail the corrective action you are taking to address any shortcomings.

Progress Reports should be submitted in the format detailed overleaf.  You must complete all boxes. Where appropriate, you may provide additional information (Gantt charts, etc.).

Please note that invoices submitted without a properly completed Progress Report will be rejected.

TECHNICAL SUPPORT FRAMEWORK

PROJECT PROGRESS REPORT

ONR Project No.		XXX			Contractor			XXX

Progress Report No. 	XXX			Report Date:			XXX

Project Title:		XXX

TSC Project Manager:		XXX

1 	PROGRESS REPORT

List the Deliverables, Key Events, Achieved in this Period

List any Problem Areas & Your Remedial Actions

List the Planned Activities for the next Reporting Period

Insert any Notes / Comments

List and Supporting Attachments

2	COSTS (exc VAT)

Agreed Monthly Cost Profile

Invoiced Costs Against Agreed Cost Profile (Include this month’s invoiced cost)

Cumulative Cost to Date (include this month’s invoiced cost)

Invoiced Cost to Date as a Percentage of Permissible Maximum Expenditure

3	EFFORT

Percentage of Work Completed to Date

4	SIGNATORY

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |