## Sheet1
Document Reference: SGMF held within Ponsharden Cemetery Draft GDR. J20-077-R-1000-01 May 2021
Item | Page/Section | Para. | Comments(10/02/2021) | Comment Category (see below). | Consultants Comments | CSL Comments | Open/Closed (date)
1 | Section H1 | 3) | Site is adjacent to A39, not B road as indicated. | B |  |  | Open (14/05/2021)
2 | Section H1 | 5) | Suggest that this is a cutting, not embankment | B |  |  | Open (14/05/2021)
3 | Section H2 | 2) | as item 2 above | B |  |  | Open (14/05/2021)
4 | Section H3 | 4) | We note that the design incorporates some stainless steel elements and that durability assessment are likely to be satisfactory in this regard. Any future amendments to materials assumed in the design may require corrosion assessment, which would be reliant upon ground chemistry. This information is not avaialble in the GIR submitted. | A |  |  | Open (14/05/2021)
5 | Section H3 | 5) | Please confirm if the possibility of voiding behind the slope has been considered, and how it will be accommodated to ensure sufficient design capability. | B |  |  | Open (14/05/2021)
6 | Section H4 | 1) | Sections provided in Platipus Conceptual Design indicate slope angles greater than 60 deg. | B |  |  | Open (14/05/2021)
7 | Section H4 | 3) | Please confirm construction materials for all anchors. | B |  |  | Open (14/05/2021)
8 | Section H4 | 6) | Please confirm the anticipated geotechnical inspection regime post construction. | B |  |  | Open (14/05/2021)
9 | Section H4 | - | Please confirm design life to be adopted within the design | B |  |  | Open (14/05/2021)
10 | Section H4 | - | Please confirm is any reprofiling of the slope will be required, and also how the design will accommodate existing trees. | B |  |  | Open (14/05/2021)
11 | Section H5 | 2) | Please confirm if the National Annex to current version of BS EN 1997-1 will be employed. Please confirm the Design Standard/Code of Practice to be adopted by the design within the SGMF, particular whether the approach is soil nail or ground anchor design. Please confirm to which Standard the partial factors cited in Table 2.0 refers to. | B |  |  | Open (14/05/2021)
12 | Section H5 | 3) | Please confirm the design approach to determine satisfactory SLS limits. | C |  |  | Open (14/05/2021)
13 | Section H5 | 6) | The variable actions quoted are not indicated on the slip circle analyses presented later in the document? Please confirm that this will be addressed in the design. | B |  |  | Open (14/05/2021)
14 | Section H5 | 7) | Please review Ru value, in light of findings of the GIR and elements of fines within the soils. Please review non-use of variable actions. Please include all slip circles with an ODF of <1.0. | B |  |  | Open (14/05/2021)
15 | Section H5 | 8) | See item 4 above | B |  |  | Open (14/05/2021)
16 | Section H5 | - | Please confirm how inter-face plate stability is to be assessed in the design. 4.7.2 of BS 8006-2:2001+A12017 provides advice of appropriate approaches (ie Soft, Flexible and Hard Facings) for various proposed design slope angles (see also Figure 13). | C |  |  | Open (14/05/2021)
17 | Section H5 | - | Please confirm that internal and external stability checks are to be performed as part of the detailed design, in accordance with the relevant CoP’s. Please could you provide outputs of preliminary design slip circle analyses within the SGMF addressing Items 11, 13 and 14 above. | C |  |  | Open (14/05/2021)
18 | Section H6 | - | Please confirm proposed Geotechnical Category for the Scheme | B |  |  | Open (14/05/2021)
19 | - | - | Please provide evidence that the proposed works do not lie within or impact historically or ecologically sensitive areas (for example SSSI, conservation areas, or other designations). If necessary, please comment on the necessary design responses to these considerations | B |  |  | Open (14/05/2021)
20 | Section H7 | - | Please provide signed copy, with name and designations | C |  |  | Open (14/05/2021)
|  | A | Typographical error. Not critical.
|  | B | Submittal is acceptable as noted, provided that the comment is clarified and taken on board as the design proceeds and any subsequent revisions or documents are modified as appropriate.
|  | C | Submittal is not accepted and must be revised for acceptance (i.e. the issue must be addressed in a revised document for consideration by Cornwall Council before design can proceed).