Contents

1	INTRODUCTION	2

2	AIMS OF THE SPECIFICATION	4

3	ACHIEVING THE AIMS: FUNCTIONS OF THE LEAD PROVIDER	5

4	ACHIEVING THE AIMS: SERVICE DELIVERY	7

5	ACHIEVING THE AIMS: EVOLUTION OF THE SERVICE	10

5.1	PHASE 2 SERVICES (INCLUDED IN THE MCP FROM OCTOBER 2017)	11

5.2	PHASE 3 SERVICES (INCLUDED IN THE MCP AFTER APRIL 2018)	11

6	PATIENT COVERAGE	13

7	CONTRACT	13

8	BUDGET CAP	14

9	GOVERNANCE	16

10	QUALITY ASSURANCE	16

11	OTHER INFORMATION	16

12	KEY PERFORMANCE INDICATORS (KPIS)	16

12.1	QUALITY INNOVATION PRODUCTIVITY PREVENTION (QIPP)	17

# Multispecialty community Provider (MCP)

# service Specification

# Introduction

The development of a Multispecialty Community Provider model (MCP), as referenced in the NHS Five Year Forward View, is the key mechanism by which Wandsworth Clinical Commissioning Group (WCCG) will realise its ambitions for transforming Primary Care and Out of Hospital Care across Wandsworth Borough, in line with the following principles:

- There should be a single integrated model of out-of-hospital care.

- The model should promote collaboration, sharing of resources and multi-disciplinary team working, with integrated IT systems to support communication.

- Patients should have a single care plan, centrally updated and accessible to all relevant professionals.

- Patients are able to see the right healthcare professional at the right time according to their needs and know how and where to access care locally when required.

- The model should seek to empower patients and health care professionals alike.

- There should be a culture of shared learning and best practice so that all patients across the Borough can benefit from innovation.

Specifically, the MCP is the contractual vehicle which will enable WCCG to deliver on the 17 specifications set out in the London Strategic Commissioning Framework for Primary Care.

The MCP sees groups of GP practices working together to deliver a wider range of services, coordinating input from Community Services, hospital specialists and others, and eventually shifting the majority of ambulatory care and outpatient consultations to out-of-hospital settings’ (The King’s Fund, 2015).

Figures 1 and 2 illustrate the long term vision for the MCP in Wandsworth. The hub sites depicted in Figure 1 will initially consist of virtual networks which serve to enable joined up working across existing services. However, the CCGs estates strategy identifies four potential sites which could be developed to physically support delivery of the MCP in future, pending further scoping and access to national funding streams.

A Lead Provider will be commissioned to deliver the MCP specification for a seven year period starting in April 2017 (with an option to extend for up to a further three years).

The MCP specification is expected to evolve over time, as learning from the initial service model is captured and evaluated. As such, services will be included within the MCP through a phased approach (see Table 1). Potential providers should note that at this point the CCG is commissioning a Lead Provider to deliver the services listed under Phase 1 in the table. This model will form the infrastructure around which other out of hospital services in Wandsworth can be aligned over the term of the contract.

Once appointed, the CCG will support the Lead Provider to undertake further competitive procurement exercises (in line with the CCGs obligations under the Procurement, Patient Choice and Competition (No.2) Regulations 2013 and Public Contracts Regulations 2015) for the services listed under Phases 2 and 3 in Table 1.

During the term of the contract (and any extension thereto), it is anticipated that the range of services included in the MCP could expand beyond those listed in Table 1 (in agreement with the Lead Provider and subject to any procurement considerations), as learning from early phases of the development accumulates and recommendations and guidance emerges from the MCP Vanguard sites around the country.

As part of this procurement, potential Lead Providers will be tested on their ability to provide the Phase 1 services, as well as their approach to delivering on the overarching responsibilities and functions listed in Section 3 of this Specification.

Figure 1. The future service model will take the form of a series of virtual locality-based hubs (or networks), co-ordinated by GPs working collaboratively and out of which an enhanced model of joined up Primary Care, Community Services and other out of hospital functions could operate. The green crosses represent Pharmacies and other Primary Care providers, whilst the amber crosses represent non-acute health centres. Patients would move in and out of the hubs, accessing services in accordance with their needs.

Figure 2. Shows the tiers of out of hospital care through which patients would flow within the locality based hubs.

| Phase | Service | Mechanism |
| --- | --- | --- |
| 1. (Service Commencement on 1st April 2017) | - Planning all Care Together (PACT), - Primary Care Diagnostics - PACT Enhanced Care Pathway - Primary Care Quality Contract - Learning Disability Primary Care Case Management | - New contract - existing providers given notice - New contract - existing providers given notice - Contract novation - service to remain under existing provider - New contract - existing contract expires 31st March 2017 - New contract - no existing service |
| 2. (Service Commencement on 1st October 2017) | - Community Adult Health Services (CAHS) - Better at Home Service | - New contract - existing providers given notice - New contract - no existing service |
| 3. (Service Commencement on or after April 2018) | - End of Life Care Co-ordination Centre - Community based care models for Long Term Conditions: - Diabetes - Heart Failure - Chronic Obstructive Pulmonary Disease (COPD) (subject to scoping) | - Contract novation - service to remain under existing provider (as at April 2018) - New contract - no existing service |

Table 1. Shows the services that will be incorporated into the MCP over the term of the contract (see Sections 4 and 5 for further information). The CCG reserves the right to amend the timetable for inclusion of any or all of the Phase 2 and 3 services, within reason, over the term of the MCP contract.

# AIMS OF THE SPECIFICATION

The development of the MCP in Wandsworth will enable delivery of the following:

- Realisation of the CCGs ambitions around Transforming Primary Care, specifically; enabling achievement of the 17 specifications set out in the London Strategic Commissioning Framework for Primary Care, development of collaborative working between General Practices and empowerment of GPs within their role of care coordinator.

- Ensure that all patients across the Borough have access to a range of local out of hospital services which meet their needs.

- Facilitate the development of joined up care pathways which enable patients to remain healthy at home for as long as possible.

- Address existing inequalities in the delivery of enhanced Primary Care services across the Borough.

- Provision of a platform around which other out of hospital services and partner agencies such as mental health, social care and the voluntary sector can be co-ordinated and integrated.

- Further the development of existing programmes of joint working between Primary Care, Community Services and other out of hospital care providers.

# Achieving the aims: FUNCTIONS OF THE LEAD PROVIDER

There are a range of clinical services that will be delivered through the MCP. These are described in Sections 4 and 5 of this specification. As referenced in the introduction, at this stage the CCG will only be testing the Lead Provider on their ability to deliver the Phase 1 services listed in Section 4, however the Lead Provider will also have a number of overarching responsibilities for delivery of the MCP over the term of the contract (or any extension thereof), which are split into the following functions:

#### Service Delivery

- Accountable for delivery of services within the MCP against set KPIs. A number of overarching KPIs will be described in the full MCP Service Specification, issued to qualifying Providers at Stage 2 of this process, further KPIs are set out within the individual clinical service specifications (Sections 4 and 5). The Lead Provider will have overall accountability for reporting and delivery on all KPIs however, it is expected that they will 'flow down' responsibility for some of them e.g. those that are activity based, to any subcontracts that are put in place. The CCG reserves the right to review KPIs on at least an annual basis and incorporate additional KPIs as appropriate, where new services are brought into the model (see Section 5).

- Delivery of all services within the overall budget for the MCP, proactively identifying and managing cost pressures that arise and escalating to the CCG where necessary.

- Ensure there are processes in place for rapid escalation and timely resolution of issues which may affect service delivery.

- Ensure that systems and processes are in place to monitor patient experience and quality of the services within the MCP and respond to feedback, adapting those services where necessary.

- Implement formal channels for managing and reporting complaints and Serious Incidents.

- Ensure that activity reporting mechanisms are in place for each element of the service and that reports can be supplied to the CCG regularly. Format and frequency of reports to be agreed.

- Ensure delivery of equitable services that are accessible for all patients across the Borough (in-line with the entry criteria set out in the individual clinical service specifications).

- Implement any national and local standards that may exist for accessing services, e.g. use of e-referral routes, publication of pathways and forms on DXS and application of the standards in the Accessible Information Specification.

#### Procurement and Contracting

- Procure and contract for services to be delivered as part of Phases 2 and 3 of the MCP development.

- Responsible for development of any procurement paperwork, process and contractual documentation that is acceptable to the CCG and complies with any procurement and contracting regulations that are applicable to the CCG.

- Undertake consultation with patients, the public and key stakeholders in accordance with CCG requirements, in relation to any planned changes to the way that services are delivered.

- Monitor performance and finances of subcontracts so that they remain within budget and provide assurance to the CCG, in agreed reporting formats on delivery against activity targets and on quality of service delivery.

- Ensure contractual arrangements with the CCG are 'flowed through' into subcontracts so that Providers of subcontracts are bound by the same terms and conditions as the Lead Provider. To give the CCG assurance on this, the Lead Provider is required to use the standard NHS subcontract (available from: https://www.england.nhs.uk/nhs-standard-contract/16-17/) in contracting with any other Providers for clinical services to be delivered as part of the MCP.

- Follow agreed procurement processes for awarding any subcontracts to Providers, the CCG reserves the right to approve award of all subcontracts.

#### Transformation and Integration

- Work with the CCG to develop and implement plans to operationalise the 17 specifications detailed in the London Strategic Commissioning Framework for Primary Care.

- Actively work together with other Providers in Wandsworth Borough to ensure joined up and integrated delivery of the MCP services to patients, increasing quality and efficiency of care delivery. These Providers will include but are not limited to:

- General Practices

- GP Federation

- Pharmacies

- Voluntary Sector organisations

- Nursing and  Residential Homes

- St Georges Hospital NHS Foundation Trust

- Wandsworth Social Services

- Public Health

- South West London and St Georges Mental Health Trust

Where possible the CCG will work to embed contractual levers with these Providers which require them to engage and work with the Lead Provider for the MCP.

- Identify opportunities to integrate services within the MCP and across the wider health and social care system and work pro-actively to implement these.

- Identify opportunities for improvements/efficiencies across the services within the MCP and the wider health and social care system and work pro-actively to develop solutions.

- Support the CCG in delivering QIPP initiatives that are linked to the services being provided through the MCP.

- Engage and consult with staff and other stakeholders across the system (including patients and the public) in order to develop and improve services.

- Engage with the CCG on pathway redesign initiatives and scoping work for including additional services in the MCP in future, as described in Section 5.

#### Co-ordination of Services

- Oversee the delivery of services across the MCP so that it functions effectively on a day to day basis.

- Act as a central point of contact for reporting and resolving operational issues that arise across services within the MCP, this point of contact should be available 8am - 6.30pm, Monday - Friday, and should be available via telephone and email.

- Take responsibility for implementing system 'enablers' where necessary e.g. data sharing agreements, EMIS templates, setting up virtual MDTs.

- Detail how the services in the MCP will integrate operationally including being responsible for the development or amendment of service specifications where necessary and identifying how staff, systems and processes will work together i.e. through pathway maps.

- Ensure that the needs of out of borough patients are addressed consistently across services within the MCP.

- Act as a central communication point for internal and external messages.

- Implement a rolling communication plan with stakeholders, including staff within the MCP and across other Providers and patients and the public to ensure there is clarity on new ways of working and around systems, processes and methods for accessing services.

#### Leadership and Management

- Accountable for delivery of all services described within this Specification.

- Lead strategic and operational meetings with internal and external stakeholders to ensure the model functions effectively, that key stakeholders are engaged and that the model is fully embedded in day to day working of MCP stakeholder organisations.

- Define roles and responsibilities of staff within the system, implementing communication plans and training programmes where necessary to ensure all staff 'buy-in' to the model and understand their roles and responsibilities.

- Implement a clear structure of accountability with built in escalation processes and a central point of contact for any issues that might arise.

- Ensure that there is leadership and management presence across services within the MCP.

#### Workforce Development

- Responsible for recruitment into key roles within the MCP services.

- Identify and address current and future workforce needs, developing and implementing a strategy for creating a sustainable workforce for delivering the MCP.

- Responsible for training and development of staff that operate as part of the MCP.

- Ensure there is an MCP induction pack available for new staff across the various MCP stakeholder organisations, this should include attendance at an MCP training session.

- Facilitate joint training for staff groups that will be involved in the MCP services, considering where dual roles and alternative roles may be utilised.

# ACHIEVING THE AIMS: SERVICE DELIVERY

This section details the clinical services which will be the responsibility of the successful Lead Provider to deliver in Phase 1 of the MCP (from April 2017). Achievement of any KPIs embedded within the service specifications will also become the responsibility of the Lead Provider and as such it is expected that these KPIs will flow through into any subcontracting arrangements that may be put in place for delivery of the clinical services.

#### Primary Care Enhanced Services - Planning all Care Together (PACT)

The PACT enhanced service has been delivered by General Practices in Wandsworth for the last 3.5 years. It uses risk stratification at a Practice level to identify patients at risk of a future hospital admission and then incentivises GPs to pro-actively manage their care, using a range of local tools and pathways to help avoid or reduce potential future hospital admission and reduce costs.

In addition, the specification includes a range of other requirements that support appropriate “shifts” of patient care from secondary care into the community and primary care e.g. DMARD drug monitoring and disease screening and prevention (e.g. bowel cancer screening and falls prevention).

In developing a future vision for the improvement of patient care through General Practice services in Wandsworth, one of the levers identified was the development of a single provider model for delivery of the PACT specification.  Over the past 9 months, Battersea Healthcare CIC have been responsible for overseeing this delivery and have had considerable success, increasing uptake and activity across the Borough.

By embedding PACT within the MCP, it is envisaged that this success will continue, with the added benefit of facilitating relationships and working patterns across wider stakeholder organisations in Wandsworth, which will enable PACT patients across the Borough to receive an even better standard of integrated care in the community.

Full details of the PACT service delivery requirements can be found in the attached specification.

#### Primary Care Enhanced Services – Diagnostics

Wandsworth Clinical Commissioning Group (WCCG) have commissioned the following primary care diagnostic services directly with practices for a number of years:

- 24hr Ambulatory Blood Pressure Monitoring

- 12-lead Electrocardiogram

- Phlebotomy

- Spirometry

A review of these services was conducted in 2014 and feedback was collated from GPs/practices, patients and WCCG staff.  The conclusion of the review was that the current services were well received but that some amendments were required to update the original specifications. In addition, it was noted that a standardised process across the Borough was key to ensuring the four diagnostic services were available to all patients. Since this review, the following amendments have been made to the specifications, which will be available to the Wandsworth population from 1st April 2016:

- All four services have been updated to ensure they are in line with current activity and national / local guidance. The specifications have been approved via a rigorous sign off process;

- The four diagnostic services have been bundled into one overarching specification to ensure a standardised, efficient service overseen by one Provider, which offers continuity of care and is available to all patients across the borough;

- Agreement that the services will continue to be available at Wandsworth practices.

Similarly to PACT, it is anticipated that embedding delivery of these diagnostic services within the MCP, will enable patients across Wandsworth to receive a more holistic, joined up out of hospital service which is consistent in terms of accessibility and quality, regardless of the practice they are registered with.

The overarching specification for delivery of this service is embedded below. Detailed requirements for delivery of the individual diagnostic specifications are contained within this document.

#### Enhanced Care Pathway

The Enhanced Care Pathway (ECP) is an integrated proactive approach to delivering care for frail older adults.  It brings together a range of health and social care professionals to provide joined up effective care planning and delivery and to act rapidly when care needs escalate.

The Enhanced Care Pathway is currently being delivered by Battersea Healthcare CIC (BHCIC) via a three year contract which is due to finish on 31st March 2019.

Terms are in place within the contract in order that once the Lead Provider for the MCP has been identified, the contract will novate from BHCIC to the Lead Provider of the MCP, who will subsequently be required to enter into sub-contracting arrangements with BHCIC to continue to deliver the Enhanced Care Pathway until at least 31st March 2019. Agreement to participate in this subcontracting arrangement will be obtained from potential Lead Providers of the MCP as part of the procurement process. This will be incorporated into the pass/fail criteria for the procurement at Stage 2.

It is anticipated that subject to successful delivery of the contract over the next three years, the MCP Lead Provider (via consultation and agreement with the CCG) may wish to extend the term of the Enhanced Care Pathway contract with Battersea Healthcare CIC, to fit in with the term of the contract for the MCP and/or any other subcontracts that may be held by the Lead Provider as part of this service.

Detailed information on the Enhanced Care Pathway can be found in the service specification embedded below:

#### Primary Care Quality Contract

Since1st April 2016, Wandsworth CCG has had delegated responsibility for holding and monitoring GP Practice contracts. The CCG also has a responsibility to assist and support NHS England to secure continuous improvement in the quality of primary medical services. A duty which has to be balanced to take account of the conflict between practices as CCG members and commissioners and practices as providers of primary care.

In 2016-17 a primary care Quality Contract, “Improvement of Quality across Local General Practices” is being delivered by Battersea Healthcare CIC. This contract was developed to consolidate and build on existing quality programmes. It utilises a more targeted approach and enables early identification and resolution of potential gaps in quality, supporting practices to deliver high quality care for their patients.

The contract operates at a borough wide as well as individual practice level, encouraging GPs to work together collaboratively, sharing learning and best practice to develop a sustainable, holistic and high quality model for primary care.

The MCP Lead Provider will need to work closely with the Wandsworth GP practices to deliver the services within the MCP, as such they will be well placed to take on and deliver the Quality Contract from April 2017 onwards, as it requires close working relationships with the practices in order to deliver ongoing improvement in primary care quality.

As such this contract will fall under the Lead Provider of the MCP to deliver from April 2017, subject to achievement of in year outcomes by the incumbent Provider and agreement of recurrent funding by the CCG.

#### Learning Disability Primary Care Case Management

People with learning disabilities die younger and have poorer health than the general population. These differences are, to some extent, avoidable and as such, they represent health inequalities. The Wandsworth Joint Strategic Assessment (JSNA) 2014 reported that by 2020, the number of people with a learning disability in Wandsworth is projected to increase by 10% from an anticipated population of 5,500 in 2012.

The MCP Learning Disability Primary Care Case Management Function will deliver a service that is able to integrate the health needs of people with learning disability with that of the general population, thereby reducing the current health inequalities. The service will support the CCG’s vision to redesign patient care in Wandsworth for those with long term conditions, enabling users to live more independent lives, remain within their own homes, and prevent unnecessary hospital admissions.

Information regarding the Learning Disability Primary Care Case Management service and the role of the MCP Lead Provider can be found in the service proposal embedded below:

# ACHIEVING THE AIMS: EVOLUTION OF THE SERVICE

During the course of the development of the MCP model it has become apparent that there are a wide range of additional clinical services that could be delivered through the model, resulting in an improved patient experience and better joined up care.

In order to incorporate these services, detailed scoping work will be required in the short to medium term, in collaboration with the Lead Provider and it is therefore envisaged that the initial version of the MCP which rolls out in April 2017 will serve as an infrastructure around which these other services can be integrated and aligned over time.

It is anticipated that the following services will be incorporated into the MCP over the term of the contract. As set out previously, the Lead Provider for the MCP will be expected to undertake procurement exercises for each of these services, in line with the procurement regulations to which the CCG is expected to adhere. These services and the planned phasing for their inclusion in the model are also summarised in Table 1.

## Phase 2 Services (Included in the MCP from October 2017)

#### Community Adult Health Services (CAHS)

Wandsworth CCG’s model for Community Services is transformational and essential. The Community Adult Health Services (CAHS) model seeks to improve the delivery of care for people in their own homes or at an appropriate clinical setting by linking systems and health professionals from health, social care and the voluntary sector together to enable staff to work more effectively. CAHS has now been operating for two years.

It is the intention of Commissioners that the CAHS service will form part of the MCP from October 2017. Once identified, the Lead Provider for the MCP will work to undertake a competitive tender process for CAHS, in order to identify the most capable subcontractor for the service and ensure they are in a position to take over the existing CAHS service from the incumbent Provider on 1st October 2017, following a handover period.

The CAHS service forms an integral part of the CCGs strategy to transform Primary Care and Out of Hospital Care across the Borough. Incorporating CAHS within the MCP under a Lead Provider model will facilitate the development of integrated working across health services in the Borough enabling the provision of better quality joined up care to our more vulnerable cohorts of patients. Detailed information on the CAHS service can be found in the specification embedded below.

#### Better at Home Service

Better at Home is a new support service that will enable an individual to remain independently in the community and help them to adjust back at home following admission into hospital, whether for an elective or non-elective admission. The service will aim to support the individual through three key functions;

- Remaining Independent

- Third Sector Support

- DIY at Home

These functions are described in further detail in the specification embedded below. Having given due consideration to relevant procurement guidelines, the MCP Lead Provider is encouraged to look at a Third Sector Provider for the delivery of this service, to align with the principles set out in Wandsworth CCG’s commissioning intentions.

## Phase 3 Services (Included in the MCP after April 2018)

#### End of Life Care Co-ordination Centre

An “End of Life Care” (EOLC) patient is someone who has an advanced, progressive and incurable illness and, whilst acknowledging that making a prognosis is difficult and imperfect, is likely to die within the next 12 months.  Supporting families and carers of patients with end of life care needs is an important element of caring for this group of patients.

The primary aim of the End of Life Care Coordination Centre is to improve the coordination and utilisation of EOLC services, thereby providing more joined-up care for patients, their families/carers and freeing-up clinical time for health and social care professionals caring for this group of patients.

It is envisaged that the MCP Lead Provider will take over responsibility for the EOLC Coordination Centre contract with effect from 1 April 2018. The “mechanics” of this proposed arrangement, are explained further in the proposal embedded below. It is anticipated that this will be the first stage of integrating key end of life care services within the MCP whilst a range of other EOLC provider contracts will continue to be held by the CCG for the foreseeable future.  Over time and as the MCP develops, discussions will take place with a view to including more specific EOLC services under the MCP umbrella where this will provide easier integration of services and care.

#### Community Based Care Models for Long Term Conditions (LTCs)

The CCG is currently undertaking a programme of redesign for diabetes services across the Borough with the aim of improving care for this cohort of patients. The intention is to achieve this improvement by moving the focus of diabetes services out of the hospital, to be led by primary care with the support of diabetes consultants and diabetes specialist nurses, creating a streamlined, smooth care pathway.

The integrated service will provide both specialist and generalist diabetes care through personalised care planning, enhancing primary care provision and supporting patients to proactively manage their condition.

The specialist diabetes consultants leading the service will be based in the community, supported by a team of specialist nurses working in an MDT model alongside the community nursing and geriatrician to build capability in primary care.

The service will dovetail into the systems and ways of working developed through the MCP and through collaborative working will enhance service provision in primary care through education and support, standardising primary diabetes care across Wandsworth.

Subject to further scoping and consideration of relevant procurement guidelines, it is anticipated that the community based model for Diabetes care will be included in the MCP as part of Phase 3. Pending success it is expected that the model will be extended to cover other Long Term Conditions such as Heart Failure and Chronic Obstructive Pulmonary Disease.

## ASSURANCE PROCESS FOR PHASE 2 and 3 SERVICES

It must be noted that detailed specifications for some of the Phase 2 and 3 services are yet to be developed and the Lead Provider will be required to engage with the CCG and other local Providers during the scoping work for each service to ensure it can be integrated effectively.

The Lead Provider will also be required to pass through a series of gateways or checkpoints, in order to take on responsibility for delivery of these additional services. These gateways are likely to consist of the following:

- Provision of Documentary Evidence

The Lead Provider will be required to submit the following documentation regarding each service to the CCG for the purposes of assurance. This documentation may be worked up in collaboration with the CCG but must be owned by the Lead Provider:

- Service specification including KPIs for the service and a performance management framework.

- Procurement documentation including timetable (where relevant).

- Contractual documentation including governance/monitoring arrangements.

- A project plan detailing how the service will integrate operationally with the MCP and the expected benefits.

- A detailed service implementation plan.

- Evidence of stakeholder/user engagement in planning for inclusion of the service within the MCP.

- Interview:

The Lead Provider will attend an interview with commissioners and key stakeholders of the service. The aim of the interview will be to assure the CCG and stakeholders regarding the Lead Providers understanding of the service and on their approach to procurement, contracting and implementation.

- Key Performance Indicators:

The Lead Provider will have to demonstrate delivery against KPIs for existing components of the MCP model. This will be assessed on an ongoing basis throughout the term of the contract.

The CCG reserves the right to amend this gateway process and/or the timetable for inclusion of any or all of these additional services within reason, over the term of the MCP contract.

Additionally, if the Lead Provider fails to deliver on any elements of the 'gateway process' described, the CCG may take the decision to remove the service element in question from the MCP model, at which point it will longer fall within the remit of the Lead Provider to deliver.

- CCG Sign off:

The evidence gathered through gateways a-c described above will be subject to signoff via an internal CCG governance process, to be determined.

# Patient Coverage

Patients must have access to the services in the MCP as per the needs based entry criteria set out in the individual service specifications – Sections 4 and 5.

The Lead Provider will be required to ensure that access to these services is equitable, regardless of which GP practice the patient is registered with.

# CONTRACT

The MCP Lead Provider will be required to sign up to the terms in the NHS Standard Contract 2016/2017 (with any national amendments or variations issued by NHS England). The Lead Provider will (save where agreed otherwise in writing in accordance with the NHS Standard Contract 2016/2017) be required to use the NHS Standard Sub-contract in setting up arrangements with any and subcontractors for the MCP services to be delivered through the MCP. The NHS Standard Contract and subcontract are available from: https://www.england.nhs.uk/nhs-standard-contract/16-17/

Subject to further development, as described in Section 5, the MCP specification will operate for the duration of seven years from 1st April 2017 until 31st March 2024, with an optional extension for up to a further three years until 31st March 2027.

Any amendments to the contract or service specification during that time period will be agreed between the Commissioner and Provider. As the service model is embryonic, the Provider will be expected to demonstrate flexibility and a creative approach to ensure key deliverables can be met (see Section 10).

There will be a review of this specification by Wandsworth Clinical Commissioning Group (WCCG) on at least a six monthly basis to inform on-going commissioning decision-making.

The contract start date (Effective Date) will be confirmed.

# Budget

The financial envelope for delivering the MCP is fixed and ultimately covers delivery of a range of clinical services. Table 2 shows an approximation of the annual budget for each service within the MCP, based on current activity and staffing levels.

| MCP Financial Phasing | Annual Funding for MCP (£000's) |
| --- | --- |
| MCP Services (Phase 1) | Service Delivery |
| Planning all Care Together (PACT) | £ 2,111 |
| Diagnostics | £ 521 |
| Enhanced Care Pathway (ECP) | £ 1,000 |
| Primary Care Quality Contract | £ 75 |
| Learning Disability Primary Care Case Management | £ 50 |
| Management | £ 400 |
| Total | £ 4,158 |
| Future Services (Phase 2) | Service Delivery |
| Community Adult Health Services (CAHS) | £ 15,990 |
| Better at Home Service | £ 161 |
| Total | £ 16,151 |
| Future Services (Phase 3) | Service Delivery |
| End of Life Care Co-ordination Centre | £ 655 |
| Total | £ 655 |
| Grand Total | £ 20,964 |

Table 2. Annual budget shown is based on achievement of 100% KPIs and utilisation of 100% of budget envelope for management.

Table 3. Annual budget shown is based on achievement of 100% KPIs and utilisation of 100% of budget envelope for management.

The fixed annual budget for delivery of clinical services within the MCP is £20,564,000. It is stipulated that 100% of this funding must be utilised for clinical service delivery at agreed tariffs and employment of clinical staff as detailed in the individual service specifications (Sections 4 and 5).

An additional budget envelope of between £350,000 and £400,000 will be available to the Lead Provider for management costs in each year of the contract. As such the maximum budget available in Year 1 of service delivery is £12,233,000 (this reflects the phasing of CAHS and the Better at Home Service into the MCP in the second half of the year).

To ensure fairness and transparency throughout the procurement process, bids from all providers will be evaluated on the basis of the maximum budget in Year 1 of £12,233,000.

There may be a slight variation from these figures and the Commissioner will confirm the actual budget to the Provider upon contract finalisation.

Providers should be aware that if the financial envelope is exceeded at any point during the term of the contract, the Commissioner will not be held liable for any additional cost for the delivery of the MCP services. The Lead Provider will need to have robust systems in place for the identification of cost pressures, which should be escalated to the CCG. The Lead Provider will be expected to manage any cost pressures that might arise within the overall budget of the MCP.

It is recognised that the cost of delivering some elements of the MCP is likely to be dependent on the successful TUPE of existing staff and recruitment of new staff into posts to operationalise the service. The Commissioner therefore reserves the right to be refunded on any under-spend in year throughout the term of the contract. Alternatively, negotiations will need to take place as to how the Provider may use the under-spend in another way to deliver the outcomes required.

The contracting authority and the successful provider will review the contract price together at the start of each contract year, in light of inflationary pressures and NHS expectations in regard to austerity and financial controls.

# Governance

The Provider is responsible for ensuring that it has appropriate clinical and information governance in place that ensures the following is carried out:

- Clinical records and safety netting systems are developed and maintained.

- Annual patient satisfaction surveys are carried out.

- An effective patient complaints procedure is in operation.

- Critical incidents are reported to the Commissioner (Significant Events/Serious Untoward Incidents).

- An information governance framework is in place that complies with NHS requirements, including management of security and confidentiality of patient information.

# Quality Assurance

The Provider is responsible for ensuring adequate internal quality controls exist to ensure day-to-day consistency in the delivery of the service requirements under this specification.  This includes ensuring there are adequate records and reporting systems and selection and appropriate training of staff.

The external quality controls will be provided by the Commissioner monitoring this specification.

# Other Information

The following points should be noted by potential Providers:

- The Provider will have access to and be trained on the Sollis Clarity software (which uses the Johns Hopkins Adjusted Clinical Groups (ACG®) System to identify patients at high risk and forecast future healthcare utilisation) or other similar tools as agreed with the Commissioner.

- Delivery of the PACT and ECP specifications requires the development of patient registers to ensure appropriate patients receive the requirements of various specifications. Patient registers should be reviewed and updated on a monthly basis.  Risk stratification software, clinical judgement / local patient knowledge or analysis of recent unplanned admissions and A&E attendances should be used to help identify which patients to include on the PACT Enhanced Care Pathway.

- The Provider will need to have in place or demonstrate how they will set up data sharing agreements with key stakeholder organisations across Wandsworth in order to deliver the requirements of a number of the clinical services within this specification. These data sharing agreements will be subject to sign off by the CCG.

- Wandsworth CCG has committed to developing a central patient record system across the Borough using EMIS Web software. Providers will need to be familiar with this software or demonstrate how they will develop an expertise in this area.

- Providers are responsible for all costs associated with the use of I.T. systems including obtaining access to EMIS and any I.T. support requirements that the delivery of the MCP might entail.

# Key Performance Indicators (KPIs)

The Commissioner has considered the outputs that they wish to achieve through the delivery of the MCP and these are reflected in a set of KPIs which will be published at Stage 2 of this process. It is recognised that the MCP is a new model of care which will result in a significantly new way of working across organisations. As such, many of the deliverables in Year 1 involve the setting up of systems and processes. WCCG has developed targets that increase throughout the financial year to reflect incremental expectations on deliverables as the model becomes more embedded.

5-10% of the annual budget for the MCP will be retained by the commissioner and will be payable to the Lead Provider at the end of each financial year, pending delivery against KPIs. The exact percentage will be considered and agreed with the Lead Provider following the procurement process.

Additional KPIs are embedded within the individual clinical service specifications (detailed in Section 4) and achievement of these will also be the responsibility of the Lead Provider.

The KPIs which are linked to the 5% financial incentive will be refined with the Provider during the contract negotiation process.

## Quality Innovation Productivity Prevention (QIPP)

A number of the services included within the MCP Specification are expected to generate a QIPP saving to the CCG through a reduction in secondary care activity, which results in reduced costs. As such, a target reduction in secondary care activity will be included in the KPIs for the Lead Provider of the MCP. Delivery on these targets will be linked to the financial incentive described above.

All Providers of large contracts commissioned by the CCG are subject to an annual QIPP. Although this has not been applied to the MCP in Year 1, due to the model being in development, it is anticipated that a non-cash releasing QIPP will be applied in future years. It is expected that this QIPP saving will be generated through more efficient delivery of integrated services within the MCP and will be re-invested into service development. The CCG reserves the right to retain or reinvest QIPP savings as necessary across the health system, as and when priorities become apparent.