[image: image1.png]IMPERIAL MUSEUMS




Tender Documentation

Contract No. 
IWM/SPG/1660
Project and Cost Consultant

All Saints New Build Accommodation
Transforming IWM London
Tender Submission Return Date
14.00 on 10 April 2017
Contents

Section 1: Introduction 

1.1 
Brief description of Imperial War Museums (IWM)
1.2 
Transforming IWM London 

1.3
Brief description of new build accommodation
Section 2: Introduction to the Appointment

2.1 
Tender procedure

2.2 
Form of appointment

Section 3: Form of enquiry
3.1 
Client
3.2 
Project information

3.3 
Project description

3.4 
Project programme

3.5 
Project budget

3.6 
Insurances

3.7 
Period of limitation
Section 4: Schedule of services
4.1
Project & Design Management
4.2 
RIBA Work Stage 1 – Preparation & Brief
4.3 
RIBA Work Stage 2 – Concept Design
4.4 
RIBA Work Stage 3 – Developed Design
4.5 
RIBA Work Stage 4 – Technical Design
4.6 
RIBA Work Stage 5 – Construction Services
4.7 

RIBA Work Stage 6 – Handover & Close Out
4.8 
Supplementary Services
4.9 
Contractual
4.10
Cost Consultant
4.11 
RIBA Work Stage 1 – Preparation & Brief
4.12 
RIBA Work Stage 2 – Concept Design
4.13 
RIBA Work Stage 3 – Developed Design
4.14 
RIBA Work Stage 4 – Technical Design
4.15 
RIBA Work Stage 5 – Construction Services
4.16 
RIBA Work Stage 6 – Handover & Close Out
4.17 
Supplementary Services
4.18 
Contractual
Section 5: Fee criteria
5.1 
Lump sum fee

5.2 
Time charges

5.3 
Expenses

5.4 
Instalment payments

5.5 
VAT
5.6 
Confirmation of fee offer

Section 6: Information regarding the tender submission

6.1 
Purpose of tender process

6.2 
Approach to working with clients
6.3 
Fees/resource Plan
6.4 
Criteria for selection
6.5 
Submission of tenders

6.6 
Interviews

6.7 
Tender response
6.8
Tender Programme
Appendices
Appendix 1: General conditions of Contract

Appendix 2: Map – All Saints

Appendix 3: Programme
Appendix 4: Client Brief

Appendix 5: Questionnaire

Appendix 6: Confirmation of Fee Offer
Appendix 7: Confidentiality Agreement
Appendix 8: Staff Security Clearance Notification Form 
Section 1

Introduction to IWM 
1.1    Imperial War Museums

Imperial War Museums (IWM) is operated by the Trustees of the Imperial War Museum, a charitable corporation established by statute.


Founded in 1917 to record the story of the Great War and the contributions to it made by the peoples of the British Empire, IWM is now the world’s leading authority on conflict and its impact, telling the story of people who have lived, fought and died in conflicts involving Britain and the Commonwealth from the First World War to the present day. 


Our unique Collections, made up of the everyday and the exceptional, reveal stories of people, places, ideas and events across our five museums. We challenge people to look at conflict from different perspectives, enriching their understanding of the causes, course and consequences of war and its impact on people’s lives.


IWM’s five branches are:

· IWM London; 

· Churchill War Rooms;

· HMS Belfast moored in the Pool of London;

· IWM Duxford, Cambridge;  

· IWM North, Trafford, Manchester.

Each branch provides a comprehensive range of exhibitions consisting of items from the permanent collections integrated with multimedia interactive displays.

IWM is, in addition to its conventional museum role, a major national art gallery, a major national archive of written and audio-visual records, and a research centre. Our activities include display, education, publishing, research, trading, conferences, as well as the acquisition, documentation, study and conservation of collections.


IWM is a non-departmental public body (NDPB) overseen by a Board of Trustees. Its sponsor department is the Department for Culture, Media & Sport (DCMS). IWM as a whole receives less than 50% of its income as grant in aid from DCMS. The grant-in-aid provides no contribution to the capital programme of development and renovation.

Further information about IWM and all of our branches can be obtained from our website, www.iwm.org.uk.

IWM is an exempt charity under the terms of the Charities Act 1993 Schedule 2 (u) and (w). As such we do not have a Charity Registration number. 
1.2
Transforming IWM London

In May 2010, we appointed Foster + Partners to develop a spatial masterplan for IWM London to:

· rationalise and capitalise on our estate

· enable the display of more from our collections in new and engaging ways

· deliver much improved visitor facilities and services

· drive income and efficiency

The masterplan provides a framework for phased development of the IWM London site over the next 10-20 years. Phase 1 was completed in July 2014 which re-configured the atrium space and new displays, updated and improved visitor facilities including the café, shops, toilets and lifts and created new First World War galleries in time for the centenary. 

Phase 2 consists of new Second World War galleries and The Holocaust Galleries by autumn 2020.  This phase will displace a number of staff and stored collections in order to open up back of house space to the public.  The masterplan identified the All Saints site as the museum’s corporate hub and the principal location for corporate teams.  The long term aim is to leave only operational staff at IWM London. 

1.3
All Saints new build accommodation 

We have been considering our current staff accommodation at All Saints following a major staff restructure and evolving ways of working.  As a result, we propose to build a new block behind the current building (there is a large yard behind) and lease the current building to others.  This procurement relates to the new build accommodation only.
Section 2
Introduction to the Project and Design Manager and Cost Consultant Appointment

2.1 
Tender Procedure 

This tender pack has been produced as a means of selecting and appointing a Project Manager and Cost Consultant (“the Consultant”) for All Saints New Build Accommodation project.

The programme for the tender process and the award selection criteria are shown in Section 6 of this tender pack.

2.2 
Form of Appointment 

It is proposed that the selected Consultant will be appointed under the terms and conditions, as contained in Appendix 1.


The following Form of Enquiry and Schedule of Services will supplement the above conditions of contract and are to be attached to the final Form of Appointment.

Section 3

Form of Enquiry
3.1    
Client

Name: 

The Trustees of the Imperial War Museum

Address:

Imperial War Museums
Lambeth Road

London

SE1 6HZ

The Project Leader will be the contract manager for this contract. IWM London is a branch of Imperial War Museums. The Project Leader has IWM’s authority to represent it in respect of the matters set out in this Contract.

Client contact:
Ann Carter, Assistant Director, Special and Creative Projects

acarter@iwm.org.uk
020 7416 5323
3.2 
Project Information
Location for All Saints new build: 

Imperial War Museum

All Saints Building
Austral Street

London

SE11 4SJ

The site is approximately 1219.5 sq.m. 

See Appendix 2 map showing the location of All Saints
3.3 
Project Description 
The project comprises:

· design, construction and fit out of new build accommodation at the All Saints site
· planning and move of staff from existing offices at All Saints and IWM London into this new accommodation.
3.4 
Project Programme. Key dates (indicative at this stage)

Please refer to the programme in Appendix 3. 

IWM will appoint a team to design the building and fit out of the new build. Please note that the Consultant will be the Principal Designer under CDM 2015 regulations. 
3.5 
Project Budget

The total project budget is £4m which covers but is not limited to:

· Design and professional team fees including BIM and BREEAM

· Contractor overheads and profits
· Surveys

· Removal of asbestos or contaminated ground

· Diversion of existing services and relocation of ICT servers 

· New build costs including M&E, fire and PAVA, security systems, ICT cabling, and connection into existing systems, e.g. BMS

· Fit out costs including loose furniture

· Landscaping 

· Planning permission and S106/278 payments

· Testing and commissioning
· Move of staff to new build
· Risk

· Contingency

3.6
Insurances

3.6.1
Professional Indemnity insurance is to be maintained by the Consultant in an amount of not less than £10m for any one occurrence or series of occurrences arising out of any one event, at any stage from the letting of this contract and for a period of twelve years from the date of Practical Completion of the project.

3.6.2
Third Party/Public Liability Insurance is to be maintained by the appointed Consultant in an amount of no less than £10m.

3.6.3
Employers Liability Insurance is to be maintained by the appointed Consultant in an amount of no less than £10m.

3.6.4
The Consultant will be required to ensure that insurance certification is maintained for the duration of the Project and to provide updated certificates upon request. 
3.7
Period of limitation

The period of limitation for the commencement of any action or proceedings against the Consultant and for breach of the Contract shall be twelve years from the date of Practical Completion of the project.

Section 4

Schedule of Services  
4.1
PROJECT AND DESIGN MANAGEMENT
4.1.1
For ease of reference the Services have been divided into stages as described below.  General obligations are identified first followed by specific obligations for each stage. Such divisions however shall not limit the Consultant’s obligations generally to provide the Services when appropriate.

4.1.2
The Services should not be viewed as definitive or prescriptive. The Consultant is encouraged to use his own initiative and expertise to assist IWM in achieving the right solution

4.1.3
The Consultant is required as part of the Services to lead IWM through the Project reviewing matters with him/her at a strategic level, constantly presenting options and alternative solutions and working partnership with him/her in relation to the Project.

4.1.4
Perform the necessary project and design management and cost management services to enable the Project team to develop a fully coordinated, affordable and sustainable Project.

Project Management

4.1.5
Assist IWM with the identification and appointment of the necessary consultants to form the Project Team. This will include drawing up scopes of work, schedules of deliverables and tender documentation, and managing the tender process on behalf of IWM. Advise IWM on the selection, the terms of appointment and fee structures for the Project Team.

The Consultant is to consult with IWM’s Procurement team, to ensure that the procurement of other consultants undertaken by the Consultant, has been undertaken within IWM’s procurement procedures. 
4.1.6
Advise IWM on the Project Team’s professional indemnity insurance cover. Annually confirm cover remains in place.

4.1.7
Establish a structure and procedure for project, design, construction and other meetings including frequency, function, required attendees, chairperson and responsibility for recording of meetings and circulating reports and other information.

4.1.8
Attend IWM, design, project, construction and other meetings as provided under this Contract.

4.1.9
Convene and chair all principal Project meetings. 

4.1.10
Prepare and maintain a Project Execution Plan, or similar management tool, identifying the roles and responsibilities of IWM, the Professional Team, the Contractor and specialist sub-contractors and suppliers. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval. Deliver the Project in line with the Project Execution Plan.

4.1.11
Liaise with the Project Team, prepare and maintain the Programme for the design, procurement and construction of the Project. Monitor actual progress against planned progress, as per the agreed Programme, and report to IWM. Monitor the production of information against the Programme and take/recommend to IWM any necessary action in accordance with the Consultant’s scope of services to minimise the disruption to the Programme and the cost impact.

4.1.12
Prepare a risk management strategy and prepare and maintain the project risk register and issues logs for the design, procurement and construction of the Project. Review the project risks with IWM and the Project Team. Report to IWM with any recommendations or appropriate remedial actions in accordance with the Consultant’s scope of services to treat and manage the risks and issues to minimise the impact to the Programme, the cost, operation of IWM’s business or any other impact.  

4.1.13
Liaise with IWM and Project Team and agree the sustainability strategy.  Monitor progress at each work stage.  NB IWM is in the process of developing a Sustainability Strategy
4.1.14
Monitor the performance of the Project Team, and report to IWM. Monitor the work and deliverables of the Project Team against the Programme and take action if there is any deviation.

4.1.15
Issue instructions, on behalf of IWM, to the Project Team in accordance with the terms of their Appointments.

4.1.16
Agree Project reporting and recording procedures with IWM, the Project Team and the Contractor/Construction Manager, and to implement the agreed procedures.

4.1.17
Agree financial and progress reporting procedures with IWM, the Project Team and the Contractor/Construction Manager, and to implement the agreed procedures.

4.1.18
Liaise with the Project Team and Contractor/Construction Manager to prepare regular/monthly reports to include quality, progress and construction costs prepared by the Cost Consultant. Advise IWM of any decisions required and obtain authorisation.

4.1.19
Agree with the Project Team and IWM an integrated ICT system that will: streamline the transfer of information between the Project Team and the Contractor/Construction Manager and manage all the documentation on the Project; enable computer modelling; and produce co-ordinated as built information and operation and maintenance manuals from both the Project Team and the Contractor/Construction Manager for ease of use by occupiers. 

4.1.20
With IWM develop the approach to communicating with and managing the internal and external stakeholders.

4.1.21
When requested, act on behalf of IWM in negotiations with external stakeholders.

4.1.22
Assist IWM in providing information to potential funders as required.

4.1.23
Attend presentations to funders and other interested parties as required.

4.1.24
Check applications for payment from the Project Team. Recommend payment authorisations to IWM.

4.1.25
Check other invoices related to the Project. Recommend payment authorisations to IWM.

4.1.26
Liaise with the Project Team, arrange for the preparation and maintenance of cash flow forecasts and other statements monitoring expenditure on the Project.

4.1.27
Support IWM and the wider Project Team throughout the design development and implementation process.

4.1.28
Convene Value Engineering exercises to ensure design development is in alignment with the budget.

4.1.29
Arrange, facilitate and manage early warning and risk reduction meetings.

4.1.30
Provide specialist procedural advice to comply with EU Regulations and/or other legislation, excluding legal advice.

4.1.31
Keep complete and accurate records in relation to the Project and distribute to IWM and the Project Team as and when necessary to keep them properly informed. This should be provided to IWM in both digital and hard copy.

Design management and CDM

4.1.32
To undertake the Principal Designer role in accordance with Regulation 5 of the CDM Regulations 2015. The Principal Designer will be required to assist IWM in discharging their duty holder role under Regulation 4 of the Regulations, and to undertake the Principal Designer duties contained set out in Regulation 8 (General duties), Regulation 11 (Duties of Principal Designer) and Regulation 12 (3),(5),(6) and (10). 

4.1.33
Project Design Stage


The Principal Designer (“PD”) will be required to:

· Fulfil the duties described under Regulation 11 of the CDM Regulations.

· In meeting the duty to Plan, monitor and coordinate the pre-construction phase, the PD must take account of the general principles of prevention (required under the Management Regulations 1999) and as set out in Appendix 1 of CDM2015.

· Ensure design work contributes to the delivery of positive health and safety outcomes.

· Attend design meetings and review design proposal to identify and discuss risks that should be addressed, decide on control measures and agree on the information that will help the Principal Contractor to prepare the Construction Phase Plan.

· Advise IWM in respect of the suitability of designers that are required to be appointed.

· So far as is reasonable practicable, identify the risks to health and safety that are significant and likely to arise whilst undertaking construction work or during maintenance, cleaning or use of the workplace once the project is complete.

· Having identified the risks above, follow the approach to manage them (Appendix 1 CDM) and ensure so far as is reasonably practicable that the design team eliminates the risks associated with design elements, or if this is not possible, reduces the remaining risk, or controls the remaining risks to an acceptable level.

· Ensure so far as is reasonably practicable that everyone involved in working on the preconstruction phase of a project cooperates with each other, and communicate effectively to share information.

· Check that designers are dealing with design risks appropriately and that designers provide clear information about elements of the design which present significant risk.

· Help IWM’s Project Manager to bring together appropriate pre construction information and advise IWM of the adequacy of same and provide advice where appropriate on the need for additional information. Note: In reviewing the information needed regard should be had to Appendix 2 of CDM2015 – the information should be relevant to the project, to an appropriate level of detail and be proportionate to the risks involved.

· Where a project is notifiable under the Regulations, submit notice to the relevant enforcing authority in accordance with Regulation 6 and Schedule 1 of CDM2015.

4.1.34
Mobilisation Phase (pre commencement)

· Assist the Principal Contractor in preparing the Construction Phase Plan (CPP) by providing to him the preconstruction information and any information obtained from designers under Reg. 9 (3) (b) – information in respect of design risks.

· IWM is aware of their responsibility to ensure the Principal Contractor provides a Construction Phase Plan (CPP).

· The PD is required to review the CPP provided by the Principal contractor to check the plan takes in to account the pre- construction information and any information from designers. The PD is not required to approve the CPP. Adequacy of the CPP remains the responsibility of the Principal Contractor.

· The PD will be required to attend a pre-start meeting with IWM, the designers, and the Principal Contractor. 

4.1.35
Construction Phase
· The PD will be required to prepare a Health and Safety file and pass this to IWM at the end of the project. 

· The Health & Safety file can be arranged to include information on operation and maintenance of plant and equipment. Otherwise the Health & Safety file should reference the location of O&M information provided.

· The Health and Safety file will be required at practical completion. The PD will be required to liaise with and cooperate with the Principal Contractor, IWM and the Designers to ensure all relevant information is provided such that the file is ready at Practical Completion. 

4.2
RIBA work stage 1 – Preparation and Brief

4.2.1
Liaise with IWM and the Project Team to determine IWM’s initial requirements and to develop the Brief. 
4.2.2
Review lessons learned from previous projects.
4.2.3
Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval. 

4.2.4
With IWM undertake a thorough options appraisal for the Project. Contribute to the development of the Strategic Business Case.

4.2.5
Liaise with the Project Team and advise IWM on structural, building, measured and other surveys and site investigations including condition reports, soil reports etc.

4.2.6
Advise IWM on demolition, strip-out, site investigation and enabling works contracts required prior to the main works.

4.2.7
Liaise with the Project Team and procure site investigation and enabling works contracts required prior to the main works.

4.2.8
Agree a set of performance targets with IWM and the Project Team for measuring the building performance post completion, energy monitoring strategy and energy metering strategy.

4.2.9
Liaise with IWM and the Project Team to determine soft landing and handover activities.

4.2.10
Liaise with the Project Team and co-ordinate the preparation of alternative viability studies, feasibility studies and sensitivity analyses.

4.2.11
Advise IWM on specialist services, including consultants, contractors, sub-contractors and suppliers required in connection with the Project.

4.2.12
Liaise with the Project Team and advise IWM on statutory approvals required and fees due in respect of the Project. 

4.3
RIBA work stage 2 – Concept Design

4.3.1
Liaise with IWM and the Project Team to finalise Brief. 

4.3.2
Manage the concept design process to enable the Project Team to fully coordinate and cost the design. Prepare a report summarising the Project design, cost, programme and risk register. Prepare recommendations for IWM’s approval.

4.3.3
Agree the procurement route with IWM and recommend, in conjunction with the Project Team, appropriate forms of contract.

4.3.4
Liaise with the Project Team and IWM to ensure that the necessary pre-application planning/listed building discussions have taken place and that any other required statutory approvals have been set in train.

4.3.5
Contribute to the Outline Business Case.

4.3.6
Assist IWM to assess the Lead Designer’s proposals for the provision of any detailed design by any Contractor/Trade Contractor and make recommendations to IWM as to the acceptability of the same.

4.4
RIBA work stage 3 – Developed Design

4.4.1
Manage the developed design process to enable the Project Team to fully coordinate and cost the design. Prepare a report summarising the Project design, cost, programme and risk register. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.4.2
Liaise with the Project Team and establish a structure and procedure for quality management. 

4.4.3
Liaise with the Project Team and establish a structure and procedure for cost management. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.4.4
Liaise with the Project Team and establish a structure and procedure for programme management. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.4.5
Confirm the scope of the key construction contract suites to IWM and advise on additional works required by third parties.

4.4.6
Liaise with the Project Team and identify any long delivery building components and systems. Liaise with the team to prepare recommendations for IWM’s approval.

4.4.7
Liaise with the Project Team and identify specialist/proprietary building components and systems. Liaise with the team to prepare recommendations for IWM’s approval.

4.4.8
Contribute to the Full Business Case.

4.4.9
Ensure that all necessary statutory approvals are in place.

4.5
RIBA work stage 4 – Technical Design

4.5.1
Manage the technical design process to enable the Project Team and any contractors to fully coordinate the design. 

4.5.2
Liaise with the Project Team and assist in preparing a pre-construction report summarising the Project design, cost, programme and risk register. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.5.3
Prepare tender lists for IWM’s approval (subject to the form of procurement). 
4.5.4
Attend pre- and post-tender interviews.

4.5.5
Monitor and report to IWM on the procurement process.

4.5.6
Advise on the tenderers’ design and construction programmes and method statements.

4.5.7
Liaise with the Project Team and prepare a tender report. Prepare recommendations for IWM’s approval.

4.5.8
Conduct negotiations with tenderers. Obtain documentation from the Project Team to confirm adjustments to the tender sum. Prepare recommendations for IWM’s approval.

4.5.9
Liaise with IWM and the Project Team and advise on methods of progressing design and/or construction works prior to the execution of the Building Contract.

4.5.10
Obtain confirmation that required insurances are in place prior to commencement of works on the Site.

4.5.11
Obtain contract drawings and specifications from IWM and the Project Team. 

4.6
RIBA Work Stage 5 - Construction Services 

4.6.1
Agree approvals required from the Professional Team under the Building Contract.

4.6.2
Obtain authorisation from IWM for additional costs where the Consultant’s limit of authority is exceeded. 

4.6.3
Agree quality standards with the Contractor/Construction Manager and seek IWM and Project Team approvals.

4.6.4
Administer the Building Contract and undertake regular Site inspections. Obtain progress and quality reports from site staff representing IWM, the Project Team and the Principal Contractor.

4.6.5
Agree all test certificates and statutory and non-statutory approvals required from the Project Team and the Contractor/Construction Manager. Prepare recommendations for IWM's approval.

4.6.6
Advise on the levying of contract charges under the Building Contract with the assistance of the Cost Consultant.

4.6.7
Liaise with IWM, the Project Team and the Contractor/Construction Manager and prepare and maintain a handover/occupation plan, or similar management tool, identifying the roles and responsibilities of IWM, the Project Team and the Contractor/Construction Manager. This plan should include (but not be limited to) requirements for coordinated drawings, witnessing of commissioning activities by IWM or facilities management staff, any post-handover commissioning or integration of building systems, the format and any other requirements for O&Ms and as built information, training for facilities management staff, technical support and aftercare following handover and any modifications to facilities management services following handover. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.6.8
Liaise with IWM, the Project Team and the Contractor/Construction Manager and assist with the preparation and maintenance of a defects administration plan, or similar management tool, to identify the roles and responsibilities of IWM, the Project Team and the Contractor/Construction Manager. Establish review, approval, variation and reporting procedures. Prepare recommendations for IWM’s approval.

4.7
RIBA Work Stage 6 Handover and Close Out

4.7.1
Agree Practical Completion with the Contractor, Project Team and IWM.

4.7.2
Ensure that the agreed handover/occupation plan is implemented and that there is a structured transfer of information to users and the facilities management team. Spot emerging issues and help to resolve problems.

4.7.3
Prepare the post construction H&S file and handover to IWM.

4.7.4
Ensure that the agreed defects administration plan is implemented. Undertake the 12 month defects assessment and follow up with Contractor.

4.7.5
Facilitate agreement to the final account or similar financial statement from the parties to the Building Contract. For the purposes of this clause the final account or similar financial statement excludes the assessment of loss and expense claims.

4.7.6
With IWM and Project Team, evaluate the success of the Project.

4.8
Supplementary Services
4.8.0
Financial

4.8.1
Advise on the implications of alternative development programmes.

4.8.2
Obtain advice on Project sustainability from the Project Team.

4.9
Contractual

With assistance from the Project Team, advise on the cost, contractual and programme consequences arising from any acceleration instruction.

4.10
COST CONSULTANT

4.10.1
For ease of reference the Services have been divided into stages as described below. General obligations are identified first followed by specific obligations for each stage. Such divisions however shall not limit the Consultant's obligations generally to provide the Services when appropriate.

4.10.2
The Services should not be reviewed as definitive or prescriptive. The Consultant is encouraged to use his own initiative and expertise to assist IWM in achieving the right solution. The Consultant is responsible for taking the lead in managing the overall cost of the Project for its duration. 

4.10.3
The Consultant is required as part of the Services to lead IWM through the Project reviewing matters with him at a strategic level, constantly presenting options and alternative solutions and working in partnership with him in relation to the Project.

4.10.4
Prior to finalising the Cost Plan and assisted by the Project Team, regularly, and at strategic points, review the potential cost with IWM and provide preliminary cash flows.

4.10.5
Assist IWM in formulating and monitoring the total cost of the Project and, in a capacity independent of the management of the costs regularly report to funding organisations regarding the cost of the Project when requested to do so by IWM.

4.10.6
Assist the Project Manager in preparing a procedures manual for the effective management of the Project. The objective is to be clear about responsibilities, to limit, not create, a need for paperwork and to streamline the management process. Amongst other things, the manual should address the distribution of information and the necessary coordination between all parties involved in the Project so that they can properly carry out their duties.

4.10.7
Keep complete and accurate records in relation to the Project and distribute to IWM and the Project Team as and when necessary to keep them properly informed. This should be provided to IWM in digital and hard copy.

4.10.8
Carry out such of the Services as may be required as a result of failure on the part of the Contractor(s) and/or any of the Project Team.

4.10.9
Following finalisation of IWM Brief, the Cost Plan and the Programme, propose any amendments to the same which may be necessary or desirable. Comply with any amendments instructed by IWM.

4.10.10
Operate a quality management procedure appropriate to the needs of the Project. Agree the same with the Project Manager.

4.10.11
Attend all appropriate meetings as requested by IWM.

4.10.12
Provide information to the occupiers, potential purchasers or any other interested parties as directed by IWM and give due attention and regard to any observations they may make and discuss them with IWM.

4.10.13
Perform value analysis and value management. Compare the design solutions with IWM's objectives and suggest areas for discussion with the Project Team and IWM where value can be enhanced and unnecessary expenditure can be eliminated. Regularly visit the Project Team members’ offices to review the design in progress and comment to IWM and the Project Team.

4.10.14
Assist the Lead Designer to produce area schedules for the Project by reference to a coloured plan defining the measured areas. The area schedules are to be updated as often as is necessary with all versions listed and annotated on the drawings.

4.10.15
Notify IWM if the Consultant becomes aware that any of the Project Team is failing to observe their responsibilities in respect of the Project.

4.10.16
Provide such of the Services as may be necessary if at any time before completion of the Project, any materials, plant or equipment whether incorporated into the Project or not, shall be damaged or destroyed. Provide cost advice, when reasonably requested to do so by IWM, on the reinstatement cost following the occurrence of an insured event in relation to the Project.

4.10.17
Understand, comment upon and implement IWM’s various policy statements, specifically its health and safety, sustainability and procurement policies.

4.10.18
Perform other duties as may reasonably be required by IWM provided they are not inconsistent with this Deed.

4.10.19
Prepare a cost analysis based on the agreed format for special requirements.

4.10.20
Prepare a cost analysis of the final account.

4.10.21
Facilitate, set up and manage value engineering exercises.

4.10.22
Prepare and maintain the risk register in conjunction with the Project Manager. Facilitate, set up and manage risk workshops at each key stage of the Project.

4.11
RIBA Work Stage 1 – Preparation and Brief

4.11.1
Review IWM's initial budget and assess the ability to achieve the Brief within that budget. Prepare the draft Cost Plan.

4.11.2
Obtain and analyse IWM's requirements including the Brief, Cost Plan and programme. Review with IWM his comments, critique and evaluation of alternative design proposals. Comment on, suggest revisions to and agree the Brief so as to enable subsequent Services to begin.

4.12
RIBA Work Stage 2 – Concept Design

4.12.1
Actively participate in the design development process and provide every assistance and support to achieve IWM's objectives.

4.12.2
Provide constructive comments and advice on the Design Team's proposals and suggest possible alternative solutions.

4.12.3
Prepare an approximation of the cost of meeting the Design Team's concept design proposals. 

4.12.4
Collaborate with the Design Team in consideration of the available range of design options affecting the built form and cost in use. 

4.12.5
At the completion of concept design, undertake with the Project Team a preliminary technical appraisal and provide information to the Lead Designer so that he may produce a report showing proposals illustrating site planning, massing, details of floor plates, space planning studies, core layouts, overall appearance, structural and services' plant strategies and provide studies on the measured areas, cost and programme. Review these with IWM, assist the Lead Designer to amend accordingly and sign off.

4.12.6
Certify any payments to be made by IWM to any person or firms carrying out special investigations and tests in relation to the Site.

4.12.7
Assist the Lead Designer in making and negotiating all necessary applications for outline planning approval. Provide assistance in connection with appeals and public enquiries.

4.13
RIBA Work stage 3 - Detailed Design

4.13.1
Review the cost of the detailed design as it is produced.

4.13.2
Assist the Design Team by advising them on whether, and how, their design will remain within the budget.

4.13.3
Assist the Project Team in assessing the energy efficiency of the Project, cost in use and life cycle costs for alternative design solutions.

4.13.4
At the completion of the detailed design, provide information to the Lead Designer to enable him to prepare a report on the scheme including a measured area schedule, the proposed Cost Plan, a method statement and a proposed programme. Discuss the report with IWM, assist the Lead Designer to amend accordingly and sign off.

4.13.5
Prepare any special cost reports or financial appraisals for use by IWM in negotiations with landlords, adjoining owners, public authorities, licensing authorities, financing bodies, public utilities and others.

4.13.6
Advise IWM concerning the desirability of pre-ordering specific items of plant and equipment and, if instructed to do so, enable IWM to place such orders.

4.13.7
Advise on tendering and contractual procurement options. Prepare recommendations for IWM’s approval.

4.13.8
Liaise with IWM and Project Team and prepare tender documentation.

4.13.9
Liaise with IWM and Project team and advise on methods of progressing design and/or construction works prior to the execution of the Building Contracts.

4.13.10
Maintain and develop the cost plan and the cash flow forecast.

4.14
RIBA Work Stage 4 – Technical Design

4.14.1
If appropriate, agree the breakdown of the design into packages with the Project Manager and produce the cost plan divided into trade elements and common service elements. Agree with IWM and the Project Team and sign off.

4.14.2
Review the Project Team's production information as it is produced against the allowances included in the Cost Plan including implications if appropriate on other elemental allowances. Assist the Project Team so that they produce solutions within such allowances.

4.14.3
Advise IWM on the most effective bidding procedures having regard to the time available and the required quality and cost. The Consultant will be required to comply with all IWM procurement procedures, and the EU Procurement Regulations.
4.14.4
Agree the format and content of each tender package with the Project Manager, Lead Designer and IWM and provide the pricing documents for inclusion. Review documentation for the contract with IWM and the Project Team and sign off prior to tendering for consistency and completeness.

4.14.5
Interview each bidder if necessary during the bid period to check and monitor that they will provide compliant bids.

4.14.6
On receipt of the bids, interview with the Project Team as many bidders as may be appropriate to resolve any queries raised by the analysis and explore how economies can be found. Assist the Project Manager to conduct any negotiations that may be appropriate to check and monitor a compliant bid. All bids should be considered, not just the lowest.

4.14.8
Assist the Project Manager to provide to IWM a tender bid placing report jointly with the Project Team recommending which Contractor/s IWM should enter into contract with and under what terms.

4.14.8
Agree with the Project Manager any amendments to the bid documents which are to be incorporated into each Trade Contract.

4.15
RIBA Work Stage 5 - Construction

4.15.1
At the commencement of the works on site, produce a risk analysis for the Project. Regularly review this analysis so that the Project Manager can use it as a management tool to limit the likelihood of such risks coming to fruition.

4.15.2
Operate a procedure that immediately advises the Project Team and IWM of potential unplanned expenditure as soon as it becomes evident. Review with the Project Manager his estimates for all variations arising from the construction of the Project. Assisted by the Project Manager, provide estimates for all potential variations arising. When necessary, assist the Project Manager in cost negotiations with the Contractor/s.

4.15.3
Implement post contract cost control and reporting procedures, and report the anticipated final construction cost to IWM at monthly intervals.

4.15.4
Prepare payment certificates and where necessary provide comment to the Project Manager and IWM. If necessary, visit site or Contractor premises to verify these applications for payment.

4.15.5
Review all final accounts with the Project Manager and advise IWM and the Project Manager of any divergence of views.

4.15.6
Assist the Project Manager to advise on the levying of contract charges under the Building Contract.

4.15.7
Provide cost estimates and advice and assistance to IWM in the calculation and/or negotiation of any fitting out works that do not form part of the Project.

4.16
RIBA Work Stage 6 – Handover and Close Out

4.16.1
Facilitate agreement to the final account or similar financial statement from the parties to the Building Contract. For the purposes of this clause the final account or similar financial statement excludes the assessment of loss and expense claims.

4.16.2
With IWM and Project Team, evaluate the success of the Project.

4.17
Supplementary Services
4.17.0
Financial

4.17.1
Advise on the implications of alternative development programmes in conjunction with the Project Manager.

4.17.2
Obtain advice on Project sustainability from the Project Team and assist with cost estimation of the same.
4.18
Contractual

Support the Project Manager with assistance from the Project Team, and advise on the cost, contractual and programme consequences arising from any acceleration instruction.

Section 5

Fee Criteria 

5.1 
Lump Sum Fee


The Offer is to be expressed as a Lump Sum Fee. 
The Defects Period shall be 12 months from the date of Practical Completion of the individual elements of the project.

5.2 Time charges

If additional services are required, following the appointment of the Consultant, it may be agreed to pay for these services on a time charge basis. Please include details of daily and hourly rates for: Partner/Director, Associate, and any other role as may be appropriate or relevant.

5.3 Expenses and travel
All expenses and travel are to be included in the Lump Sum Fee. 
5.4 Instalment payments
Please include a proposed fee draw-down schedule in the tender.

5.5 VAT
All fees and other charges are exclusive of Value Added Tax, the amount of which shall be invoiced by the Consultant and paid by IWM at the rate and in the manner prescribed by the law.

5.6 Confirmation of Fee Offer

The Confirmation of Fee Offer (Appendix 6) must be completed, signed, and returned within the tender return.

Section 6

Information regarding the tender submission
6.1
Purpose of tender process

The purpose of this tender process is to enable the selection of an experienced project and cost consultancy who can work closely with the Project Leader to provide the project and cost consultancy services for all phases of the Project. 

6.2
Approach to working with clients
IWM believes that project success depends on effective working relationships. As such methods of working with clients will be discussed at the Tender interview. Tenderers are asked to include examples of/detail their approach towards creating a successful client/consultant relationship. 
6.3
Fees/Resource Plan

Tenderers are required to:

· submit their fee structure (inclusive of their proposed staff resource), and complete the Confirmation of Fee Offer (Appendix 6);

· provide their proposed resource plan identifying the resource to be allocated to the project, based upon their proposed project programme. Please identify the individuals within your team, allocated to deliver each task;

· submit their project schedule to deliver the project by the required completion date.

6.4
Criteria for selection

As a public organisation responsible for the expenditure of public monies, IWM seeks value for money in all its contracts. Keen pricing for this tender is anticipated and IWM will be seeking the most economically advantageous tender taking into account relevant experience and references. In order that IWM can judge submissions effectively, tenderers should provide information to support the following criteria: 

· Fee/Resource Schedule (5) assessing the overall project costs/fees, the proposed draw down schedule, and an assessment of the Resource Plan/Schedule and project programme, and their ability to deliver within the timescale. Comments relating to the programme contained as Appendix 3 are welcomed
· A written outline project methodology and key risks assessment, including an understanding of the specific challenges and risks of this project including construction work adjacent to an operational building (current All Saints) and residential properties (5)
· Communication approach (3) – an overview of the approach taken to working in partnership with IWM 

· Evidence of recent relevant experience as Project Manager and Cost Consultant on a project of a similar size and complexity (3)

· Overall Quality and Approach to the Tender (2) – an assessment of the tenderers approach throughout the tender stage, and in the quality of their tender, inclusive of the completion of the questionnaire and the associated documentation. 

6.5
Submission of Tenders
6.5.1
Tenders must answer all questions as raised, and provide all information requested in this tender pack, otherwise they will not be considered, and complete and return the Confirmation of Fee Offer (Appendix 6) and the Confidentiality Agreement (Appendix 7). 
6.5.2
Tenderers should submit three hard copies of their tender and one copy on memory stick, in English, by no later than 2pm on 10 April 2017 to:

Mr Simon Bourne
Head of Procurement

Imperial War Museums

Lambeth Road
London

SE1 6HZ
Tenderers must ensure that their submission arrives on time. We regret that tenders received after this deadline will not be considered.  

6.5.3
If tenderers have any further questions they should be submitted in writing to IWM no later than seven working days before the tender submission date to sbourne@iwm.org.uk. IWM will circulate a Q&A sheet to all tenderers via Contracts Finder within two working days of receipt.
6.6
Interviews

6.6.1
Tenderers will be evaluated and those short-listed will be invited to attend an interview to discuss their tender, to be held at IWM London on the afternoon of 24 April 2017.
6.6.2
Your team should include the main staff members that have been nominated to undertake the project as stated in your tender.

6.6.3
IWM interview panel

The panel will consist of:

· John Brown, Executive Director Commercial Services & Operations

· Ann Carter, Assistant Director, Special and Creative Projects

· Simon Bourne, Head of Procurement and Compliance
6.7
Tender response

IWM will inform unsuccessful tenderers of the reason for the selection on the basis of the tender selection criteria.

6.8
Tender Programme

This tender is to be awarded under the following programme:
Place Contracts Finder notice


15 March 2017

Tender Returns


10 April 2017

Tender Evaluations


10 – 18 April 2017

Internal review meeting/selection short-list

Interviews


18 April 2017

Interviews (if required)


24 April 2017

Tender Recommendation


25 – 27 April 2017

Issue Award/Notice letters


28 April 2017

Contract Start Date


1 May 2017
Appendix 1: General conditions of contract
THIS CONTRACT is made on …………………………………2017
BETWEEN:

· THE TRUSTEES OF THE IMPERIAL WAR MUSEUM of the Imperial War Museum, Lambeth Road, London SE1 6HZ, hereby referred to as “IWM”; and

· [INSERT CONSULTANT’S NAME] (company no. [●]) of [insert registered address] hereby referred to as “the Consultant”.
RECITAL

IWM wishes to appoint the Consultant to act as [project and design manager and cost consultant]
 in connection with the Project on the terms and conditions set out in this Contract and the Consultant has agreed to so act for the Project.

THE PARTIES AGREE AS FOLLOWS: 
1.
Definitions
In this Contract the following expressions shall have the following meanings: 
“Background IPR” means all Intellectual Property Rights excluding Foreground IPR, owned by either IWM or the Consultant prior to their accession to this Contract, as well as any Intellectual Property Rights pertaining to such information, the application for which has been filed before their accession to this Contract, and which is needed for creating the Materials or for using Foreground IPR in accordance with this Contract.
"Brief" means the document contained in schedule x identifying generally IWM's requirements in relation to the Project including those as to scope, cost and timing as the same may be amended from time to time in accordance with IWM's instructions;

"CDM Regulations" means the Construction (Design and Management) Regulations 2015.

"Construction Act" means Part II of the Housing Grants, Construction and Regeneration Act 1996 as amended by Part 8 of the Local Democracy, Economic Development and Construction Act 2009; 

"Consultant Material" means all schedules, reports, calculations, correspondence   and other documents (including any computer software developed by the Consultant used to generate them) prepared or provided by the Consultant; 

"Cost Plan" means the cost plan detailing the estimated construction cost of the Project and the individual Work Stages contained in schedule x as the same may be amended by IWM from time to time in accordance with clause 3.4;

"Fee" means the fee specified in schedule 1 and payable to the Consultant in respect of the Services or any adjusted sum agreed under clause 5;

“Foreground IPR” means all Intellectual Property Rights in the Consultant Material, IWM Material and/or the Project Material arising as a direct result of and in the performance of this Contract.

“Intellectual Property Rights” means patents, Trade Marks, trade names, design rights, copyright (including rights in computer software and moral rights), performers’ rights, database rights, and other Intellectual Property Rights, in each case whether registered or unregistered and including applications for the grant of any of the foregoing and all rights or forms of protection having equivalent or similar effect to any of the foregoing which may subsist anywhere in the world.

"IWM Material" means all schedules, reports, calculations, correspondence and other documents prepared or provided by IWM to the Consultant; 
"Principal Designer" means the person so named in the Brief or any other person appointed by IWM to perform the functions of Principal Designer under the CDM Regulations for the Project.

"Programme" means the programme for the design, procurement, construction, completion and commissioning of the Project and the individual Phases agreed by IWM and the Consultant contained in schedule 4 as the same may be amended by IWM from time to time in accordance with clause 3.4;

"Project" means the Project described in the Brief;

"Project Material" means all schedules, reports, calculations, correspondence and other documents prepared or provided as a result of the work by the Consultant for or in connection with the Project; 
"Project Team" means collectively the Consultant, the Lead Designer, the Construction Manager, those consultants listed in the Brief and any further or other consultants engaged by IWM in connection with the Project and notified in writing to the Consultant;

"Scheme" means the Scheme for Construction Contracts SI No. 649 of 1998 as amended by SI No. 2333 of 2011;
"Services" means the services set out and referred to in schedule 5 and any additional services instructed by IWM pursuant to clause 0;

"Site" means the site of the Project briefly described in the Brief;

“Third Party IPR” means Intellectual Property Rights, not owned by Parties subject to this Contract and any other consents or permissions acquired by the Architect to fulfil the terms of the Contract.
2.
Consultant's Obligations
2.1.1
The Consultant shall provide the Services upon and subject to the terms of this Contract. The Consultant confirms that it has exercised and that it will continue to exercise in the performance of the Services the reasonable skill, care and diligence to be expected of a project manager and cost consultant holding himself out as having the competence, experience and resources necessary for the proper performance of such Services in connection with a project of a size, scope and complexity similar to that of the Project.

2.1.2
IWM appoints the Consultant to perform the Services in accordance with and subject to the terms of this Contract.

· hidden

2.2
Without prejudice to the generality of clause 2.1, the Consultant further warrants that it will not specify for use in the Project or knowingly allow to be used in the Project products or materials which are generally known within the construction industry to be deleterious at the time of specification in the particular circumstances in which they are used or those identified as potentially hazardous in or not in conformity with:
(a)     the advice guidance and recommendations set out in the report entitled "Good Practice in the Selection of Construction Materials" (2011, published by the British Council for Offices);

(b)     relevant British or European Standards or Codes of Practice; or

(c)     any publications of the Building Research Establishment related to the specification of products or materials,


and that it has used and will continue to use the reasonable skill, care and diligence required by clause 2.1 to see that no such products or materials have been or will be used in the construction of any part of the Project.

2.3
The Consultant shall act as leader of the Project Team in relation to the programming, co-ordination and management of the Project. The Consultant shall, subject to clause 8.1, give such instructions and directions to the other members of the Project Team as may be necessary in relation to such programming, co-ordination and management. 

2.4
The Consultant shall comply at all times with IWM's instructions in relation to the Project.

2.5
The Consultant shall procure that all those for whom it is responsible, when employed within the boundaries of the Site, shall comply with such rules, regulations and requirements of IWM (including those relating to security arrangements) as may be in force for the conduct of personnel at the Site, and have been notified to the Consultant.

3
Client's Brief, Cost Plan and Programme

3.1
The Consultant shall use the reasonable skill care and diligence referred to in clause 2.1 to comply with the Brief.

3.2
The Consultant shall use the reasonable skill care and diligence required by clause 2.1 to perform the Services in accordance with the Programme. If the Consultant is prevented or delayed in the performance of the whole or any part of the Services for any reason (whether arising out of delay, by any Contractor, by the Project Team, by IWM and/or whether amounting to force majeure of otherwise), then the Consultant shall use all reasonable endeavours as soon as practicable to resume and expedite the performance of the Services so as to complete the same with all reasonable speed.

3.3
The Consultant shall use the reasonable skill, care and diligence required by clause 2.1 to perform the Services such that each element of the Project separately identified in the Cost Plan can be constructed within the allowances therefor contained in the Cost Plan. To the extent that any tender for any Trade Contract exceeds the allowances therefore contained in the Cost Plan, the Consultant shall, in conjunction with the Project Team, continue to perform the Services at no cost to IWM in accordance with IWM's Brief so that tenders for the same are within such allowances.

3.4
If the Consultant considers that any amendments should be made to the Programme and/or the Cost Plan at any time, it shall notify IWM accordingly. 

4.
Health and Safety and the Statutory Requirements

4.1
The Consultant shall carry out the Services in accordance with all applicable British Standards and with all the requirements of any directly applicable provision of the EEC Treaty or any EC regulation, any statutory enactment or any regulation, rule or order made pursuant thereto or any regulation or bye-law of any local authority or under and pursuant to any notices served under any such enactment, regulation, rule or order, regulation or bye-law.
4.2

The Consultant shall comply with all the obligations imposed on it as a “designer” under the CDM Regulations insofar as they apply to the Project and shall co-operate with the other members of the Project Team, each Trade Contractor and each Contractor and sub-contractor as necessary to enable them to comply with their respective obligations under the CDM Regulations in relation to the Project.

4.3
The Consultant shall act as Principal Designer for the Project and shall perform the functions and duties of the Principal Designer required and as defined by the CDM Regulations.

4.4
The Consultant shall in the performance of the Services observe the requirements of any codes of practice, guidance notes and recommendations for the time being in force and approved by the Health and Safety Commission or published by the Health and Safety Executive or specified by IWM.

4.5
The Consultant shall in the performance of the Services observe the requirements of the Joint Code on Protection from Fire on Construction Sites and Buildings Undergoing Renovation (current edition) published by the FPA and the RISC Authority. 
5.
variation of Services

5.1
IWM shall be entitled to instruct variations to the timing, programming, nature or scope of the Services (a "Variation") (including without limitation the omission of Services irrespective of whether the omitted Services are to be undertaken by another consultant or contractor engaged by IWM). If an instruction given by IWM constitutes a Variation, the Consultant shall forthwith and prior to performing such Variation give notice to IWM of the same. It is a condition precedent to the Consultant's right to payment under clause 11 that he shall notify IWM prior to commencing additional services, that he intends to seek additional payment and it is a precondition to the Consultant’s obligations to undertake such additional services that IWM has authorised these additional services and their costs.

5.2
The value of any Variation referred to in clause 5.1 shall be agreed as a lump sum between IWM and the Consultant or, failing agreement, shall be a sum calculated by IWM on the basis of any additional time reasonably and properly expended by the Consultant in performing such Variation calculated by IWM on a fair and reasonable basis. The giving of the notice referred to in clause 5.1 shall be a condition precedent to the Consultant's right to payment under this clause 5.2.

5.3
The value of any Variation which constitutes an omission shall be agreed between IWM and the Consultant or, failing agreement, shall be a reasonable sum calculated by IWM. The value of any such Variation shall be deducted from the Fee and the Fee instalments referred to in schedule x shall be adjusted accordingly by IWM acting reasonably. The Consultant shall not be entitled to any payment in respect of loss of profit or opportunity or similar losses incurred by the Consultant due to any such Variation.

5.4
No additional fees or other additional payment shall be payable to the Consultant to the extent that they relate to additional work necessitated, in whole or in part, by any negligence, omission or default on the part of the Consultant, including without limitation any failure to comply with the notification requirements pursuant to this clause 5.

6.
Third parties

6.1
The Consultant acknowledges that IWM may enter into contracts with third parties in connection with the funding of the whole or part of the Project. The Consultant shall have due regard to the obligations owed by IWM to any such third parties under such Contracts to the extent that IWM shall have notified the Consultant of them or provided the Consultant with copies of the same or of the relevant extracts therefrom.

6.2
The Consultant shall, as and when reasonably requested to do so by IWM in writing: 

(a) supply information relating to the Project to; and

(b) have due regard to any observations made by or on behalf of, 


any of the third parties referred to in clause 6.1.

6.3
The Consultant shall so perform the Services as not to put IWM or the Consultant in breach of any of their respective obligations under this Contract.

6.4
The Parties hereby confirm that, notwithstanding any other provision of this Contract, nothing in this Contract is intended to confer on any person any right to enforce any term of this Contract which that person would not have had but for the Contracts (Rights of Third Parties) Act 1999. 
7.
Consultant's Personnel

7.1
The persons named in schedule x or any replacements of them in accordance with clause 7.3 shall carry out the functions respectively allocated to them. The person identified in schedule x as the Partner or Director in charge shall direct and control the overall performance by the Consultant of the Services and such person or any replacement of him in accordance with clause 7.3 shall have full authority to act on behalf of the Consultant for all purposes in connection with this Contract.

7.2
The Consultant shall not remove the persons named in schedule 1 or any replacements of any of them in accordance with clause 7.3 without the prior written consent of IWM which consent shall not be required in case of permanent incapacity, death, sickness or where such person leaves the employment of the Consultant. IWM shall be entitled to require the removal from the performance of the Services of any persons employed by the Consultant whose performance or conduct is, in the reasonable opinion of IWM, unsatisfactory.

7.3
If any of the persons named in schedule x or any replacements of them in accordance with clause 7.3 are removed in accordance with clause 7.2, the Consultant shall replace such person with a person of at least the same experience and expertise whose identity shall be subject to the prior written approval of IWM, which approval shall not be unreasonably withheld or delayed.

7.4
IWM shall have the right (not to be exercised unreasonably or vexatiously) to require the Consultant, at no additional cost to IWM, to appoint additional persons to perform the Services if this is, in IWM's reasonable opinion, necessary for the proper performance of the Services.

7.5
The Consultant is responsible for the ensuring that all their employees and any sub-contractors, agents etc. who are due to work at the Site, for longer than four weeks in duration in the delivery of the Contract, whether in a continuous period, or over the duration of the Contract, have been security vetted to Basic level, as defined by Disclosure Scotland1.
1     Please note that Disclosure Scotland is the agency that all security vetting providers will approach to undertake the security vetting.

7.6 
For a company with a small employee base, IWM will be prepared to undertake the security clearance on behalf of the company, provided that this is made known at the time of the appointment, and that this is agreed by IWM, and that the company agrees to pay the administration charge of £41 per clearance that IWM is charged for this service.
7.7
This requirement will apply to an employee who has not worked at an IWM branch, within the previous 12 months.

7.8   
A minimum of 48 hours before any individual commences work on the Sites, the Consultant is required to complete and submit the Security Notification Form (see Appendix 8) to the Technical Security Manager at IWM London.
7.9
Upon arrival at the Site, each new employee must report individually to the Control Room with a copy of their certificate of proof of vetting, and some form of ID. IWM will note the details of the certificate of proof of vetting, but will not retain any documents.

7.10
IWM will accept a certificate of proof of vetting which is dated within 12 months of the date of their site commencement at IWM, although IWM reserves the right to request they are security vetted, at its discretion, which IWM agrees not to action unreasonably. 

7.11
Failure to comply with this requirement could result in the employee not being granted access to IWM.

8.
Consultant's Authority

8.1
The Consultant shall not, without the prior written approval of IWM (such approval not to be unreasonably withheld): 

(a) make any amendment to the Brief;

(b) make any material alteration to or omission from the design of any part of the Project which has previously been approved or agreed by IWM;

(c) give any approval, or issue any instruction that would cause the period for completion of the Project and/or the commencement or completion dates to be varied;

(d) give any approval, or issue any instruction which would cause any element separately identified in the Cost Plan to increase; or

(e) enter into any contractual or other commitment on behalf of IWM other than those authorised pursuant to clause 8.1.

8.2
No approvals, comments or consents from IWM in connection with the Project shall in any way relieve the Consultant of its obligations under this Contract.

9.
Insurance AND LIMIT ON LIABILITY

9.1
Without prejudice to its obligations, the Consultant shall effect and shall maintain for a period of twelve years from the date of practical completion of the Project under this Contract:
(a) a professional indemnity insurance policy with a limit of indemnity of not less than ten million pounds (£10,000,000) 
(b) a third party/public liability insurance policy with a limit of indemnity of not less than ten million pounds (£10,000,000)
(c) an employer’s liability insurance policy with a limit of indemnity of not less than ten million pounds (£10,000,000)  
for any one occurrence or series of occurrences arising out of any one event in respect of any negligence and/or breach of contract by the Consultant in the performance of the Services, provided always that such insurance is available in the market at reasonable premium rates. Such insurance shall be with a well-established insurance office or underwriter of repute.

9.1.1
Save in relation to death or personal injury the total liability of the Consultant under or in connection with this Contract whether in contract, in tort, in negligence, for breach of statutory duty or otherwise for any claim or series of claims arising out of the same occurrence or series of occurrences shall not exceed £10,000,000. No proceedings shall be commenced against the Consultant following the expiry of twelve years from the date of completion of the Services.

9.1.2
The Consultant is not responsible for advising on matters relating to asbestos, terrorism or pollution and contamination and the Consultant’s liability for issues arising out of such matters is hereby excluded.

9.2
The Consultant shall immediately inform IWM if the insurance referred to in clause 9.1 ceases to be available at reasonable premium rates or if, for any other reason, the Consultant believes that it will be unable to maintain insurance, in order that the means of protecting each Party's respective position in respect of the Project in the absence of such insurance can be discussed.

9.3
As and when reasonably requested to do so by IWM, the Consultant shall produce for inspection documentary evidence to the reasonable satisfaction of IWM that the insurance referred to in clause 9.1 is being maintained.

9.4
Should the Consultant be in breach of any of the provisions of clause 9.1, IWM may insure against any risk with respect to which the breach shall have occurred and may deduct the sum or sums equivalent to the amount paid or payable in respect of premiums from any monies due or to become due to the Consultant under this Contract or recover the same as a debt. ADVANCE \l 43 
10.
IWM's Obligations

10.1
IWM shall, if so requested by the Consultant, supply to the Consultant in such reasonable time as not to delay or disrupt the performance by the Consultant of the Services, any necessary and relevant data and information in the possession of IWM or which may only be obtained by IWM.

10.2
IWM shall give, and shall procure the Project Team give, such assistance to the Consultant as shall reasonably be required by the Consultant in the performance of the Services, provided that any such obligation of IWM shall be without prejudice to the Consultant's obligations under clause 2.3. 

11.
Payment

11.1
IWM shall pay to the Consultant the Fee as agreed and contained in Schedule x for the performance of the Consultant's obligations in accordance with this Contract: 


The Fee is inclusive of all fees, costs, expenses, disbursements and profits which may be incurred by the Consultant in connection with the Services.

11.2
The Fee shall be payable by the instalments set out in schedule x.

11.3
The Consultant shall submit to IWM invoices from time to time as and when any sums become due to the Consultant under this Contract (but not more frequently than monthly). Such invoices shall show both sums due and all sums previously invoiced. Such invoices shall be supported by such evidence as may reasonably be required to prove that the sums shown on them are properly due and payable. The Consultant’s invoice shall be the “payment notice” required by Section 110A(1) of the Construction Act.
11.4
If IWM intends to pay less than the amount specified as due in any invoice submitted by the Consultant in accordance with Clause 11.3, he shall give to the Consultant a notice of his intention to do so, specifying the sum that he considers to be due to the Consultant as at the date such notice is given and the basis on which such sum has been calculated.  Such notice (which shall be the “pay less” notice referred to in Section 111(3) of the Construction Act) shall be given not later than three days before the final date for payment of each invoice under clause 11.5.

11.5
IWM shall pay the Consultant the amount specified as due in any invoice submitted by the Consultant in accordance with clause 11.3, or if less, the amount specified in IWM’s notice under clause 11.4, on or before the final date for payment which shall be 30 days from receipt of invoices in accordance with clause 11.3.

11.6
IWM shall pay to the Consultant the total amount of value added tax properly chargeable on the supply to IWM of any goods or services under this Contract upon receipt of a tax invoice in accordance with regulations 13 and 14 of the Value Added Tax Regulations 1995 or any amendment or re-enactment thereof.
11.7
Where any amount due under this Contract is not paid in full by the final date for payment of each invoice under clause 11.5 and no effective notice is given under clause 11.4, the Consultant shall be entitled (without prejudice to any other right or remedy) to suspend performance of its obligations under this Contract by giving not less than seven days' notice to IWM stating the ground or grounds on which it is intended to suspend performance. The right to suspend performance shall cease when IWM makes payment in full of the amount due and any period during which performance is validly suspended pursuant to clause 11.7 shall be disregarded in computing the time taken by the Consultant to complete any of the Services affected by the suspension.

11.8
The Consultant shall ensure that the same terms and conditions as stated in clause 11, regarding payment of invoices, is included, verbatim, excluding the use of appropriate terminology, in any contract entered into by the Consultant, with any sub-consultant, supplier etc. in their fulfilment of this Contract.  
11.9
Failure by the Consultant to fully comply with Clause 11.8, will be considered a breach of the Contract, and subject to the remedies as identified in Clause 14.
12.
Copyright and Confidentiality


Consultant Material

12.1
Copyright in the Consultant Material shall remain vested in the Consultant, but the Consultant hereby grants to IWM an irrevocable, royalty-free, non-exclusive licence to copy and use the Consultant Material for any purpose whatsoever relating to the Project including, but without limitation, the construction, completion, reconstruction, reinstatement, modification, extension, maintenance, repair, mortgaging, letting, sale, promotion, advertisement or use of the Project. IWM shall be entitled to grant sub-licences to others in relation to the Consultant Material. The Consultant shall not be liable to IWM or any sub-licensee, for any use of the Consultant Material for any purpose other than that for which the same was prepared or provided by the Consultant.

12.2
The Consultant warrants that all Intellectual Property Rights in the Consultant Material is owned by the Consultant, or in the case of Third Party IPR is licensed to the Consultant for use in the Consultant Material, and that the Consultant Material does not infringe the Intellectual Property Rights of any third party.

12.3  
The Consultant agrees that IWM shall have no liability and the Consultant shall indemnify, defend and hold IWM harmless against any and all damages, liabilities, claims, causes of action, legal fees and costs incurred by IWM in defending against any third-party claim of Intellectual Property Rights infringements or threats of claims thereof with respect of IWM’s or any use of the Consultant Material, provided that: 

(a) the use of the Consultant Material has been in full compliance with the terms and conditions of this Contract; 

(b) IWM provides the Consultant with prompt notice of any such claim or threat of claim; 

(c) the Consultant has sole and complete control over the defence or settlement of such claim.
IWM Material

12.4
Copyright in IWM Material shall remain vested in IWM, but IWM hereby grants the Consultant a revocable, royalty-free, non-exclusive licence to copy and use IWM Material for any purpose whatsoever relating to the Project only. The Consultant shall be entitled to grant sub-licences to others in relation to IWM Material, only in relation to any purpose relating to the Project. IWM shall not be liable to the Consultant or any sub-licensee, for any use of IWM Material for any purpose other than that for which the same was prepared or provided to the Consultant.

12.5
IWM warrants that all Intellectual Property Rights in IWM Material is owned by IWM, or in the case of Third Party IPR is licensed to IWM for use in IWM Material, and that IWM Material does not infringe the Intellectual Property Rights of any third party.

12.6  
IWM agrees that the Consultant shall have no liability and IWM shall indemnify, defend and hold the Consultant harmless against any and all damages, liabilities, claims, causes of action, legal fees and costs incurred by the Consultant in defending against any third-party claim of Intellectual Property Rights infringements or threats of claims thereof with respect of the Consultant’s use of IWM Material, provided that: 

(d) the use of IWM Material has been in full compliance with the terms and conditions of this Contract; 

(e) the Consultant provides IWM with prompt notice of any such claim or threat of claim; 

(f) IWM has sole and complete control over the defence or settlement of such claim.
Project Material

12.7
Copyright in the Project Material shall remain vested in IWM, but IWM hereby grants to the Consultant a revocable, royalty-free, non-exclusive licence to copy and use the Material for any purpose whatsoever relating to the Project only. The Consultant shall be entitled to grant sub-licences to others in relation to IWM Material, only in relation to any purpose relating to the Project. IWM shall not be liable to the Consultant or any sub-licensee, for any use of IWM Material for any purpose other than that for which the same was prepared or provided to the Consultant.

12.8
Both Parties warrants that all Intellectual Property Rights in the Project Material is owned by the Party responsible for the development of the Project Material, or in the case of Third Party IPR is licensed for use in the Project Material, and that the Project Material does not infringe the Intellectual Property Rights of any third party.

12.9  
In respect of Project Material, the Party responsible for the development of the Project material (“the Draftee”) agrees that the other Party (“the Recipient”) shall have no liability and the Draftee shall indemnify, defend and hold the Recipient harmless against any and all damages, liabilities, claims, causes of action, legal fees and costs incurred by the Recipient in defending against any third-party claim of Intellectual Property Rights infringements or threats of claims thereof with respect of the Recipient’s use of the Project Material, provided that: 

(g) the use of the Project Material has been in full compliance with the terms and conditions of this Contract; 

(h) the Recipient provides the Draftee with prompt notice of any such claim or threat of claim; 

(i) the Draftee has sole and complete control over the defence or settlement of such claim.
12.10
The Consultant shall not during its engagement hereunder (save to essential employees in the proper course of their duties), or at any time after its expiry or termination for any reason disclose to any person any information relating to this Contract or the Project (including but without limitation the identity of any potential purchaser or tenant of the Project or part thereof) unless and until such information becomes public knowledge through no fault of the Consultant. The Consultant shall use reasonable endeavours to ensure that any persons having access to such information are aware of these obligations.

12.11
The Consultant shall not, without the prior written approval of IWM (not to be unreasonably withheld or delayed), take or permit to be taken any photographs of the Project for use in any publicity or advertising or publish alone or in conjunction with any other person, any articles, photographs or other illustrations relating to the Project or any part thereof. The Consultant shall not without the approval of IWM (not to be unreasonably withheld or delayed) impart to any publication, journal or newspaper or any radio or television programme any information regarding the Project.

12.12
IWM shall, wherever in its discretion it considers the same to be appropriate, endeavour to identify the Consultant as being the author of the Consultant Material and/or the Project Material.

13.
Assignment and Sub-Contracting

13.1
The Consultant shall not, without the prior written consent of IWM, assign, transfer or sub-contract to any person the performance of any of the Services or all or any of its rights or obligations under or pursuant to this Contract.

13.2
IWM, provided that the same shall in no way limit the Consultant's obligations hereunder, hereby consents to the appointment of (details to be inserted subject to tender return).

The Consultant shall:
(a) procure that it enters into an appointment with a sub-consultant on substantially the same terms as this Contract and shall provide a copy of the sub-consultant appointment on execution of the same by the Consultant and the sub-consultant;

(b) not, in respect of the sub-consultant, omit or vary the scope of services or amend, rescind or terminate the appointment or waive the Consultant's rights thereunder without IWM's prior written consent, such consent not to be unreasonably withheld or delayed.
13.3
The Consultant hereby consents to any assignment or transfer by IWM at any time of all or any of its rights under or pursuant to this Contract subject to the Consultant being subsequently notified of such assignment.

13.4
Subject to clause 13.3 IWM may not, without the prior written consent of the Consultant, such consent not to be unreasonably withheld or delayed, assign or transfer any obligation under this Contract.

14.
Termination and Suspension

14.1
IWM may terminate or suspend the Consultant's engagement under this Contract at any time forthwith by notice in writing to the Consultant.

14.2
If either Party fails to discharge their duties under this Contract, or is shall be in material or persistent breach of its obligations under this Contract and shall fail to remedy the same within ten working days of receiving a notice from the other Party specifying the breach and requiring its remedy, then the initiating Party shall be entitled forthwith by notice in writing to other Party to terminate its engagement under this Contract.

14.3
If, following a suspension of the Services under clause 14.1, IWM shall not have required the Consultant to resume performance of the Services under clause 14.6 within six calendar months of the date of the suspension, then the Consultant may thereafter forthwith by notice in writing to IWM terminate its engagement under this Contract.

14.4
Upon any termination or suspension of the Consultant's engagement under this Contract, the Consultant shall take immediate steps to bring to an end the Services in an orderly manner, but with all reasonable speed and economy. The Consultant shall also deliver to IWM within ten working days of any such termination or suspension all of the Material prepared by or in the course of preparation by the Consultant or in the Consultant's possession relating to the Project.

14.5
Without prejudice to IWM's rights in respect of any breach by the Consultant of its obligations under this Contract, IWM shall in accordance with clause 11, pay to the Consultant any sums which have accrued due to the Consultant up to the date of termination or suspension together with a proportion of the next following instalment of the Fee, commensurate with the Services properly performed up to the date of termination or suspension. No termination or suspension of the Consultant's engagement under this Contract shall render IWM liable to the Consultant for any claim for loss of profit, loss of fees or other similar losses.

14.6
Following a suspension of the Services under clause 14.1, IWM may at any time require the Consultant to resume the performance of the Services in accordance with this Contract and any payments made under clause 14.5 shall be treated as payments on account of the Fee.

14.7
The Consultant shall notify IWM immediately if the control of the Consultant passes to another company. IWM may terminate this Contract (in whole or in part) by notice in writing with immediate effect within six (6) months of:

(a)     being notified that a change of ownership has occurred; or

(b)     where no notification has been made, the date that IWM becomes aware of the change of ownership,

but shall not be permitted to terminate where express prior written approval was issued by IWM which accepted the change of ownership.

15.
General

15.1
The addresses for service of the Parties shall be those set out in Schedule x or subsequently notified in accordance with this clause 15.1. Any notice required to be given by either Party shall be in writing and service shall be effected either: 

(a) personally, in which case service shall be deemed effective on delivery; or

(b) by pre-paid recorded delivery post, in which case service shall be deemed effective two working days after the day after posting.

hidden

15.2.1
The Consultant shall not:

(a) offer, or give, or agree to give to any person in the service of IWM any gift or consideration of any kind as an inducement or reward for doing or forbearing to do; or for having done or forborne to do any act in relation to the obtaining or execution of this or any other contract for IWM's service or for showing or forbearing to show favour or disfavour to any person in relation to this or any other contract for the service of IWM, or;

(b) enter into this Contract in connection with which commission has been paid or has been agreed to be paid by the Consultant, or on the Consultant's behalf or to the Consultant's knowledge, unless before entering into the Contract it disclosed the particulars of any such commission and of the terms and conditions of any Contract for the payment thereof in writing to IWM.

15.2.2
Any breach of this clause by the Consultant or by anyone employed by the Consultant acting on the Consultant's behalf (whether with or without the knowledge of the Consultant) or by anyone employed by them or acting on their behalf under the Bribery Act 2010, the Prevention of Corruption Acts, 1889 to 1916, or any updated or related legislation, in relation to this Contract for IWM's service shall entitle IWM to determine the Consultant's appointment under this Contract and recover from the Consultant the amount of any loss resulting from such determination and/or to recover from the Consultant the amount or value of any such gift, consideration or commission.
15.3
The Consultant acknowledges that IWM is subject to the requirements of the Freedom of Information Act (“FOIA”) and the Environmental Information Regulations (“EIRs”). The Consultant shall, at its own expense, assist and cooperate with IWM to enable IWM to comply with its information disclosure obligations. 

15.4
Where the Consultant holds on behalf of IWM information that is subject to the FOIA and EIR, the Contractor shall and shall procure that its sub-contractors shall:

(a) transfer any request for information received by the Consultant to IWM as soon as practicable after receipt and in any event within two working days of receiving a request for information;

(b) provide IWM with a copy of all information in its possession, or power in the form that IWM requires within five Working Days (or such other period as IWM may specify) of IWM’s request; and, 

(c) provide all necessary assistance, as reasonably requested by IWM to enable IWM to respond to the request for information within the time for compliance set out in section 10 of the FOIA or Regulation 5 of the EIRs. 

15.5
IWM shall be responsible for determining in its absolute discretion and notwithstanding any other provision in this Contract or any other contract whether the Commercially Sensitive Information and/or any other Information is exempt from disclosure in accordance with the provisions of the FOIA or the EIRs. 

15.6
The Consultant shall only respond to a request for information unless this has been submitted by a nominated representative of IWM. 

15.7
The Consultant acknowledges that IWM may, acting in accordance with the Secretary of State for Constitutional Affairs Code of Practice on the Discharge of the Functions of Public Authorities under Part 1 of the Freedom of Information Act 2000 (“the Code”), be obliged under the FOIA, or the EIRs to disclose information concerning the Contractor or the Services in certain circumstances: 

(a) without consulting the Consultant; or 

(b) following consultation with the Consultant and having taken their views into account, 

provided always that where clause 15.7(a) applies IWM shall, in accordance with any recommendations of the Code, take reasonable steps, where appropriate, to give the Consultant advanced notice, or failing that, to draw the disclosure to the Consultant’s attention after any such disclosure. 

15.8
The Consultant shall ensure that all Information is retained for disclosure and shall permit IWM to inspect such records as requested from time to time. 

15.9
The Consultant acknowledges that the [Commercially Sensitive Information listed in the Commercially Sensitive Information Schedule] is of indicative value only and that IWM may be obliged to disclose it in accordance with this clause 15.

15.10
Any dispute or difference arising under or in connection with this Contract may be referred to adjudication in accordance with the following provisions: 

(a) the Scheme shall apply;

(b) the Adjudicator shall be Christopher Miers of Probyn Miers or such other person as may be appointed from time to time under clause 15.10 to act as Adjudicator in place of the Adjudicator so appointed
(c) the Adjudicator's decision is binding until the dispute or difference is finally determined by the courts;

(d) the Adjudicator shall not be liable for anything done or omitted in the discharge or purported discharge of his functions as Adjudicator unless the act or omission is in bad faith, and any employee or agent of the Adjudicator is similarly protected;

(e) if the Adjudicator fails to give his decision in accordance with the provisions of paragraph 20 of the Scheme for Construction Contracts, all disputes or differences  shall be referred to and settled by a person to be appointed in accordance with the provisions of paragraph 2(1)(b) of the Scheme by the Royal Institution of Chartered Surveyors;

(f)     notwithstanding the fact that the Adjudicator may have acted or may be acting as adjudicator in relation to a dispute or difference that raises issues which are substantially the same as, or connected with issues raised in any dispute or difference referred to the Adjudicator under this Contract, neither IWM nor the Consultant shall object to the Adjudicator adjudicating on the dispute or difference referred to him under this Contract.

15.11
Disputes and differences between the parties arising out of or in relation to this Contract shall, subject to clause 15.10, be referred to the exclusive jurisdiction of the English courts. This Contract shall be governed by and construed in accordance with English law.

15.12
This Contract supersedes any previous contracts between the Parties in respect of the Services. Notwithstanding the date of this Contract, the Consultant's engagement hereunder shall take effect from the date when the Consultant first commenced performance of the Services in respect of the Project.

15.13
No variation in the terms of this Contract after the date hereof shall be effective unless contained in a written memorandum signed by the Parties.

15.14
Any reference to a statute or section of a statute includes any statutory amendment or modification or re-enactment of it for the time being in force and every instrument order notice direction regulation bye-law permission or condition being made or issued under it or deriving validity from it from time to time.

15.15
For the purposes of this Contract, where an act is required to be done within a specified period or from a specified date, the period begins immediately after that date. Where the period would include Christmas Day, Good Friday or a day which under the Banking and Financial Dealings Act 1971 is a bank holiday in England and Wales, that day should be excluded.

15.16
Neither Party shall be liable for any failure or delay in performing any of its obligations hereunder if such failure or delay is caused by the occurrence of an event of force majeure.

15.17
No whole or partial waiver of any breach of this Contract shall be held to be a waiver of any other or any subsequent breach. The whole or partial failure of either party to enforce at any time the provisions within this Contract shall in no way be construed to be a waiver of such provisions nor in any way affect the validity of this Contract or any part of it, or the right of either Party to enforce subsequently each and every provision.

15.18
If any part of this Contract is found by a court of competent jurisdiction or other competent authority to be invalid, unlawful or unenforceable then such part will be severed from the remainder of this Contract, which will continue to be valid and enforceable to the fullest extent permitted by law. In the event of a holding of invalidity so fundamental as to prevent the accomplishment of the purpose of the Contract, the Parties shall promptly commence good faith negotiations to remedy such invalidity.

15.19
This Contract is the complete and exclusive statement of the Contract between the Parties relating to the subject matter of this Contract which supersedes all previous communications, contract and other arrangements, written or oral.

15.20
The Parties hereto are independent organisations, and nothing herein contained shall constitute to create a partnership, agency or joint venture between the Parties.

16.
Anti-Bribery
16.1
The Consultant is aware of IWM’s obligation to comply with the anti-bribery rules relevant to the contracting parties, and represents that it will not use money or other consideration, paid by IWM for unlawful purposes, including purposes violating anti-bribery laws including the Bribery Act 2010, such as make or cause to be made direct or indirect payments to any public official in order to assist IWM or any group member organisation or anyone acting on their behalf in obtaining or retaining business with, or directing business to, any person, or securing any improper advantage.

16.2
The Consultant hereby declares that:

(a) its members, officers, owners or employees are not public officials;

(b) it does not and will not employ or otherwise compensate any public officials or make or cause another to make any direct or indirect offers of payments to any public officials, for the purpose of influencing or inducing any decision for the benefit of IWM and it will not employ any sub-consultant, consultant, agent or representative in connection with this Contract without a documented examination of his person, reputation and integrity, and;

(c) it will not employ any sub-consultant, consultant, agent or representative who does not comply with the anti-corruption rules and if such a violation comes to its attention to inform IWM immediately.

16.3
IWM may immediately terminate this Contract if the Consultant violates any of the anti-corruption laws and the provisions as defined in this clause.

16.4
The Consultant agrees to comply fully with all applicable anti-bribery laws, including those in the jurisdiction where they are registered and the jurisdiction where the relevant contract will be performed (if different), and to comply with IWM’s Anti-Bribery Policy. 
16.5
The Consultant agrees that all payments made to the Consultant will be made only after receipt by IWM of a detailed and accurate invoice supported by detailed records. IWM will make all payments under this Contract in Pounds Sterling, only by bank transfer to the account of the Consultant at a financial institution within the United Kingdom.

16.6
The Consultant agrees to keep accurate books, accounts, records and invoices and agrees that IWM is entitled, with the help of outside auditors if it deems necessary, to audit all books, accounts, records and invoices and accompanying documentation of the Consultant for compliance with any applicable anti-bribery laws and that the Consultant will cooperate fully in any such audit.

16.7
The Consultant’s failure to comply with all applicable anti-bribery laws or IWM’s Anti-bribery Policy will be deemed to be a material breach of the Contract entitling IWM to terminate the Contract. In the event the Consultant will surrender any claim for payment under the Contract including payment for services previously performed.

16.8
IWM may also terminate the Contract or suspend or withhold payment if it has a good faith belief that the Consultant has violated, intends to violate, or has caused a violation of any anti-bribery laws. IWM will not be liable for any claims, losses or damages arising from or related to failure by the Consultant of the Contract under this clause, and the Consultant will indemnify and hold IWM harmless against any such claims, losses or damages.  
IN WITNESS whereof this Contract has been executed as a deed and delivered on the date first above written.

	Signed on behalf of the Trustees of the Imperial War Museum
	
	Signed on behalf of the Consultant


	Signed
	
	
	Signed
	

	Name


	
	
	Name
	

	Title


	
	
	Title
	

	Date
	
	
	Date
	

	
	
	
	
	

	Signed on behalf of the Trustees of the Imperial War Museum
	
	
	

	
	
	
	
	

	Signed

	
	
	
	

	Name


	
	
	
	

	Title


	
	
	
	

	Date
	
	
	
	

	
	
	
	
	


Variation Notice
VARIATION TO CONTRACT
Contract Title:  Project and Cost Consultant: All Saints New Build Accommodation, Transforming IWM London
Contract Ref:
IWM/SPG/1660
Variation no:

Date:
 
Between:

	The Trustees of the Imperial War Museum (hereinafter called “IWM”) and xxxx (hereinafter called “the Consultant”)


1.
The Contract is varied as follows: 

	Details of Variation:
.


	Variation effective from:             



1
 2.
Words and expressions in this Variation shall have the meaning given to them in the Contract.

3.
The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

SIGNED:

	For:
IWM

	For:
Consultant

	By:


	By:



	Full Name:


	Full Name:



	Position:


	Position:




Appendix 2 – Map of All Saints Building
This plan is provided as a separate document but can be accessed by clicking on the attached hyperlink.
20170313_All Saints location plan.pdf
Appendix 3 – Programme

This plan is provided as a separate document but can be accessed by clicking on the attached hyperlink.

20170317_draft programme.pdf
Appendix 4 – Client Brief

Brief for a new Corporate Headquarters

Ambition
The aim of this project is to change the way that we work.  In 2015, IWM reorganised itself into three directorates – Collections and Governance, Commercial Services and Operations and Content and Programmes. Staff now operate across all five museum sites and with colleagues across directorates, both operationally and on a range of projects.  However, our current accommodation does not make this collaboration easy. In London where most of the corporate teams are based, staff are spread across two/three sites and in accommodation organised to reflect previous structures. To make our new structure work effectively we want to create an exceptional corporate hub within a new build at our All Saints site in London (the current All Saints building will be used for other purposes).  Excellent accommodation which co-locates teams and provides an environment which encourages interaction, relationship building and shared thinking and problem solving is vital to the future of IWM’s business.   
Objectives
These have been arranged under our three strategic objectives:
Prioritise our audiences
· Modernise the working environment for staff to encourage collaboration, innovation  and creativity as well as efficient working (it should be a good place to work)
· Create a corporate hub which provides a welcoming and professional environment for visitors and stakeholders

Increase our financial sustainability
· Create a sustainable corporate hub which provides good value in terms of construction, best use of space and operation, and which can evolve with minimal cost to meet the changing needs of IWM over the next 20-30 years

· Relocate staff to release the existing All Saints building for commercial development
· Consider how the new build can also generate a revenue stream, e.g. from the commercial hire of conference rooms/meeting rooms
Deliver effective stewardship of our collection
· Rationalise the museum archive material retained within the new build
Location (see location plan in Appendix 2)
· The All Saints site is located in Austral Street, London SE11. It is close to Elephant and Castle in the NW of the London Borough of Southwark, close to the boundary with London Borough of Lambeth. 

· The site is currently occupied by the All Saints building which was erected in the 1870s as an orphanage and was later converted into a hospital. Since the 1980s this building has been an annexe to IWM and is used as its headquarters building. The site for the new build sits directly behind the All Saints building. 

· The site is surrounded by residential properties and the Geraldine Mary Harmsworth Park and falls into the West Square conservation area.

· It is just a short walk across the park from IWM London (122m) so it is easy for staff to move between the two sites and also between our other London sites, Churchill War Room and HMS Belfast.  
· The site of proposed new build is currently an open yard with two portakabin buildings and some storage containers.  There are four mature trees and a sub-station. 
· Vehicle and pedestrian access to the site is from Austral Street.  Staff can also access the rear of the site through the park.  Vehicle access via the park is possible but limited.  

· It is approximately 1219.5 sq.m.
· Planning permission was granted for an extension to the All Saints building in 1995, and renewed in 2000 but was never implemented. As a result we hold some information about the site, e.g. archaeological report, planning documents.
Requirements of new build 

Adjacencies and zoning
· Create a new corporate HQ and relocate 100 staff based in the existing All Saints building and another 100 from IWM London 

· Establish optimum occupancy levels.  Average occupancy levels were low before the restructure and observation suggests that they have shrunk further still.
· Create adjacencies with more shared and less owned spaces.  
· Zone spaces – work, support and back of house 
· Good communal spaces and support facilities, e.g. changing/shower facilities will be vital to the success of these new offices.
Design, environment and connectivity 

· Design should be simple, elegant and appropriate to the location

· Light and airy – good cooling and heating, ideally using good building design rather than lots of mechanical plant. 

· Sustainable, maximise energy efficiency and to minimise and reduce energy consumption and CO2 emissions.  We will need to meet BREAAM excellent.
· Step free access.  Lifts and stairs between floors and circulation/accessible for staff and visitors with a range of disabilities.
· Digitally enabled

· Decent external space for staff to use with parking for two-three vehicles and cycle rack provision

Operation and servicing
· Low cost in terms of running and maintenance – it should not add to our bottom line

How do we want to work?

On appointment, we will work closely with the PM/Cost Consultant to refine the brief and appoint the right design team to create this new accommodation. The process below relates to the design development and build process.

Part 1
· Appoint design team

· Consultation with Executive and Senior Management teams and with staff and the teams who will be operating the building
· Options appraisal and business case including lifecycle costs

Part 2
· Design of preferred option
· Procurement 

· Construction and fit out

· Handover  and occupation

Timeline
Part 1 – spring-summer 2017 

Part 2 – autumn 2017-end 2019
Cost
We have a limited budget of £4m (see main tender documents in terms of what this covers) and solutions must offer us value for money both in terms of construction and operation.

Appendix 5 – Questionnaire

	Company Questionnaire – Project & Cost Consultant: All Saints Mew Build Accommodation: Transforming IWM London

	All information supplied will be treated as strictly private and confidential and will not be divulged to any other parties other than those directly involved in the project.

	

	Section 1 – General Company Information

	1  Name of Company:



	2  Registered Office Address:



	3  Company Registration Number:



	4  Year of Registration:



	5  Telephone No:



	6  E-mail Address:



	7  Nature of Business and Range of Services:



	8  Please indicate, if applicable, any subsidiary companies run by your company:



	9 If part of a group, please indicate the details of the ultimate holding company:



	10 VAT Registration No:



	11 Address of Office to support the Contract:

	12 Please illustrate diagrammatically, the structure of your company, showing the inter-relationships with other members of the group, and how the management of this contract fits into the company’s management structure:



	Section 2: Staffing/Management

	13 Please identify the number of staff employed. Please indicate numbers of full-time and part-time staff:

· Director(s):

· Managers:

· Technical:

· Administration:

·    Operations:

	14 Annual Staff Turnover (in percentage format):

	15 Name of Employee responsible for the management of the Contract:

	16 Please submit your project team structure for the delivery & management of the Contract, inclusive of the full CV’s for each team member identified?

	17 Please identify whether you plan to use any sub-contractors to deliver any services within the Contract. If so, please:

· identify those services that would be undertaken by the sub-contractor(s)?;

· the name of any nominated sub-contractor(s)?, and;

· your methodology of appointment and management of  the sub-contractor(s)?

	Section 3: Financial/Banking

	18 Please attach one copy of your last three years of audited accounts. This must   include both your Profit & Loss Accounts and your Balance Sheets.

	19 If part of a group of companies, please attach one copy of their last three years of audited accounts. Again, to include Profit & Loss accounts and Balance Sheets.

	Section 4: Policy/Procedures

	20 If you are registered under BS5750/ISO 9000 or any other scheme, please provide a copy of your registration certificate and a summary of your Quality Management (QM) procedures.

	21 Please provide copies of the following policies:

· your outline health & safety policy

· your outline environmental policy, inclusive of your sustainability policy

· your equal opportunities policy



	22 Please complete the following with regards to your company’s insurance policies:

      Professional Liability (to £10m): 

      Policy No:

      Expiry Date:

      Limit of Indemnity:

      Third Party/Public Liability (to £10m): 

      Policy No:

      Expiry Date:

      Limit of Indemnity:

      Employer’s Liability (to £10m): 

      Policy No:

      Expiry Date:

      Limit of Indemnity:

Please include a copy of the insurance certificate for each policy.

	23 Have you been prosecuted under any relevant health & safety legislation in the last five years? If the answer is Yes, please provide details of the incidence and the outcome.

	24 Have you been prosecuted under any relevant employment legislation in the last five years? If the answer is Yes, please provide details of the incidence and the outcome.

	25 Do you have a Business Continuity Plan (BCP), or equivalently titled document? If so;

· what are the key risks and what are the control mechanisms in place?;

· how often and to what extent is the BCP tested?;

· how is the BCP managed and reviewed by your Board of Directors?

	26 Please provide a statement of assurance that you are committed to counter bribery, and please advise of any cases or convictions for bribery made against the company? 

	Section 5 - References

	27 Please provide summaries (no more than two sides per project) of similar current or recent projects where you have provided similar services


[image: image2.png]IMPERIAL MUSEUMS



Appendix 6
Confirmation of Fee Offer
To: 

The Trustees of the Imperial War Museums



Lambeth Road



London



SE1 6HZ

Dear Sirs,

Tender –   (Contract No: IWM/SPG/1660)
I/We having read the tender documentation issued in relation to the above tender, do hereby confirm that the fee for the delivery of the Services is:

Fee (written): 

Fee (numerical): 

All Fees are exclusive of VAT.

I/We undertake in the event of your acceptance to execute with you a Contract upon the terms and conditions of contract as included within IWM’s tender documentation.

I/We understand that IWM does not bind itself to accept the lowest or any tender and that neither he, not his professional advisors, are responsible for paying the tendering costs incurred by the lowest of any tenderer.

I/We agree that this Tender remain open for consideration by IWM until 30 June 2017.
Sign:



............................................................................................

Name:



............................................................................................

Date: 



............................................................................................

In the capacity of: 

............................................................................................

Name of Company: 

............................................................................................
Appendix 7
Confidentiality Agreement

CONFIDENTIALITY AGREEMENT

To: Head of Procurement & Compliance, IWM

	Contract No
	IWM/SPG/1660

	Contract Title: 
	Project and Cost Consultant: 
All Saints New Build Accommodation 
Transforming IWM London


1 In consideration of IWM supplying information relating to the Project and Cost Consultant: All Saints New Build Accommodation: Transforming IWM London (“the Confidential Information”) solely for the purpose of enabling us to develop a Contract (“the Permitted Use”), we hereby confirm to you that we shall exercise all reasonable skill and care (without prejudice to any rights which we may have at law in connections with the Confidential Information) that we agree that:

(a) we shall hold the Confidential Information at all times in strict confidence and under conditions of secrecy, and we shall take all necessary steps to preserve confidentiality;

(b) we shall disclose the Confidential Information only to our directors, officers and employees as is strictly necessary for evaluating the Confidential Information and we shall procure that such persons are aware of and shall comply with the terms of this Confidentiality Agreement and we shall be responsible for any breaches by such persons;

(c) we shall not use the Confidential Information for any purpose other than the Permitted Use;

(d) we may only disclose the Confidential Information, without prior consent, to any third party, to enable the facilitation of the scope of works of this Confidentiality Agreement (including for the purposes of consulting legal/insurance advisors);

(e) we shall not mix, add, merge, combine, store or amalgamate (including without limitation store on or add to hard or soft disk) any of the Confidential Information with any other information, material or intellectual property except for the Permitted Use. In the event of any mixture, merger, addition, combination, storage or amalgamation of the Confidential Information contrary to the terms of this Confidentiality Agreement, then the product of such process shall become your exclusive property;

(f) we shall upon your oral or written request at any time return to you forthwith by such means as you may specify all Confidential Information supplied to us, all material prepared by us which uses or incorporates any of the Confidential Information, any material on which any such information is recorded or stored and all copies thereof and all such information on hard disk upon shall be irretrievably and permanently erased and any soft disk upon which such information is stored or recorded shall be delivered and become your property;

(g) we shall not make any statement or announcement to any customers, representatives of the Press, competitors or any third parties about any arrangements contemplated between us without your prior written consent; and 

(h) we confirm that the expression “Confidential Information” includes all such information (if any) relating to the idea described above as we may have disclosed to you already.

2 Subject to paragraph 3 below, the above limitations on use and disclosures shall not apply to information which is known to us before receipt thereof from you (unless such information was then disclosed in confidence);

(a) is learned from a third party entitled to disclose it;

(b) becomes known publicly other than through disclosures by us;

(c) is authorised in writing by you to be released.

3 Nothing in this Confidentiality Agreement shall be constructed as a grant of rights to us in the confidential information nor as placing you under any obligations to grant us future rights in the Confidential Information in any subsequent agreement.

4 Our obligations under this Agreement shall survive any termination of any existing or future agreement between us whether or not that agreement relates in any way to the Confidential Information.

5 Without prejudice to any other rights or remedies that you may have, we acknowledge and agree that damages alone would not be an adequate remedy for any breach by us of the provisions of this Confidentiality Agreement and, accordingly, you shall be entitled without proof of special damage to the remedies of injunction, specific performance and other equitable relief for any threatened or actual breach of the provisions hereof by us.

6 Any notice or other communication under this Confidentiality Agreement shall (unless otherwise specified in this Confidentiality Agreement) be in writing and may be sent by post. A notice sent by post shall be deemed to have been delivered on the third day after posting and in proving service it shall be sufficient to prove that the envelope containing the notice was properly addressed, prepaid and posted.

7 In the event that it is determined in any legal proceedings before a competent tribunal, that any paragraph, or part of any paragraph of this Confidentiality Agreement is invalid, illegal, or unenforceable, such paragraph or part thereof shall be deemed to be severed from this Confidentiality Agreement and the remainder of this Confidentiality Agreement shall continue in full force and effect.

8 No failure or delay by either party in exercising any right, power or privilege available under this Confidentiality Agreement shall operate as a waiver thereof.

9 This Confidentiality Agreement is personal only to the parties to it, and shall be governed in all respects by the laws of England and may only be amended with the written consent of both parties and each party submits to the non-exclusive jurisdiction of the English courts.

Signed on behalf of (insert your company name):

	Signed by:
	

	Print Name (in Block Capitals)
	

	In capacity of:
	

	Date
	


Appendix 8
STAFF SECURITY CLEARANCE





NOTIFICATION FORM
CONTRACTOR:

	Level of CRB

	IWM Branch
	Start Date
	Staff Name
	Basic
	Standard
	Enhanced

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	


	Signed
	

	Name
	

	Job Title
	

	Date
	


Please complete all sections of the Form and forward to IWM’s Technical Security Manager at jpawley@iwm.org.uk or addressed to Technical Security Manager, CWR, Clive Steps, King Charles Street, London SW1A 2AQ, a minimum of 48 hours prior to the individual(s) commencing work at IWM.







