VARIATION TO CONTRACT FORM

CONTRACT TITLE: Customer response to pre-population

CONTRACT REF: 15-16 EC.01      VARIATION No:	1	DATE: 23/12/15

BETWEEN:

The Commissioners of HM Revenue & Customs (hereinafter referred to as “the Client”) & (IFF research) (hereinafter referred to as “the Contractor”)

1.	The Contract is varied as follows:

# Description of Variation The research with Self Assessment customers will not go ahead. This means cancellation of 30 planned interviews and associated analysis and reporting. 5 additional interviews will be carried out with BBSI customers (bringing the total to 25 from the originally planned 20). Revised project costs: Milestones - revised; Milestone date; Value. Project set-up and draft opt-out letter; 1st December; 1,283. Development and sign-off of BBSI/SA screeners and topic guides for BBSI, first 50% of BBSI fieldwork and delivery of interim findings; 20th February; 12,898. Completion of final 50% of BBSI fieldwork and analysis, and delivery of findings presentation; 20th March; 14,731. Final report; 12th April; 4,163. * - The anticipated delivery date is not a fixed invoice point. Payment is made upon satisfactory receipt of services, certified by the Project Manager.; Grand Total (£); 33,075. Details of any further documentation appended None. Effect of Variation on previous documentation 1. Words and expressions in this Variation shall have the meanings given to them in the Contract. 2. The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

SIGNED:

| For: The Client | For: The Contractor |
| --- | --- |
| By: | By: |
| Full Name: | Full Name: Angus Matthew Tindle |
| Title: | Title: Director, IFF Research Ltd. |