# Joint Schedule 2 (Variation Form)

This form is to be used in order to change a contract in accordance with Clause 24 (Changing the Contract)

| Contract Details |  |  |
| --- | --- | --- |
| This variation is between: | The Department for Education ( “the Buyer") And PA Consulting Services Ltd ("the Supplier") |  |
| Contract name: | # Project_7840 SEND Change Programme- Delivery Partner |  |
| Contract reference number: | # con_22180 |  |
| Details of Proposed Variation |  |  |
| Variation initiated by: | Buyer |  |
| Variation number: | 1 |  |
| Date variation is raised: | 8th September 2023 |  |
| Proposed variation |  |  |
| Reason for the variation: | Incomplete schedules on contract signature |  |
| An Impact Assessment shall be provided within: | NA |  |
| Impact of Variation |  |  |
| Likely impact of the proposed variation: | NA |  |
| Outcome of Variation |  |  |
| Contract variation: | This Contract detailed above is varied as follows: - Refer to Annex 1 for amended/ updated contract schedules for the following- - RM6187 Call off Schedule 10- Exit Management - RM6187 Call off Schedule 13- Implementation Plan and Testing- Plan added - RM6187 Call off Schedule 15- Contract management - RM6187 Framework Schedule 5- Management Charges and Information - RM6187 Joint Schedule 3 – Insurance Requirements - RM6187 Call Off Schedule_Specification- Milestone dates updated - RM6187 Joint Schedule 4- Commercially Sensitive information - RM6187 Joint Schedule 11 – Processing Data |  |
| Financial variation: | Original Contract Value: | £ 7,619,450 |
|  | Additional cost due to variation: | £ 0 |
|  | New Contract value: | £ 7,619,450 |

- This Variation must be agreed and signed by both Parties to the Contract and shall only be effective from the date it is signed by Buyer.

- Words and expressions in this Variation shall have the meanings given to them in the Contract.

- The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

Signed by an authorised signatory for and on behalf of the Buyer

| Signed by person authorised to sign on behalf of the ‘Buyer’ Department for Education: |  |
| --- | --- |
| Signature: | {{Sig2_es_:signer2:signature }} |
| Name: | {{ N2_es_:signer2:fullname }} |
| Role: | {{ Ttl2_es_:signer2:title }} |
| Date: | {{ Dte2_es_:signer2:date }} |

| Signed by a person authorised to sign on behalf of the ‘Supplier’ PA Consulting Services Ltd: |  |
| --- | --- |
| Signature: | {{Sig_es_:signer1:signature }} |
| Name: | {{ N_es_:signer1:fullname }} |
| Role: | {{ Ttl_es_:signer1:title }} |
| Date: | {{ Dte_es_:signer1:date }} |

Annex 1- Completed contract Schedules

# Call-Off Schedule 10 (Exit Management)

- Definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):

| "Exclusive Assets" | - Supplier Assets used exclusively by the Supplier or a Key Subcontractor in the provision of the Deliverables; |
| --- | --- |
| "Exit Information" | has the meaning given to it in Paragraph 3.1 of this Schedule; |
| "Exit Manager" | the person appointed by each Party to manage their respective obligations under this Schedule; |
| “Exit Plan” | the plan produced and updated by the Supplier during the Initial Period in accordance with Paragraph 4 of this Schedule; |
| "Net Book Value" | the current net book value of the relevant Supplier Asset(s) calculated in accordance with the Framework Tender or Call-Off Tender (if stated) or (if not stated) the depreciation policy of the Supplier (which the Supplier shall ensure is in accordance with Good Industry Practice); |
| "Non-Exclusive Assets" | those Supplier Assets used by the Supplier or a Key Subcontractor in connection with the Deliverables but which are also used by the Supplier or Key Subcontractor for other purposes; |
| "Registers" | the register and configuration database referred to in Paragraph 2.2 of this Schedule; |
| "Replacement Goods" | any goods which are substantially similar to any of the Goods and which the Buyer receives in substitution for any of the Goods following the End Date, whether those goods are provided by the Buyer internally and/or by any third party; |
| "Replacement Services" | any services which are substantially similar to any of the Services and which the Buyer receives in substitution for any of the Services following the End Date, whether those goods are provided by the Buyer internally and/or by any third party; |
| "Termination Assistance" | the activities to be performed by the Supplier pursuant to the Exit Plan, and other assistance required by the Buyer pursuant to the Termination Assistance Notice; |
| "Termination Assistance Notice" | has the meaning given to it in Paragraph 5.1 of this Schedule; |
| "Termination Assistance Period" | the period specified in a Termination Assistance Notice for which the Supplier is required to provide the Termination Assistance as such period may be extended pursuant to Paragraph 5.2 of this Schedule; |
| "Transferable Assets" | Exclusive Assets which are capable of legal transfer to the Buyer; |
| "Transferable Contracts" | Sub-Contracts, licences for Supplier's Software, licences for Third Party Software or other agreements which are necessary to enable the Buyer or any Replacement Supplier to provide the Deliverables or the Replacement Goods and/or Replacement Services, including in relation to licences all relevant Documentation; |
| "Transferring Assets" | has the meaning given to it in Paragraph 8.2.1 of this Schedule; |
| "Transferring Contracts" | has the meaning given to it in Paragraph 8.2.3 of this Schedule. |

Supplier must always be prepared for contract exit

The Supplier shall within 30 days from the Start Date provide to the Buyer a copy of its depreciation policy to be used for the purposes of calculating Net Book Value.

During the Contract Period, the Supplier shall promptly:

create and maintain a detailed register of all Supplier Assets (including description, condition, location and details of ownership and status as either Exclusive Assets or Non-Exclusive Assets and Net Book Value) and Sub-contracts and other relevant agreements required in connection with the Deliverables; and

create and maintain a configuration database detailing the technical infrastructure and operating procedures through which the Supplier provides the Deliverables

("Registers").

The Supplier shall:

ensure that all Exclusive Assets listed in the Registers are clearly physically identified as such; and

procure that all licences for Third Party Software and all Sub-Contracts shall be assignable and/or capable of novation (at no cost or restriction to the Buyer) at the request of the Buyer to the Buyer (and/or its nominee) and/or any Replacement Supplier upon the Supplier ceasing to provide the Deliverables (or part of them) and if the Supplier is unable to do so then the Supplier shall promptly notify the Buyer and the Buyer may require the Supplier to procure an alternative Subcontractor or provider of Deliverables.

Each Party shall appoint an Exit Manager within three (3) Months of the Start Date. The Parties' Exit Managers will liaise with one another in relation to all issues relevant to the expiry or termination of this Contract.

Assisting re-competition for Deliverables

The Supplier shall, on reasonable notice, provide to the Buyer and/or its potential Replacement Suppliers (subject to the potential Replacement Suppliers entering into reasonable written confidentiality undertakings), such information (including any access) as the Buyer shall reasonably require in order to facilitate the preparation by the Buyer of any invitation to tender and/or to facilitate any potential Replacement Suppliers undertaking due diligence (the "Exit Information").

The Supplier acknowledges that the Buyer may disclose the Supplier's Confidential Information (excluding the Supplier’s or its Subcontractors’ prices or costs) to an actual or prospective Replacement Supplier to the extent that such disclosure is necessary in connection with such engagement.

The Supplier shall provide complete updates of the Exit Information on an as-requested basis as soon as reasonably practicable and notify the Buyer within five (5) Working Days of any material change to the Exit Information which may adversely impact upon the provision of any Deliverables (and shall consult the Buyer in relation to any such changes).

The Exit Information shall be accurate and complete in all material respects and shall be sufficient to enable a third party to prepare an informed offer for those Deliverables; and not be disadvantaged in any procurement process compared to the Supplier.

Exit Plan

The Supplier shall, within three (3) Months after the Start Date, deliver to the Buyer an Exit Plan which complies with the requirements set out in Paragraph 4.3 of this Schedule and is otherwise reasonably satisfactory to the Buyer.

The Parties shall use reasonable endeavours to agree the contents of the Exit Plan. If the Parties are unable to agree the contents of the Exit Plan within twenty (20) Working Days of the latest date for its submission pursuant to Paragraph 4.1, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

The Exit Plan shall set out, as a minimum:

a detailed description of both the transfer and cessation processes, including a timetable;

how the Deliverables will transfer to the Replacement Supplier and/or the Buyer;

details of any contracts which will be available for transfer to the Buyer and/or the Replacement Supplier upon the Expiry Date together with any reasonable costs required to effect such transfer;

proposals for the training of key members of the Replacement Supplier’s staff in connection with the continuation of the provision of the Deliverables following the Expiry Date;

proposals for providing the Buyer or a Replacement Supplier copies of all documentation relating to the use and operation of the Deliverables and required for their continued use;

proposals for the assignment or novation of all services utilised by the Supplier in connection with the supply of the Deliverables;

proposals for the identification and return of all Buyer Property in the possession of and/or control of the Supplier or any third party;

proposals for the disposal of any redundant Deliverables and materials;

how the Supplier will ensure that there is no disruption to or degradation of the Deliverables during the Termination Assistance Period; and

any other information or assistance reasonably required by the Buyer or a Replacement Supplier.

The Supplier shall:

maintain and update the Exit Plan (and risk management plan) no less frequently than:

every six (6) months throughout the Contract Period; and

no later than twenty (20) Working Days after a request from the Buyer for an up-to-date copy of the Exit Plan;

as soon as reasonably possible following a Termination Assistance Notice, and in any event no later than ten (10) Working Days after the date of the Termination Assistance Notice;

as soon as reasonably possible following, and in any event no later than twenty (20) Working Days following, any material change to the Deliverables (including all changes under the Variation Procedure); and

jointly review and verify the Exit Plan if required by the Buyer and promptly correct any identified failures.

Only if (by notification to the Supplier in writing) the Buyer agrees with a draft Exit Plan provided by the Supplier under Paragraph 4.2 or 4.4 (as the context requires), shall that draft become the Exit Plan for this Contract.

A version of an Exit Plan agreed between the parties shall not be superseded by any draft submitted by the Supplier.

Termination Assistance

The Buyer shall be entitled to require the provision of Termination Assistance at any time during the Contract Period by giving written notice to the Supplier (a "Termination Assistance Notice") at least four (4) Months prior to the Expiry Date or as soon as reasonably practicable (but in any event, not later than one (1) Month) following the service by either Party of a Termination Notice. The Termination Assistance Notice shall specify:

the nature of the Termination Assistance required; and

the start date and initial period during which it is anticipated that Termination Assistance will be required, which shall continue no longer than twelve (12) Months after the End Date.

The Buyer shall have an option to extend the Termination Assistance Period beyond the initial period specified in the Termination Assistance Notice in one or more extensions, in each case provided that:

no such extension shall extend the Termination Assistance Period beyond the date twelve (12) Months after the End Date; and

the Buyer shall notify the Supplier of any such extension no later than twenty (20) Working Days prior to the date on which the Termination Assistance Period is otherwise due to expire.

The Buyer shall have the right to terminate its requirement for Termination Assistance by serving not less than twenty (20) Working Days' written notice upon the Supplier.

In the event that Termination Assistance is required by the Buyer but at the relevant time the parties are still agreeing an update to the Exit Plan pursuant to Paragraph 4, the Supplier will provide the Termination Assistance in good faith and in accordance with the principles in this Schedule and the last Buyer approved version of the Exit Plan (insofar as it still applies).

Termination Assistance Period

Throughout the Termination Assistance Period the Supplier shall:

continue to provide the Deliverables (as applicable) and otherwise perform its obligations under this Contract and, if required by the Buyer, provide the Termination Assistance;

provide to the Buyer and/or its Replacement Supplier any reasonable assistance and/or access requested by the Buyer and/or its Replacement Supplier including assistance and/or access to facilitate the orderly transfer of responsibility for and conduct of the Deliverables to the Buyer and/or its Replacement Supplier;

use all reasonable endeavours to reallocate resources to provide such assistance without additional costs to the Buyer;

subject to Paragraph 6.3, provide the Deliverables and the Termination Assistance at no detriment to the Performance Indicators (PI’s) or Service Levels, the provision of the Management Information or any other reports nor to any other of the Supplier's obligations under this Contract;

at the Buyer's request and on reasonable notice, deliver up-to-date Registers to the Buyer;

seek the Buyer's prior written consent to access any Buyer Premises from which the de-installation or removal of Supplier Assets is required.

If it is not possible for the Supplier to reallocate resources to provide such assistance as is referred to in Paragraph 6.1.2 without additional costs to the Buyer, any additional costs incurred by the Supplier in providing such reasonable assistance shall be subject to the Variation Procedure.

If the Supplier demonstrates to the Buyer's reasonable satisfaction that the provision of the Termination Assistance will have a material, unavoidable adverse effect on the Supplier's ability to meet one or more particular Service Levels, the Parties shall vary the relevant Service Levels and/or the applicable Service Credits accordingly.

Obligations when the contract is terminated

The Supplier shall comply with all of its obligations contained in the Exit Plan.

Upon termination or expiry or at the end of the Termination Assistance Period (or earlier if this does not adversely affect the Supplier's performance of the Deliverables and the Termination Assistance), the Supplier shall:

vacate any Buyer Premises;

remove the Supplier Equipment together with any other materials used by the Supplier to supply the Deliverables and shall leave the Sites in a clean, safe and tidy condition. The Supplier is solely responsible for making good any damage to the Sites or any objects contained thereon, other than fair wear and tear, which is caused by the Supplier;

provide access during normal working hours to the Buyer and/or the Replacement Supplier for up to twelve (12) Months after expiry or termination to:

such information relating to the Deliverables as remains in the possession or control of the Supplier; and

such members of the Supplier Staff as have been involved in the design, development and provision of the Deliverables and who are still employed by the Supplier, provided that the Buyer and/or the Replacement Supplier shall pay the reasonable costs of the Supplier actually incurred in responding to such requests for access.

Except where this Contract provides otherwise, all licences, leases and authorisations granted by the Buyer to the Supplier in relation to the Deliverables shall be terminated with effect from the end of the Termination Assistance Period.

Assets, Sub-contracts and Software

Following notice of termination of this Contract and during the Termination Assistance Period, the Supplier shall not, without the Buyer's prior written consent:

terminate, enter into or vary any Subcontract or licence for any software in connection with the Deliverables; or

(subject to normal maintenance requirements) make material modifications to, or dispose of, any existing Supplier Assets or acquire any new Supplier Assets.

Within twenty (20) Working Days of receipt of the up-to-date Registers provided by the Supplier, the Buyer shall notify the Supplier setting out:

which, if any, of the Transferable Assets the Buyer requires to be transferred to the Buyer and/or the Replacement Supplier ("Transferring Assets");

which, if any, of:

the Exclusive Assets that are not Transferable Assets; and

the Non-Exclusive Assets,

the Buyer and/or the Replacement Supplier requires the continued use of; and

which, if any, of Transferable Contracts the Buyer requires to be assigned or novated to the Buyer and/or the Replacement Supplier (the "Transferring Contracts"),

in order for the Buyer and/or its Replacement Supplier to provide the Deliverables from the expiry of the Termination Assistance Period. The Supplier shall provide all reasonable assistance required by the Buyer and/or its Replacement Supplier to enable it to determine which Transferable Assets and Transferable Contracts are required to provide the Deliverables or the Replacement Goods and/or Replacement Services.

With effect from the expiry of the Termination Assistance Period, the Supplier shall sell the Transferring Assets to the Buyer and/or the Replacement Supplier for their Net Book Value less any amount already paid for them through the Charges.

Risk in the Transferring Assets shall pass to the Buyer or the Replacement Supplier (as appropriate) at the end of the Termination Assistance Period and title shall pass on payment for them.

Where the Buyer and/or the Replacement Supplier requires continued use of any Exclusive Assets that are not Transferable Assets or any Non-Exclusive Assets, the Supplier shall as soon as reasonably practicable:

procure a non-exclusive, perpetual, royalty-free licence for the Buyer and/or the Replacement Supplier to use such assets (with a right of sub-licence or assignment on the same terms); or failing which

procure a suitable alternative to such assets, the Buyer or the Replacement Supplier to bear the reasonable proven costs of procuring the same.

The Supplier shall as soon as reasonably practicable assign or procure the novation of the Transferring Contracts to the Buyer and/or the Replacement Supplier.  The Supplier shall execute such documents and provide such other assistance as the Buyer reasonably requires to effect this novation or assignment.

The Buyer shall:

accept assignments from the Supplier or join with the Supplier in procuring a novation of each Transferring Contract; and

once a Transferring Contract is novated or assigned to the Buyer and/or the Replacement Supplier, discharge all the obligations and liabilities created by or arising under that Transferring Contract and exercise its rights arising under that Transferring Contract, or as applicable, procure that the Replacement Supplier does the same.

The Supplier shall hold any Transferring Contracts on trust for the Buyer until the transfer of the relevant Transferring Contract to the Buyer and/or the Replacement Supplier has taken place.

The Supplier shall indemnify the Buyer (and/or the Replacement Supplier, as applicable) against each loss, liability and cost arising out of any claims made by a counterparty to a Transferring Contract which is assigned or novated to the Buyer (and/or Replacement Supplier) pursuant to Paragraph 8.6 in relation to any matters arising prior to the date of assignment or novation of such Transferring Contract. Clause 19 (Other people's rights in this contract) shall not apply to this Paragraph 8.9 which is intended to be enforceable by Third Parties Beneficiaries by virtue of the CRTPA.

No charges

Unless otherwise stated, the Buyer shall not be obliged to pay for costs incurred by the Supplier in relation to its compliance with this Schedule.

Dividing the bills

All outgoings, expenses, rents, royalties and other periodical payments receivable in respect of the Transferring Assets and Transferring Contracts shall be apportioned between the Buyer and/or the Replacement and the Supplier as follows:

the amounts shall be annualised and divided by 365 to reach a daily rate;

the Buyer or Replacement Supplier (as applicable) shall be responsible for or entitled to (as the case may be) that part of the value of the invoice pro rata to the number of complete days following the transfer, multiplied by the daily rate; and

the Supplier shall be responsible for or entitled to (as the case may be) the rest of the invoice.

# Call-Off Schedule 13 (Implementation Plan and Testing)

# Part A - Implementation

- Definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):

| "Delay" | - a delay in the Achievement of a Milestone by its Milestone Date; or - a delay in the design, development, testing or implementation of a Deliverable by the relevant date set out in the Implementation Plan; |
| --- | --- |
| "Deliverable Item" | an item or feature in the supply of the Deliverables delivered or to be delivered by the Supplier at or before a Milestone Date listed in the Implementation Plan; |
| "Milestone Payment" | a payment identified in the Implementation Plan to be made following the issue of a Satisfaction Certificate in respect of Achievement of the relevant Milestone; |
| “Implementation Period" | has the meaning given to it in Paragraph 7.1; |

- Agreeing and following the Implementation Plan

  - A draft of the Implementation Plan is set out in the Annex to this Schedule.  The Supplier shall provide a further draft Implementation Plan 5 days after the Call-Off Contract Start Date.

  - The draft Implementation Plan:

    - must contain information at the level of detail necessary to manage the implementation stage effectively and as the Buyer may otherwise require; and

    - it shall take account of all dependencies known to, or which should reasonably be known to, the Supplier.

  - Following receipt of the draft Implementation Plan from the Supplier, the Parties shall use reasonable endeavours to agree the contents of the Implementation Plan.  If the Parties are unable to agree the contents of the Implementation Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

  - The Supplier shall provide each of the Deliverable Items identified in the Implementation Plan by the date assigned to that Deliverable Item in the Implementation Plan so as to ensure that each Milestone identified in the Implementation Plan is Achieved on or before its Milestone Date.

  - The Supplier shall monitor its performance against the Implementation Plan and Milestones (if any) and report to the Buyer on such performance.

- Reviewing and changing the Implementation Plan

  - Subject to Paragraph 2.3, the Supplier shall keep the Implementation Plan under review in accordance with the Buyer’s instructions and ensure that it is updated on a regular basis.

  - The Buyer shall have the right to require the Supplier to include any reasonable changes or provisions in each version of the Implementation Plan.

  - Changes to any Milestones, Milestone Payments and Delay Payments shall only be made in accordance with the Variation Procedure.

  - Time in relation to compliance with the Implementation Plan shall be of the essence and failure of the Supplier to comply with the Implementation Plan shall be a material Default.

- Security requirements before the Start Date

  - The Supplier shall note that it is incumbent upon them to understand the lead-in period for security clearances and ensure that all Supplier Staff have the necessary security clearance in place before the Call-Off Start Date. The Supplier shall ensure that this is reflected in their Implementation Plans.

  - The Supplier shall ensure that all Supplier Staff and Subcontractors do not access the Buyer's IT systems, or any IT systems linked to the Buyer, unless they have satisfied the Buyer's security requirements.

  - The Supplier shall be responsible for providing all necessary information to the Buyer to facilitate security clearances for Supplier Staff and Subcontractors in accordance with the Buyer's requirements.

  - The Supplier shall provide the names of all Supplier Staff and Subcontractors and inform the Buyer of any alterations and additions as they take place throughout the Call-Off Contract.

  - The Supplier shall ensure that all Supplier Staff and Subcontractors requiring access to the Buyer Premises have the appropriate security clearance. It is the Supplier's responsibility to establish whether or not the level of clearance will be sufficient for access. Unless prior approval has been received from the Buyer, the Supplier shall be responsible for meeting the costs associated with the provision of security cleared escort services.

  - If a property requires Supplier Staff or Subcontractors to be accompanied by the Buyer’s Authorised Representative, the Buyer must be given reasonable notice of such a requirement, except in the case of emergency access.

- What to do if there is a Delay

  - If the Supplier becomes aware that there is, or there is reasonably likely to be, a Delay under this Contract it shall:

    - notify the Buyer as soon as practically possible and no later than within two (2) Working Days from becoming aware of the Delay or anticipated Delay;

    - include in its notification an explanation of the actual or anticipated impact of the Delay;

    - comply with the Buyer’s instructions in order to address the impact of the Delay or anticipated Delay; and

    - use all reasonable endeavours to eliminate or mitigate the consequences of any Delay or anticipated Delay.

- Compensation for a Delay

  - If Delay Payments have been included in the Implementation Plan and a Milestone has not been achieved by the relevant Milestone Date, the Supplier shall pay to the Buyer such Delay Payments (calculated as set out by the Buyer in the Implementation Plan) and the following provisions shall apply:

    - the Supplier acknowledges and agrees that any Delay Payment is a price adjustment and not an estimate of the Loss that may be suffered by the Buyer as a result of the Supplier’s failure to Achieve the corresponding Milestone;

    - Delay Payments shall be the Buyer's exclusive financial remedy for the Supplier’s failure to Achieve a Milestone by its Milestone Date except where:

      - the Buyer is entitled to or does terminate this Contract pursuant to Clause 10.4 (When CCS or the Buyer can end this contract); or

      - the delay exceeds the number of days (the "Delay Period Limit") specified in the Implementation Plan commencing on the relevant Milestone Date;

    - the Delay Payments will accrue on a daily basis from the relevant Milestone Date until the date when the Milestone is Achieved;

    - no payment or other act or omission of the Buyer shall in any way affect the rights of the Buyer to recover the Delay Payments or be deemed to be a waiver of the right of the Buyer to recover any such damages; and

    - Delay Payments shall not be subject to or count towards any limitation on liability set out in Clause 11 (How much you can be held responsible for).

- Implementation Plan

  - The Implementation Period will be a 3 Month period.

  - During the Implementation Period, the incumbent supplier shall retain full responsibility for all existing services until the Call-Off Start Date or as otherwise formally agreed with the Buyer. The Supplier's full service obligations shall formally be assumed on the Call-Off Start Date as set out in Order Form.

  - In accordance with the Implementation Plan, the Supplier shall:

    - work cooperatively and in partnership with the Buyer, incumbent supplier, and other Framework Supplier(s), where applicable, to understand the scope of Services to ensure a mutually beneficial handover of the Services;

    - work with the incumbent supplier and Buyer to assess the scope of the Services and prepare a plan which demonstrates how they will mobilise the Services;

    - liaise with the incumbent Supplier to enable the full completion of the Implementation Period activities; and

    - produce an Implementation Plan, to be agreed by the Buyer, for carrying out the requirements within the Implementation Period including, key Milestones and dependencies.

  - The Implementation Plan will include detail stating:

    - how the Supplier will work with the incumbent Supplier and the Buyer Authorised Representative to capture and load up information such as asset data ; and

    - a communications plan, to be produced and implemented by the Supplier, but to be agreed with the Buyer, including the frequency, responsibility for and nature of communication with the Buyer and end users of the Services.

  - In addition, the Supplier shall:

    - appoint a Supplier Authorised Representative who shall be responsible for the management of the Implementation Period, to ensure that the Implementation Period is planned and resourced adequately, and who will act as a point of contact for the Buyer;

    - mobilise all the Services specified in the Specification within the Call-Off Contract;

    - produce a Implementation Plan report for each Buyer Premises to encompass programmes that will fulfil all the Buyer's obligations to landlords and other tenants:

      - the format of reports and programmes shall be in accordance with the Buyer's requirements and particular attention shall be paid to establishing the operating requirements of the occupiers when preparing these programmes which are subject to the Buyer's approval; and

      - the Parties shall use reasonable endeavours to agree the contents of the report but if the Parties are unable to agree the contents within twenty (20) Working Days of its submission by the Supplier to the Buyer, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

    - manage and report progress against the Implementation Plan;

    - construct and maintain a Implementation risk and issue register in conjunction with the Buyer detailing how risks and issues will be effectively communicated to the Buyer in order to mitigate them;

    - attend progress meetings (frequency of such meetings shall be as set out in the Order Form) in accordance with the Buyer's requirements during the Implementation Period. Implementation meetings shall be chaired by the Buyer and all meeting minutes shall be kept and published by the Supplier; and

    - ensure that all risks associated with the Implementation Period are minimised to ensure a seamless change of control between incumbent provider and the Supplier.

# Annex 1: Implementation Plan

The supplier (Delivery Partner) should note the following project milestones that the buyer (DfE) will measure the quality of delivery against:

- Milestone 1: All CPPs have a finalised strategic delivery plan in place ready for sign off by DfE Timeframe By 3 November 2023.

- Milestone 2: All CPPs and individual local authorities have commenced the formal testing phase Timeframe: By end November 2023

- Milestone 3: The delivery partner will create and commence a mechanism/forum for sharing real time feedback.

  - Set-up feedback process in place by October 2023

  - Formal feedback loop in place by end November 2023

- Milestone 4: The Delivery Partner will support all CPPs to develop a menu of support options that they can deliver to other LAs in the region. Timeframe: by end of April 2024.

- Milestone 5: The delivery partner will create and commence a mechanism/forum for sharing programme learning nationally and across all the system, delivering regular events/webinars as agreed with the department. Timeframe: from April 2024 – end of the contract.

In order to track  the programme, the buyer (DfE) may use the following measures:

| KPI No | Indicative KPI criterion | Measured by | Suggested % for supplier to meet | Service Period | Service credit to be applied if target not met |
| --- | --- | --- | --- | --- | --- |
| 1 | Management Information | Submission of Monthly reports on programme progress to support the continuous feedback loop, providing the department with real time insight Submission of Quarterly evidence based reports on learning from REPs to support dissemination of learning to the sector. | 98% of all requested Management Information reports to be supplied to DfE by the date agreed for each monthly and quarterly return | Monthly/ Quarterly | n/a |
| 2 | Customer satisfaction | Summary of anonymous responses /feedback from local areas on their experience of the quality of support given to them, as well as feedback from the department. This will be captured through quarterly surveys issued by the delivery partner with content agreed in advance with DfE, further details of content to be included can be found in section 3.3. | 80% or more of customer satisfaction survey respondents rate delivery as satisfactory or higher. | Quarterly | n/a |
| 3 | Invoice Accuracy / Timelines | All invoices will be valid in accordance with the criteria in 4.5 of the Core Terms and submitted in line with timescales to be agreed with DfE | 98% | monthly | n/a |
| 4 | Set Up & Planning | All REPs and individual local authorities have a finalised strategic delivery plan and individual inclusion plans, signed off by DfE (see milestone 1) | 100% | By 3 November 2023 | Maximum of 1% of contract payments from contract start date to 30th October 2023 |
| 5 | Test & Refine Tranche 1 | All REPs and individual local authorities have started to test the first wave of reforms outlined in their local inclusion plans (see milestone 2) Timeframe: By end November 2023 | 100% | By end November 2023 | Maximum of 1% of contract payments from quarter ending 30th November 2023. |
| 6 | Test & Refine Tranche 2 | All REPs and individual local authorities have started to test the full suite of reforms outlined in their local inclusion plans Timeframe: By September 2024 | 100% | By September 2024 | Maximum of 0.5% of contract payments from quarter ending 30th September 2024 |
| 7 | Taskforce Support | The Delivery Partner will support all CPPs to develop a menu of support options that they can deliver to other LAs in the region. Timeframe: by end of April 2024. | 100% | By 30th April 2024 | Maximum of 0.5% of contract payments from quarter ending 30th April 2024 |
| 8 | Continuous Feedback Loop | A mechanism for sharing real time feedback (see milestone 3) has been created and implemented by the Delivery Partner and signed off by DfE. | 100% | By 30th November 2023 | n/a |
| 9 | Dissemination of Learning | A mechanism for sharing learning has been created and implemented by the Delivery Partner and signed off by DfE. (see milestone 5) | 100% | By 30th April 2024 | n/a |
| 10 | Dissemination of Learning | The Delivery Partner will share programme learning nationally and across all of the system, delivering regular events/webinars – schedule to be agreed with the Department.(see milestone 5) From January 2024 to contract end. | In line with schedule to be agreed by DfE | Monthly from end April 2024 until contract end | n/a |

# Part B - Testing

- Definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):

| "Component" | any constituent parts of the Deliverables; |
| --- | --- |
| "Material Test Issue" | a Test Issue of Severity Level 1 or Severity Level 2; |
| "Satisfaction Certificate" | a certificate materially in the form of the document contained in Annex 2 issued by the Buyer when a Deliverable and/or Milestone has satisfied its relevant Test Success Criteria; |
| "Severity Level" | the level of severity of a Test Issue, the criteria for which are described in Annex 1; |
| "Test Issue Management Log" | a log for the recording of Test Issues as described further in Paragraph 8.1 of this Schedule; |
| "Test Issue Threshold" | in relation to the Tests applicable to a Milestone, a maximum number of Severity Level 3, Severity Level 4 and Severity Level 5 Test Issues as set out in the relevant Test Plan; |
| "Test Reports" | the reports to be produced by the Supplier setting out the results of Tests; |
| "Test Specification" | the specification that sets out how Tests will demonstrate that the Test Success Criteria have been satisfied, as described in more detail in Paragraph 6.2 of this Schedule; |
| "Test Strategy" | a strategy for the conduct of Testing as described further in Paragraph 3.2 of this Schedule; |
| "Test Success Criteria" | in relation to a Test, the test success criteria for that Test as referred to in Paragraph 5 of this Schedule; |
| "Test Witness" | any person appointed by the Buyer pursuant to Paragraph 9 of this Schedule; and |
| "Testing Procedures" | the applicable testing procedures and Test Success Criteria set out in this Schedule. |

- How testing should work

  - All Tests conducted by the Supplier shall be conducted in accordance with the Test Strategy, Test Specification and the Test Plan.

  - The Supplier shall not submit any Deliverable for Testing:

    - unless the Supplier is reasonably confident that it will satisfy the relevant Test Success Criteria;

    - until the Buyer has issued a Satisfaction Certificate in respect of any prior, dependant Deliverable(s); and

    - until the Parties have agreed the Test Plan and the Test Specification relating to the relevant Deliverable(s).

  - The Supplier shall use reasonable endeavours to submit each Deliverable for Testing or re-Testing by or before the date set out in the Implementation Plan for the commencement of Testing in respect of the relevant Deliverable.

  - Prior to the issue of a Satisfaction Certificate, the Buyer shall be entitled to review the relevant Test Reports and the Test Issue Management Log.

- Planning for testing

  - The Supplier shall develop the final Test Strategy as soon as practicable after the Start Date but in any case no later than twenty (20) Working Days after the Start Date.

  - The final Test Strategy shall include:

    - an overview of how Testing will be conducted in relation to the Implementation Plan;

    - the process to be used to capture and record Test results and the categorisation of Test Issues;

    - the procedure to be followed should a Deliverable fail a Test, fail to satisfy the Test Success Criteria or where the Testing of a Deliverable produces unexpected results, including a procedure for the resolution of Test Issues;

    - the procedure to be followed to sign off each Test;

    - the process for the production and maintenance of Test Reports and a sample plan for the resolution of Test Issues;

    - the names and contact details of the Buyer and the Supplier's Test representatives;

    - a high level identification of the resources required for Testing including Buyer and/or third party involvement in the conduct of the Tests;

    - the technical environments required to support the Tests; and

    - the procedure for managing the configuration of the Test environments.

- Preparing for Testing

  - The Supplier shall develop Test Plans and submit these for Approval as soon as practicable but in any case, no later than twenty (20) Working Days prior to the start date for the relevant Testing as specified in the Implementation Plan.

  - Each Test Plan shall include as a minimum:

    - the relevant Test definition and the purpose of the Test, the Milestone to which it relates, the requirements being Tested and, for each Test, the specific Test Success Criteria to be satisfied; and

    - a detailed procedure for the Tests to be carried out.

  - The Buyer shall not unreasonably withhold or delay its approval of the Test Plan provided that the Supplier shall implement any reasonable requirements of the Buyer in the Test Plan.

- Passing Testing

  - The Test Success Criteria for all Tests shall be agreed between the Parties as part of the relevant Test Plan pursuant to Paragraph 4.

- How Deliverables will be tested

  - Following approval of a Test Plan, the Supplier shall develop the Test Specification for the relevant Deliverables as soon as reasonably practicable and in any event at least ten (10) Working Days prior to the start of the relevant Testing (as specified in the Implementation Plan).

  - Each Test Specification shall include as a minimum:

    - the specification of the Test data, including its source, scope, volume and management, a request (if applicable) for relevant Test data to be provided by the Buyer and the extent to which it is equivalent to live operational data;

    - a plan to make the resources available for Testing;

    - Test scripts;

    - Test pre-requisites and the mechanism for measuring them; and

    - expected Test results, including:

      - a mechanism to be used to capture and record Test results; and

      - a method to process the Test results to establish their content.

- Performing the tests

  - Before submitting any Deliverables for Testing the Supplier shall subject the relevant Deliverables to its own internal quality control measures.

  - The Supplier shall manage the progress of Testing in accordance with the relevant Test Plan and shall carry out the Tests in accordance with the relevant Test Specification. Tests may be witnessed by the Test Witnesses in accordance with Paragraph 9.3.

  - The Supplier shall notify the Buyer at least ten (10) Working Days in advance of the date, time and location of the relevant Tests and the Buyer shall ensure that the Test Witnesses attend the Tests.

  - The Buyer may raise and close Test Issues during the Test witnessing process.

  - The Supplier shall provide to the Buyer in relation to each Test:

    - a draft Test Report not less than two (2) Working Days prior to the date on which the Test is planned to end; and

    - the final Test Report within five (5) Working Days of completion of Testing.

  - Each Test Report shall provide a full report on the Testing conducted in respect of the relevant Deliverables, including:

    - an overview of the Testing conducted;

    - identification of the relevant Test Success Criteria that have/have not been satisfied together with the Supplier's explanation of why any criteria have not been met;

    - the Tests that were not completed together with the Supplier's explanation of why those Tests were not completed;

    - the Test Success Criteria that were satisfied, not satisfied or which were not tested, and any other relevant categories, in each case grouped by Severity Level in accordance with Paragraph 8.1; and

    - the specification for any hardware and software used throughout Testing and any changes that were applied to that hardware and/or software during Testing.

  - When the Supplier has completed a Milestone it shall submit any Deliverables relating to that Milestone for Testing.

  - Each party shall bear its own costs in respect of the Testing.  However, if a Milestone is not Achieved the Buyer shall be entitled to recover from the Supplier, any reasonable additional costs it may incur as a direct result of further review or re-Testing of a Milestone.

  - If the Supplier successfully completes the requisite Tests, the Buyer shall issue a Satisfaction Certificate as soon as reasonably practicable following such successful completion.  Notwithstanding the issuing of any Satisfaction Certificate, the Supplier shall remain solely responsible for ensuring that the Deliverables are implemented in accordance with this Contract.

- Discovering Problems

  - Where a Test Report identifies a Test Issue, the Parties shall agree the classification of the Test Issue using the criteria specified in Annex 1 and the Test Issue Management Log maintained by the Supplier shall log Test Issues reflecting the Severity Level allocated to each Test Issue.

  - The Supplier shall be responsible for maintaining the Test Issue Management Log and for ensuring that its contents accurately represent the current status of each Test Issue at all relevant times.  The Supplier shall make the Test Issue Management Log available to the Buyer upon request.

  - The Buyer shall confirm the classification of any Test Issue unresolved at the end of a Test in consultation with the Supplier.  If the Parties are unable to agree the classification of any unresolved Test Issue, the Dispute shall be dealt with in accordance with the Dispute Resolution Procedure using the Expedited Dispute Timetable.

- Test witnessing

  - The Buyer may, in its sole discretion, require the attendance at any Test of one or more Test Witnesses selected by the Buyer, each of whom shall have appropriate skills to fulfil the role of a Test Witness.

  - The Supplier shall give the Test Witnesses access to any documentation and Testing environments reasonably necessary and requested by the Test Witnesses to perform their role as a Test Witness in respect of the relevant Tests.

  - The Test Witnesses:

    - shall actively review the Test documentation;

    - will attend and engage in the performance of the Tests on behalf of the Buyer so as to enable the Buyer to gain an informed view of whether a Test Issue may be closed or whether the relevant element of the Test should be re-Tested;

    - shall not be involved in the execution of any Test;

    - shall be required to verify that the Supplier conducted the Tests in accordance with the Test Success Criteria and the relevant Test Plan and Test Specification;

    - may produce and deliver their own, independent reports on Testing, which may be used by the Buyer to assess whether the Tests have been Achieved;

    - may raise Test Issues on the Test Issue Management Log in respect of any Testing; and

  - may require the Supplier to demonstrate the modifications made to any defective Deliverable before a Test Issue is closed.

- Auditing the quality of the test

  - The Buyer or an agent or contractor appointed by the Buyer may perform on-going quality audits in respect of any part of the Testing (each a "Testing Quality Audit") subject to the provisions set out in the agreed Quality Plan.

  - The Supplier shall allow sufficient time in the Test Plan to ensure that adequate responses to a Testing Quality Audit can be provided.

  - The Buyer will give the Supplier at least five (5) Working Days' written notice of the Buyer’s intention to undertake a Testing Quality Audit.

  - The Supplier shall provide all reasonable necessary assistance and access to all relevant documentation required by the Buyer to enable it to carry out the Testing Quality Audit.

  - If the Testing Quality Audit gives the Buyer concern in respect of the Testing Procedures or any Test, the Buyer shall prepare a written report for the Supplier detailing its concerns and the Supplier shall, within a reasonable timeframe, respond in writing to the Buyer’s report.

  - In the event of an inadequate response to the written report from the Supplier, the Buyer (acting reasonably) may withhold a Satisfaction Certificate until the issues in the report have been addressed to the reasonable satisfaction of the Buyer.

- Outcome of the testing

  - The Buyer will issue a Satisfaction Certificate when the Deliverables satisfy the Test Success Criteria in respect of that Test without any Test Issues.

  - If the Deliverables (or any relevant part) do not satisfy the Test Success Criteria then the Buyer shall notify the Supplier and:

    - the Buyer may issue a Satisfaction Certificate conditional upon the remediation of the Test Issues;

    - the Buyer may extend the Test Plan by such reasonable period or periods as the Parties may reasonably agree and require the Supplier to rectify the cause of the Test Issue and re-submit the Deliverables (or the relevant part) to Testing; or

    - where the failure to satisfy the Test Success Criteria results, or is likely to result, in the failure (in whole or in part) by the Supplier to meet a Milestone, then without prejudice to the Buyer’s other rights and remedies, such failure shall constitute a material Default.

  - The Buyer shall be entitled, without prejudice to any other rights and remedies that it has under this Contract, to recover from the Supplier any reasonable additional costs it may incur as a direct result of further review or re-Testing which is required for the Test Success Criteria for that Deliverable to be satisfied.

  - The Buyer shall issue a Satisfaction Certificate in respect of a given Milestone as soon as is reasonably practicable following:

    - the issuing by the Buyer of Satisfaction Certificates and/or conditional Satisfaction Certificates in respect of all Deliverables related to that Milestone which are due to be Tested; and

    - performance by the Supplier to the reasonable satisfaction of the Buyer of any other tasks identified in the Implementation Plan as associated with that Milestone.

  - The grant of a Satisfaction Certificate shall entitle the Supplier to the receipt of a payment in respect of that Milestone in accordance with the provisions of any Implementation Plan and Clause 4 (Pricing and payments).

  - If a Milestone is not Achieved, the Buyer shall promptly issue a report to the Supplier setting out the applicable Test Issues and any other reasons for the relevant Milestone not being Achieved.

  - If there are Test Issues but these do not exceed the Test Issues Threshold, then provided there are no Material Test Issues, the Buyer shall issue a Satisfaction Certificate.

  - If there is one or more Material Test Issue(s), the Buyer shall refuse to issue a Satisfaction Certificate and, without prejudice to the Buyer’s other rights and remedies, such failure shall constitute a material Default.

  - If there are Test Issues which exceed the Test Issues Threshold but there are no Material Test Issues, the Buyer may at its discretion (without waiving any rights in relation to the other options) choose to issue a Satisfaction Certificate conditional on the remediation of the Test Issues in accordance with an agreed Rectification Plan provided that:

    - any Rectification Plan shall be agreed before the issue of a conditional Satisfaction Certificate unless the Buyer agrees otherwise (in which case the Supplier shall submit a Rectification Plan for approval by the Buyer within ten (10) Working Days of receipt of the Buyer’s report pursuant to Paragraph 10.5); and

    - where the Buyer issues a conditional Satisfaction Certificate, it may (but shall not be obliged to) revise the failed Milestone Date and any subsequent Milestone Date.

- Risk

  - The issue of a Satisfaction Certificate and/or a conditional Satisfaction Certificate shall not:

    - operate to transfer any risk that the relevant Deliverable or Milestone is complete or will meet and/or satisfy the Buyer’s requirements for that Deliverable or Milestone; or

    - affect the Buyer’s right subsequently to reject all or any element of the Deliverables and/or any Milestone to which a Satisfaction Certificate relates.

# Annex 1: Test Issues – Severity Levels

- Severity 1 Error

  - This is an error that causes non-recoverable conditions, e.g. it is not possible to continue using a Component.

- Severity 2 Error

  - This is an error for which, as reasonably determined by the Buyer, there is no practicable workaround available, and which:

    - causes a Component to become unusable;

    - causes a lack of functionality, or unexpected functionality, that has an impact on the current Test; or

    - has an adverse impact on any other Component(s) or any other area of the Deliverables;

- Severity 3 Error

  - This is an error which:

    - causes a Component to become unusable;

    - causes a lack of functionality, or unexpected functionality, but which does not impact on the current Test; or

    - has an impact on any other Component(s) or any other area of the Deliverables;

but for which, as reasonably determined by the Buyer, there is a practicable workaround available;

- Severity 4 Error

  - This is an error which causes incorrect functionality of a Component or process, but for which there is a simple, Component based, workaround, and which has no impact on the current Test, or other areas of the Deliverables.

- Severity 5 Error

  - This is an error that causes a minor problem, for which no workaround is required, and which has no impact on the current Test, or other areas of the Deliverables.

# Annex 2: Satisfaction Certificate

To:		[insert name of Supplier]

From:		DfE

[insert Date dd/mm/yyyy]

Dear Sirs,

Satisfaction Certificate

Deliverable/Milestone(s): [Insert relevant description of the agreed Deliverables/Milestones].

We refer to the agreement ("Call-Off Contract") [insert Call-Off  Contract reference number] relating to the provision of the [insert description of the Deliverables] between the [insert Buyer name] ("Buyer") and [insert Supplier name] ("Supplier") dated [insert Call-Off  Start Date dd/mm/yyyy].

The definitions for any capitalised terms in this certificate are as set out in the Call-Off  Contract.

[We confirm that all the Deliverables relating to [insert relevant description of Deliverables/agreed Milestones and/or reference number(s) from the Implementation Plan] have been tested successfully in accordance with the Test Plan [or that a conditional Satisfaction Certificate has been issued in respect of those Deliverables that have not satisfied the relevant Test Success Criteria].

[OR]

[This Satisfaction Certificate is granted on the condition that any Test Issues are remedied in accordance with the Rectification Plan attached to this certificate.]

[You may now issue an invoice in respect of the Milestone Payment associated with this Milestone in accordance with Clause 4 (Pricing and payments)].

Yours faithfully

[insert Name]

[insert Position]

acting on behalf of [insert name of Buyer]

# Call-Off Schedule 15 (Call-Off Contract Management)

# Definitions

## In this Schedule, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):

| "Operational Board" | the board established in accordance with paragraph 4.1 of this Schedule; |
| --- | --- |
| "Project Manager" | the manager appointed in accordance with paragraph 2.1 of this Schedule; |

# Project Management

## The Supplier and the Buyer shall each appoint a Project Manager for the purposes of this Contract through whom the provision of the Services and the Deliverables shall be managed day-to-day.

## The Parties shall ensure that appropriate resources are made available on a regular basis such that the aims, objectives and specific provisions of this Contract can be fully realised.

## Without prejudice to paragraph 4 below, the Parties agree to operate the boards specified as set out in the Annex to this Schedule.

Role of the Supplier Contract Manager

The Supplier's Contract Manager'(s) shall be:

### the primary point of contact to receive communication from the Buyer and will also be the person primarily responsible for providing information to the Buyer;

### able to delegate his position to another person at the Supplier but must inform the Buyer before proceeding with the delegation and it will be delegated person's responsibility to fulfil the Supplier’s Contract Manager's responsibilities and obligations;

### able to cancel any delegation and recommence the position himself; and

### replaced only after the Buyer has received notification of the proposed change.

The Buyer may provide revised instructions to the Supplier's Contract Manager(s) in regards to the Contract and it will be the Supplier's Contract Manager's responsibility to ensure the information is provided to the Supplier and the actions implemented.

Receipt of communication from the Supplier's Contract Manager(s) by the Buyer does not absolve the Supplier from its responsibilities, obligations or liabilities under the Contract.

# Role of the Operational Board

## The Operational Board shall be established by the Buyer for the purposes of this Contract on which the Supplier and the Buyer shall be represented.

## The Operational Board members, frequency and location of board meetings and planned start date by which the board shall be established are set out in the Order Form.

## In the event that either Party wishes to replace any of its appointed board members, that Party shall notify the other in writing for approval by the other Party (such approval not to be unreasonably withheld or delayed). Each Buyer board member shall have at all times a counterpart Supplier board member of equivalent seniority and expertise.

## Each Party shall ensure that its board members shall make all reasonable efforts to attend board meetings at which that board member’s attendance is required. If any board member is not able to attend a board meeting, that person shall use all reasonable endeavours to ensure that a delegate attends the Operational Board meeting in his/her place (wherever possible) and that the delegate is properly briefed and prepared and that he/she is debriefed by such delegate after the board meeting.

## The purpose of the Operational Board meetings will be to review the Supplier’s performance under this Contract. The agenda for each meeting shall be set by the Buyer and communicated to the Supplier in advance of that meeting.

Contract Risk Management

Both Parties shall pro-actively manage risks attributed to them under the terms of this Call-Off Contract.

The Supplier shall develop, operate, maintain and amend, as agreed with the Buyer, processes for:

### the identification and management of risks;

the identification and management of issues; and

monitoring and controlling project plans.

The Supplier allows the Buyer to inspect at any time within working hours the accounts and records which the Supplier is required to keep.

The Supplier will maintain a risk register of the risks relating to the Call Off Contract which the Buyer and the Supplier have identified.

# Annex: Contract Boards

The Parties agree to operate the following boards at the locations and at the frequencies set out below:

All meetings virtual between PA Consulting and DfE but there is a plan to do Face to Face once a quarter either in London or Manchester at the DfE offices. Dates below for 23/24

1 November

6 December- Face to Face

03 January

07 February

06 March- Face to face

03 April

01 May

05 June – Face to face

03 July

07 August

04 September – Face to face

# Framework Schedule 5 (Management Charges and Information)

- How to provide management information to CCS

  - The Supplier shall, at no charge, provide timely, full, accurate and complete MI Reports to CCS which incorporate the data, in the correct format, required by the MI Reporting Template and such guidance that CCS may issue from time to time.

The initial MI Reporting Template is set out in the Annex to this Schedule and CCS may change it from time to time (including the data required and/or format) and issue a replacement version.  CCS shall give at least thirty (30) days' notice in writing of any such change and shall specify the date from which it must be used. The Supplier may not make any amendment to the current MI Reporting Template without the prior Approval of CCS.

2	   Reporting period

2.1   MI Reports must be completed and returned to CCS by the fifth Working Day of every month during the Framework Contract Period and thereafter until all transactions relating to Call-Off Contracts have permanently ceased. If at any point there is a period of a month where no reportable transactions occur, then a declaration must be made confirming no business has been conducted, in place of data submission.

2.2	In an MI Report, the Supplier should report contract data that is one month in arrears. For example, if an invoice is raised for October but the work was actually completed in September, the Supplier must report the invoice in October's MI Report and not September's.  Each Order received by the Supplier must be reported only once, i.e. when the Order is received.

- Submitting the information

  - MI Reports shall be completed electronically and uploaded to the CCS data submission service available at: https://www.reportmi.crowncommercial.gov.uk

MI Reports must be completed in pounds sterling unless CCS has given prior written consent to the use of another currency.

CCS may reasonably require that MI Reports be submitted by an alternative means such as email.

Where requested by CCS, the Supplier shall provide Management Information to a Buyer as specified by CCS.

The Supplier shall:

3.4.1 promptly after the Framework Start Date provide an email and/or postal address to which CCS will send invoices for the Management Charge and monthly statements relating to the invoicing of the Management Charge;

3.4.2 promptly after the Framework Start Date provide at least one contact name and contact details for the purposes of queries relating to either Management Information or invoicing; and

3.4.3 immediately notify CCS of any changes to the details previously provided to CCS under this Paragraph 3.4.

How CCS can use the Management Information

The Supplier grants CCS a non-exclusive, transferable, perpetual, irrevocable, royalty free licence to:

use and to share with any Buyer, Other Contracting Authority and relevant person; and/or

publish (subject to any information that is exempt from disclosure in accordance with the provisions of FOIA, being redacted),

any Management Information supplied to CCS for CCS’ normal operational activities including administering this Contract and/or all Call-Off Contracts, monitoring public sector expenditure, identifying savings or potential savings and planning future procurement activity.

CCS may consult with the Supplier to inform its decision to publish information. However, CCS shall retain absolute discretion regarding the extent, content and format of any disclosure.

Following receipt of the completed MI Report, CCS shall invoice the Supplier for the Management Charge payable for the Month to which the MI report relates.

Paying the Management Charge

The Management Charge excludes VAT which is payable on provision of a valid VAT invoice.

The Supplier shall pay CCS the Management Charge (and other charges payable in accordance with this Schedule) in cleared funds within 30 days of receipt by the Supplier of an undisputed invoice to such bank or building society account set out in the invoice.

What happens if the Management Charge is not paid?

6.1    Payment of undisputed and valid CCS invoices should be completed within thirty (30) days. CCS may take action on outstanding invoices by:

6.1.1	issuing the supplier with reminders that an invoice payment is due and/or overdue;

6.1.2	charging statutory interest and charges on overdue invoices, as per the Late Payment of Commercial Debts (Interest) Act 1998;

6.1.3	suspending the supplier from the agreement until such time that overdue invoices are paid; and/or

6.1.4  terminating this contract.

6.2	If an Audit reveals that the Supplier has not paid any amount equal to or greater than:

6.2.1 	one percent (1%) of the Management Charge due in respect of any one Contract Year or of any Call-Off Contract then, without prejudice to CCS’s other rights under this Framework Contract, the Supplier shall reimburse CCS its reasonable costs incurred in relation to the Audit; and

6.2.2	five per cent (5%) of the Management Charge due in respect of any one Contract Year of this Framework Contract or of any Call-Off Contract then, without prejudice to CCS’s other rights under the Framework Contract, the supplier reimburse CCS its reasonable costs incurred in relation to the Audit and CCS shall be entitled to terminate this Framework Contract.

- What happens if the Management Information is wrong?

  - If the Supplier or CCS identify error(s) and/or omission(s) in historic MI Report(s), the Supplier must provide corrected MI report(s) to CCS on or before the date when the next MI Report is due.  Corrections may be either in the form of an addendum to the next MI submission, or a resubmission of existing historic returns, at the discretion of CCS.

Following an MI Failure, CCS may issue reminders to the Supplier and require the Supplier to correctly complete the MI Report.  The Supplier shall rectify any deficient or incomplete MI Report as soon as possible and not more than five (5) Working Days following receipt of any such reminder.

Meetings

The Supplier agrees to attend meetings between the Parties in person to discuss the circumstances of any MI Failure(s) at the request of CCS.  If CCS requests such a meeting the Supplier shall propose and document measures as part of a Rectification Plan to ensure that the MI Failure(s) are corrected and do not occur in the future.

Admin fees

If, in any rolling three (3) Month period, two (2) or more MI Failures occur, the Supplier acknowledges and agrees that CCS shall have the right to invoice the Supplier Admin Fee(s) with respect to any MI Failures as they arise in subsequent Months.

The Supplier acknowledges and agrees that the Admin Fees are a fair reflection of the additional costs incurred by CCS as a result of the Supplier failing to provide Management Information as required by this Contract.

What happens if Management Information Reports are not provided?

If two (2) MI Reports are not provided in any rolling six (6) month period then an MI Default shall be deemed to have occurred and CCS shall be entitled to:

charge and the Supplier shall pay a Default Management Charge in respect of the Months in which the MI Default occurred and subsequent Months in which they continue, calculated in accordance with Paragraph 8.2.1 and/or

suspend the Supplier from the agreement until such time that deficient MI reports(s) are rectified; and/or

terminate this Contract.

The Default Management Charge shall be the higher of:

the average Management Charge paid or payable by the Supplier in the previous six (6) Month period or, if the MI Default occurred within less than six (6) months from the commencement date of the first Call-Off Contract, in the whole period preceding the date on which the MI Default occurred; or

the sum of five hundred pounds (£500).

If the Supplier provides sufficient Management Information to rectify any MI Default(s) to the satisfaction of CCS and the Management Information demonstrates that:

the Supplier has overpaid the Management Charge as a result of the application of the Default Management Charge then the Supplier shall be entitled to a refund of the overpayment, net of any Admin Fees where applicable; or

the Supplier has underpaid the Management Charge during the period when a Default Management Charge was applied, then CCS shall be entitled to immediate payment of the balance as a debt together with interest.

# Annex: MI Reporting Template

[Guidance Note: Framework-specific template must be inserted.

The MI Collection team in Data Insights create MI Templates. A minimum standard template is embedded below.

Contact:

https://www.reportmi.crowncommercial.gov.uk/

# Joint Schedule 3 (Insurance Requirements)

### The insurance you need to have

  - The Supplier shall take out and maintain, or procure the taking out and maintenance of the insurances as set out in the Annex to this Schedule, any additional insurances required under a Call-Off Contract (specified in the applicable Order Form) ("Additional Insurances") and any other insurances as may be required by applicable Law (together the “Insurances”).  The Supplier shall ensure that each of the Insurances is effective no later than:

the Framework Start Date in respect of those Insurances set out in the Annex to this Schedule and those required by applicable Law; and

the Call-Off Contract Effective Date in respect of the Additional Insurances.

The Insurances shall be:

maintained in accordance with Good Industry Practice;

(so far as is reasonably practicable) on terms no less favourable than those generally available to a prudent contractor in respect of risks insured in the international insurance market from time to time;

taken out and maintained with insurers of good financial standing and good repute in the international insurance market; and

maintained for at least six (6) years after the End Date.

The Supplier shall ensure that the public and products liability policy contain an indemnity to principals clause under which the Relevant Authority shall be indemnified in respect of claims made against the Relevant Authority in respect of death or bodily injury or third party property damage arising out of or in connection with the Deliverables and for which the Supplier is legally liable.

### How to manage the insurance

Without limiting the other provisions of this Contract, the Supplier shall:

take or procure the taking of all reasonable risk management and risk control measures in relation to Deliverables as it would be reasonable to expect of a prudent contractor acting in accordance with Good Industry Practice, including the investigation and reports of relevant claims to insurers;

promptly notify the insurers in writing of any relevant material fact under any Insurances of which the Supplier is or becomes aware; and

Hold all policies in respect of the Insurances and cause any insurance broker affecting the Insurances to hold any insurance slips and other evidence of placing cover representing any of the Insurances to which it is a party.

### What happens if you aren’t insured

The Supplier shall not take any action or fail to take any action or (insofar as is reasonably within its power) permit anything to occur in relation to it which would entitle any insurer to refuse to pay any claim under any of the Insurances.

Where the Supplier has failed to purchase or maintain any of the Insurances in full force and effect, the Relevant Authority may elect (but shall not be obliged) following written notice to the Supplier to purchase the relevant Insurances and recover the reasonable premium and other reasonable costs incurred in connection therewith as a debt due from the Supplier.

### Evidence of insurance you must provide

The Supplier shall upon the Start Date and within 15 Working Days after the renewal of each of the Insurances, provide evidence, in a form satisfactory to the Relevant Authority, that the Insurances are in force and effect and meet in full the requirements of this Schedule.

### Making sure you are insured to the required amount

The Supplier shall ensure that any Insurances which are stated to have a minimum limit "in the aggregate" are maintained at all times for the minimum limit of indemnity specified in this Contract and if any claims are made which do not relate to this Contract then the Supplier shall notify the Relevant Authority and provide details of its proposed solution for maintaining the minimum limit of indemnity.

### Cancelled Insurance

The Supplier shall notify the Relevant Authority in writing at least five (5) Working Days prior to the cancellation, suspension, termination or non-renewal of any of the Insurances.

The Supplier shall ensure that nothing is done which would entitle the relevant insurer to cancel, rescind or suspend any insurance or cover, or to treat any insurance, cover or claim as voided in whole or part.  The Supplier shall use all reasonable endeavours to notify the Relevant Authority (subject to third party confidentiality obligations) as soon as practicable when it becomes aware of any relevant fact, circumstance or matter which has caused, or is reasonably likely to provide grounds to, the relevant insurer to give notice to cancel, rescind, suspend or void any insurance, or any cover or claim under any insurance in whole or in part.

### Insurance claims

The Supplier shall promptly notify to insurers any matter arising from, or in relation to, the Deliverables, or each Contract for which it may be entitled to claim under any of the Insurances.  In the event that the Relevant Authority receives a claim relating to or arising out of a Contract or the Deliverables, the Supplier shall cooperate with the Relevant Authority and assist it in dealing with such claims including without limitation providing information and documentation in a timely manner.

Except where the Relevant Authority is the claimant party, the Supplier shall give the Relevant Authority notice within twenty (20) Working Days after any insurance claim in excess of 10% of the sum required to be insured pursuant to Paragraph 5.1 relating to or arising out of the provision of the Deliverables or this Contract on any of the Insurances or which, but for the application of the applicable policy excess, would be made on any of the Insurances and (if required by the Relevant Authority) full details of the incident giving rise to the claim.

Where any Insurance requires payment of a premium, the Supplier shall be liable for and shall promptly pay such premium.

Where any Insurance is subject to an excess or deductible below which the indemnity from insurers is excluded, the Supplier shall be liable for such excess or deductible.  The Supplier shall not be entitled to recover from the Relevant Authority any sum paid by way of excess or deductible under the Insurances whether under the terms of this Contract or otherwise.

# ANNEX: REQUIRED INSURANCES

- The Supplier shall hold the following [standard] insurance cover from the Framework Start Date in accordance with this Schedule:

  - professional indemnity insurance [with cover (for a single event or a series of related events and in the aggregate) of not less than] five million pounds (£5,000,000);

public liability insurance [with cover (for a single event or a series of related events and in the aggregate)] of not less than five million pounds (£5,000,000); and

employers’ liability insurance [with cover (for a single event or a series of related events and in the aggregate) of not less than] five million pounds (£5,000,000).

[Guidance: adjust the above as required for your procurement and add any other insurance required for the framework tender. Note that this is not the place for Additional Insurances – they are specified in the order form by the Buyer.

# Joint Schedule 4 (Commercially Sensitive Information)

- What is Commercially Sensitive Information?

  - In this Schedule the Parties have sought to identify the Supplier's Confidential Information that is genuinely commercially sensitive and the disclosure of which would be the subject of an exemption under the FOIA and the EIRs.

Where possible, the Parties have sought to identify when any relevant Information will cease to fall into the category of Information to which this Schedule applies in the table below and in the Order Form (which shall be deemed incorporated into the table below).

Without prejudice to the Relevant Authority's obligation to disclose Information in accordance with FOIA or Clause 16 (When you can share information), the Relevant Authority will, in its sole discretion, acting reasonably, seek to apply the relevant exemption set out in the FOIA to the following Information:

| No. | Date | Item(s) | Duration of Confidentiality |
| --- | --- | --- | --- |
|  | August 2023 | Team details and CVs – this information is of commercial value to other suppliers and recruitment agencies | Project duration plus 5 years |
|  | August 2023 | Day rates – this information is of commercial value to competitors | Project duration plus 5 years |
|  | August 2023 | Project methodologies from PA and key sub-contractors – this information is of commercial value to competitors | Project duration plus 5 years |