Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

Research Specification: customer perceptions of personalised digital prompts

CCS Research & Insights DPS (RM6126)

Invitation to Tender

January 2023

Definitions

“Confidential Information” - all information, whether written or oral (however recorded), 				provided by the disclosing Party to the receiving Party and 					which (i) is known by the receiving Party to be confidential; (ii) 				is marked as or stated to be confidential; or (iii) ought 					reasonably to be considered by the receiving Party to be 					confidential;

“Economic Operator” - means any person or public entity or group of such persons and 				entities, including any temporary association of undertakings, which 			offers the execution of works or a work, the supply of products or the 			provision of services on the market.

“Public Contracts Regulations” - means the Regulations laid down in statute in the Public 					Contracts Regulations 2015 and any subsequent 						amendments.

“Sub-contractor" - 	any third party with whom:

(a) the Supplier enters into a Subcontract; or

(b) a third party under (a) above enters into a 		Subcontract,

or the servants or agents of that third party;

“Supplier” -	 has the meaning given in the Form of Agreement;

“Tender” -	 means the formal offer or proposal submitted by a Tenderer in response to 		the Client’s invitation to tender.

“Tenderer” - 	means an Economic Operator that has submitted a Tender.

Contents

Overview of Requirements	4

1.	Introduction	4

2.	Context	4

3.	Research Aims & Objectives	5

4	Methodology & Scope	6

5	Timetable	7

6	Length of Contract	8

7	Outputs	8

8	Quality and Risk Management	9

9	Expertise and Capability	10

10	Project Management and Contract Administration	11

11	Queries on this research specification	11

Submission of Tenders	11

12	Information on how and when to return tenders	11

13	Summary of requirements	12

14	Alternative Bids	14

Evaluation Criteria	14

15	Tender Evaluation approach	14

16	Quality criteria and how we assess quality	15

17	Price and how we assess price	17

18	Summary of evaluation criteria	19

19	Group Bids	19

# Overview of Requirements

## Introduction

  - HM Revenue & Customs (HMRC) invites Tenderers from the Research & Insights DPS (RM6126) to undertake qualitative research aimed at understanding customer perception of personalised “intelligent” digital prompts in their digital filing journeys.

  - HMRC intends for this contract to be in place by w/c 13th March 2023, with final outputs expected by 31st July 2023 at the latest.

  - HMRC will maintain the overall management of the project.

  - The contract will be awarded to the organisation that is deemed to have submitted the most economically advantageous tender (MEAT). Assessment will be based on the factors outlined in sections 15 to 18.

  - To ensure fairness all tenderers are required to submit their tenders in accordance with these instructions and any further requirements contained in the invitation letter. Failure to comply could invalidate your tender.

## Context

  - HMRC’s Digital Prompts (DP) Programme aims to reduce tax errors made by customers submitting tax returns. DP involves presenting nudges to taxpayers as they make submissions, highlighting potential specific mistakes, general potential problems, and directing them to relevant guidance/support.

  - HMRC has previously used basic digital prompts to ‘pop-up’ messages to influence customer behaviour in digital filing journeys with the aim to reduce errors made by customers submitting returns. New technology (data-mastery) now allows for more personalised ‘intelligent’ prompts, drawing on wider HMRC data sources which should be more impactful than basic prompts. Previous research on Self Assessment customers’ responses to trigger prompts (HMRC report 602, 2017) supports the value of basic prompts. However, we lack detailed understanding of the behavioural change value ‘premium’ and improved customer experience to be generated by intelligent prompts.

  - Although the DP Programme has trialled some personalised intelligent prompt examples for customers submitting their 2020 to 2021 returns, with further live trials proposed for implementation, most existing prompts are basic and not personalised.

  - While ongoing trials will provide quantitative data to show whether personalised intelligent prompts are more effective than basic prompts, HMRC requires qualitative research and insight to understand which kinds of intelligent prompts work best and why, as well as understanding participants thoughts and feelings when presented with intelligent prompts to better interpret the quantitative data. Quantitative data from ongoing trials may inform the development of topic guides for in-depth interviews and present areas that can be probed further during interviews.

  - The findings from this research will be used to fill a significant evidence gap surrounding the perceptions of personalised intelligent digital prompts. Understanding the premium from designing personalised intelligent prompts will help HMRC invest in system architecture changes underpinned by evidence and insight and will support Transactional Risking as part of Making Tax Digital (MTD).

## Research Aims & Objectives

  - The core objective of this research is to gain a greater understanding of customer perceptions of personalised ‘intelligent’ digital prompts during their digital filing journeys. Exploring whether intelligent prompts are perceived as:

  - supportive and helpful to the customer

  - corrective and/or judgemental, or

  - less supportive and more unhelpful by adding undue pressure to change details.

  - The research aims to answer the following questions:

- Is there a value “premium” in terms of positive behavioural change from the use of personalised digital prompts?

- Is there a reputational impact for HMRC in fielding personalised prompts? E.g. positive perception of HMRC’s power, capability and reach, or negative perception of HMRC’s capability if prompts are incorrectly targeted?

- Do personalised intelligent prompts create a greater impact by indicating HMRC uses customer data compared to generic digital prompts?

- If the customer is advised to ‘take required and appropriate action’, would they have the capacity/capability to do so themselves? If not, how would they take action (e.g. defer or seek advice, either from HMRC, friends/family or tax advisors)?

- What are customers’ perceptions towards the information provided – did customers want to check or change the information provided/held by HMRC?

- What is the impact of a secondary prompt built into filing processes? Some intelligent prompts being trialled pre-select sections of the tax return for customers. If they de-select the sections, then a second prompt asks them to check if this is what they really want to do. How would the customer respond to this?

- Would customers try to ‘game’ the intended action of the prompt (i.e. keep amending a figure until the prompt disappears, or act on the prompt and change other details to get the same result)?

- How do customers perceive personalised data delivered via a digital prompt compared to a non-digital HMRC channel (e.g. a letter)?

## Methodology & Scope

HMRC requires qualitative research that must involve a minimum of 45 in-depth interviews. The in-depth interviews will be undertaken with Income Tax Self Assessment (ITSA) customers, to explore their digital Self Assessment filing journey. The interviews will ascertain customer reactions and perceptions to basic and personalised intelligent prompts.

HMRC requests that the interviews will be with customers who have filed their Income Tax Self Assessment (ITSA) digitally. There are several digital compliance interventions in the form of intelligent prompt trials that are currently underway, however, not all customers will have been previously exposed to them. Therefore, the methodology must take into account customers who may have seen personalised digital prompts before (though they may not be initially aware) and those who have not.

The nature of intelligent personalised prompts must be explained/shown to the participants. They must then be asked hypothetical questions to explore how they would feel should they see a personalised intelligent prompt during their tax return. This could be in terms of asking how customers would feel if they were exposed to personalised intelligent prompts in real time, compared to how they would feel about receiving a letter containing written personalised prompts.

Tenderers must demonstrate their proposed approach to maximise the value of these in-depth interviews. We also welcome suggestions on the relevant use of stimulus materials that are appropriate for this type of research.

4.2 Sample

The sample for the research should be split into the following sub-groupings, with a minimum of 15 participants in each group:

- ITSA business customers new to filing (2 years or less) with no tax agent

- ITSA non-business customers new to filing (2 years or less) with no tax agent

- ITSA customers (a mixture of business and non-business) with no tax agent but with 3 or more years of filing history

All ITSA customers must have filed their tax return for the year 2021 to 2022 (deadline 31st January 2023) so their filing journeys are recent to improve recall and engagement during the interviews.

Please note that HMRC will not be able to supply a sample of ITSA customers to the supplier, so bidders must demonstrate how they would find and recruit the sample within the timescales.

Bidders can provide alternative target sample sizes that they deem appropriate for robust analyses between a range of customer segments. Bidders must then provide their rationale in their tenders. The successful bidder will be expected to meet these targets.

HMRC are open to suggestions and welcome suppliers to suggest alternative methodologies that would also meet the project objectives as an alternative bid (see section 14). Any alternative methodology must be separately costed with supporting justification.

HMRC will design the exact approach in collaboration with the research contractor. Suppliers must consider in their methodology how they will address any other challenges they identify as pertinent to this project. Suppliers must identify in their bid any related annexes and risks relating to the methodology, and distinct mitigations or plans to handle these risks.

4.3 Analysis

The Supplier must demonstrate how they will robustly analyse the data to answer the research questions outlined in 3.2. We anticipate the successful contractor will draft and confirm the research materials and the analysis plan alongside HMRC, the outputs required from the analysis are outlined in section 7.

## Timetable

  - The timeline provided below is indicative of the timelines expected by HMRC. Tenderers are required to demonstrate in their tenders that they will be able to complete the research within the below timelines or sooner.

| Activity | Date |
| --- | --- |
| ITT issued | Monday 23rd January 2023 |
| Deadline for queries on ITT | 5pm on Monday 30th January 2023 |
| HMRC response to ITT queries | 5pm on Thursday 2nd February 2023 |
| Notification of intention to bid | 5pm on Wednesday 8th February 2023 |
| Deadline for response to ITT | 5pm on Friday 17th February 2023 |
| Contract awarded | w/c Monday 13th March 2023 |
| Set-up meeting | w/c Monday 20th March 2023 |
| Fieldwork | April to May 2023 |
| Presentation of interim findings | April to May 2023 |
| Presentation of findings | June 2023 |
| Final outputs signed off, project close | July 2023 |

  - The successful Supplier will be expected to attend a set-up meeting in the week commencing Monday 20th March 2023.

  - All stages of the project must be completed by 31 July 2023. Tenderers must demonstrate that they can meet this deadline.

## Length of Contract

  - The contract term will be for 9 months with an optional extension period of 3 months.

## Outputs

  - The Supplier must deliver the following outputs:

- A detailed project plan that outlines key dates and milestones and indicates any actions for HMRC, including revisions should any substantial changes to this plan occur.

- Lead an initial project set-up meeting to further plan the project.

- Draft and final copies of the screener which will be used during recruitment.

- Draft and final copies of topic guides.

- Weekly, written progress updates and additional updates when requested (such as during recruitment and fieldwork).

- The first five anonymised transcripts, to be delivered before the interim findings, to review how the topic guide is working in practice and whether any amendments are required to ensure objectives are met.

- An ‘informal’ presentation/written report of interim findings.

- An analysis plan and outputs produced from analysis sessions detailed enough for HMRC to follow to quality assure the data, results, and outputs – to be sent to HMRC to quality assure before the final findings presentation.

- A presentation of final findings, with draft and final copies of the slides/materials used.

- Draft and final copies of a written report of the findings from the research project including but not limited to; an executive summary, and a technical appendix that is suitable for publication. Draft copies must be in the same format of the final report’s intended structure.

  - All summaries, reports, data outputs (e.g. tables and graphs) and presentations should be provided in an electronic format, compatible with Microsoft Office applications. All presentations and reports should be concise and written in plain English. They should be of a high (publishable) standard suitable for online publication.  HMRC expects all drafts to be complete, to have been proof-read before delivery and for data in the drafts to have been quality assured. HMRC may arrange for any final reports produced to be peer-reviewed, either in-house or externally.

  - Tenderers are also reminded that any research reports to be published on www.gov.uk must meet the accessibility requirements for public sector bodies’ publications:

https://www.gov.uk/guidance/accessibility-requirements-for-public-sector-websites-and-apps#accessibility-standards

## Quality and Risk Management

  - Tenderers must include a project plan and time schedule for the work that identifies the main tasks and key milestones that will be used to monitor progress, indicating clearly where HMRC is expected to contribute.

  - Tenderers must include a quality control plan with their proposal, which must demonstrate their internal procedures to assure quality control. This must include a strategy for receiving a response rate to meet our minimum targets for each outlined sample group and securing reliable qualitative data from respondents. This should also include monitoring interviewers’ performance and producing high quality analysis and outputs that meets HMRC’s requirements.

  - Tenders must also include an assessment of the key risks to this project. This should identify the most significant risks to successful completion of the programme of work, assess the degree of risk (likelihood and impact), and set out strategies for minimising these risks and managing the consequences if problems occur. A risk register template is attached.

## Expertise and Capability

  - HMRC acknowledges that considerable resources are required for the successful delivery of this project to time. It is possible that agencies invited to tender have the skills and ability within their organisation to undertake all or part of this research but do not have sufficient resources required to successfully deliver the whole research requirement. We therefore encourage agencies to collaborate with other suppliers if required to ensure that they are fully capable of undertaking this work.

  - HMRC is looking for tenderers who can demonstrate that their proposed team incorporates those with:

- An understanding of the context of the research and the ability to understand and look at research within a broader strategic context

- Expertise to deliver the required methodology and scope.

- An organisational capacity to deliver the project within the timelines given.

- Experience of conducting qualitative research and building strong interviewer-participant rapport with individuals on potentially sensitive topics, ideally related to tax.

  - Proposals must summarise the skills and expertise relevant to this requirement that particular members of staff bring to the team and clearly identify the project manager, with CVs included as an annex, which should not have any pictures of members of staff.

  - The tender must specify details of which parts (if any) of the project will be sub-contracted, the name of the sub-contractor who will work on the project, their experience of related research, and their responsibilities within the project. If it is proposed to sub-contract any of the work, the same details as those provided by the tenderer should be given about the qualifications, experience and responsibilities of sub-contractor staff involved along with a description of their respective roles and the management arrangements put in place.  Ultimately, the successful Supplier will be held to account for the performance of any sub-contractor and needs to demonstrate their confidence to successfully manage sub-contractors. This should also be considered for any joint submissions, as the second tenderer will be treated as a sub-contractor.

## Project Management and Contract Administration

  - Amba Moffitt is HMRC Manager for this project. They will be responsible for the day-to-day management of the contract. Once the contract has been awarded, all contact with HMRC concerning the project should be made through them. The research organisation will be required to appoint a contract manager who will act as the principal point of contact for the Department.

  - The research organisation will be expected to work closely with the HMRC project manager and through them, with internal customers within HMRC throughout the duration of the contract. They must be kept informed of progress and be involved in key decisions. Proposed changes in project staffing (at all levels) or deviations from the agreed work programme must be discussed and agreed with the project manager in advance. Amba Moffitt is responsible for all decisions that involve funding.

  - In costing your tender you must allow for attendance at a minimum of 3 meetings. Most meetings are expected to take place remotely via Microsoft Teams. Although some may take place at HMRC offices in Manchester, Newcastle, Stratford, or the research organisation’s premises by arrangement. These might include the following:

- Project set-up meeting;

- Presentation of interim findings and ensure robustness of the 		research;

- Presentation of key findings and final analysis.

## Queries on this research specification

  - Tenderers with any queries about the research specification should contact Sam Burton on e-mail: sam.burton@hmrc.gov.uk.  The deadline for queries is 5 pm on Monday 30th January 2023. Responses will be sent to all tenderers by 5pm Thursday 2nd February 2023.

  - Please note that the responses to any queries will be shared with all tenderers. See 11.25 to 11.29 of the tender instructions for more information.

# Submission of Tenders

## Information on how and when to return tenders

  - Tenderers should provide notification of their intention to submit a tender by email to Sam Burton at sam.burton@hmrc.gov.uk by 5pm Wednesday 8th February 2023.

  - You must send a PDF or read-only electronic copy of your tender (excluding costs information which will be sent separately as an excel spreadsheet as per 12.3) by e-mail to arrive at the following address: Sam Burton at sam.burton@hmrc.gov.uk and Fintan Bradley at fintan.bradley@hmrc.gov.uk, no later than 5pm on Friday 17th February 2023 (unless the date is subsequently amended in writing by the Department). No hard copies of the tender are required.

  - Costs information should be submitted separately from the tender to the following email address: Fintan Bradley at fintan.bradley@hmrc.gov.uk by the same time as stated in 12.2. You should not send the costs information to the named contact in 12.2.

  - Tenderers should note the following:

| Action | Start date | End date | Contact |
| --- | --- | --- | --- |
| ITT issued | 23/01/23 | 23/01/23 | amba.moffitt@hmrc.gov.uk |
| Submit queries | 23/01/23 | 30/01/23 | sam.burton@hmrc.gov.uk |
| Answers will be provided by | 30/01/23 | 02/02/23 | amba.moffitt@hmrc.gov.uk or chloe.watts@hmrc.gov.uk |
| Notify your intention to submit a proposal | 23/01/23 | 08/02/23 | sam.burton@hmrc.gov.uk |
| Submit read only tender and costs via email | 23/01/23 | 17/02/23 | Tender: sam.burton@hmrc.gov.uk and fintan.bradley@hmrc.gov.uk Costs: fintan.bradley@hmrc.gov.uk |
| Evaluation | 20/02/23 | 10/03/23 | amba.moffitt@hmrc.gov.uk and fintan.bradley@hmrc.gov.uk |
| Contract award completed | w/c 13/03/23 | w/c 13/03/23 | fintan.bradley@hmrc.gov.uk |
| Unsuccessful providers notified of outcome | w/c 13/03/23 | w/c 13/03/23 | fintan.bradley@hmrc.gov.uk |

  - If your tender is submitted in the name of one company or organisation but you intend submitting invoices in the name of another, or require payments to be made to another, please give full details. Otherwise, there may be delay in payment.

## Summary of requirements

  - Tenders must include the following information:

- A written tender in a read-only pdf including:

      - A detailed written tender detailing how you will meet the requirements, aims and objectives as outlined in Sections 3-10 of the ITT. This must also include the proposed team composition including the staffing level (grade) of each member of the team and the number of days given to each key stage of the project per team member in this section (excluding costs). This document must not exceed 25 pages; information beyond this limit will not be considered during evaluation;

- Where incentives are proposed, you must include a description of the type of incentive to be used and their total cost in your written tender (no other cost should be contained within your written proposal).

- A detailed timetable for the proposed research for each specific information requirement, taking into account that outlined in Section 5;

- A quality control plan as requested in 8.2 to demonstrate the procedures that will be implemented to assure quality control. This particular document must be attached to the written tender as an annex and not exceed 2 pages; information beyond this limit will not be considered during evaluation;

- A risk register as outlined in 8.3 which outlines in detail the risks to the project and methods for mitigating them. This particular document must be attached to the written tender as an annex and not exceed 2 pages; information beyond this limit will not be considered during evaluation;

- The Curriculum Vitae (CV) of key personnel proposed, their status within the company and area of expertise. This particular document must be attached to the written tender as an annex and each CV must not exceed 2 pages; information beyond this limit will not be considered during evaluation.  The CVs must not include any pictures of the personnel.

- A firm price (exclusive of VAT) in a read-only excel spreadsheet as detailed in Section 17. This must be separate from the proposal. It must include:

- a firm and specific total price;

- Details of key individual personnel’s chargeable day rates;

- Chargeable rates for other personnel proposed. Where these can be identified as groups (e.g. administration, support etc.) then a group rate will suffice;

- Any further costs identified.

- A fully completed compliance check form (see Annex C) which provides the information necessary for HMRC to undertake the appropriate tax compliance checks. By providing the details requested on this form the tenderer consents to HMRC completing tax compliance checks on their organisation. The Sub-Contractors Revenue Compliance Consent form (see Annex E) will also be required where the supplier intends to use key subcontractors to deliver the service.

- A fully completed security questionnaire, provided in Annex B.  The purpose of this is to outline the tenderer’s security arrangements.  

This will not be evaluated to determine the highest-scoring tenderer as part of the tender, but as per 5.7 and 5.8 of the Tendering Instructions document that will be provided, each tenderer will need to complete this in full prior to be considered for award.

  - Tenders must not exceed 25 pages (excluding annexes). Information included after this limit will not be considered.

## Alternative Bids

14.1 HMRC welcome tenders to also provide a secondary proposal outlining an alternative approach to meet the research aims and objectives. Tenders must provide justification for how you would meet the specified requirements set out in the ITT and costs for the suggested alternative in addition to costings for the approach set out in this tender.

14.2 Alternative approaches will only be considered where provided for in the ITT and when accompanied by a fully compliant primary tender.

14.3 Both the primary tender and the alternative approach should be submitted in the one tender document.

14.4 Where an alternative approach has been invited and submitted, HMRC will first fully evaluate the primary tender by scoring all of the responses to the sections under the Quality and Price sections.

14.5 Once all of the responses to the Quality and Price sections in the primary tender have been scored, a total score for that bid, according to the weightings as specified in the ITT, will be calculated.

14.6 HMRC will then (a) review the alternative approach in order to identify the differences between the primary and the alternative approach and (b) adjust each score for the Quality and Cost sections in the primary tender to take account of the extent of changes contained in the alternative approach to arrive at a new overall score for the alternative approach.

14.7 The overall score achieved for the primary tender and the alternative approach will then be compared and the one with the highest overall score will be taken forward for the purpose of comparison with the scores of other tenderers.

# Evaluation Criteria

## Tender Evaluation approach

  - HMRC will evaluate the contract based on MEAT. Quality forms 80 per cent and price 20 per cent of our assessment of MEAT.

## Quality criteria and how we assess quality

  - The tender will be evaluated by a minimum of 3 evaluators to determine the Quality score.

  - Quality will be assessed separately to cost. Quality criteria will be evaluated on a scale from 0 to 100 (where 0 = totally fails to meet the criteria and 100 = fully meets the requirement, with detailed explanation/evidence in support). A detailed breakdown of the evaluation methodology is as follows:

| Score | ‘Open’ Question Criteria |
| --- | --- |
| 100 | The response is excellent and completely relevant. The response is comprehensive, unambiguous and demonstrates an excellent understanding of, and meets, the requirements in all aspects, with no clarification required. The response is well thought out and/or provides - highly credible examples; - benefits; or - innovation |
| 80 | The response is good and highly relevant. The response indicates a good understanding of the requirements and provides sufficient detail across all areas. The response demonstrates how the requirements will be met in the main, which may require minor clarification only. |
| 60 | The response is satisfactory and relevant. The response indicates a satisfactory understanding of the requirements in most aspects, although may lack detail in certain areas. The response suggests that the requirements would be met satisfactorily but may require some clarification. |
| 40 | The response is limited and partially relevant. The response indicates partial understanding of the requirement. The response contains ambiguities which suggests that the requirements would not be met unless significant revisions were made to the proposal. |
| 20 | The response is poor and only partially relevant. The response addresses some aspects of the requirements but contains insufficient/limited detail or explanation. The response demonstrates only limited understanding of the requirement. The response contains deficiencies which suggest the requirements would not be met. |
| 0 | The response is not considered relevant. The response is unconvincing, flawed or otherwise unacceptable. Response fails to demonstrate an understanding of the requirement. |

  - HMRC reserves the right to not consider for award a tender that scores below  60% in any of the quality criteria as listed at 16.5.

  - Tenderers must submit a written tender demonstrating how they can best meet HMRC’s research and service delivery requirements as set out within sections 3-10 of this ITT. In their tender tenderers will be evaluated on:

- Addressing Aims & Objectives (15%)

- The extent to which the proposed approach demonstrates that it will deliver in full the aims and objectives as specified in Section 3.

- The extent to which the tenderer demonstrates that they have understood the context and key issues for the project and have subsequently presented an approach which has been tailored to meet HMRC’s requirements.

- Methodology and scope (25%)

- The extent to which the proposed methodology meets the requirements as set out in Section 4 in full.

- The extent to which the tenderer proposes an appropriate and effective recruitment strategy for the specified research participants

- The extent to which data collection strategies maximise successful contact with the sample.

- The extent to which the tenderer can demonstrate that their approach incorporates proven methods to maximise response rates and manage recruitment risk.

- The extent to which the approach to developing research tools meets the requirements for robust findings.

- The extent to which the proposed outputs meet the requirements as set out in Section 7 in full, and the extent to which these have been tailored to best suit the aims and objectives.

- The extent to which key risks to the project have been identified in the risk register and how effective the proposed mitigation strategies are in minimising the impact and/or likelihood of these risks.

- Project Plan (15%)

- Whether the tenderer has satisfactorily demonstrated that their strategy will deliver each of the required activities as set out in Section 5 and any additional activities as outlined by the tenderer in their approach, in full within the required timelines or sooner.

- The extent to which key risks to the project have been identified in the risk register and how effective the proposed mitigation strategies are in minimising the impact and/or likelihood of these risks.

- Team (10%)

- The extent to which the tenderer can demonstrate that their proposed team meets the required experience and expertise in full as outlined in Section 9.  Please include the staffing level of each member of the team and the number of days given to each key stage of the project per team member in this section (but do not include the costs).

- The extent to which the tenderer demonstrates that their proposed team composition and team management approach will ensure that the team has the capacity to deliver the requirement in full, even during busy periods or in periods of absence and/or illness.

- Quality standards (15%)

- Whether the tenderer has satisfactorily demonstrated that they are able to meet the professional accreditation and/or quality standards as set out in Section 8.

- The extent to which the quality control plan submitted by the tenderer satisfactorily demonstrates that the proposed internal procedures will effectively assure quality control as set out in clause 8.3 of the ITT.

  - Tenderers should set out their tender according to the quality criteria set out under 16.4 but can add additional sections such as an introduction and summary.

  - HMRC may invite tenderers to clarify elements of their tender as part of the process to assess the quality score.

## Price and how we assess price

  - The budget available for this research is £70,000.  Tenderers are asked to submit costings within this budget.

  - Due to budgetary constraints, HMRC may not consider for award a tender with a total cost exceeding £70,000.

  - For evaluation purposes, price forms 20% of the tenderer’s overall score.

  - Tenderers must separately provide a firm total cost offer (excluding VAT) giving a breakdown of costs in ‘person days’ to each task, as outlined below. This should be sent separately from the main tender. Separate tables should be provided for the lead tenderer and any sub-contractor.

Team to specify detail of costs table

| Activity | Personnel staffing level (grade) | Number of days per team member | Day rate per team member | Over-heads | Total (£) |
| --- | --- | --- | --- | --- | --- |
| Project Management: including initial setup meeting, regular updates, progress checks and additional meetings |  |  |  |  |  |
| Draft and final copies of research materials, agreed with HMRC |  |  |  |  |  |
| Recruitment of participants |  |  |  |  |  |
| Fieldwork: delivery of qualitative interviews (minimum of 45) |  |  |  |  |  |
| Analysis: including analysis plan |  |  |  |  |  |
| Presentation of interim and final findings (inclusive of drafting and amends) |  |  |  |  |  |
| Writing of final report for publication on GOV.UK (inclusive of drafting and amends to draft report) |  |  |  |  |  |
| Other costs, including administration, travel and subsistence |  |  |  |  |  |
| VAT (if applicable) |  |  |  |  |  |

  - For the avoidance of doubt, the unit costs/rate provided in the cost model at 17.4 must be the total cost of delivering that activity/service, inclusive of all third-party costs.

  - Tenders that do not supply a schedule of costs in the format outlined above will not be accepted. Rows/columns can be added to the above table as necessary.

  - HMRC may require additional meetings and presentations to those as itemised in paragraph 10.3 above. Tenderers must supply costs per meeting and presentation.

  - If the decision not to continue with this project at any stage has additional costs associated, this must be clearly identified and a justification for these costs provided. Any additional costs identified will be subject to negotiation and agreement with HMRC prior to any contract being awarded.

## Summary of evaluation criteria

  - The scores for quality and cost will be added to provide an overall score from 0 to 100, as summarised below.

Scoring Matrix:

| Evaluation criteria | Weighting |
| --- | --- |
| Quality | 80% |
| - Addressing aims & objectives - Methodology & scope - Project Plan - Team - Quality standards | 15% 25% 15% 10% 15% |
| Price | 20% |
| Total | 100% |

  - The tender with the highest overall mark will be selected by HMRC as the tendering organisation deemed to best meet the requirement and provide greatest value for money.

  - Clarifications with tenderers may be required at any point of the tendering process in order to clarify any aspects of their proposals.

## Group Bids

  - A single entity must enter into the contract. In the event of a group of service providers submitting an acceptable offer, the group will be required to nominate a lead partner with whom the Authority can contract. Alternatively, the group will need to set up a special purpose vehicle (SPV) before contract signature. An undertaking that the group will so form themselves must be provided when the tender is submitted.

  - Where a group intends to form a SPV, as described above, they must provide the undertaking in the form of an electronic document (e.g., PDF), separate to other documents.

  - A fully completed compliance check form which provides the information necessary for HMRC to undertake the appropriate tax compliance checks, including the details of any proposed subcontractors and all group participants in the event of a group bid must be submitted with the tender. The Subcontractors Revenue Compliance Check form can be found in the ITT email.

HMRC research report 602: Customer responses to trigger prompts within the online Self Assessment tax return process (publishing.service.gov.uk)