Pre-Procurement Market Consultation for Coastal Works.   Small Projects.

- Context and purpose of document

In April of 2016 Coastal Partnership East (CPE) was formed when the coastal management teams of 4 local authorities (LA) joined to form a single unit.

Those LAs are North Norfolk (NNDC), Great Yarmouth (GYBC), Waveney (WDC) and Suffolk Coastal (SCDC) covering parts of the Anglia coast from Kelling in the north to Felixstowe in the south.  There is no lead authority.  The group is managed by a board made-up of representatives from each LA.

An early action by the CPE team is to seek contractors to deliver projects to repair and enhance coast protection structures, promenades and similar assets over the four LA frontages (Small Projects).  The individual value of each is in the range £20k to £150k, typically £50k.  The anticipated aggregated annual value is around £400k.

It is felt that a Framework covering all four LAs is the best method of delivering this objective.  The perceived benefits of a Framework are removal of the need for formal tenders for each separate work package with savings to all parties in time and cost, to allow each LA to contract directly with the supplier either by direct award or by use of a mini bid process and to enable a working relationship to develop between Framework suppliers and clients.

The Small Projects Framework needs to be in place by mid 2017 and will replace 3 existing and different works delivery models.

One LA (probably WDC) will lead the procurement process on behalf of the CPE group with the aim of creating a single works delivery model that other LAs will have access to.

The purpose of this document is to set out the proposed draft strategies for the procurement, contractual and operational arrangements for the new work delivery process and to raise awareness of the forthcoming tender amongst potential bidders and to identify options that are available in the market place.

Written comments on the draft proposals are invited, in particular to express preferences where options are shown and / or to suggest other approaches.  If a meeting is required a written request should be made not less than 7 days before the feedback deadline.

See Appendix A of this document for a list of issues which we seek your feedback on.

The feedback received will be used to maximise the attractiveness of the opportunity to assist the process and also to add efficiency, flexibility, value for money and revenue generation to the contract delivery phase.

CPE has a need to procure other services such as Minor R&M, consultancy and large (>£150k) complex civils projects.

Procurement of Minor R&M is to be the subject of a separate Market Testing consultation running in parallel with this one.

For the foreseeable future consultancy services and large (>£150k) complex civils projects will be let by individual competitive tenders or, in case of low value consultancy, by direct award under each LA Standing Orders .  Work of this nature is not covered by this consultation exercise.

It is at your discretion as to whether you wish to take part on this process.  Your decision to not reply will not affect your opportunity to bid for the works when / if they are formally tendered in the future. However, we would value your input.

To enable us to take full consideration of your comments can you please aim to respond within the indicative procurement timetable in Section 6.

- Scope of services, value estimates and duration

The anticipated scope of works on or adjacent to the coast to be covered in the Small Projects tender will include, but not be limited to:

- Works  of repair and / or enhancement  to structures on or adjacent to the coast e.g.

Concrete and masonry (including heritage) walls,

Concrete slabs and revetments,

Rock-filled gabions,

Rock armour groynes and revetments,

Flood embankments,

Sheet piling,

Timber groynes,

Timber revetments,

Slipways, ramps and steps to beach and over cliffs.

Local aids to navigation potentially including work afloat,

Promenades,

Cliff stabilisation,

Beach recycling,

Beach hazard clearance,

Drainage works.

It is anticipated that the framework contract will be in place from June 2017 and operate for up to 4 years with an option for the Employer to extend by up to 2 years.

The annual indicative anticipated spending forecast for each authority is shown in Table 1 below:

Table 1

| LA | Small projects £k |
| --- | --- |
| NNDC | 170 |
| GYBC | See note below. |
| WDC | 160 |
| SCDC | 70 |
| Totals | 400 |

GYBC would allocate funding on a project by project bases but there is no annual budget.

- Key aims

The key aims of the contract are to:

- provide each LA with access to suppliers with the capability, flexibility  and capacity to deliver Small Projects to repair / improve coastal structures;

- be broad enough to capture all foreseeable requirements;

- allow for flexibility to address changing work requirements and market conditions;

- give suppliers a long-term contract to enable them to invest in resource and build a strong working relationship with the client.

- Procurement strategy

The initial thought is that there is no requirement to break the Framework  into geographical Lots..

The Framework will comprise a group of 4 or 5 contractors who would then typically compete for projects via a mini bid process.

Each LA would issue Task Orders to the appropriate supplier(s) under the WDC-procured Framework.

The Framework Agreement will be established through an (OJEU compliant if applicable) Open tender procedure. WDC reserve the right to change the procurement process. Following an Open procedure is in accordance with central government policy to use it where possible to make the procurement quicker, simpler and more cost-effective for all parties. As such there will be no PQQ shortlisting process and all tenderers who are confident that they can meet the minimum requirements defined within the tender documentation will be able to submit bids.

- Indicative Procurement timetable (we reserve the right to amend)

The following timetable is proposed to undertake the procurement process:

The following timetable is proposed to undertake the framework procurement process:

Monday 6  February 2017 - Issue Market Consultation documents.

Wednesday 22 February 2017 - Market Consultation documents returned.

Thursday 23 February 2017 to Friday 10 March 2017 Market Consultation evaluation completed.

Week commencing Monday 20 March 2017 issue Invitation to Tender documents.

Invitation to Tender submissions on Friday 21 April 2017.

Tender Evaluation completed Friday 5 May 2017.

Approval process to award (if any contracts awarded) June 2017.

Framework commencement June 2017.

- Contracting strategy

It is envisaged that the framework will be let under the terms of the NEC3 Framework Agreement.  The call-off tasks will be let under the NEC3 Engineering and Construction Short contract.

The specification will be CESWI 7 with amendments.

The measurement of works shall use the current CESMM.

The valuation of work will be by use of Bill of Quantities or fixed price quotations determined on a job by job basis.

Suppliers shall provide a competent supervisory and admin resource to prepare all relevant Construction H&S works planning and control information and attend regular meetings with the client.

- Framework  management.

Waveney District Council is likely to be  responsible for the overall procurement of the framework and the CPE for its general operation.  Each participating LA will be able to call-off Tasks at any time.

A user manual including call-off guidance and framework governance will be created to ensure call-off consistency across the framework and allow for effective monitoring and continuous improvement.

8 Feedback

The proposals above are based upon lessons learned by CPE staff from operating current contracts over recent years.   CPE is very keen to understand how these proposals sit with the market.

Suppliers are therefore requested to provide a response to the attached feedback form in as much detail as necessary to assist with development of the scope, structure and operational requirements of this coastal works framework.

The feedback we receive will be invaluable in preparing the documents for a successful tender exercise.

Thank you in anticipation of your cooperation.

APPENDIX A  FEEDBACK FORM

Supplier Name:

Supplier Address:

Supplier Contact Name, email and telephone number:

Q1 Are you interested in bidding for a place on a Small Projects Framework? Response. Q2 From your perspective is a Small Projects Framework preferable to each Small Project being the subject of a bespoke open tender? Response. Q3 What would be the most appropriate number of contractors on a Small Projects Framework list? Response. Q4 Should the Small Projects Framework be broken in geographical Lots? If so what are appropriate boundaries? Response. Q5 The form of contract proposed to be used for works call off is the NEC3 Engineering and Construction Short contract, or a similar `Minor Works’ Contract. Does use of this form deter you from bidding? If yes what other contract form do you regard as more appropriate for the nature and scale of works proposed? Response Q6 A Framework period of 4 years is proposed with an option to extend by up to 3 years. What is your view on the optimum contract duration to maximise your interest in the tender? Response. Q7. Do you have any comments on the procurement timetable in Section 6? Response Q8. Please add any general additional feedback you would like to be considered. Response Q9. . Social Value. Link to https://www.gov.uk/government/publications/social-value-act-information-and-resources/social-value-act-information-and-resources Social Value. What is your view on if and how Social Value considerations might apply to a contract of this nature and scale? Response

Return this Form please to Paul Patterson Senior Coastal Engineer email  coastalmanagement@eastsuffolk.gov.uk by Wednesday 22 February 2017