Contract for Evaluation of The Teachers’ Student Loan Reimbursement Scheme

project reference nO: DFERPPU/EOR/SBU/2018/004

This Contract is dated 6 June 2018

Parties

1)	The Secretary of State for Education whose Head Office is at Sanctuary Buildings, Great Smith Street, London, SW1P 3BT (“the Department”); and

2)	CFE Research whose registered office is CFE Research Ltd., Phoenix Yard, Upper Brown St, Leicester, LE1 5TE (“the Contractor”).

Recitals

The Contractor has agreed to undertake the Project on the terms and conditions set out in this Contract. The Department's reference number for this Contract is DFERPPU/EOR/SBU/2018/004.

Commencement and Continuation

The Contractor shall commence the Project on the date the Contract was signed by the Department (as above) and, subject to Schedule Three, Clause 10.1 shall complete the Project on or before 31st March 2022.

Contents

Interpretations

Schedule One
Schedule Two
Schedule Three

Schedule Four

Signatories page 62

1.	Interpretation

1.1	In this Contract the following words shall mean:-

“the Project”	the project to be performed by the Contractor as described in Schedule One;

“the Project Manager”

<redacted>

“the Contractor’s Project Manager”

<redacted>

“the Act and the Regulations” 	means the Copyright Designs and Patents Act 1988 and the Copyright and Rights in Databases Regulations 1997;

“Affiliate”				in relation to a body corporate, any other entity which directly or indirectly Controls, is Controlled by, or is under direct or indirect common Control with, that body corporate from time to time;

"Commercially Sensitive Information" information of a commercially sensitive nature relating to the Contractor, its IPR or its business or which the Contractor has indicated to the Department that, if disclosed by the Department, would cause the Contractor significant commercial disadvantage or material financial loss;

"Confidential Information"	means all information which has been designated as confidential by either party in writing or that ought to be considered as confidential (however it is conveyed or on whatever media it is stored) including but not limited to information which relates to the business, affairs, properties, assets, trading practices, services, developments, trade secrets, Intellectual Property Rights, know-how, personnel, customers and suppliers of either party and commercially sensitive information which may be regarded as the confidential information of the disclosing party;

"Contracting Department"	any contracting authority as defined in Regulation 5(2) of the Public Contracts (Works, Services and Supply) (Amendment) Regulations 2000 other than the Department;

"Contractor Personnel"	all employees, agents, consultants and Contractors of the Contractor and/or of any Sub-Contractor;

"Contractor Software"	software which is proprietary to the Contractor, including software which is or will be used by the Contractor for the purposes of providing the Services;

“Control”	means that a person possesses, directly or indirectly, the power to direct or cause the direction of the management and policies of the other person (whether through the ownership of voting shares, by contract or otherwise) and "Controls" and "Controlled" shall be interpreted accordingly;

“Controller”	take the meaning given in the GDPR;

“Copyright”				means any and all copyright, design right (as defined by the Act) and all other rights of a like nature which may, during the course of this Contract, come into existence in or in relation to any Work (or any part thereof);

“Copyright Work”			means any Work in which any Copyright subsists;

"Crown Body"	any department, office or agency of the Crown;

"Data"					 means all data, information, text, drawings, diagrams, images or sound embodied in any electronic or tangible medium, and which are supplied or in respect of which access is granted to the Contractor by the Department pursuant to this Contract, or which the Contractor is required to generate under this Contract;

“Data Loss Event”	any event that results, or may result, in unauthorised access to Personal Data held by the Contractor under this Contract, and/or actual or potential loss and/or destruction of Personal Data in breach of this Contract, including any Personal Data Breach;

“Data Protection Impact Assessment” an assessment by the Controller of the impact of the envisaged processing on the protection of Personal Data;

"Data Protection Legislation"	(i) the GDPR, the LED and any applicable national implementing Laws as amended from time to time (ii) the DPA 2018 [subject to Royal Assent] to the extent that it relates to processing of personal data and privacy; (iiii) all applicable Law about the processing of personal data and privacy;

“Data Protection Officer”	take the meaning given in the GDPR

"Data Subject"	 take the meaning given in the GDPR;

“Data Subject Access Request”	a request made by, or on behalf of, a Data Subject in accordance with rights granted pursuant to the Data Protection Legislation to access their Personal Data;

"Department Confidential Information" all Personal Data and any information, however it is conveyed, that relates to the business, affairs, developments, trade secrets, know-how, personnel, and suppliers of the Department, including all IPRs, together with all information derived from any of the above, and any other information clearly designated as being confidential (whether or not it is marked "confidential") or which ought reasonably be considered to be confidential;

"Department Data" 			(a) the data, text, drawings, diagrams, images or sounds (together with any database made up of any of these) which are embodied in any electronic, magnetic, optical or tangible media, and which are:

(i) supplied to the Contractor by or on behalf of the 							Department; or

(ii) which the Contractor is required to 								generate, process, store or transmit pursuant 							to this Contract; or		

						(b) any Personal Data for which the Department is 							the Data Controller;

“DPA 2018”				Data Protection Act 2018

"Effective Date"	the date on which this Contract is signed by both parties;

"Environmental Information		the Environmental Information Regulations 2004
Regulations”				together with any guidance and/or codes of practice 					issues by the Information Commissioner or relevant 					Government Department in relation to such 							regulations;

"FOIA"	the Freedom of Information Act 2000 and any subordinate legislation made under this Act from time to time together with any guidance and/or codes of practice issued by the Information Commissioner or relevant Government Department in relation to such legislation;

“GDPR”	the General Data Protection Regulation (Regulation (EU) 2016/679)

"ICT"	information and communications technology;

"ICT Environment"	the Department’s System and the Contractor System;

“Information”	has the meaning given under section 84 of the Freedom of Information Act 2000;

"Intellectual Property Rights”	means patents, trade marks, service marks, design (rights whether registerable or otherwise), applications for any of the foregoing, know-how, rights protecting databases, trade or business names and other similar rights or obligations whether registerable or not in any country (including but not limited to the United Kingdom).

“LED”	Law Enforcement Directive (Directive (EU) 2016/680);

"Malicious Software"	any software program or code intended to destroy, interfere with, corrupt, or cause undesired effects on program files, data or other information, executable code or application software macros, whether or not its operation is immediate or delayed, and whether the malicious software is introduced wilfully, negligently or without knowledge of its existence;

“Original Copyright Work”		 means the first Copyright Work created in whatever form;

"Personal Data"	 take the meaning given in the GDPR;

“Personal Data Breach”	take the meaning given in the GDPR;

“Processor”	take the meaning given in the GDPR;

“Protective Measures”	appropriate technical and organisational measures which may include: pseudonymising and encrypting Personal Data, ensuring confidentiality, integrity, availability and resilience of systems and services, ensuring that availability of and access to Personal Data can be restored in a timely manner after an incident, and regularly assessing and evaluating the effectiveness of the such measures adopted by it;

“Regulatory Bodies”	those government departments and regulatory, statutory and other entities, committees and bodies which, whether under statute, rules, regulations, codes of practice or otherwise, are entitled to regulate, investigate, or influence the matters dealt with in this Contract or any other affairs of the Department and "Regulatory Body" shall be construed accordingly;

"Request for Information"	a request for information or an apparent request under the Code of Practice on Access to Government Information, FOIA or the Environmental Information Regulations;

"Staff Vetting Procedures"	the Department's procedures and departmental policies for the vetting of personnel whose role will involve the handling of information of a sensitive or confidential nature or the handling of information which is subject to any relevant security measures, including, but not limited to, the provisions of the Official Secrets Act 1911 to 1989;

“Sub-Contractor”	the third party with whom the Contractor enters into a Sub-contract or its servants or agents and any third party with whom that third party enters into a Sub-contract or its servants or agents;

“Sub-processor”	any third Party appointed to process Personal Data on behalf of the Contractor related to this Contract;

"Third Party Software"	software which is proprietary to any third party [other than an Affiliate of the Contractor] which is or will be used by the Contractor for the purposes of providing the Services, and

“Work”					means any and all works including but not limited to literary, dramatic, musical or artistic works, sound recordings, films, broadcasts or cable programmes, typographical arrangements and designs (as the same are defined in the Act) which are created from time to time during the course of this Contract by the Contractor or by or together with others at the Contractor’s request or on its behalf and where such works directly relate to or are created in respect of the performance of this;

"Working Day"	any day other than a Saturday, Sunday or public holiday in England and Wales.

1.2	References to “Contract” mean this contract (and include the Schedules).  References to “Clauses” and “Schedules” mean clauses of and schedules to this Contract.  The provisions of the Schedules shall be binding on the parties as if set out in full in this Contract.

  - Reference to the singular include the plural and vice versa and references to any gender include both genders.  References to a person include any individual, firm, unincorporated association or body corporate.

Schedule One

1	Background

The purpose of the research covered by this contract is to assess the awareness and understanding of the Department for Education’s (DfE) Loan Reimbursement Scheme amongst the target groups, assess the effectiveness of the scheme’s implementation and understand the impact the scheme has had on recruitment and retention in the target subjects.

The scheme has been introduced, because evidence suggests there are a number of subjects that are consistently under-recruiting against their initial teacher training targets; these include sciences and modern foreign languages (MFL). In order to support both recruitment and retention in these subjects, the Department for Education (DfE) is investing in a loan reimbursement scheme in 25 Pilot Local Authorities, made up of Local Authority Districts, which suffer low levels of pupil progress and poor access to high quality schools.

The Teachers’ Student Loan Reimbursement Scheme

The Teachers’ Student Loan Reimbursement Scheme Pilot was announced at the Conservative Party conference on 1 October 2017.  The Pilot in 25 Local Authorities (LA) will test whether or not offering student loan reimbursements will support higher levels of recruitment and improve teacher retention in some of the hardest to recruit for subjects: Biology, Chemistry, Computer Science, Physics, and Modern Foreign Languages (MFL).  The scheme will be open to teachers who;

•	Teach in one of the 25 LA Pilot areas in a state funded secondary school.

•	Have undertaken Initial Teacher Training (ITT) in academic year (AY)2018/19  or were awarded QTS in AY2013/14 to AY2017/18 inclusive.

•	Have more than 50% of their timetable teaching MFL, Biology, Chemistry, Computer Science or Physics.

•	Are still in teaching (in any area) when they submit the claim (for the preceding academic year when they were based in a Pilot area).

The scheme will enable eligible teachers to claim back the amount they have paid (via PAYE) to Student Finance England (SFE) in the preceding AY for up to ten years into their teaching careers. The first reimbursements will be made in Autumn 2019 (for AY2018/19) and the final reimbursements will be made in Autumn 2030 for the AY2029/30. The total number of teachers who will be eligible for reimbursements on their student loans in the first five years of the scheme is estimated to be around 12,500. The total number of secondary schools across the 25 Pilot regions is 474.

This will be an ‘opt-in’ programme, backed with targeted communications, to both schools and eligible teachers, to remind teachers that they can apply to have the loan payments they have made (via PAYE) to SFE in the previous tax year reimbursed. Applications will be made using forms published on gov.uk and the window for applications will open on the first Monday in September, for each year of the Pilot, for a period of six weeks. In order for their application to be processed, they will need to provide proof of payment in the form of their payslips. Once the application is received, it will be verified and payments reimbursed to the teacher’s nominated bank account.

The loan reimbursement scheme may be extended to include those who complete initial teacher training in AY 2019/20. A decision about whether or not the scheme will be extended to those completing training in AY 2019/20 will be made in the autumn of 2018.  This contract includes provision to evaluate the AY 2019/20 cohort.  If the decision is taken not to include the AY 2019/20 cohort the contract will be varied to remove the AY 2019/20 cohort from the variation and the project budget reviewed to reflect this.

2	Aim

The Contractor shall use all reasonable endeavours to achieve the following aims:

To provide the Department for Education with an assessment of how successful the loan reimbursement scheme has been in terms of its implementation and how it has had an impact on recruitment and retention in the target subjects in the pilot areas.

3	Objectives

To enable the Contractor to achieve this overall aim, the Contractor shall use all reasonable endeavours to achieve the following objectives:

- Assess awareness and understanding of the Teachers’ Loan Reimbursement Scheme.

- Identify any influence the Pilot has had on the recruitment and retention of teacher trainees in the target subjects.

- Understand any influence the Pilot has had on the recruitment and retention of qualified teachers in the target subjects and areas.

- Assess the effectiveness of the scheme application process and how efficiently reimbursements are made.

- Explore attitudes towards the Pilot amongst eligible and ineligible teachers and school leaders in eligible schools.

Research Questions

Assessing Awareness and Understanding

This element of the evaluation shall focus on assessing awareness and understanding of the loan reimbursement scheme amongst those interested in becoming a teacher, ITT applicants and eligible teachers and trainees in the target subjects.  The impact evaluation shall include, but not be limited to addressing the following research questions:

- What is their awareness of the loan reimbursement scheme? And if aware, how did they hear about it? Do they understand it?

- What are their attitudes towards the scheme?

- What influence does the existence of the scheme have on them – both on ITT and their view on for how long/where they will teach?

- Does it have an influence on the subject they choose to teach?

- How does it sit alongside other financial offers that are available?

Process Evaluation

This shall focus on the implementation process – to measure awareness and take-up of the scheme amongst eligible teachers, and how effectively the scheme is being implemented, including application and repayment processes, from the perspective of teachers and school leaders. This shall identify any areas for improvement in the implementation process. The process evaluation shall include, but not be limited to addressing the following research questions:

- How efficient and effective is the process for claiming the reimbursements?  How could it be improved, if at all?

- How could the overall scheme be improved, if at all?

Impact Evaluation

This shall focus on measuring the perceived impact of the intervention among school leaders, trainees and both eligible and ineligible teachers. In particular, it shall explore school-level impacts in terms of:

- teacher supply and recruitment;

- teacher retention

- teacher mobility

The impact evaluation shall include, but not be limited to addressing the following research questions:

- Does the Pilot encourage people to apply to, successfully complete ITT courses and go on to teach?

- Does the scheme influence where applicants choose to train to teach? For example, has the Pilot encouraged potential trainees to apply to training providers in or near the Pilot areas?

- What impact, if any, do participants feel the scheme has had on their behaviour (e.g. decisions to leave teaching or relocate to teach in a different/neighbouring LA to take advantage of the scheme?)

- Has the Pilot improved the recruitment of qualified teachers in the target subjects and areas in comparison to the control areas?

- Has the Pilot improved the retention of teachers in the target subjects and areas?  How does this vary between participating and non-participating teachers in the Pilot areas?

- Has the Pilot had an influence on mobility within and between Pilot and other areas?  What impact, if any, has there been on eligible teachers’ behaviours?

- How do eligible and ineligible teachers and schools view the Pilot? Have there been any intended and unintended consequences?

- What are the views of those claiming through the scheme?  Has the Pilot influenced the way they see their career in teaching and their mobility?

- If there are teachers who are eligible and do not claim through the scheme - what are their reasons for not claiming? What are their subsequent behaviours (e.g. retention and mobility) in comparison to those who do claim?

- Do schools understand the scheme?

- How does the scheme work alongside other local recruitment and retention initiatives?  Has the scheme been helpful?

4	METHODOLOGY AND TASKS

4.1	Inception and scoping

Inception Activities

Following the post-tender meeting and from discussion with the Department, the Contractor shall produce a Project Initiation Document and a project information sheet that summarises the agreed scope and approach for the study, a clear timetable showing tasks and responsibilities, clear milestones for deliverables and an updated risk log.

The contractor shall conduct a review of the proposed control areas and recommendations on alternatives shall be made if the contractors consider there to be a better match to the pilot areas.

<redacted>

Document review

The contractor shall undertake a desk-based review of any documentation pertaining to the introduction of the loan reimbursement scheme, in particular any context setting work produced by the DfE. This review shall include any relevant policy documentation and any initial outputs from DfE’s internal quantitative analysis of the loan reimbursement scheme.

The contractor shall use their findings from the scoping interviews and document review including the resulting logic chain to inform the design of the evaluation and key documents such as the questionnaire and discussion guides.  A summary of the findings from the scoping interviews, document review and the logic chain will be included in the first awareness report to be delivered 31st July 2018.

Design of the evaluation framework

Using evidence gathered from discussions with the Department, scoping interviews and document review the contractor shall develop an evaluation framework and Theory of Change (ToC) model that will form the basis for the final design of the evaluation. The ToC model shall be presented in the form of a logic chain with an accompanying narrative and shall summarise the key pathways through which outcomes and impacts are intended to be realised. The evaluation framework shall specify the data to collect from each group, and how this shall be used to draw conclusions about impact on participants’ behaviour and ultimately on the recruitment and retention of teachers in target subjects and areas.

4.2	Survey design and implementation

Survey of potential trainees

The contractor shall undertake an online survey in Spring 2018 with potential trainees to assess awareness and understanding of the loan reimbursement scheme.

The sample shall be:

- potential trainees registered on the Get into Teaching (GiT) website who have expressed an interest in teaching Chemistry, Biology, Physics, Computer Sciences or Modern Foreign Languages.

- <redacted>

The length of the survey shall be a maximum of 15 minutes. The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. Where relevant respondents will be routed through the questionnaire to ensure the questions presented are relevant to individuals based on their previous responses. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes.  The Contractor shall design and administer online surveys using Confirmit software and the invitation to participate in the survey will be sent out via email with a link to the survey. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

The Contractor shall ensure an adequate response rate for the GiT and UCAS surveys through unique online links to track non-responses, and the Contractor shall send a minimum of three targeted reminders. The number of GiT registrants is unpublished and shall be shared with the Contractor upon signing this contract.  <redacted>.  The minimum number of interviews to be collected shall be agreed between the Department and the contractor when these figures are confirmed, but shall reflect an agreed response rate between the Department and contractor of at least 30%.  That is, if the total number of eligible GiT registrants and UCAS Media applicants is 1,000 the minimum number of completed survey responses will be 300.

The contractor shall run the survey in June 2018. Should the scheme be extended for those training in the AY 19/20 the survey would be run again in May/June 2019. In 2018/19 this survey will feed into awareness report 1 (to be delivered by 31.07.2019) and in 2019/20 this will feed into the first annual report (to be delivered by 28 February 2020).

Survey of trainees

The contractor shall also conduct an online survey of teacher trainees in November 2018 to assess awareness and understanding of the loan reimbursement scheme and the results shall be delivered in an awareness report  by 21st December 2018.

The sample shall be taken from the Database of Qualified Teachers (DQT) and will cover all trainees in the eligible subjects: Chemistry, Biology, Physics, Computer Sciences or Modern Foreign Languages.

The length of the survey shall be a maximum of 15 minutes. The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. Where relevant respondents will be routed through the questionnaire to ensure the questions presented are relevant to individuals based on their previous responses. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes.  The Contractor shall design and administer online surveys using Confirmit software and the invitation to participate in the survey will be sent out via email with a link to the survey. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

The Contractor shall ensure an adequate response rate for the trainee survey by using unique online links to track non-responses, and the Contractor shall send a minimum of three targeted reminders. The number of trainees will not be confirmed until the publication of the ITT Census in November 2018 and shall be shared with the contractor at this point. At this time, the minimum number of interviews to be collected shall be agreed between the Department and the contractor, but will reflect a response rate agreed between the Department and contractor of at least 30%.  That is, if the total number of eligible trainees is 1,000 the minimum number of completed survey responses will be 300.

The contractor shall run the survey in November 2018. Should the scheme be extended for those training in the AY 19/20 the survey shall be run again in November 2019. In 2018/19 this survey will feed into awareness report 2 (to be delivered by 21st December 2018) and in 2019/20 this will feed into the first annual report (to be delivered by 28th February 2020).

Survey of teachers who have expressed an interest in the loan reimbursement scheme

The contractor shall carry out a single cross-sectional online survey in September 2018 of teachers who have completed the Department’s form expressing an interest in the loan reimbursement scheme prior to its launch. The purpose of this survey is to understand the teachers’ awareness and understanding of the scheme, including making an assessment of how many teachers who have completed the form and expressed an interest are eligible.

The survey shall be a census of all the teachers that have submitted the form expressing an interest in the scheme and who are willing to be recontacted for research purposes.  At the time of writing the contract the number of teachers expressing an interest was 1,000, but this is expected to have increased by the time of the survey. The contact details shall be provided by the Department from the database created by the Department of the details of the teachers who have submitted a form expressing an interest in the loan reimbursement scheme.

The length of the survey shall be a maximum of 15 minutes. The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. Where relevant respondents will be routed through the questionnaire to ensure the questions presented are relevant to individuals based on their previous responses. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes.  The Contractor shall design and administer online surveys using Confirmit software and the invitation to participate in the survey will be sent out via email with a link to the survey. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

The contractor shall achieve a response rate of 30% of the final number of people returning the expression of interest form who are willing to take part in research and for whom contact details are available.

The survey shall be conducted in September 2018 and will feed into awareness report 2 to be delivered 21 December 2018.

Surveys of qualified teachers in pilot areas

Initial awareness and intentions survey of teachers teaching eligible subjects in the pilot areas

The contractor shall conduct an online survey of eligible teachers in the pilot areas in April 2019 to assess awareness and understanding of, intention to participate in and behaviours relating to their career and mobility linked to the loan reimbursement scheme and the results shall be delivered in an awareness report by 12th July 2019.

The survey will be carried out by disseminating a link to all 474 secondary schools in the Pilot areas and asking them to forward the link to teachers in their schools teaching in the relevant subjects. It is anticipated that not all the teachers receiving the link will be eligible for the loan reimbursement scheme and respondents will be routed through the questionnaire to ensure the questions presented are relevant to individuals based on their previous responses.

The length of the survey shall be a maximum of 15 minutes. The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. The Contractor shall design and administer online surveys using Confirmit software. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

The Contractor shall ensure an adequate response rate for the survey by using unique online links to track non-responses and identify whether or not schools have forwarded the link to their teachers, and the Contractor shall send a minimum of three targeted reminders to schools asking them to forward the link to their teachers. The contractor shall achieve a minimum engagement rate of 27% with the schools in the pilot areas resulting in 128 schools agreeing to disseminate the link.  It is estimated that the number of teachers who will be eligible for the scheme will be 12,500 – with 2,500 of these eligible within the first year.  The contractor shall therefore achieve a response rate of 30% of the teachers that are contacted through their schools resulting in a minimum of 200 completed teacher questionnaires.

Follow-up surveys of teachers teaching eligible subjects in the pilot areas

Once the window for loan reimbursement applications has closed in October 2019, 2020 and 2021, the contractor shall conduct online surveys with teachers teaching in the eligible subjects in the pilot areas. This shall include their awareness of the scheme and their reasons for participating/not participating, experiences of using the scheme, including their perceptions of the efficiency and effectiveness of the scheme, and of the processes for claiming their reimbursements, including any improvements that could be made; and finally any influences on how they perceive their career and their mobility.

The sample for the survey shall be generated in three ways:

- The contractor shall send a link to all 474 secondary schools in the Pilot areas asking them to forward the survey link to teachers in their school who are teaching the eligible subjects. The contractor shall follow up this contact with three targeted reminders to schools from which no response has been received.

- Three weeks after the deadline closes for applications to the scheme the Department shall provide the contractor with the contact details of those participants who have applied to the scheme.  After de-duping against responses that have already been received the contractor shall email the survey link to all those who have made an application to the scheme and follow this up with three targeted reminders.

- The contractor shall also email the link to all respondents to previous versions of this survey and those who responded to the Initial awareness and intentions survey of teachers teaching eligible subjects in the pilot areas, using recontact permissions from the earlier surveys inviting them to take part in that year’s survey.  Previous respondents will be invited to take part in the survey even if they are no longer eligible to claim under the scheme to enable the Department to understand how the scheme effects teacher behaviour, particularly in relation to mobility and career choices.

The length of the survey shall be a maximum of 15 minutes. It is anticipated that not all the teachers receiving the link will be eligible for the loan reimbursement scheme and respondents will be routed through the questionnaire to ensure the questions presented are relevant to individuals based on their previous responses.

The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes. The Contractor shall design and administer online surveys using Confirmit software. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

For those teachers who are ineligible and fall into one of the following four groups  (QTS gained before 2013/14, salary is under the threshold, have no loan repayments or do not spend 50% of their time teaching the target subjects) the contractor will include them in the survey, but route to a shorter questionnaire. Results from other ineligible teachers will be excluded.

The contractor shall achieve a response rate of 30% for teachers joining the sample each year (i.e. they were ineligible the previous year) and 45% for those tracked longitudinally across multiple sampling points (i.e. from the initial awareness survey through to sampling point C). This will amount to a minimum of 2,000 survey completions each year.

The survey results will feed into the annual reports to be delivered by February 2020 and 2021 and final report in 2022.

Surveys of ineligible teachers

Survey of qualified teachers in non-pilot areas

The contractor shall carry out an online survey in September 2020 of teachers teaching eligible subjects in non-pilot areas that are adjacent to the pilot areas. The non-pilot areas of interest are: Rochdale, Tameside, Warrington, Liverpool, East Riding of Yorkshire, North Lincolnshire, Sheffield, Kirklees, Milton Keynes and Nottingham.  This survey will enable the evaluation to capture what influence the scheme is having on neighbouring areas, for example in terms of teacher mobility, and awareness and understanding of the scheme.

The September 2020 survey will be carried out by disseminating a link to all the secondary schools in the agreed non-Pilot areas and asking them to forward the link to teachers in their schools teaching in the relevant subjects. The length of the survey shall be a maximum of 15 minutes. The number of pre-coded and open questions in the survey shall be agreed between the Contractor and the Department. The Contractor shall ensure that ‘other’ options are available to allow specification of a response when a suitable pre-coded answer is not provided. The Contractor shall discuss and agree an approach to the un-coded responses with the Department. The questionnaire shall include a question requesting the respondent’s permission to recontact them if necessary for research purposes. The Contractor shall design and administer online surveys using Confirmit software. Piloting of the survey shall be agreed between the Contractor and the Department. DfE shall agree and approve the questionnaire with the Contractor.

The Contractor shall ensure an adequate response rate for the survey by using unique online links to track non-responses and identify whether or not schools have forwarded the link to their teachers, and the Contractor shall send a minimum of three targeted reminders to schools asking them to forward the link to their teachers. The contractor shall achieve a minimum engagement rate of 27% with the 191 secondary schools in the non-pilot areas.  Assuming a response rate of 30% from the teachers within the these schools we anticipate minimum of 800 survey returns.

The findings from the survey shall contribute to the annual report to be delivered by 28th February 2021.

4.3	Qualitative fieldwork

In-depth interviews with school leaders

The contractor shall undertake telephone depth interviews with school leaders in April/May 2019 and November 2020 and 2021.  The purpose of these interviews is to understand how the loan reimbursement scheme is being understood and received; whether or not it is influencing recruitment and retention rates and overall teacher mobility; understanding of the scheme/offer; how the scheme could be improved; how the scheme works alongside other recruitment and retention initiatives; attitudes towards the scheme and any impacts on or changes to teacher retention in both eligible and ineligible schools.

The school leaders shall be drawn from the 474 secondary schools in the pilot areas.   In each of the <redacted> waves the contractor shall interview <redacted> school leaders from the 474 pilot area schools, resulting in a total of <redacted> interviews over the lifetime of the evaluation.  The contractor shall ensure that the school leaders are purposively sampled to reflect a range of school characteristics such as size and Ofsted rating. These characteristics shall be agreed between the Department and the contractor.

<redacted>.

The contractor shall design interview topic guides for school leaders and agree these with the Department.

The contractor shall send an email/letter outlining the purpose of the interview to each school leader; followed by a telephone call to schedule a time for an interview. The interviews will be conducted via telephone at a time that is most convenient for the respondents. The interviews with school leaders will last for up to 45 minutes.  With the respondent’s permission, the interviews will be recorded and transcribed for quality assurance purposes.

The findings from the April/May 2019 qualitative interviews shall feed into the third awareness report due to be delivered on 12th July 2019 and the subsequent waves into the annual reports to be delivered by 28th February 2021 and 2022.

In-depth interviews with Get into Teaching registrants, trainees, eligible teachers and participating and non-participating teachers

The contractor shall undertake telephone depth interviews with Get into Teaching registrants, trainees, eligible teachers and eligible teachers who are participating and not participating.  The purpose of the interviews will be to assess awareness and understanding of the scheme; perceptions of the claim processes (for those who are already participating); perceptions of how the scheme sits alongside other initiatives and any areas for improvement; and finally any evidence of impact on attitudes towards teaching, mobility, decisions to pursue teaching, and or their retention in the teaching profession.

The number of interviews by group and their timing in each year are shown in the table below:

<redacted>

| <redacted> |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

The sample for each group will be developed from recontact details collected through the online surveys conducted with the groups.  For each of the qualitative sets of interviews the contractor shall work with DfE to ensure that a purposive sample is developed to ensure a sample with a range of characteristics to be agreed between the contractor and DfE is selected to ensure the full range of themes are identified through the research.

The contractor shall send an email/letter outlining the purpose of the interview to each contact; followed by a telephone call to schedule a time for an interview. The interviews will be conducted via telephone at a time that is most convenient for the respondents. With the respondent’s permission, the interviews will be recorded and transcribed for quality assurance purposes.

The contractor shall design appropriate discussion guides for each of these groups and each guide shall be agreed with the Department.  The telephone depth interviews shall last no more than 45 minutes.

The findings from the GiT registrants July 2018 qualitative interviews shall feed into the second awareness report due to be delivered on 21st December 2018 and the second wave into the annual report to be delivered by 28th February 2020.

The findings from the trainees November/December 2018 qualitative interviews shall feed into the third awareness report in to be delivered by 12th July 2018 and the second wave into the annual report to be delivered by 28th February 2020.

The findings from the April/May 2019 qualitative interviews with eligible teachers in the pilot areas will be reported in the third awareness report to be delivered by 12th July 2019.

The findings from the remaining qualitative interviews with participating and non-participating teachers shall feed into the following years’ annual reports to be delivered by 28th February 2020, 2021 and 2022.

4.4	Analysis

Analysis of qualitative data

The contractor shall use NVivo software to capture and code the interview data and will adopt an inductive approach to data analysis to establish clear links between the evaluation objectives and the findings.  The contractor shall ensure these links are both transparent and defensible.

Analysis of quantitative data

The contractor shall undertake a series of quality checks to ensure the quantitative data is fit for analysis. This shall include cleaning and checking the data. The contractor shall undertake a full data clean once the data is downloaded to eradicate any errors, which have the potential to distort the findings. The contractor shall then ensure the data is able to be used for a broad range of analysis. This shall involve restructuring variables to maximise the opportunities for statistical analysis including, but not limited to, re-coding continuous data into categorical data to create variables such as age group. The contractor shall then agree with the Department the extent to which weighting strategies are required to account for the census approach taken in the surveys and where appropriate the contractor shall use weighting to overcome the limitations of available sample. The purpose of weighting is to address selection and non-response bias and strategies shall concentrate on variables that have a hypothetical relationship to the topic of interest.

<redacted>

The contractor shall then undertake quantitative data analysis, which shall involve the interrogation of data in relation to the key aims and objectives of the evaluation. Top-line analysis will enable the determination of the bivariate analysis to be used, such as cross-tabulations, that are possible given the sample size within key sub-groups. This may include demographic characteristics along with other teaching career stage, school level and engagement with the scheme to date variables. The variables to be used will be discussed and agreed with the Department.  The contractor’s descriptive statistical analysis will be supplemented by advanced multivariate techniques including linear and logistic regression.  Having analysed the data using SPSS, it shall be visualized using Excel and Tableau for presentational purposes and ease of interpretation.

Department for Education analysis of quantitative impact data

The DfE will be conducting internal analysis of the quantitative data used to assess the impact on recruitment and retention, the detail of which shall be discussed with the contractor and the contractor shall be expected to use these findings as part of their analysis in their annual reports to develop an overall understanding of the impact of the evaluation.

4.5	Reporting

The Contractor shall deliver a series of awareness reports, followed by an annual report in February of each year of the evaluation and a final report and research brief in February 2022.

The reporting timetable is as follows:

| Report | Date |
| --- | --- |
| Awareness report 1 including: - document review - scoping interviews - theory of change model - summary of scoping decisions - 2018 potential trainees survey findings (GiT survey) | 31st July 2018 |
| Awareness report 2 including: - 2018 trainees survey findings - 2018 survey of teachers who have expressed an interest in the scheme - qualitative findings from potential trainees 2018 interviews (GiT registrants) - qualitative findings from trainee 2018/19 interviews | 21st December |
| Awareness report 3 including: - 2019 potential trainees survey findings (GiT survey) - 2019 surveys of eligible teachers awareness and intentions in pilot areas - 2019 qualitative findings from school leader interviews - 2019 qualitative interviews with eligible teachers in pilot areas | 12th July 2019 |
| 2019/20 Annual report including - 2019/20 trainees survey findings - 2019 surveys of eligible teachers in pilot areas - qualitative findings from 2019/20 trainees interviews - qualitative findings from potential trainees 2019 interviews (GiT registrants) - Nov/Dec 2019 qualitative findings from interviews with eligible participating and non-participating teachers in the pilot areas - the quantitative impact data collected and analysed by DfE | 28th February 2020 |
| 2020/21 Annual report - 2020 surveys of eligible teachers in pilot areas - Nov/Dec 2020 qualitative findings from interviews with eligible participating and non-participating teachers in the pilot areas - 2020 survey with teachers in eligible subjects in non-pilot areas - qualitative findings from 2020 school leaders interviews - qualitative interviews with 10 school leaders from neighbouring non-pilot areas - the quantitative impact data collected and analysed by DfE | 28th February 2021 |
| 2021/22 Final report and research brief reporting on: - 2021 surveys with eligible teachers in pilot areas - Nov/Dec 2021 qualitative findings from interviews with eligible participating and non-participating teachers in the pilot areas - qualitative findings from 2021 school leaders interviews This report will also bring together the overall findings of the evaluation, including the quantitative impact data collected and analysed by DfE | To be signed off for publication by 28th February 2022 |

The Department will have the opportunity to review and comment on all reports produced as part of the evaluation.  All reports and the final research brief will be delivered in plain English and in line with the Department’s guide for publication, using the Department’s report and research brief template and ready for publication on gov.uk.

When fieldwork concludes more than 3 months prior to when the final report is due the contractor shall provide a brief, headline summary to facilitate immediate policy decisions.

4.6	Project Management

The Contractor shall ensure robust project management and quality assurance systems in place, underpinned by the principles of PRINCE2.

Based on initial discussions with DfE concerning this study and the proposed Evaluation of the Phased Maths Bursary Scheme, the Contractor shall use a cross-project team to ensure streamlined management and capture findings between the Phased Maths Bursary and Loan Reimbursement projects.

The Contractor shall adopt a flexible, pragmatic and collaborative approach and will work closely with DfE throughout the study to ensure requirements are fully met.

The Contractor shall use its resource planning tool to review resourcing across the organisation to quickly identify additional capacity for a project in the event of unforeseen staff absence/turnover to prevent slippage. The Contractor shall seek approval from DfE before making any changes to the core delivery team.

The Contractor shall also have systems in place to monitor project income and expenditure and actual time spent to ensure projects remain on budget. For issues identified, alternate approaches shall initially be considered to help prevent the escalation of costs. Where this proves ineffective, the Contractor shall identify cost-savings in consultation with DfE’s Project Manager.

The timing of catch up meetings shall be agreed between the contractor and DfE according to the intensity of project work, but are expected to take place weekly during the set-up phase.

A steering group meeting will take place every 6 months to review the project’s progress and to ensure the Contractor’s work is meeting the Department’s needs.

Timeline

The table below show the tasks and outputs of the project and the corresponding dates. The Contractor shall produce a more detailed timetable of tasks, responsibilities and dates following the inception of the project.

The first table is designed to give an overview of the different work to be undertaken at different stages of the project in the project. The second table gives a detailed year-by-year description of tasks and outputs required with specific end dates.

The dates given in the second table are according to the Department’s best current understanding of the project. Given the length of the evaluation, indicative end dates are given for later years, which may be revised in light of better understanding of resource and outputs closer to the time.  The dates for project meetings to review progress and findings shall be agreed between DfE and the contractor when the project steering group has been finalised.

| Task | Output | Date/s |
| --- | --- | --- |
| Throughout project lifetime |  |  |
| Project & risk management | Initially weekly written progress updates via email or update calls to inform DfE of progress. This timing shall be reviewed as the project progressed to reflect the project intensity. | Project lifetime |
|  | Develop and maintain appropriate and up-to-date project documentation, including a project plan outlining key actions, milestones and deliverable dates. To be shared with DfE termly or as requested. | Project lifetime |
|  | Develop and maintain a risk register for the project, including at the strand level. This should be monitored and discussed in the regular update calls. | Project lifetime |
| Stage 1: Inception & scoping |  |  |
|  |  | Date/s |
| Project initiation |  | June 2018 |
| Scoping Interviews |  | June/July 2018 |
| Document review |  | June/July 2018 |
| Design of evaluation framework |  | July 2018 |
| Stage 2: Survey design and implementation |  |  |
|  |  | Date/s |
| Sampling strategy and survey schedule design |  | June 2018 |
| Survey of potential trainees |  | June 2018, June 2019 (subject to addition of 19/20 cohort) |
| Survey of trainees |  | November 2018, November 2019 (subject to addition of 19/20 cohort) |
| Longitudinal surveys of participating teachers |  | April 2019, October 2019, October 2020, October 2021 |
| Surveys of eligible non-participating and ineligible teachers (in pilot areas) |  | April 2019, October 2019, October 2020, October 2021 |
| Surveys of qualified teachers in non-pilot areas |  | September 2020 |
| Stage 3: Qualitative fieldwork |  |  |
|  |  | Date/s |
| Topic guide for school leaders |  | February 2019 |
| Topic guide for eligible teachers, participating teachers and trainees |  | Interview guide for potential trainees: June 2018; all others in September 2019 |
| Interviews with school leaders |  | April/May 2019, November 2020, November 2021 |
| Interviews with eligible teachers, participating teachers and trainees |  | Potential trainee interviews: July 2018 and July 2019; trainee interviews: November 2018 and November 2019; and participating eligible/ineligible interviews: November/December 2019, November/December 2020 and November/December 2021. |
| Stage 3: Analysis and reporting. Date/s. Analysis of qualitative data; July 2018, November 2018, June 2019, December 2019, December 2020, December 2021. Analysis of quantitative data (subject to DfE sharing); July 2018, November 2018, May 2019, December 2019, December 2020, December 2021. Assessment of awareness reporting; 31st July 2018, 21st December 2018, 12th July 2019. Finalised annual report; 28th February 2020, 28th February 2021. Finalised overall evaluation report; 28th February 2022. |

| Task | Output | End Date |
| --- | --- | --- |
| Academic Year 2017/18 |  |  |
| Drafting of set-up documentation | Project initiation document and project information sheet delivered to DfE | 8th June 2018 |
| Potential trainee survey – 2018/19 cohort | Development and delivery of online survey to those registered on GiT and accepted a place on an ITT course | 6th July 2018 |
| Scoping interviews | Development of topic guide, organising and undertaking interviews | 20th July 2018 |
| Document review | Review of documents and data | 20th July 2018 |
| Depth interviews with potential trainees | Development of topic guide, organising and undertaking interviews | 31st July 2018 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 31st July 2018 |
| Evaluation Framework | Evaluation Framework delivered to DfE | 31st July 2018 |
| Awareness Report 1 | Final Awareness Report 1delivered to DfE | 31st July 2018 |
| Meeting to review findings and progress | Attend meeting | TBC |
| Academic Year 2018/19 |  |  |
| Survey of teachers who have expressed an interest in the scheme | Development and delivery of online survey of those who have expressed an interest drawing upon DfE data | 28th September 2018 |
| Trainee survey – 2018/19 cohort | Development and delivery of online survey of those who have accepted a place on an ITT course | 30th November 2018 |
| Depth interviews with trainees | Development of topic guide, organising and undertaking interviews | 14th December 2018 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 21st December 2018 |
| Awareness Report 2 | Final Awareness Report 2 delivered to DfE | 21st December 2018 |
| Meeting to review findings and progress | Attend meeting | TBC |
| Initial awareness survey | Development and delivery of online survey of teachers teaching eligible subjects in the pilot areas | 30th April 2019 |
| Depth interviews with teachers | Development and delivery of depth interviews with teachers teaching eligible subjects regarding initial awareness | 31st May 2019 |
| Depth interviews with Headteachers | Development and delivery of depth interviews with Headteachers | 31st May 2019 |
| Potential trainee survey – 2019/20 cohort | Development and delivery of online survey to those registered on GiT and accepted a place on an ITT course | 28th June 2019 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 12th July 2019 |
| Awareness Report 3 | Final Awareness Report 3 delivered to DfE | 12th July 2019 |
| Meeting to review findings and progress | Attend meeting | TBC |
| Depth interviews with potential trainees | Development of topic guide, organising and undertaking interviews | 31st July 2019 |
| 2019/20 |  |  |
| Trainee survey – 2019/20 cohort | Development and delivery of online survey of those who have accepted a place on an ITT course | 29th November 2019 |
| Follow-up surveys of teachers teaching eligible subjects in pilot areas | Development and delivery of online survey of teachers teaching eligible subjects drawn from: i) schools in the pilot areas; and ii) DfE data on those participating in the scheme | 29th November 2019 |
| Depth interviews with Headteachers | Development and delivery of depth interviews with Headteachers | 20th December 2019 |
| Depth interviews with teachers | Development and delivery of depth interviews with teachers (participating and non-participating eligible teachers in pilot areas) | 20th December 2019 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 28th February 2020 |
| Annual Report 1 | Final Report delivered to DfE | 28th February 2020 |
| Meeting to review findings and progress | Attend meeting | TBC |
| 2020/21 |  |  |
| Survey of qualified teachers in non-pilot areas | Development and delivery of online survey of qualified teachers in non-pilot areas who meet the eligibility criteria | 28th September 2020 |
| Depth interviews with Headteachers in non-pilot areas | Development and delivery of depth interviews with Headteachers | 31st October 2020 |
| Follow-up surveys of teachers teaching eligible subjects in pilot areas | Development and delivery of online survey of teachers teaching eligible subjects drawn from: i) schools in the pilot areas; ii) DfE data on those participating in the scheme; and iii) longitudinal follow-up surveys | 30th November 2020 |
| Depth interviews with Headteachers | Development and delivery of depth interviews with Headteachers | 18th December 2020 |
| Depth interviews with teachers | Development and delivery of depth interviews with teachers (participating and non-participating eligible teachers in pilot areas) | 18th December 2020 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 26th February 2021 |
| Annual Report 2 | Final Report delivered to DfE | 28th February 2021 |
| Meeting to review findings and progress | Attend meeting | TBC |
| 2021/22 |  |  |
| Follow-up surveys of teachers teaching eligible subjects in pilot areas | Development and delivery of online survey of teachers teaching eligible subjects drawn from: i) schools in the pilot areas; ii) DfE data on those participating in the scheme; and iii) longitudinal follow-up surveys | 30th November 2021 |
| Depth interviews with Headteachers | Development and delivery of depth interviews with Headteachers | 17th December 2021 |
| Depth interviews with teachers | Development and delivery of depth interviews with teachers (participating and non-participating eligible teachers in pilot areas) | 17th December 2021 |
| Analysis of primary research data | Data cleaning, checking, modification, manipulation. Descriptive statistical analysis, multivariate analysis. Nvivo analysis of qualitative findings. | 28th February 2022 |
| Final Report | Final Report and Research Brief delivered to DfE | 28th February 2022 |
| Meeting to review findings and progress | Attend meeting | TBC |

6.	Staffing

CFE Research

<redacted>

: Independent critical review of evaluation design and output

<redacted>

: Project Director with responsibility for contract compliance, quality-assurance and strategic oversight of the evaluation.

<redacted>

: Lead for sampling strategy and weighting.

<redacted>

Associate Director: Responsibility for evaluation design. Leads on design of tools, analysis and reporting. Cross-project support to ensure learning from the Phased Maths Bursary evaluation is applied.

<redacted>

Senior Research Manager to provide expert input in relation to the design and implementation of the surveys.

<redacted>

Research Manager with day-to-day responsibility for project implementation, budget management and communication with DfE. Oversight of project team, including sub-contractors.

<redacted>

Senior Research Executive responsible for online survey programming, involvement in undertaking qualitative interviews and support for data analysis.

<redacted>

Research Executive responsible for project administration and support

# 7	STEERING COMMITTEE

The Project Manager shall set up a Steering Committee for the Project, consisting of representatives from the Department, the Contractor, and any other key organisations whom the project will impact on, to be agreed between the parties. The function of the Steering Committee shall be to review the scope and direction of the Project against its aims and objectives, monitor progress and efficiency. The Committee shall meet at times and dates agreed by the parties, or in the absence of agreement, specified by the Department. The Contractor’s representatives on the Steering Committee shall report their views on the progress of the Project to the Steering Committee in writing if requested by the Department. The Contractor’s representatives on the Steering Committee shall attend all meetings of the Steering Committee unless otherwise agreed by the Department.

8.	Risk Management

<redacted>

9	Data Collection

The Department seeks to minimise the burdens on Schools, Children’s Services and Local Authorities (LAs) taking part in surveys.

When assessing the relative merits of data collection methods the following issues should be considered;

- only data essential to the project shall be collected;

- data should be collected electronically where appropriate/preferred;

- questionnaires should be pre-populated wherever possible and appropriate;

- schools must be given at least four working weeks to respond to the exercise from the date they receive the request; and

- LAs should receive at least two weeks, unless they need to approach schools in which case they too should receive 4 weeks to respond;

The Contractor shall clear any data collection tools with the Department before engaging in field work.

The Contractor shall check with the Department whether any of the information that they are requesting can be provided centrally from information already held.

10.	CONSENT ARRANGEMENTS

The Department and the contractor shall agree in advance of any survey activity taking place the consent arrangements that shall apply for each of the participant groups. All participants should be informed of the purpose of the research, that the Contractor is acting on behalf of the Department and that they have the option to refuse to participate (opt out). Contact details should be provided including a contact person at the Department. Children who are 16 or over will usually be able to give their own consent but even where this is so, the Contractor, in consultation with the Department, should consider whether it is also appropriate for parents, guardians or other appropriate gatekeepers (e.g. schools, Local Authorities) to be informed when a child has been invited to participate in research.

End of Schedule One

Schedule Two

1	Eligible expenditure

1.1	The Department shall reimburse the Contractor for expenditure incurred for the purpose of the Project, provided that:-

(a)	the expenditure falls within the heading and limits in the Table below; and

- the expenditure is incurred, and claims are made, in accordance with this Contract.

Table

| Project Milestone | Payment Amount | Payment Date |
| --- | --- | --- |
| Delivery of Awareness Report 1 | <redacted> | 31st July 2018 |
| Delivery of Awareness Report 2 | <redacted> | 21st December 2018 |
| Delivery of Awareness Report 3 | <redacted> | 12th July 2019 |
| Delivery of 2019/2020 finalised Annual Report | <redacted> | 28th February 2020 |
| Delivery of 2020/21 finalised annual report | <redacted> | 28th February 2021 |
| Delivery of finalised Final Evaluation Report | <redacted> | 28th February 2022 |

Expenditure for the financial year 2018/19 shall not exceed

<redacted>

.
Expenditure for the financial year 2019/20 shall not exceed

<redacted>

.
Expenditure for the financial year 2020/21 shall not exceed

<redacted>

.

Expenditure for the financial year 2021/22 shall not

<redacted>

.

Total Project expenditure shall not exceed £200,000 exclusive of VAT.

The length of the evaluation is dependent on whether the scheme is continued or discontinued. A decision about continuation is to be taken in August 2018. If continued, a further decision will be taken in August 2019 on whether the scheme is continued for longer. If the pilot scheme is discontinued, the evaluation will no longer cover subsequent cohorts and the evaluation will be reduced in its scope.

2	The allocation of funds in the Table may not be altered except with the prior written consent of the Department.

3	The Contractor shall maintain full and accurate accounts for the Project against the expenditure headings in the Table.  Such accounts shall be retained for at least 6 years after the end of the financial year in which the last payment was made under this Contract.  Input and output VAT shall be included as separate items in such accounts.

4	The Contractor shall permit duly authorised staff or agents of the Department or the National Audit Office to examine the accounts at any reasonable time and shall furnish oral or written explanations of the accounts if required.  The Department reserves the right to have such staff or agents carry out examinations into the economy, efficiency and effectiveness with which the Contractor has used the Department's resources in the performance of this Contract.

- Invoices shall be submitted on the invoice dates specified in the Table, be detailed against the task headings set out in the Table and must quote the Department’s Order Number. The Purchase order reference number shall be provided by the department when both parties have signed the paperwork. The Contractor or his or her nominated representative or accountant shall certify on the invoice that the amounts claimed were expended wholly and necessarily by the Contractor on the Projects in accordance with the Contract and that the invoice does not include any costs being claimed from any other body or individual or from the Department within the terms of another contract.

Invoices shall be sent to the

<redacted>

and/or by email to

<redacted>

- . Invoices submitted by email must be in PDF format, with one PDF file per invoice including any supporting documentation in the same file. Multiple invoices may be submitted in a single email but each invoice must be in a separate PDF file. The Department undertakes to pay correctly submitted invoices within 10 days of receipt. The Department is obliged to pay invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.  Any correctly submitted invoices that are not paid within 30 days may be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.  A correct invoice is one that: is delivered in timing in accordance with the contract; is for the correct sum; in respect of goods/services supplied or delivered to the required quality (or are expected to be at the required quality); includes the date, supplier name, contact details and bank details; quotes the relevant purchase order/contract reference and has been delivered to the nominated address.  If any problems arise, contact the Department's Project Manager.  The Department aims to reply to complaints within 10 working days.  The Department shall not be responsible for any delay in payment caused by incomplete or illegible invoices.

7	The Contractor shall have regard to the need for economy in all expenditure.  Where any expenditure in an invoice, in the Department's reasonable opinion, is excessive having due regard to the purpose for which it was incurred, the Department shall only be liable to reimburse so much (if any) of the expenditure disallowed as, in the Department's reasonable opinion after consultation with the Contractor, would reasonably have been required for that purpose.

8	If this Contract is terminated by the Department due to the Contractor's insolvency or default at any time before completion of the Projects, the Department shall only be liable under paragraph 1 to reimburse eligible payments made by, or due to, the Contractor before the date of termination.

9	On completion of the Project or on termination of this Contract, the Contractor shall promptly draw-up a final invoice, which shall cover all outstanding expenditure incurred for the Project.  The final invoice shall be submitted not later than 30 days after the date of completion of the Projects.

10	The Department shall not be obliged to pay the final invoice until the Contractor has carried out all the elements of the Projects specified as in Schedule 1.

11	It shall be the responsibility of the Contractor to ensure that the final invoice covers all outstanding expenditure for which reimbursement may be claimed.  Provided that all previous invoices have been duly paid, on due payment of the final invoice by the Department all amounts due to be reimbursed under this Contract shall be deemed to have been paid and the Department shall have no further liability to make reimbursement of any kind.

End of Schedule Two

SCHEDULE THREE

- Contractor's Obligations

  - The Contractor shall promptly and efficiently complete the Project in accordance with the provisions set out in Schedule One.

  - The Contractor shall comply with the accounting and information provisions of Schedule Two.

  - The Contractor shall comply with all statutory provisions including all prior and subsequent enactments, amendments and substitutions relating to that provision and to any regulations made under it.

  - The Contractor shall inform the Department immediately if it is experiencing any difficulties in meeting its contractual obligations.

- Department's Obligations

  - The Department will comply with the payment provisions of Schedule Two provided that the Department has received full and accurate information and documentation as required by Schedule Two to be submitted by the Contractor for work completed to the satisfaction of the Department.

- Changes to the Department's Requirements

  - The Department shall notify the Contractor of any material change to the Department's requirement under this Contract.

  - The Contractor shall use its best endeavours to accommodate any changes to the needs and requirements of the Department provided that it shall be entitled to payment for any additional costs it incurs as a result of any such changes.  The amount of such additional costs to be agreed between the parties in writing.

- Management

  - The Contractor shall promptly comply with all reasonable requests or directions of the Project Manager in respect of the Services.

  - The Contractor shall address any enquiries about procedural or contractual matters in writing to the Project Manager.  Any correspondence relating to this Contract shall quote the reference number set out in the Recitals to this Contract.

- Contractor's Employees and Sub-Contractors

5.1       Where the Contractor enters into a contract with a supplier or

contractor for the purpose of performing its obligations under the Contract (the “Sub-contractor”) it shall ensure prompt payment in accordance with this clause 5.1. Unless otherwise agreed by the Department in writing, the Contractor shall ensure that any contract requiring payment to a Sub-contractor shall provide for undisputed sums due to the Sub-contractor to be made within a specified period from the receipt of a valid invoice not exceeding:

5.1.1      10 days, where the Sub-contractor is an SME; or

5.1.2      30 days either, where the sub-contractor is not an SME, or

both the Contractor and the Sub-contractor are SMEs,

The Contractor shall comply with such terms and shall provide, at the Department’s request, sufficient evidence to demonstrate compliance.

5.2    	The Department shall be entitled to withhold payment due under clause

5.1 for so long as the Contractor, in the Department’s reasonable opinion, has failed to comply with its obligations to pay any Sub-contractors promptly in accordance with clause 5.1.  For the avoidance of doubt the Department shall not be liable to pay any interest or penalty in withholding such payment.

  - The Contractor shall immediately notify the Department if they have any concerns regarding the propriety of any of its sub-contractors in respect of work/services rendered in connection with this Contract.

  - The Contractor, its employees and sub-contractors (or their employees), whilst on Departmental premises, shall comply with such rules, regulations and requirements (including those relating to security arrangements) as may be in force from time to time.

  - The Contractor shall ensure the security of all the Property whilst in its possession, during the supply of the Project, in accordance with the Department’s reasonable security requirements as required from time to time.

  - If the Department notifies the Contractor that it considers that an employee or sub-contractor is not appropriately qualified or trained to perform the Project or otherwise is not performing the Project in accordance with this Contract, then the Contractor shall, as soon as is reasonably practicable, take all such steps as the Department considers necessary to remedy the situation or, if so required by the Department, shall remove the said employee or sub-contractor from performing the Project and shall provide a suitable replacement (at no cost to the Department).

  - The Contractor shall take all reasonable steps to avoid changes of employees or sub-contractors assigned to and accepted to perform the Project under the Contract except whenever changes are unavoidable or of a temporary nature.  The Contractor shall give at least four week’s written notice to the Project Manager of proposals to change key employees or sub-contractors

- Ownership of Intellectual Property Rights and Copyright

6.1.	Ownership of Intellectual Property Rights including Copyright, in any guidance, specifications, instructions, toolkits, plans, data, drawings, databases, patents, patterns, models, designs or other materials prepared by or for the Contractor on behalf of the Department for use, or intended use, in relation to the performance by the Contractor of its obligations under the Contract shall belong to the Contractor

6.2	The Contractor hereby grants to the Department a non-exclusive licence without payment of royalty or other sum by the Department in the Copyright to:

6.2.1	do and authorise others to do any and all acts restricted by the Act as amended from time to time or replaced in whole or part by any statute or other legal means in respect of any Copyright Work in the United Kingdom and in all other territories in the world for the full period of time during which the Copyright subsists; and

6.2.2	exercise all rights of a similar nature as those described in Clause 6.1 above which may be conferred in respect of any Copyright Work by the laws from time to time in all other parts of the world.

6.3	Each party will at the request and reasonable expense of the other execute all such documents and do all such acts as may be reasonably necessary in order to vest in the other the rights granted to the other under this Clause 6.

- Data Protection Act

  - The Parties acknowledge that for the purposes of the Data Protection Legislation, the Department is the Controller and the Contractor is the Processor. The only processing that the Contractor is authorised to do is listed in Schedule [X] by the Department and may not be determined by the Contractor.

  - The Contractor shall notify the Department immediately if it considers that any of the Department's instructions infringe the Data Protection Legislation.

  - The Contractor shall provide all reasonable assistance to the Department in the preparation of any Data Protection Impact Assessment prior to commencing any processing.  Such assistance may, at the discretion of the Department, include:

(a)	a systematic description of the envisaged processing operations and the purpose of the processing;

(b)	an assessment of the necessity and proportionality of the processing operations in relation to the Services;

(c)	an assessment of the risks to the rights and freedoms of Data Subjects; and

(d)	the measures envisaged to address the risks, including safeguards, security measures and mechanisms to ensure the protection of Personal Data.

  - The Contractor shall, in relation to any Personal Data processed in connection with its obligations under this Contract:

(a)	process that Personal Data only in accordance with Schedule 4, unless the Contractor is required to do otherwise by Law. If it is so required the Contractor shall promptly notify the Department before processing the Personal Data unless prohibited by Law;

(b)	ensure that it has in place Protective Measures, which have been reviewed and approved by the Department as appropriate to protect against a Data Loss Event having taken account of the:

(I)	nature of the data to be protected;

(ii)	harm that might result from a Data Loss Event;

(iii)	state of technological development; and

(iv)	cost of implementing any measures;

(c)	 ensure that :

(I)	the Contractor Personnel do not process Personal Data except in accordance with this Contract (and in particular Schedule 4);

(ii)	it takes all reasonable steps to ensure the reliability and integrity of any Contractor Personnel who have access to the Personal Data and ensure that they:

(A)	are aware of and comply with the Contractor’s duties under this clause;

(B)	are subject to appropriate confidentiality undertakings with the Contractor or any Sub-processor;

(C)	are informed of the confidential nature of the Personal Data and do not publish, disclose or divulge any of the Personal Data to any third Party unless directed in writing to do so by the Department or as otherwise permitted by this Contract; and

(D)	have undergone adequate training in the use, care, protection and handling of Personal Data; and

(d)	not transfer Personal Data outside of the EU unless the prior written consent of the Department has been obtained and the following conditions are fulfilled:

(I)	the Department or the Contractor has provided appropriate safeguards in relation to the transfer (whether in accordance with GDPR Article 46 or LED Article 37) as determined by the Department;

(ii)	the Data Subject has enforceable rights and effective legal remedies;

(iii)	the Contractor complies with its obligations under the Data Protection Legislation by providing an adequate level of protection to any Personal Data that is transferred (or, if it is not so bound, uses its best endeavours to assist the Department in meeting its obligations); and

(iv)	the Contractor complies with any reasonable instructions notified to it in advance by the Department with respect to the processing of the Personal Data;

(e)	at the written direction of the Department, delete or return Personal Data (and any copies of it) to the Department on termination of the Contract unless the Contractor is required by Law to retain the Personal Data.

  - Subject to clause 17.6, the Contractor shall notify the Department immediately if it:

(a)	receives a Data Subject Access Request (or purported Data Subject Access Request);

(b)	receives a request to rectify, block or erase any Personal Data;

(c)	receives any other request, complaint or communication relating to either Party's obligations under the Data Protection Legislation;

(d)	receives any communication from the Information Commissioner or any other regulatory authority in connection with Personal Data processed under this Contract;

(e)	receives a request from any third Party for disclosure of Personal Data where compliance with such request is required or purported to be required by Law; or

(f)	becomes aware of a Data Loss Event.

  - The Contractor’s obligation to notify under clause 7.5 shall include the provision of further information to the Department in phases, as details become available.

  - Taking into account the nature of the processing, the Contractor shall provide the Department with full assistance in relation to either Party's obligations under Data Protection Legislation and any complaint, communication or request made under clause 7.5 (and insofar as possible within the timescales reasonably required by the Department) including by promptly providing:

(a)	the Department with full details and copies of the complaint, communication or request;

(b)	such assistance as is reasonably requested by the Department to enable the Department to comply with a Data Subject Access Request within the relevant timescales set out in the Data Protection Legislation;

(c)	the Department, at its request, with any Personal Data it holds in relation to a Data Subject;

(d)	assistance as requested by the Department following any Data Loss Event;

(e)	assistance as requested by the Department with respect to any request from the Information Commissioner’s Office, or any consultation by the Department with the Information Commissioner's Office.

  - The Contractor shall maintain complete and accurate records and information to demonstrate its compliance with this clause. This requirement does not apply where the Contractor employs fewer than 250 staff, unless:

(a)	the Department determines that the processing is not occasional;

(b)	the Department determines the processing includes special categories of data as referred to in Article 9(1) of the GDPR or Personal Data relating to criminal convictions and offences referred to in Article 10 of the GDPR; and

(c)	the Department determines that the processing is likely to result in a risk to the rights and freedoms of Data Subjects.

  - The Contractor shall allow for audits of its Data Processing activity by the Department or the Department’s designated auditor.

  - The Contractor shall designate a data protection officer if required by the Data Protection Legislation.

  - Before allowing any Sub-processor to process any Personal Data related to this Contract, the Contractor must:

(a)	notify the Department in writing of the intended Sub-processor and processing;

(b)	obtain the written consent of the Department;

(c)	enter into a written agreement with the Sub-processor which give effect to the terms set out in this clause such that they apply to the Sub-processor; and

(d)	provide the Department with such information regarding the Sub-processor as the Department may reasonably require.

  - The Contractor shall remain fully liable for all acts or omissions of any Sub-processor.

  - The Contractor may, at any time on not less than 30 Working Days’ notice, revise this clause by replacing it with any applicable controller to processor standard clauses or similar terms forming part of an applicable certification scheme (which shall apply when incorporated by attachment to this Contract).

  - The Parties agree to take account of any guidance issued by the Information Commissioner’s Office. The Department may on not less than 30 Working Days’ notice to the Contractor amend this Contract to ensure that it complies with any guidance issued by the Information Commissioner’s Office.

8.	Department’s Data

8.1	The Contractor shall employ appropriate organisational, operational and technological processes and procedures to keep the Department’s Data safe from unauthorised use or access, loss, destruction, theft or disclosure.  The organisational, operational and technological processes and procedures adopted are required to comply with the requirements of ISO/IEC 27001 as appropriate to the services being provided to the Department.

8.2	The Contractor shall not delete or remove any proprietary notices contained within or relating to the Department’s Data.

8.3	The Contractor shall not store, copy, disclose, or use the Department’s Data except as necessary for the performance by the Contractor of its obligations under this Contract or as otherwise expressly authorised in writing by the Department.

8.4	To the extent that the Department’s Data is held and/or processed by the Contractor, the Contractor shall supply that the Department’s Data to the Department as requested by the Department in the format specified by the Department.

8.5	The Contractor shall take responsibility for preserving the integrity of the Department’s Data and preventing the corruption or loss of the Department’s Data.

8.6	 The Contractor shall ensure that any files containing the Department’s Data are stored on the Contractor’s secure servers and/or secured IT equipment.  The Contractor shall ensure that the Department’s Data relating to the project is segregated from other data on their IT systems.

8.7	The Contractor shall not keep the Department’s Data on any laptop or other removable drive or device unless that laptop, other removable drive or device is protected by being fully encrypted and password protected, and the use of the device or laptop is necessary for the provision of the services set out in the Contract.  Laptops should have full disk encryption using either a CESG (Communications Electronic Security Group) CAPS approved product or alternatively a product that complies with the FIPS 140-2 Standard. USB devices used for transferring the Department’s Data should be encrypted to the FIPS 140-2 Standard.

8.8	The Contractor shall keep an audit trail of where the Department’s Data is held, including hardware, laptops, drives and devices.

8.9	The Contractor shall ensure that the Department’s Data is stored in locked cabinets.

8.10	The Contractor shall ensure that the Department’s Data is securely removed from their systems and any printed copies securely destroyed at the end of this work, or on termination of the contract.  In complying with this clause, electronic copies of the Department’s Data shall be securely destroyed by either physical destruction of the storage media or secure deletion using appropriate electronic shredding software, using a minimum setting of US DOD overwriting standard (7 passes).  Any hard copy shall be destroyed by cross-cut shredding and secure re-cycling of the resulting paper waste.

8.11	The Contractor shall perform secure back-ups of all the Department’s Data and shall ensure that up-to-date back-ups are stored off-site.  The Contractor shall ensure that such back-ups are available to the Department at all times upon request.

8.12	The Contractor shall ensure that any of the Department’s Data to be sent between the Contractor’s offices/staff, and/or the sub-contractors, and/or any other third party are sent by CD or DVD and are fully encrypted and password protected.  The Contractor shall ensure that the password for files is sent separately from the data to the named recipient of the data.  The Department’s Data shall be transferred by a secure courier or registered postal service (special delivery) and not by e-mail or on USB pens.

8.13	If the Department’s Data is corrupted, lost or sufficiently degraded as a result of the Contractor's Default so as to be unusable, the Department may:

8.13.1	require the Contractor (at the Contractor's expense) to restore or procure the restoration of the Department’s Data shall do so as soon as practicable and/or

8.13.2	itself restore or procure the restoration of the Department Data, and shall be repaid by the Contractor any reasonable expenses incurred in doing so.

8.14	If at any time the Contractor suspects or has reason to believe that the Department’s Data has or may become corrupted, lost or sufficiently degraded in any way for any reason, then the Contractor shall notify the Department immediately and inform the Department of the remedial action the Contractor proposes to take.

- Warranty and Indemnity

  - The Contractor warrants to the Department that the obligations of the Contractor under this Contract will be performed by appropriately qualified and trained personnel with reasonable skill, care and diligence and to such high standards of quality as it is reasonable for the Department to expect in all the circumstances.  The Department will be relying upon the Contractor's skill, expertise and experience in the performance of the Project and also upon the accuracy of all representations or statements made and the advice given by the Contractor in connection with the performance of the Project and the accuracy of any documents conceived, originated, made or developed by the Contractor as part of this Contract.  The Contractor warrants that any goods supplied by the Contractor forming part of the Services will be of satisfactory quality and fit for their purpose and will be free from defects in design, material and workmanship.

  - Without prejudice to any other remedy, if any part of the Project is not performed in accordance with this Contract then the Department shall be entitled, where appropriate to:

    - require the Contractor promptly to re-perform or replace the relevant part of the Project without additional charge to the Department; or

    - assess the cost of remedying the failure (“the assessed cost”) and to deduct from any sums due to the Contractor the Assessed Cost for the period that such failure continues.

  - The Contractor shall be liable for and shall indemnify the Department in full against any expense, liability, loss, claim or proceedings arising under statute or at common law in respect of personal injury to or death of any person whomsoever or loss of or damage to property whether belonging to the Department or otherwise arising out of or in the course of or caused by the performance of the Project.

  - Without prejudice to any other exclusion or limitation of liability in this Contract, the liability of the Contractor for any claim or claims under this Contract shall be limited to such sums as it would be just and equitable for the Contractor to pay having regard to the extent of his responsibility for the loss or damage giving rise to such claim or claims etc.

  - All property of the Contractor whilst on the Department's premises shall be there at the risk of the Contractor and the Department shall accept no liability for any loss or damage howsoever occurring to it.

  - The Contractor shall ensure that it has adequate insurance cover with an insurer of good repute to cover claims under this Contract or any other claims or demands which may be brought or made against it by any person suffering any injury damage or loss in connection with this Contract.  The Contractor shall upon request produce to the Department, it's policy or policies of insurance, together with the receipt for the payment of the last premium in respect of each policy or produce documentary evidence that the policy or policies are properly maintained.

- Termination

  - This Contract may be terminated by either party giving to the other party at least 30 days’ notice in writing.

  - In the event of any breach of this Contract by either party, the other party may serve a notice on the party in breach requiring the breach to be remedied within a period specified in the notice which shall be reasonable in all the circumstances.  If the breach has not been remedied by the expiry of the specified period, the party not in breach may terminate this Contract with immediate effect by notice in writing.

  - In the event of a material breach of this Contract by either party, the other party may terminate this Contract with immediate effect by notice in writing.

  - This Contract may be terminated by the Department with immediate effect by notice in writing if at any time:-

10.4.1	the Contractor passes a resolution that it be wound-up or that an application be made for an administration order or the Contractor applies to enter into a voluntary arrangement with its creditors; or

10.4.2	a receiver, liquidator, administrator, supervisor or administrative receiver be appointed in respect of the Contractor's property, assets or any part thereof; or

10.4.3	the court orders that the Contractor be wound-up or a receiver of all or any part of the Contractor's assets be appointed; or

10.4.4	the Contractor is unable to pay its debts in accordance with Section 123 of the Insolvency Act 1986.

10.4.5	there is a change in the legal or beneficial ownership of 50% or more of the Contractor's share capital issued at the date of this Contract or there is a change in the control of the Contractor, unless the Contractor has previously notified the Department in writing.  For the purpose of this Sub-Clause 10.4.5 “control” means the power of a person to secure that the affairs of the Contractor are conducted in accordance with the wishes of that person by means of the holding of shares or the possession of voting power.

10.4.6	the Contractor is convicted (or being a company, any officers or representatives of the Contractor are convicted) of a criminal offence related to the business or professional conduct

10.4.7	the Contractor commits (or being a company, any officers or representatives of the Contractor commit) an act of grave misconduct in the course of the business;

10.4.8	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to the payment of Social Security contributions;

10.4.9	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to payment of taxes;

10.4.10 the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to disclose any serious misrepresentation in supplying information required by the Department in or pursuant to this Contract.

10.5	Nothing in this Clause 10 shall affect the coming into, or continuance in

force of any provision of this Contract which is expressly or by implication intended to come into force or continue in force upon termination of this Contract.

- Status of Contractor

  - In carrying out its obligations under this Contract the Contractor agrees that it will be acting as principal and not as the agent of the Department.

  - The Contractor shall not say or do anything that may lead any other person to believe that the Contractor is acting as the agent of the Department.

12.	Freedom of information

12.1	The Contractor acknowledges that the Department is subject to the requirements of the FOIA and the Environmental Information Regulations and shall assist and cooperate with the Department to enable the Department to comply with its information disclosure obligations.

12.2	The Contractor shall and shall procure that its Sub-contractors shall:

12.2.1	transfer to the Department all Requests for Information that it receives as soon as practicable and in any event within two Working Days of receiving a Request for Information;

12.2.2	provide the Department with a copy of all Information in its possession, or power in the form that the Department requires within five Working Days (or such other period as the Department may specify) of the Department's request; and

12.2.3	provide all necessary assistance as reasonably requested by the Department to enable the Department to respond to the Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations.

12.3	The Department shall be responsible for determining in its absolute discretion and notwithstanding any other provision in this Contract or any other agreement whether any Information is exempt from disclosure in accordance with the provisions of the FOIA or the Environmental Information Regulations.

12.4	In no event shall the Contractor respond directly to a Request for Information unless expressly authorised to do so by the Department.

12.5	The Contractor acknowledges that (notwithstanding the provisions of Clause 13) the Department may, acting in accordance with the Ministry of Justice’s Code of Practice on the Discharge of the Functions of Public Authorities under Part 1 of the Freedom of Information Act 2000 (“the Code”), be obliged under the FOIA, or the Environmental Information Regulations to disclose information concerning the Contractor or the Project:

12.5.1	in certain circumstances without consulting the Contractor; or

12.5.2	following consultation with the Contractor and having taken their views into account;

12.5.3	provided always that where 12.5.1 applies the Department shall, in accordance with any recommendations of the Code, take reasonable steps, where appropriate, to give the Contractor advanced notice, or failing that, to draw the disclosure to the Contractor’s attention after any such disclosure.

12.6	The Contractor shall ensure that all Information is retained for disclosure and shall permit the Department to inspect such records as requested from time to time.

13.	CONFIDENTIALITY

13.1	Except to the extent set out in this clause or where disclosure is expressly permitted elsewhere in this Contract, each party shall:

13.1.1	treat the other party's Confidential Information as confidential and safeguard it accordingly; and

13.3.2	not disclose the other party's Confidential Information to any other person without the owner's prior written consent.

13.2	Clause 13 shall not apply to the extent that:

13.2.1	such disclosure is a requirement of Law placed upon the party making the disclosure, including any requirements for disclosure under the FOIA, Code of Practice on Access to Government Information or the Environmental Information Regulations pursuant to clause 12 (Freedom of Information);

13.2.2	such information was in the possession of the party making the disclosure without obligation of confidentiality prior to its disclosure by the information owner;

13.2.3	such information was obtained from a third party without obligation of confidentiality;

13.2.4	such information was already in the public domain at the time of disclosure otherwise than by a breach of this Contract; or

13.2.5	it is independently developed without access to the other party's Confidential Information.

13.3	The Contractor may only disclose the Department's Confidential Information to the Contractor Personnel who are directly involved in the provision of the Services and who need to know the information, and shall ensure that such Contractor Personnel are aware of and shall comply with these obligations as to confidentiality.

13.4	The Contractor shall not, and shall procure that the Contractor Personnel do not, use any of the Department's Confidential Information received otherwise than for the purposes of this Contract.

13.5	At the written request of the Department, the Contractor shall procure that those members of the Contractor Personnel identified in the Department's notice signs a confidentiality undertaking prior to commencing any work in accordance with this Contract.

13.6	Nothing in this Contract shall prevent the Department from disclosing the Contractor's Confidential Information:

13.6.1	to any Crown Body or any other Contracting Department.  All Crown Bodies or Contracting Authorities receiving such Confidential Information shall be entitled to further disclose the Confidential Information to other Crown Bodies or other Contracting Authorities on the basis that the information is confidential and is not to be disclosed to a third party which is not part of any Crown Body or any Contracting Department;

13.6.2	to any consultant, contractor or other person engaged by the Department or any person conducting an Office of Government Commerce gateway review;

13.6.3  for the purpose of the examination and certification of the Department's accounts; or

13.6.4	for any examination pursuant to Section 6(1) of the National Audit Act 1983 of the economy, efficiency and effectiveness with which the Department has used its resources.

13.7	The Department shall use all reasonable endeavours to ensure that any government department, Contracting Department, employee, third party or Sub-contractor to whom the Contractor's Confidential Information is disclosed pursuant to clause 13 is made aware of the Department's obligations of confidentiality.

13.8	Nothing in this clause 13 shall prevent either party from using any techniques, ideas or know-how gained during the performance of the Contract in the course of its normal business to the extent that this use does not result in a disclosure of the other party's Confidential Information or an infringement of IPR.

13.9	The parties acknowledge that, except for any information which is exempt from disclosure in accordance with the provisions of the FOIA, the content of this Contract is not Confidential Information. The Department shall be responsible for determining in its absolute discretion whether any of the content of the Contract is exempt from disclosure in accordance with the provisions of the FOIA.

13.10	Subject to Clause 13.9, the Contractor hereby gives his consent for the Department to publish the Contract in its entirety, including from time to time agreed changes to the Contract, to the general public.

13.11	The Department may consult with the Contractor to inform its decision regarding any redactions but the Department shall have the final decision in its absolute discretion.

13.12	The Contractor shall assist and cooperate with the Department to enable the Department to publish this Contract.

14.	Access and Information

14.1	The Contractor shall provide access at all reasonable times to the Department's internal auditors or other duly authorised staff or agents to inspect such documents as the Department considers necessary in connection with this Contract and where appropriate speak to the Contractors employees.

15.	Transfer of Responsibility on Expiry or Termination

15.1	The Contractor shall, at no cost to the Department, promptly provide such assistance and comply with such timetable as the Department may reasonably require for the purpose of ensuring an orderly transfer of responsibility upon the expiry or other termination of this Contract.  The Department shall be entitled to require the provision of such assistance both prior to and, for a reasonable period of time after the expiry or other termination of this Contract.

15.2	Such assistance may include (without limitation) the delivery of documents and data in the possession or control of the Contractor which relate to this Contract, including the documents and data, if any, referred to in the Schedule.

15.3	The Contractor undertakes that it shall not knowingly do or omit to do anything that may adversely affect the ability of the Department to ensure an orderly transfer of responsibility.

16.	Tax indemnity

  - 16.1	Where the Contractor is liable to be taxed in the UK in respect of consideration received under this contract, it shall at all times comply with the Income Tax (Earnings and Pensions) Act 2003 (ITEPA) and all other statutes and regulations relating to income tax in respect of that consideration.

  - 16.2	Where the Contractor is liable to National Insurance Contributions (NICs) in respect of consideration received under this contract, it shall at all times comply with the Social Security Contributions and Benefits Act 1992 (SSCBA) and all other statutes and regulations relating to NICs in respect of that consideration.

  - 16.3	The Department may, at any time during the term of this contract, ask the Contractor to provide information which demonstrates how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it.

  - 16.4	A request under Clause 16.3 above may specify the information which the Contractor must provide and the period within which that information must be provided.

  - 16.5	The Department may terminate this contract if-

## (a)	in the case of a request mentioned in Clause 16.3 above if the Contractor:

## (I) fails to provide information in response to the request within a reasonable time, or

## (ii) provides information which is inadequate to demonstrate either how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it;

## (b)	in the case of a request mentioned in Clause 16.4 above, the Contractor fails to provide the specified information within the specified period, or

## (c)	it receives information which demonstrates that, at any time when Clauses 16.1 and 16.2 apply, the Contractor is not complying with those Clauses.

  - 16.6	The Department may supply any information which it receives under Clause 16.3 to the Commissioners of Her Majesty’s Revenue and Customs for the purpose of the collection and management of revenue for which they are responsible.

  - 16.7	The Contractor warrants and represents to the Department that it is an independent contractor and, as such, bears sole responsibility for the payment of tax and national insurance contributions which may be found due from it in relation to any payments or arrangements made under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

  - 16.8	The Contractor will account to the appropriate authorities for any income tax, national insurance, VAT and all other taxes, liabilities, charges and duties relating to any payments made to the Contractor under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

  - 16.9	The Contractor shall indemnify Department against any liability, assessment or claim made by the HM Revenue and Customs or any other relevant authority arising out of the performance by the parties of their obligations under this Contract (other than in respect of employer's secondary national insurance contributions) and any costs, expenses, penalty fine or interest incurred or payable by Department in connection with any such assessment or claim.

  - 16.10	The Contractor authorises the Department to provide the HM Revenue and Customs and all other departments or agencies of the Government with any information which they may request as to fees and/or expenses paid or due to be paid under this Contract whether or not Department is obliged as a matter of law to comply with such request.

17.	Amendment and variation

17.1	No amendment or variation to this Contract shall be effective unless it is in writing and signed by or on behalf of each of the parties hereto.  The Contractor shall comply with any formal procedures for amending or varying contracts that the Department may have in place from time to time.

18. 	Assignment and Sub-contracting

18.1	The benefit and burden of this Contract may not be assigned or sub-contracted in whole or in part by the Contractor without the prior written consent of the Department.  Such consent may be given subject to any conditions which the Department considers necessary.  The Department may withdraw its consent to any sub-contractor where it no longer has reasonable grounds to approve of the sub-contractor or the sub-contracting arrangement and where these grounds have been presented in writing to the Contractor.

19. 	The Contract (Rights of Third Parties) Act 1999

19.1	This Contract is not intended to create any benefit, claim or rights of any kind whatsoever enforceable by any person not a party to the Contract.

20.	Waiver

20.1	No delay by or omission by either Party in exercising any right, power, privilege or remedy under this Contract shall operate to impair such right, power, privilege or remedy or be construed as a waiver thereof.  Any single or partial exercise of any such right, power, privilege or remedy shall not preclude any other or further exercise thereof or the exercise of any other right, power, privilege or remedy.

21. 	Notices

21.1	Any notices to be given under this Contract shall be delivered personally or sent by post or by facsimile transmission to the Project Manager (in the case of the Department) or to the address set out in this Contract (in the case of the Contractor).  Any such notice shall be deemed to be served, if delivered personally, at the time of delivery, if sent by post, forty-eight hours after posting or, if sent by facsimile transmission, twelve hours after proper transmission.

22.	Dispute resolution

22.1 	The Parties shall use all reasonable endeavours to negotiate in good faith and settle amicably any dispute that arises during the continuance of this Contract.

22.2	Any dispute not capable of resolution by the parties in accordance with the terms of Clause 21 shall be settled as far as possible by mediation in accordance with the Centre for Dispute Resolution (CEDR) Model Mediation Procedure.

22.3	No party may commence any court proceedings/arbitration in relation to any dispute arising out of this Contract until they have attempted to settle it by mediation, but any such mediation may be terminated by either party at any time of such party wishing to commence court proceedings/arbitration.

23.	Law and Jurisdiction

23.1	This Contract shall be governed by and interpreted in accordance with English Law and the parties submit to the jurisdiction of the English courts.

24.	Discrimination

24.1	The Contractor shall not unlawfully discriminate within the meaning and scope of any law, enactment, order, or regulation relating to discrimination (whether in race, gender, religion, disability, sexual orientation or otherwise) in employment.

24.2	The Contractor shall take all reasonable steps to secure the observance of Clause 24.1 by all servants, employees or agents of the Contractor and all suppliers and sub-contractors employed in the execution of the Contract.

25.	Safeguarding children who participate in research

25.1 	The Contractor will put in place safeguards to protect children from a risk of significant harm which could arise from them taking part in the Project. The Contractor will agree these safeguards with the Department before commencing work on the Project.

25.2 	In addition, the Contractor will carry out checks with the Disclosure and Barring Service (DBS checks) on all staff employed on the Project in a Regulated Activity. Contractors must have a DBS check done every three years for each relevant member of staff for as long as this contract applies. The DBS check must be completed before any of the Contractor’s employees work with children in Regulated Activity. Please see https://www.gov.uk/crb-criminal-records-bureau-check for further guidance.

26.	Project outputs

26.1 	Unless otherwise agreed between the Contractor and the Project Manager, all outputs from the Project shall be published by the Department on the Department’s research website.

26.2	The Contractor shall ensure that all outputs for publication by the Department adhere to the Department’s Style Guide and MS Word Template, available to download from: https://www.gov.uk/government/publications/eoi-guide

26.3 	Unless otherwise agreed between the Contractor and Project Manager, the Contractor shall supply the Project Manager with a draft for comment at least eight weeks before the intended publication date, for interim reports, and eight weeks before the contracted end date, for final reports.

26.4 	The Contractor shall consider revisions to the drafts with the Project Manager in the light of the Department’s comments. The Contractor shall provide final, signed off interim reports and other outputs planned within the lifetime of the Project to the Department by no later than four weeks before the intended publication date, and final, signed off reports and other outputs at the end of the Project to the Department by no later than the contracted end date for the Project.

26.5	Until the date of publication, findings from all Project outputs shall be treated as confidential, as set out in the Clause 13 above. The Contractor shall not release findings to the press or disseminate them in any way or at any time prior to publication without approval of the Department.

26.6	Where the Contractor wishes to issue a Press Notice or other publicity material containing findings from the Project, notification of plans, including timing and drafts of planned releases shall be submitted by the Contractor to the Project Manager at least three weeks before the intended date of release and before any agreement is made with press or other external audiences, to allow the Department time to comment. All Press Notices released by the Department or the Contractor shall state the full title of the research report, and include a hyperlink to the Department’s research web pages, and any other web pages as relevant, to access the publication/s. This clause applies at all times prior to publication of the final report.

26.7	Where the Contractor wishes to present findings from the Project in the public domain, for example at conferences, seminars, or in journal articles, the Contractor shall notify the Project Manager before any agreement is made with external audiences, to allow the Department time to consider the request. The Contractor shall only present findings that will already be in the public domain at the time of presentation, unless otherwise agreed with the Department. This clause applies at all times prior to publication of the final report.

End of Schedule Three

Schedule ​4 Processing, Personal Data and Data Subjects

The Contractor shall comply with any further written instructions with respect to processing by the Department.

Any such further instructions shall be incorporated into this Schedule.

| Description | Details |
| --- | --- |
| Subject matter of the processing | Personal and management data for evaluation purposes. |
| Duration of the processing | Processing will be ongoing throughout the duration of the contract on a number of research and analysis activities. All data will be processed by February 2022. |
| Nature and purposes of the processing | The data will be processed for the purpose of evaluating the impact of the Teacher Student Loan Reimbursement Scheme on teacher retention. Management information data (including personal information) will be sent by the DfE to the Contractor on an ongoing basis. This will include data from Get into Teaching, the Database of Qualified Teachers, and data regarding those who have participated in the scheme. The data will be stored by the Contractor and used as a sampling frame to contact research participants (who will be invited to take part in online surveys). Data will be held under encryption on CFE’s servers. Only individuals working on the study will have access to the data held in secure areas. The data may also be used in data analysis, i.e. matching survey responses to the original dataset variables. Data will also be collected by the Contractor through primary research, for example, in the form of survey responses or in-depth interviews. Data will be in the form of survey responses, fieldwork notes, audio recording files and transcripts. This data will be securely stored, and reported anonymously back to DfE. Anonymous copies of the survey response datasets will be transferred to DfE. Data will be destroyed by the Contractor when no longer needed (or at the conclusion of the contract if needed throughout project lifetime). Telephone interviews will be conducted, recorded and transcribed for aggregated analysis. Express permission for recording and transcription will be sought before the interview. CFE will store audio recordings for the duration of the study. |
| Type of Personal Data | Personal data on participants includes (where available): full name, telephone number, email address, TRN, start date (if undertaking initial teacher training), and variables relevant to their claim (such as amount claimed). This may be supplemented by special category or sensitive data including gender and ethnicity where deemed relevant to the evaluation’s objectives by the Department. Individual data will be linked to create longitudinal datasets for analysis purposes. This may also be linked to other data sources in which personal information is stored such as Get into Teaching or the Database of Qualfiied Teachers. |
| Categories of Data Subject | Teachers and senior leaders regarding their interaction with the scheme. These include: teachers/senior leaders in eligible schools and teachers/senior leaders in non-eligible, neighbouring local authorities. |
| Plan for return and destruction of the data once the processing is complete UNLESS requirement under union or member state law to preserve that type of data | The data will be destroyed by the Contractor at the completion of the contract (specific datasets will be destroyed earlier where no longer required for the evaluation). |

End of Schedule Four

Authorised to sign for and on		Authorised to sign for and on

behalf of the Secretary of		behalf of the Contractor

State for Education

Signature		Signature

Name in CAPITALS		Name in CAPITALS

Position and Address		Position and Address

Date								Date