## Stage 0
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
0
|  | 2.1 | Strategic Definition - Stage 0
Deliverables for Stage 0 (delete/add to as required)
Core Deliverables
Optional Deliverables

## Stage 1
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
1
|  | 2.2 | Preparation and Brief- Stage 1
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
|  | 2.2.1 | Seek the Brief and instructions from the Client or the Client's authorised representative describing the Client's requirements in respect of the Works, what they are intended to achieve, their cost and programme. | X
|  | 2.2.2 | Discuss with the client the role of the consultant and the Client's relationship with the lead Consultant if appointed and any other consultants, the various contractors and sub-contractor and any Principal Designer appointed in accordance with with the Construction (Design and Management) Regulations 2015. | X
|  | 2.2.3 | Discuss with the Client the likely requirements for Site Staff; these shall be considered again prior to and following the appointment of Contractors. | X
|  | 2.2.4 | Discuss with the client and agree the submissions and approvals required of statutory Authorities. | X
|  | 2.2.5 | Discuss and agree the design services to be undertaken by various contractors, sub-contractors and other consultants. | X
|  | 2.2.6 | Discuss with the Client and agree the type of construction contract and the timing of the tender activities in relation to the various stages of design. | X
|  | 2.2.7 | Discuss with the Client and agree whether Building Information Modelling is to be utilised in the production of information and if so agree any appropriate protocol. | X
|  | 2.2.8 | Seek from the client all information and data relevant to the works in the Client's possession or control and in accordance with the Construction (Design and Management) Regulations 2015. | X
|  | 2.2.9 | Outline the effects of limitations of the Site on the Works caused by the topography and any reasonably identifiable previous uses thereof and the presence or possible presence of contaminants as a result of such uses where such matters are apparent from the data and other information provided by the Client. | X
|  | 2.2.10 | Review such information as is contained in readily available data on the existence and extent of relevant public services such as water, gas, electricity, sewerage, culverts, tunnels and telecommunications services. Comment to the Client on any effect that these may have on the works, both during construction of the works and on completion. | X
|  | 2.2.11 | Comment to the client on any physical site restrictions including access which may affect the engineering options for the works. | X
|  | 2.2.12 | Liaise with those appointed to prepare a desk study of the site. If necessary, and with the Client's agreement, bring forward from 2.3.3 of stage 2 a site geotechnical investigation. |  | X
|  | 2.2.13 | Collaborate with the Lead consultant if appointed and any other consultants in seeking from the client any further information needed so that they can perform their services under their various agreements with the client. | X
|  | 2.2.14 | Collaborate in making initial recommendations to the client on the technical viability of the works. | X
|  | 2.2.15 | Seek the client's consent to proceed to stage 2. | X
Deliverables for Stage 1 (delete/add to as required)
Core Deliverables
|  |  | Provide or obtain written confirmation of Client’s brief and instructions. | X
Optional Deliverables
|  | i. | Provide initial project brief. |  | X
|  | ii. | Provide initial design programme. | X
|  | iii. | Provide assessment of significant risks from any existing Health & Safety file. |  | X
|  | iv. | Provide a Schedule that describes the BIM information to be delivered to an agreed information delivery plan. |  | X

## Stage 2
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
2
|  | 2.3 | Concept Design – Stage 2
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
After receiving the Client’s consent to proceed to the concept design Stage:
|  | 2.3.1 | Visit the Site as appropriate and study data and information relating to the Project and relevant to the Works which are reasonably accessible to the Consultant, and consider reports relating to the Works which have either been prepared by the Consultant or have been prepared by others and made available to the Consultant by the Client. | X
|  | 2.3.2 | Liaise as may be necessary with any Other Consultants to agree a programme for the whole of the design and construction of the Works. | X
|  | 2.3.3 | Advise the Client on the need for arrangements to be made for geotechnical investigations of the Site. Arrange as agent for the Client, when authorised by the Client, for such investigations and interpretive report to be undertaken, certify the amount of any payments to be made by the Client to the persons or firms carrying out such investigations and advise the Client on the results and recommendations of such investigations. |  | X
|  | 2.3.4 | Advise the Client on the need for arrangements to be made for topographical and dimensional surveys of the site, surveys to obtain details of construction in existence on or adjacent to the site, special investigations or model tests. Arrange, as agent for the Client when authorised by the Client, for such works to be undertaken, certify the amount of any payments to be made by the Client to the persons or firms carrying out such works, and advise the Client on the results of such works. |  | X
|  | 2.3.5 | Where appropriate consult any local or other authorities about matters of principle in connection with the design of the Works | X
|  | 2.3.6. | Consider alternative outline solutions for the Works. | X
|  | 2.3.7 | Develop the Client’s Brief into a full Brief for the Project in consultation with the Client and any Other Consultants. Such Brief shall describe the Client’s requirements in respect of the Services and both the Client and the Consultant shall work to the Brief. Discuss and agree with the Client any changes to the arrangements for payments to be made to the Consultant which may have become necessary as a result of changes to the Brief. Comment to the Client on any restrictions the Brief may impose on any future use of the Project suggested by the Client. | X
|  | 2.3.8 | Provide sufficient preliminary information in relation to the Works in the form of advice, sketches, reports or outline specifications to enable the Lead Consultant if appointed to collate the concept design and assist any Other Consultant to prepare the outline Cost Plan. | X
|  | 2.3.9 | After review, seek the Client’s approval of the concept design and the Client’s consent to proceed to Stage 3. | X
Deliverables for Stage 2 (delete/add to as required)
Core Deliverables
|  | i. | Provide outline scheme sketches and layouts indicating basic proposals, general grid layout of typical area of the development with preliminary sizing of primary structural elements. | X
Typically for a building structural design:
|  | a. | Updated Client Brief. | X
|  | b. | Sketch layouts of structural solution in plan and section for critical elements of the building with typically structural steel weights per gross area of steel building or element sizing for buildings of structural concrete and other materials. | X
|  | c. | Documentation for procurement of geotechnical investigation and topographical and dimensional surveys. |  | X
|  | d. | Foundation types and size estimates. | X
|  | e. | Requirements for earth retaining structures. |  | X
|  | f. | Outline specification. | X
Optional Deliverables
|  | i. | Provide external drainage layouts showing primary routes and connection locations to adopted sewers | X
|  | ii. | Provide external road and car park typical construction sections. | X
|  | iii. | Provide concept structural design model including appropriate geometric detail and object information. | X

## Stage 3
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
3
|  | 2.4 | Developed Design- Stage 3
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
After receiving the Client’s approval of the concept design and the Client’s consent to proceed to the developed design Stage:
|  | 2.4.1 | Develop the design of the Works in collaboration with any Other Consultants and prepare sufficient calculations, drawings, schedules and specifications to enable the Consultant, or any Other Consultant to prepare the final developed design. | X
|  | 2.4.2 | Integrate into the design of the Works any requirements of specialist sub-consultants, Contractors or sub-contractors (if available at this Stage). | X
|  | 2.4.3 | Prepare such representative sketches, drawings, specifications, and/or calculations in respect of the Works as are necessary to enable the preparation of the Cost Plan. | X
|  | 2.4.4 | Collaborate with any Other Consultants to prepare detailed proposals for presentation to the Client, drawing attention to any significant differences from the previously agreed requirements for the Works. | X
|  | 2.4.5 | Assist in coordinating the design of the Works into the overall design. | X
|  | 2.4.6 | Seek the Client’s approval of the developed design and the Client’s consent to proceed to Stage 4. | X
Deliverables for Stage 3 (delete/add to as required)
Core Deliverables
|  | i. | Provide drawings showing the extent of the civil and structural solutions that are co-ordinated with the architecture and building services. | X
Typically for a building structural design:
|  | a. | Layout and section drawings of all floor levels indicating structural element sizes and structural zones. Drawings should generally be at a level of detail commensurate with a printed scale of 1:100 (or suitable for development). | X
|  | b. | Typical structural system support and restraint details. | X
|  | c. | Details of building stability elements and sizes. | X
|  | d. | Foundation details and sizes. | X
|  | e. | Sizing and construction of retaining structures. | X
|  | f. | Drainage layouts. | X
|  | g. | Road layout and details. | X
|  | h. | Detailed specification. | X
Optional Deliverables
|  | i. | Provide developed design model including appropriate geometric detail and object information.

## Stage 4
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
4
|  | 2.5 | Technical Design- Stage 4
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
After receiving the Client’s approval of the Developed Design and the Client’s consent to proceed to the Technical design
|  | 2.5.1 | Develop the design of the Works in collaboration with any Other Consultants and prepare sufficient calculations, information, drawings, schedules and specifications to enable the Consultant and/or any Other Consultants to prepare Tender Documentation in respect of the Works. | X
|  | 2.5.2 | Integrate into the design of the Works any requirements of specialist sub-consultants, Contractors or sub-contractors if available at this Stage. | X
|  | 2.5.3 | Prepare such calculations or certification and details relating to the Works as may be required for submission to any appropriate statutory authority as agreed under 2.2.4 including the coordination of such information for the Works submitted by specialist suppliers and/or Contractors as is available which may need to be included in such submissions excluding any submissions or applications for planning consents and approvals. | X
|  | 2.5.4 | Continue to prepare any further drawings and schedules necessary to enable Contractors to commence the Works, but excluding Co-ordination Information, designs and details for temporary works, formwork, shop fabrication and connection details. In the case of reinforced concrete work, general arrangement information and information of non- standard details should be prepared sufficient to enable a Contractor to prepare full details and bar bending schedules for the Works. |  | X
|  | 2.5.5 | Assist in advising the Client on the need for any special conditions of contract relevant to the Works and on appropriate forms of contract and invitations to tender for the Works. | X
|  | 2.6 | Tender Documentation and tender action (the Stage at which this may occur is dependent on 2.2.6)
After receiving the Client’s consent to proceed to the production of Tender Documentation and tender action:
|  | 2.6.1 | Assist in advising the Client as to the suitability for carrying out the Works of persons and firms to be invited to tender for any contract involving the construction, supply and/or installation of all or part of the Works. | X
|  | 2.6.2 | Assist the Client in assembling the Tender Documentation and to issue it to firms selected to tender. | X
|  | 2.6.3 | Assist in advising the Client as to the relative merits of tenders, prices and estimates received for execution of all or part of the Works. | X
|  | 2.6.4 | Seek the Client’s consent to proceed to Stage 5. | X
Deliverables for Stage 4 (delete/add to as required)
Core Deliverables
|  | i. | Provide Information showing the extent of the technical definition of civil and structural solution except where detailed design is by a Contractor in which case sufficient information will be provided for development by the Contractor. This information will be appropriate to the method of procurement and programme of the Project and sufficient, in association with the Contractor’s information, for Building Regulations submission. | X
Typically for a building structural design:
|  | a. | Plan layouts should be to a scale of at least 1:100 (to suit building size). Fully dimensioned and including all section sizes and reinforcement requirements for concrete elements but not including reinforcement details or bar bending schedules. |  | X
|  | b. | Sectional information for the building information. |  | X
|  | c. | All critical building structure details at a scale appropriate for the element. |  | X
|  | d. | Details of all foundations, layouts of piles (if required) including reinforcement requirements and typical details for buildings of structural concrete and other materials. |  | X
|  | e. | Details of all retaining structures. |  | X
|  | f. | Detailed elemental specification documentation. |  | X
|  | g. | Below slab and external drainage details. |  | X
|  | h. | Road/car park construction details. |  | X
|  | i. | Performance specifications for contractor design elements. | X
Optional Deliverables
|  | i. | Provide technical design model including appropriate geometric and object information. |  | X

## Stage 5
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
5
|  | 2.7 | Construction – Stage 5
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
After receiving the Client’s consent to proceed to Stage 5:
|  | 2.7.1 | Continue to prepare any further information and schedules necessary to enable Contractors to complete the Works, but excluding Coordination Information, designs and details for temporary works, form work, shop fabrication and connection details. In the case of reinforced concrete work, general arrangement information and information of non- standard details should be prepared sufficient to enable a Contractor to prepare full details and bar bending schedules for the Works. |  | X
|  | 2.7.2 | Advise the Client on the finalisation of formal contract documents relating to accepted tenders for carrying out the Works or any part of the Works. The Consultant shall not accept any tender in respect of the Works. | X
|  | 2.7.3 | Examine detailed designs, shop fabrication drawings, standard details, bar bending schedules and specifications submitted by Contractors or sub-contractors for the Works or parts thereof, manufactured or supplied by Contractors or sub-contractors in respect of conformity with the Consultant’s performance specifications. The Consultant shall not be required to examine the design of any proprietary products. | X
|  | 2.7.4 | Advise the Client on the need for special inspections or tests arising during the construction of the Works. | X
|  | 2.7.5 | Advise on the appointment and duties of Site Staff and, where they have been appointed, instruct Site Staff in accordance with the appointment agreement. |  | X
|  | 2.7.6 | Attend relevant site meetings and make other periodic visits to the Site as stated in the appointment agreement to monitor that the Works are being executed generally in accordance with the contract documents and with good engineering practice and advise the Client on the need for instructions to Contractors. | X
|  | 2.7.7 | Advise the Client on certificates for payment to Contractors in respect of the Works. |  | X
|  | 2.7.8 | Perform any services which the Consultant may be so required to do under any contract for the execution of the Works including, where appropriate, the witnessing of any specified tests, provided that the Consultant may decline to perform any services specified in a contract, the terms of which have not been approved by the Consultant. | X
Deliverables for Stage 5 (delete/add to as required)
Core Deliverables
|  | i. | Complete deliverables identified in Stage 4. | X
|  | ii. | Provide Site visit reports. | X
|  | iii. | Provide comments on technical submissions.Provide comments on technical submissions. | X
|  | iv. | Provide completion observation report. | X
Optional Deliverables

## Stage 6
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
6
|  | 2.8 | Handover and Close Out – Stage 6
The placing of a tick in a tickbox before a service or deliverable indicates that the relevant service or deliverable is to be carried out or provided (as applicable). Other bespoke deliverables may be agreed and added in the text boxes provided.
|  | 2.8.1 | Inspect the Works on completion and, in conjunction with any Site Staff, record and report any defects observed | X
|  | 2.8.2 | On completion of the Works deliver upon request to the Client one copy of each of the final drawings supplied by the Consultant to Contractors for the purpose of constructing the Works. | X
Deliverables for Stage 6
Core Deliverables
|  | i. | Provide completion defects list. | X
Optional Deliverables
|  | i. | Provide completion letter | X

## Stage 7
STAGE | DESCRIPTION | CLAUSE NUMBER | SERVICE | INCLUDE | EXCLUDE
7
|  | 2.9 | In Use – Stage 7
This box may be amended to record any agreed bespoke requirements.

## Part 3
3 | ADDITIONAL SERVICES THAT MAY BE PERFORMED BY THE CONSULTANT IF INSTRUCTED IN WRITING BY THE CLIENT.
Note: | These additional Services if instructed can be added to if appropriate and are subject to additional remuneration:
(Select or amend Services as required).
The placing of a tick in a tickbox before a service indicates that the relevant service is to be carried out.
Only ticked items will appear in the printable version of this Schedule.
3.1 | Prepare any report or documentation required for consideration of proposals for alternative Works.
3.2 | Work done in connection with any application by the Client for any order, sanction, licence, permit or other consent,
approval or authorisation necessary to enable the Works to proceed including planning consents or approvals
but other than applications for approvals under 2.5.3. (List here any relevant approvals which may be required).
3.3 | Prepare any information necessary for the Client’s negotiations with third parties including ground landlords, financing
bodies and adjoining site owners.
3.4 | Advise the Client on the need for arrangements to be made for contamination investigations on the Site.
Arrange as agent for the Client when authorised by the Client for such investigations to be undertaken,
certifying the amountof any payments to be made by the Client to the persons or firm carrying out such
investigations and advise the Client on the results of such investigations.
3.5 | Work in connection with providing a feasibility study.
3.6 | Assist the Client to understand any necessary remediation works required to the Site and/or any necessary
protection measures required in the building specification as a result of any investigations carried out by others under 4.2.
3.7 | Work in considering alternative designs for the Works submitted by Contractors.
3.8 | Prepare drawings for shop fabrication of structural steel or metal, timber or plastics frameworks or other specialist
supplied components.
3.9 | Prepare detailed drawings and bar bending schedules for reinforced concrete work.
3.1 | Check and/or advise upon any part of the Works not designed by the Consultant if competent to do so.
3.11 | Make visits to Site in addition to those allowed for in 2.7.6.
3.12 | Provide further information to enable bills of quantities to be prepared for the Works.
3.13 | Perform work or advise the Client in connection with any claim or matter where such claim or matter arises out of any contract for the execution of the Works provided that this service shall not extend to the detailed examination of any financial claim nor to advising the Client following the taking of any step in or towards any resolution of any dispute or difference or towards any adjudication, arbitration or litigation in connection with the Works.
3.14 | Provide “as built” drawings incorporating as built information provided by Contractors and/or sub-Contractors.
3.15 | Provide site based engineering inspection staff.
3.16 | Provide Principal Designer services in accordance with the Construction (Design and Management) Regulations 2015.
3.17 | Provide any service required in 2.1 Strategic Definition – Stage 0.
3.18 | Provide any service required in 2.9 In Use – Stage 7.

## Part 4
4 | SERVICES TO BE ARRANGED BY THE CONSULTANT AND TO BE PERFORMED BY OTHERS AND APPOINTED BY THE CLIENT
Note: | Unless included in the appointment agreement the arrangement of these Services if instructed by the Client is
subject to an additional fee: (select or amend Services as required).
The placing of a tick in a tickbox before a service indicates that the relevant service is to be carried out.
Only ticked items will appear in the printable version of this Schedule.
4.1 | Desk study of the Site.
4.2 | Specialist technical advice on any aspect of the Works which is not within the expertise of the Consultant.
4.3 | Contamination and geotechnical investigations on site.
4.4 | Design and remediation works and associated validation and approvals.
4.5 | Topographical, dimensional, condition or analytical survey of sites or existing works.
4.6 | Quantity surveying services including the preparation and pricing of bills of quantities for the Works.
4.7 | Investigation of the nature and strength of existing structures.
4.8 | Model tests or special investigations under 2.3.4.
4.9 | Independent checking of structural or other designs.
4.1 | Special inspections or tests advised by the Consultant under 2.7.4.
4.11 | Preparation, or assistance in the preparation, of an environmental impact assessment in respect of the Works.
4.12 | Special studies on durability and longevity issues and the minimisation of environmental impact.
4.13 | Investigation into public services to and in the Site.
4.14 | Advising upon road and public transport access to the site.