## Sheet1
Highways England Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties. Redacted under Section 40 and Section 43 of the FOI Act (2000)
Supplier: | Atkins
Project Title: | M20 J7 – Kent Medical Campus GHF Stage 3 Assessment
Contract Ref. | 2589 | CPA No.: | 4094486 |  | BPA No.: | 4098452
PIN Description: | M20 J7 Kent | Sub Pin: | 13 |  | PIN No.: | 569260
HE Reference: | SE 73 17/18ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5142263.441 | Consultant Contact: |  |  | Redacted
Start & End Date: | 11/01/2018 - 30/03/2018 | CTO Authorisation No. |  |  | 93257
Task Overview
The scheme is a fundamental component of the adopted Maidstone Integrated Transport Strategy (2016) and is required to support the delivery of the Maidstone Borough Local Plan (2011-2031). Delivery of the scheme will help to accelerate the development of the key strategic employment site at M20 J7, which forms part of the North Kent Enterprise Zone, and will support the delivery of the significant new housing developments committed in and around the Maidstone Urban Area in the Maidstone Borough Local Plan. The scheme is supported by the South East Local Enterprise Partnership’s (SELEP) Strategic Economic Plan, Kent County Council’s Local Transport Plan 4: Delivering Growth without Gridlock 2016-2031and Maidstone Borough Council’s adopted Economic Development Strategy. The scheme involves the signalisation and enlargement of the M20 J7, A249 Bearsted Road and A249 Bearsted Road/New Cut Road roundabouts, including the use of Smart technology to ease congestion, improve traffic flow and accommodate traffic associated with the Kent Medical Campus Enterprise Zone and growth in the town centre and south Maidstone. The scheme is a required condition of the full development of the Kent Medical Campus planning application, but this requirement would not be triggered until the development reaches 70% of the vehicle movements or 70% of floorspace, whichever is sooner. KCC has committed public funding of £2.5m from its £8.9m Local Growth Fund Round 2 award to deliver Maidstone Integrated Transport Package; and private funding from Kent Medical Campus Limited will amount to £1.5m cash and £420k in-kind land contribution. In total, public and private funding to match GHF contribution amounts to 50% of the scheme cost. Methodology - Completion of the method statement will be supplied to the HE GHF contact in draft form for comment and amended as required. - A kick-off meeting will be held in January 2018 with Highways England and key stakeholders to confirm the workplan. In particular, areas to cover will include specification of data inputs (and confirmation of their availability), confirmation of schedule and scope, and confirmation of the form of deliverables expected. - Assist Highways England by defining the scope of the viability and deliverability (V&D) and land value uplift (LVU) appraisals and coordinate the receipt of technical deliverables. - Complete the GHF Economic Impacts Assessment Toolkit and feed the results into the IDC Business Case report. - Liaise with Highways England and GHF applicant to gather information required to complete the GHF Full Assessment Form. - Carry out stakeholder management activities to ensure that the Highways England’s GHF, Local Regional and Transport Planning Group (TPG) teams are fully up-to-date with the scheme progress on transport modelling, appraisal and design matters. - Complete the GHF Full Assessment Form. - Organise and facilitate the Value Management Workshop and create record that will include the final Value for Money score; the rationale for this rating; and the recommendation for investment (approve / approve with conditions / defer / reject). - Complete the IDC Business Case report. A detailed methodology of each task is provided in the attached Method Statement.
Task Objectives and Milestones
Objectives • To collate and supply the necessary Economic Impact and Deliverability and Viability assessments (produced by GVA Billfinger) for Highways England to support their need to make an informed decision regarding the allocation of budget from the ring-fenced Growth and Housing Fund (GHF) in the M20 J7 scheme • To deliver the task, in accordance with task delivery processes • To identify and then control, manage and minimise risks • To deliver the project and associated output within time and budget constraints Milestones • Milestone 1a – Completion of CTO • Milestone 1b – Workplan meeting • Milestone 2 – Viability and Deliverability Appraisal (by third party GVA Bilfinger) • Milestone 3 – Economic Impact Assessment • Milestone 4 – Completion of GHF Full Assessment • Milestone 5 – VM Workshop • Milestone 6 – Completion of Business Case Template • Milestone 7 – Task Management Assumptions • Collation of information from and liaison with the GHF applicant and local authorities so that a timely submission should be made for an informed decision. • A monthly telephone client and stakeholder liaison meeting with Highways England, KCC, and MBC. • A fortnightly progress teleconference meeting the GHF applicant. • The SAR assessment is not required as a part of this assignment, as the WebTAG SAR is being completed by GHF applicant (MBC) that should include benefit-cost ratio and value for money rating. • The SAR and transport modelling work will be reviewed and signed off by HE Transport Planning Group (TPG). • The scheme design work will be reviewed and signed off by HE Local Regional team. • The scheme costs will be provided by the GHF applicant and will be reviewed by Highways England. • Highways England will procure GVA Billfinger and pay their fees and costs directly. Atkins will not be responsible to the technical work and recommendations made by GVA in their reports. Atkins will extract the V&D and LVU appraisal related information from the report and complete the GHF Full Assessment Form. • It is anticipated that detailed discussions will have been had between the land owner(s)/ developer(s) and the local authority in respect of the viable level of affordable housing/planning gain viability that can be supported by the M20 J7 scheme. • No site visits will be conducted. • No review of the environmental assessment work is needed. • One iteration of comments is allowed for HE teams to review the documents.
Task Outcomes
This task order brief requires the completion of the following: • GHF Full Economic Assessment including: o Review of Viability and Deliverability Assessment and Land Value Uplift Appraisal (completed by GVA Billfinger and procured directly by Highways England) o Complete Economic Impact Assessment Toolkit • Completion of the Scheme Full GHF form including: o Review and sign off of the methodologies of the SAR and associated transport modelling work by TPG. • VM Workshop – for presentation and discussion of GHF Assessment forms and Scheme Appraisal Report (SAR), including any modelling approaches and DfT WebTAG guidance applied. Assumed to be attended by Highways England, Kent County Council (KCC), and Maidstone Borough Council (MBC), and developer(s) and their consultants. • Completion of the IDC Business Case report.
Project Risk and Management
Risks • Information required from scheme stakeholders and promoters (Kent County Council, Maidstone Borough Council, South East Local Enterprise Partnership) is either absent, incomplete, not finalised or not provided in a timely manner. • Initial findings of the appraisal do not support the estimated GHF viability gap of £4.5 million. • Timescales for preparation of the SAR by Highways England may create uncertainty with regard to timescales for preparation of the GHF Full Assessment Form and supporting documents. • Whilst we will engage with GVA to scope and agree requirements for the Viability and Deliverability Appraisal and LVU Appraisal, delivery of this is outside of Atkins’ control as it is assumed it will be procured via AECOM on the Midlands Spatial Planning Contract. Whilst Atkins will endeavour to provide information in a timely manner, the accuracy and timely nature of GVA’s reporting remains outside of Atkins’ control. It is assumed that the information required to complete this task will be forthcoming from the client and/or the local authorities and development community. Scope and workplan will be subject to verification of this assumption during the initial kick off meeting in January 2018 (subject to securing approvals from Highways England). In the event that further meetings are required, including meetings for stakeholder engagement, or information is not available, and/or not available in the 3-month timeframe envisaged for this study, the task order will be amended to reflect the gaps identified and/or the timeline changes required. As standard, time has also been allocated to Redacted and Redacted for the over-arching coordination, contract management and task handling. Management • Contract - Redacted • Task Management - Redacted • Project Manager - Redacted • Technical Lead - Redactedr
Project Title: | M20 J7 – Kent Medical Campus GHF Stage 3 Assessment |  |  |  | HE Reference: | SE 73 17/18ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 73 17/18ATK | 32613.92 | 0 |  | 2018-01-10 | 32613.92 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 32613.92
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 32613.92
Total Project Fee Estimate |  |  |  |  | 32613.92
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Planner/ Engineer | Redacted | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2018-01-11 |  | Works Total |  | 32613.92
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 32613.92
|  |  | Expenses |  | 650
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 33263.92