## 2023-24 closures
Activities due 2023/24 - closures booked
Rebaselined SP New Planned Finish | (All)
Resource (formula) | (All)
Yearly Pass 1-6 | (Multiple Items)
Actual Start | Area 12 TM Reference | ScAR | Activity Name | TM Needed? | Qts Remaining
2023-12-08 | YNE17 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 49
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 2
| YNE20 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 85
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 4
| YNE41 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 11
| YNE41 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 22
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | (blank) | 5
2023-12-11 | YNE70 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 13981.75
| YNE71 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 14579.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 1515
| YNE72 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | No | 10264.5
| YNE89 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 7665
| YNE89 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 7665
2023-12-12 | YNE89 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 7665
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (blank) | 604
| WS Link Langham | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 17
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 1
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | (blank) | 1427
2023-12-13 | YNE15 Closure 2 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 14
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3326.9091
| YNE15 Closure 2 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 15
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3326.9091
| YNE89 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 7665
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (blank) | 469
2023-12-14 | YNE72 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 10264.5
| YNE74 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6773
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | Yes | 2240
| YNE88 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (blank) | 505
| YNE88 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 7659.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (blank) | 621
2023-12-15 | YNE6 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 23
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 9
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 15689.5
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (blank) | 6957
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | (blank) | 19249
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | Yes | 5296
|  |  | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | Yes | 2148
| YNE90 Closure 1 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 4097.5
| YNE90 Closure 1 WB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 4097.5
2023-12-18 | YNE69 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6994
| YNE69 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | No | 6994
| YNE91 Closure 1 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 8878.25
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | No | 8556
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | No | 6809
| YNE91 Closure 2 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 8878.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | No | 3619
2024-01-08 | YNE82 Closure 1 NB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 90
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 7
| YNE82 Closure 1 SB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 1
2024-01-09 | YNE3 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 63
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 5
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 2766.75
| YNE5 Closure 1 WB NS | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 8
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | (blank) | 12
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 15819
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | Yes | 1179
| YNE54 Closure 2 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 43
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 3
2024-01-10 | YNE9 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 35
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 4
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 10946.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | (blank) | 1068
2024-01-12 | YNE3 Closure 1 EB OS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 8300.25
| YNE3 Closure 1 WB OS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 2766.75
| YNE5 Closure 1 EB OS | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (blank) | 633
2024-01-15 | YNE54 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 58
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 3
| YNE6 Closure 1 EB OS | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (blank) | 6957
2024-01-17 | YNE78 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 11
| YNE78 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 161
2024-01-19 | YNE106 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6991
| YNE106 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6991
2024-01-22 | YNE106 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6991
| YNE106 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6991
2024-01-24 | YNE108 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 544
| YNE108 Closure 1 SB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 547
2024-01-25 | YNE109 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 375
| YNE109 Closure 1 SB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 343
2024-01-26 | YNE83 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 15548
| YNE83 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 15548
| YNE84 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6795.3636
| YNE84 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 6795.3636
2024-01-29 | YNE110 Closure 1 NB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 81
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 3
| YNE110 Closure 1 SB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 108
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (blank) | 4
| YNE84 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3397.6818
| YNE84 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3397.6818
2024-01-30 | YNE84 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3397.6818
| YNE84 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 3397.6818
2024-01-31 | YNE85 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 13092.6136
| YNE85 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 13092.6136
2024-02-01 | YNE86 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
| YNE86 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
2024-02-02 | YNE86 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
| YNE86 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
2024-02-05 | YNE86 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
| YNE86 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 5863.4167
2024-02-06 | YNE87 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 13731.5
| YNE87 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (blank) | 13731.5
Grand Total |  |  |  |  | 444752.5

## 2023-24 Due - no date
Actual Start | (Multiple Items) |  | Activities due 2023/24 - closures not yet booked
Resource (formula) | (All)
Asset Type | (All)
Rebaselined SP New Planned Finish | Area 12 Maintenance Segments | ScAR | Activity Name | Qts Remaining
2023-12-31 | YNE15: M62 J37-38 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 6796.9
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 63
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 15
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 45
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 4
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 61
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 7
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 34438
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6653.8182
| YNE16: A63 North Cave - South Cave | 4.3.1.1 | Gullies - Emptying / clear covers | 282
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 90
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 69
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 69
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 85845
| YNE17: A63 South Cave - Welton | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 0
| YNE18: A63 Welton - Melton | 4.2.1 | VRS - Check all Road Restraint System - ILM | 1990.63
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2331.8
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 147
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 1088.7
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 169.97
|  | 4.3.3.3 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 11
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 105
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 2
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 36
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 5
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 75
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 91
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 98
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 47164
| YNE19: A63 Melton - WesternInt | 4.2.1 | VRS - Check all Road Restraint System - ILM | 3277.43
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1616.99
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 110
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 48
|  | 4.5.1 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 16
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 16
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 54
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 57
| YNE20: A63 Western Int - Priory Way | 4.2.1 | VRS - Check all Road Restraint System - ILM | 1642.91
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 8
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 24
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 126
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 44
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
| YNE3: M62 J24-25 | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1993.63
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 90
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 72
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 9
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 72
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 5533.5
| YNE45: A64 Bilbrough - Askham | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE54: A64 Pickering Int - Brambling | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE56: A64 Rillington - Sherburn | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE57: A64 Sherburn - Staxton | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE67: M1 J35-35a | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 70
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 5128.5
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 22529
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2550
| YNE68: M1 J35a-36 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 14
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
| YNE69: M1 J36-37 | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
| YNE71: M1 J38-39 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 11
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 1359
|  |  | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 1359
| YNE88: M18 J5-6 | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.8.2 | Woodland - Thin / coppice | 33686
| YNE89: M18 J6-7 | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
|  | 4.8.2 | Woodland - Thin / coppice | 51269
| YNE90: M180 Ings - J1 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE91: M180 J1-2 | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
2024-01-30 | YNE92: M180 J2-3 | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
2024-01-31 | DBFO 27 - technology assets only | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 9
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 45
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 16
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 16
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 16
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 17
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 17
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 15
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 65
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 12
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 40
| YNE1: M62 J22-23 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 4
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 34
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.6 | Meteorological sites - Clean fog sensors | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE10: M62 J32-33 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 25
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 3
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 3
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 3
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 3
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 3
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 3
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 21
| YNE106: A1M J34-35 | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 300
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5934.17
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 17
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6991
| YNE107: A1M J35-36 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 15
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 4221
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6924.75
| YNE109: A1M J37-38 | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 11
| YNE11: M62 J33-34 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3760.54
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 11
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 24830
| YNE110: A1 Redhouse - Barnsdale | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 23
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 5
| YNE114: A58 Chainbar | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE12: M62 J34-35 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 7848.51
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 508
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 233.42
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 21377.62
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 53
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 2
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 93
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 8
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 16
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 13
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 54849
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 14604
| YNE13: M62 J35-36 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 8750.11
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 159
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 136
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 846
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1374.66
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 282
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2376.71
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 57
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 46
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 21
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 50276
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 50176.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2431
| YNE14: M62 J36-37 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9321.13
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 589
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 223
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 1477.85
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 74
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 9
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 45
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.6 | Meteorological sites - Clean fog sensors | 1
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 36251
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 36408
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2124
| YNE15: M62 J37-38 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4424
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 659
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6236.73
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 127
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 80
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 83
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 16
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 2
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 47652
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 13307.6364
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2394
| YNE17: A63 South Cave - Welton | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE19: A63 Melton - WesternInt | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.3 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE2: M62 J23-24 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 10
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 20
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 1
|  |  | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 23
| YNE20: A63 Western Int - Priory Way | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
| YNE25: A63 Garrison - Southcoates | 4.6.3 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
| YNE26: A1033 Southcoates - Northern Gate | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
| YNE27: A1033 Northern Gate - Marfleet | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
| YNE28: A1033 Marfleet - Somerden | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE29: A1033 Somerden - Salt End | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE3: M62 J24-25 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 19
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 20
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 23
| YNE30: M606 J1-2 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 9
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
| YNE31: M606 J2-3 | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
| YNE32: M621 Gildersome - J1 | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE4: M62 J25-26 | 4.6.11 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 17
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 4
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 13
| YNE5: M62 J26-27 | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 17
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 4
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 4
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 4
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 11
| YNE54: A64 Pickering Int - Brambling | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE6: M62 J27-28 | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 31
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 13
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 8
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 8
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 7
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE62: M1 J31-32 | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 5336
| YNE63: M1 J32-33 | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 13603
| YNE7: M62 J28-29 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9884.49
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 238.2
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 167
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 141
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 1565
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5855.11
|  | 4.3.3.1 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 66
|  | 4.3.3.3 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 18
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 106
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 17
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 35
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 81
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 40
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 14
|  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 1
|  | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 11
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 26
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 6
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 6
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 6
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 7
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 3
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 16
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 23998.5
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 6533
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 35283
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5916
| YNE8: M62 J29-31 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9089.6
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3540.59
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 441
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2310
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 203
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 77
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 104
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 3
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 83
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 25
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 6
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 6
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 6
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 15
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 1
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 20550.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2834
| YNE9: M62 J31-32 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4804.02
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2522.15
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 43
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 16
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 11
| YNE91: M180 J1-2 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 4
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 2
| YNE92: M180 J2-3 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 27
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 9924.1667
| YNE94: M180 J4-5 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 5
| YNE96: A180 Barnetby - Brocklesby | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 831.11
|  |  | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 831.11
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 19
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 17
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
| YNE97: A180 Brocklesby - Stallingborough | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1204.27
|  |  | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1204.27
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 6
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 1
| YNE98: A180 Stallingborough - Great Coates | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 217
| YNE99: A180 Great Coates - Pyewipe | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 23
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE11: M62 J33-34 (actually J32a-33) | 4.3.1.1 | Gullies - Emptying / clear covers | 72
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 52
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 11286.25
2024-02-29 | YNE43: A64 A162 - Tadcaster | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 1615.21
| YNE44: A64 Tadcaster - Bilbrough | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 635.53
| YNE48: A64 Fulford - Grimston | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5556.82
| YNE49: A64 Grimston - Hopgrove | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3267.48
| YNE61: M1 J30-31 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 10
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 8
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 8
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 8
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 8
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 8
| YNE62: M1 J31-32 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 24
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 9
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 9
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 9
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 8
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 8
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 8
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2660
| YNE63: M1 J32-33 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 53
|  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 3
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 3
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 3
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 6795
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 18677
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9261
| YNE64: M1 J33-34 South | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 4
|  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 2
|  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 1
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 14
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 11
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 12
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 12
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 12
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 12
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 12
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 12
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7532
| YNE65: M1 Tinsley | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 74
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2104
| YNE66: M1 J34 North - 35 | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 892.27
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 4
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 11
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 31
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 20
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 20
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 20
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 19
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 19
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 19
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 8
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8159
| YNE67: M1 J35-35a | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2546
| YNE68: M1 J35a-36 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 5
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N]
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1056
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 8315
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1944
| YNE69: M1 J36-37 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2
| YNE70: M1 J37-38 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5
| YNE71: M1 J38-39 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 1515
| YNE72: M1 J39-40 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 1
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N]
| YNE73: M1 J40-41 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 9
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N]
|  | 4.6.11 | Ramp Metering Traffic Light Signals - Check alignment and condition of site
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 23145
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 11771
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 22002
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7413
| YNE77: A628 Crowden - Flouch | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE85: M18 J2-3 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2495.94
| YNE86: M18 J3-4 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 11378.63
|  | 4.8.2 | Woodland - Thin / coppice | 161474
| YNE87: M18 J4-5 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 7422.6
|  | 4.8.2 | Woodland - Thin / coppice | 26629
| YNE88: M18 J5-6 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 4825.7
| YNE89: M18 J6-7 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 18866.84
2024-03-31 | YNE100: A160 Brocklesby - Habrough | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6113.31
| YNE101: A160 Habrough - Manby | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3137.75
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE106: A1M J34-35 | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE107: A1M J35-36 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2
| YNE108: A1M J36-37 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
| YNE109: A1M J37-38 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
| YNE113: A1 Darrington - A162 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2
| YNE12: M62 J34-35 | 4.3.1.1 | Gullies - Emptying / clear covers | 22
| YNE15: M62 J37-38 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 4219.54
| YNE16: A63 North Cave - South Cave | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 995.92
| YNE24: A63 Mytongate - Garrison | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 223
| YNE25: A63 Garrison - Southcoates | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4499.99
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 1
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 4120
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1816.02
|  | 4.3.3.1 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 24
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 57
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 90
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 105
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 781
| YNE26: A1033 Southcoates - Northern Gate | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1174.23
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 94
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 11
| YNE27: A1033 Northern Gate - Marfleet | 4.3.1.1 | Gullies - Emptying / clear covers | 3
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 636.41
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 60
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 3
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 17
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 2
| YNE28: A1033 Marfleet - Somerden | 4.3.1.1 | Gullies - Emptying / clear covers | 15
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 988.94
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 146
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
| YNE29: A1033 Somerden - Salt End | 4.3.1.1 | Gullies - Emptying / clear covers | 2
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 640.22
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3038.48
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 80
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1
| YNE84: M18 J1-2 | 4.8.2 | Woodland - Thin / coppice | 175011
| YNE85: M18 J2-3 | 4.8.2 | Woodland - Thin / coppice | 6873
| YNE87: M18 J4-5 | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE91: M180 J1-2 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 16569.86
| YNE92: M180 J2-3 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 9197.33
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE93: M180 J3-4 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 15252.95
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 15
| YNE94: M180 J4-5 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 7414.67
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
| YNE95: M181 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 41.66
| YNE96: A180 Barnetby - Brocklesby | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5055.49
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE97: A180 Brocklesby - Stallingborough | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2960.83
| YNE98: A180 Stallingborough - GreatCoates | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE83: M18 Link-J1 | 4.8.2 | Woodland - Thin / coppice | 133349
| YNE45: A64 Bilbrough-Askham | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 448.63
Grand Total |  |  |  | 1720243.7012