YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 190.41 |  | 190.41 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 658.69 |  | 658.69 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 310.77 |  | 310.77 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 523.06 |  | 523.06 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 65.47 |  | 65.47 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5111 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 598.22 |  | 598.22 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5111 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 264.11 |  | 264.11 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5111 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 403.88 |  | 403.88 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5111 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 529.57 |  | 529.57 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5112 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 278.88 |  | 278.88 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | 45925773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5112 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 770 |  | 770 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | 45925773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5112 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 708.8 |  | 708.8 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | 45925773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5113 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1270 |  | 1270 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 109/0 | 104/6 | 45925773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5113 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 36.16 |  | 36.16 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 109/0 | 104/6 | 45925773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5114 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 322.42 |  | 322.42 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5114 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 2107.36 |  | 2107.36 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5114 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 111.28 |  | 111.28 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5114 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 1103.48 |  | 1103.48 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 691.72 |  | 691.72 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1386.64 |  | 1386.64 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1593.12 |  | 1593.12 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1044.6 |  | 1044.6 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 2420.92 |  | 2420.92 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 5108.48 |  | 5108.48 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1081.42 |  | 1081.42 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5115 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 1192.4 |  | 1192.4 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | 45925841 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5116 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | EB | 200.29 |  | 200.29 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5116 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | EB | 497.81 |  | 497.81 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5117 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 186.89 |  | 186.89 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5117 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 200.75 |  | 200.75 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5117 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 276.25 |  | 276.25 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5118 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | EB | 50 |  | 50 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/6 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5119 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 59.98 |  | 59.98 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5119 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 143.55 |  | 143.55 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5119 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 40 |  | 40 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5119 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 36 |  | 36 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 113/3 | 108/5 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5120 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | EB | 160.15 |  | 160.15 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5120 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | EB | 315 |  | 315 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5121 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 1737.17 |  | 1737.17 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5121 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-10-02 | 2023-11-30 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 44dys | WB | 978.82 |  | 978.82 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5122 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | EB | 711.16 |  | 711.16 | 0 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 378.28 |  | 378.28 | 0 |  |  |  | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 1115.66 |  | 1115.66 | 0 |  |  |  | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 448.84 |  | 448.84 | 0 |  |  |  | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 830.08 |  | 830.08 | 0 |  |  |  | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 979.16 |  | 979.16 | 0 |  |  |  | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 908.16 |  | 908.16 | 0 |  |  |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5123 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 76.84 |  | 76.84 | 0 |  |  |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE7 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5124 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | EB | 120 |  | 120 | 0 |  |  |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5124 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | EB | 263 |  | 263 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5125 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | CW | 90.01 |  | 90.01 | 0 |  |  |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5126 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | EB | 178.42 |  | 178.42 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5126 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | EB | 1018.04 |  | 1018.04 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5125 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace - full closures | 44dys | WB | 125.82 |  | 125.82 | 0 |  |  |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5127 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 69.26 |  | 69.26 | 0 |  |  |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5127 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 64.92 |  | 64.92 | 0 |  |  |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5128 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 117.31 |  | 117.31 | 0 |  |  |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5129 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 184.13 |  | 184.13 | 0 |  |  |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5130 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 440 |  | 440 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 & 3 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5130 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 460 |  | 460 | 0 |  |  |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 & 3 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5131 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 1410 |  | 1410 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 & 3 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5132 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 44.54 |  | 44.54 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5132 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1020.92 |  | 1020.92 | 0 |  |  |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5132 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 165.28 |  | 165.28 | 0 |  |  |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5132 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1307.64 |  | 1307.64 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5132 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 531.48 |  | 531.48 | 0 |  |  |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5133 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 64.35 |  | 64.35 | 0 |  |  |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5133 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 47.72 |  | 47.72 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5134 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 518.58 |  | 518.58 | 0 |  |  |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032539
YNE9 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5134 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1058.78 |  | 1058.78 | 0 |  |  |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032539
YNE9 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5134 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 936.75 |  | 936.75 | 0 |  |  |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032539
YNE9 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5134 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 8.04 |  | 8.04 | 0 |  |  |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032539
YNE9 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5135 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1999.26 |  | 1999.26 | 0 |  |  |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893659
YNE9 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5135 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 4333.15 |  | 4333.15 | 0 |  |  |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893659
YNE9 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5135 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 529.88 |  | 529.88 | 0 |  |  |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893659
YNE9 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5136 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 105.88 |  | 105.88 | 0 |  |  |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893659
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 23.9229 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 139.45 | 139.45 | 0 | 1 |  |  |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 65.1418 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 379.72 | 379.72 | 0 | 1 |  |  |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 50.4346 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 293.99 | 293.99 | 0 | 1 |  |  |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 68.2657 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 397.93 | 397.93 | 0 | 1 |  |  |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 29.3268 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 170.95 | 170.95 | 0 | 1 |  |  |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5137 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 86.7179 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 505.49 | 505.49 | 0 | 1 |  |  |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5138 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 216.1557 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 175 | 175 | 0 | 1 |  |  |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032150
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 65.3394 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 726.92 | 726.92 | 0 | 1 |  |  |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 244.6265 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2721.54 | 2721.54 | 0 | 1 |  |  |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 185.4595 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2063.29 | 2063.29 | 0 | 1 |  |  |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5140 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 82.2649 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 915.22 | 915.22 | 0 | 1 |  |  |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 219.9818 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2447.36 | 2447.36 | 0 | 1 |  |  |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5140 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 76.0457 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 846.03 | 846.03 | 0 | 1 |  |  |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 110.6372 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1230.87 | 1230.87 | 0 | 1 |  |  |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5140 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 47.0145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 523.05 | 523.05 | 0 | 1 |  |  |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE10 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5139 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 19.9231 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 221.65 | 221.65 | 0 | 1 |  |  |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893664
YNE11 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5141 | VRS - Check all Road Restraint System - ILM | 1.0761 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 83.64 | 83.64 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 3.3938 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 263.77 | 263.77 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 5.3411 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 415.12 | 415.12 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 0.93629 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 72.77 | 72.77 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5143 | VRS - Check all Road Restraint System - ILM | 28.1303 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2186.34 | 2186.34 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52031722
YNE11 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5143 | VRS - Check all Road Restraint System - ILM | 0.46641 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 36.25 | 36.25 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52031722
YNE11 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5143 | VRS - Check all Road Restraint System - ILM | 0.88778 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 69 | 69 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52031722
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 10.2695 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 798.16 | 798.16 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 0.67497 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 52.46 | 52.46 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5142 | VRS - Check all Road Restraint System - ILM | 10.1439 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 788.4 | 788.4 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5141 | VRS - Check all Road Restraint System - ILM | 2.7758 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 215.74 | 215.74 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5141 | VRS - Check all Road Restraint System - ILM | 0.53035 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 41.22 | 41.22 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5141 | VRS - Check all Road Restraint System - ILM | 0.38599 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 30 | 30 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5144 | VRS - Check all Road Restraint System - ILM | 0.56484 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 43.9 | 43.9 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52031722
YNE11 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5144 | VRS - Check all Road Restraint System - ILM | 2.1281 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 165.4 | 165.4 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52031722
YNE11 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5141 | VRS - Check all Road Restraint System - ILM | 1.0068 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 78.25 | 78.25 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032161
YNE11 Closure 2 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5145 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 66.1699 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 857.14 | 857.14 | 0 | 1 | 15/9: job closed. Evidence on do forms |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52032177
YNE11 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5146 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 4.7145 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 61.07 | 61.07 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52032177
YNE11 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5147 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 43.0191 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 478.6 | 478.6 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832536
YNE11 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5147 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 35.253 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 392.2 | 392.2 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832536
YNE11 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5148 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 603.9234 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 6718.82 | 6718.82 | 0 | 1 | 15/9: Grass cut and litter picked. Grass jobs closed - no litter jobs |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45837588
YNE11 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5148 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 445.4403 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 4955.65 | 4955.65 | 0 | 1 | 15/9: Grass cut and litter picked. Grass jobs closed - no litter jobs |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45837588
YNE11 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5148 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 378.5791 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 4211.8 | 4211.8 | 0 | 1 | 15/9: Grass cut and litter picked. Grass jobs closed - no litter jobs |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45837588
YNE11 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5147 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 193.3649 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2151.24 | 2151.24 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832536
YNE11 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5147 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 212.6849 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2366.18 | 2366.18 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832536
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 669468.0109 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 119.61 |  | 119.61 | 435015.6843 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5150 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 506.59 |  | 506.59 | 0 |  | N | 2/10 cancelled rain | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 205.35 |  | 205.35 | 0 |  | N | 2/10 cancelled rain | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5150 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1382.48 |  | 1382.48 | 0 |  | N | 2/10 cancelled rain | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 115.09 |  | 115.09 | 0 |  | N | 2/10 cancelled rain | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5150 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 62.23 |  | 62.23 | 0 |  | N | 2/10 cancelled rain | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 112.51 |  | 112.51 | 0 |  | N | 2/10 cancelled rain | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5151 | VRS - Check all Road Restraint System - ILM | 26.8532 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2087.08 | 2087.08 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032225
YNE12 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5151 | VRS - Check all Road Restraint System - ILM | 10.2792 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 798.92 | 798.92 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032225
YNE12 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5152 | VRS - Check all Road Restraint System - ILM | 0.98788 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 76.78 | 76.78 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032225
YNE12 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5151 | VRS - Check all Road Restraint System - ILM | 15.4152 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1198.1 | 1198.1 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032225
YNE12 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5152 | VRS - Check all Road Restraint System - ILM | 7.3028 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 567.59 | 567.59 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032225
YNE12 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5153 | VRS - Check all Road Restraint System - ILM | 25.775 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2003.28 | 2003.28 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5154 | VRS - Check all Road Restraint System - ILM | 2.8991 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 225.32 | 225.32 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5153 | VRS - Check all Road Restraint System - ILM | 25.6924 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1996.86 | 1996.86 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5154 | VRS - Check all Road Restraint System - ILM | 3.0977 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 240.76 | 240.76 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5150 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1660.08 |  | 1660.08 | 0 |  | N | 2/10 cancelled rain | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 120.08 |  | 120.08 | 0 |  | N | 2/10 cancelled rain | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 1025.21 |  | 1025.21 | 0 |  | N | 2/10 cancelled rain | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5150 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1942.49 |  | 1942.49 | 0 |  | N | 2/10 cancelled rain | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226
YNE12 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5149 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 716.4 |  | 716.4 | 0 |  | N | 2/10 cancelled rain | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032226 |  |  |  |  | Langham ES Link
YNE12 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5155 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 2008.44 |  | 2008.44 | 0 |  | N | 2/10 cancelled rain | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5155 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 3438.98 |  | 3438.98 | 0 |  | N | 2/10 cancelled rain | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5156 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 3442.39 |  | 3442.39 | 0 |  | N | 2/10 cancelled rain | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5157 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 87.2274 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 970.43 | 970.43 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5157 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 161.1689 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1793.05 | 1793.05 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5158 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 183.7652 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 2044.44 | 2044.44 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5157 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 203.9022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2268.47 | 2268.47 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5158 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 78.1913 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 869.9 | 869.9 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5158 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 216.9419 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 2413.54 | 2413.54 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5159 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 223.2797 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2484.05 | 2484.05 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 3 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5160 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 107.2017 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1192.65 | 1192.65 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5159 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 286.8646 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3191.45 | 3191.45 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 3 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5160 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 114.9193 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1278.51 | 1278.51 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5155 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 236.3 |  | 236.3 | 0 |  | N | 2/10 cancelled rain | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5156 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 157.64 |  | 157.64 | 0 |  | N | 2/10 cancelled rain | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5156 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 436.67 |  | 436.67 | 0 |  | N | 2/10 cancelled rain | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE12 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5155 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 2200.4 |  | 2200.4 | 0 |  | N | 2/10 cancelled rain | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45896351
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 396.41 |  | 396.41 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5162 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 119.44 |  | 119.44 | 0 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5162 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 129.98 |  | 129.98 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 2036.05 |  | 2036.05 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 864.44 |  | 864.44 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5162 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 89.73 |  | 89.73 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 487.6 |  | 487.6 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5162 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 85.81 |  | 85.81 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5162 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 54.6 |  | 54.6 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 951.7 |  | 951.7 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 74 |  | 74 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 103.91 |  | 103.91 | 0 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5161 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 118.18 |  | 118.18 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5163 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1158.63 |  | 1158.63 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE13 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5164 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 130.56 |  | 130.56 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5164 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 4294.43 |  | 4294.43 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5164 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1303.36 |  | 1303.36 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5164 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 2089.86 |  | 2089.86 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 255.03 |  | 255.03 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 108.79 |  | 108.79 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 59.17 |  | 59.17 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 584.89 |  | 584.89 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 69.13 |  | 69.13 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 80.76 |  | 80.76 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 2045.66 |  | 2045.66 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 1070.72 |  | 1070.72 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 92.34 |  | 92.34 | 0 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5165 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | EB | 71.77 |  | 71.77 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 599.17 |  | 599.17 | 0 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5166 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2024-01-31 | Subject to roadspace approval | 44dys | WB | 95.1 |  | 95.1 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5167 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1596.38 |  | 1596.38 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5167 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1670.04 |  | 1670.04 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5167 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 240.88 |  | 240.88 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5167 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 838.65 |  | 838.65 | 0 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5168 | VRS - Check all Road Restraint System - ILM | 0.64409 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 50.06 | 50.06 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5169 | VRS - Check all Road Restraint System - ILM | 1.4618 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 113.61 | 113.61 | 0 | 1 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5168 | VRS - Check all Road Restraint System - ILM | 2.1598 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 167.86 | 167.86 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5169 | VRS - Check all Road Restraint System - ILM | 23.5688 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1831.81 | 1831.81 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5168 | VRS - Check all Road Restraint System - ILM | 0.92162 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 71.63 | 71.63 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5168 | VRS - Check all Road Restraint System - ILM | 1.5966 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 124.09 | 124.09 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5169 | VRS - Check all Road Restraint System - ILM | 6.0543 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 470.55 | 470.55 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5169 | VRS - Check all Road Restraint System - ILM | 19.2509 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1496.21 | 1496.21 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 3.9129 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 304.12 | 304.12 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 1.9179 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 149.06 | 149.06 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5171 | VRS - Check all Road Restraint System - ILM | 1.2138 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 94.34 | 94.34 | 0 | 1 | All Barrier checked inside the closure. 2.2k of barrier and 2.3k on concrete wall in this closure. 1 x men x1 van |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 2.9419 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 228.65 | 228.65 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 0.71499 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 55.57 | 55.57 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 11.714 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 910.43 | 910.43 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 2.8889 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 224.53 | 224.53 | 0 | 1 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 2.3679 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 184.04 | 184.04 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 5.2611 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 408.9 | 408.9 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 5.2611 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 408.9 | 408.9 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5169 | VRS - Check all Road Restraint System - ILM | 0.31175 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 24.23 | 24.23 | 0 | 1 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5168 | VRS - Check all Road Restraint System - ILM | 0.86642 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 67.34 | 67.34 | 0 | 1 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years |  |  | 52032272
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 4.6814 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 363.85 | 363.85 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5170 | VRS - Check all Road Restraint System - ILM | 3.9627 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 307.99 | 307.99 | 0 | 1 |  |  |  | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 7.787 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 605.22 | 605.22 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5172 | VRS - Check all Road Restraint System - ILM | 6.1297 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 476.41 | 476.41 | 0 | 1 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 2 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5173 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 3.0756 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 39.84 | 39.84 | 0 | 1 | No asset in centre |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52032296
YNE15 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5174 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 479.247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 5331.76 | 5331.76 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45778803
YNE15 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5175 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 29.8473 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 332.06 | 332.06 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45778803
YNE15 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5174 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 72.2247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 803.52 | 803.52 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45778803
YNE15 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5175 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 76.2138 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 847.9 | 847.9 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45778803
YNE15 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5175 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 292.6118 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3255.39 | 3255.39 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45778803
YNE15 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5176 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 423.7339 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 4714.16 | 4714.16 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5176 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 313.7412 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3490.46 | 3490.46 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5176 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 519.8222 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 5783.17 | 5783.17 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5177 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 18.9379 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 210.69 | 210.69 | 0 | 1 | 28/9: complete |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5178 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4.7594 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 52.95 | 52.95 | 0 | 1 | 28/9: complete |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5178 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 169.219 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1882.61 | 1882.61 | 0 | 1 | 28/9: complete |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5179 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 491.2845 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 5465.68 | 5465.68 | 0 | 1 | 28/9: complete |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5179 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 16.1578 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 179.76 | 179.76 | 0 | 1 | 28/9: complete |  |  | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5178 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 165.8897 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1845.57 | 1845.57 | 0 | 1 | 28/9: complete |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5177 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 211.6872 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2355.08 | 2355.08 | 0 | 1 | 28/9: complete |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE16 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5180 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 17.6715 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 196.6 | 196.6 | 0 | 1 | 28/9: complete |  |  | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893631
YNE17 Closure 2 WB OS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5181 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 59.5853 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1438.4 | 1438.4 | 0 | 1 |  |  |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | 3 time per year (Apr - Sep)
YNE17 Closure 1 WB OS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5182 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 32.4264 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 782.78 | 782.78 | 0 | 1 |  |  |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 time per year (Apr - Sep) |  |  | 45893759
YNE17 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5183 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 271.9031 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 3025 | 3025 | 0 | 1 | 28/9: complete |  |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5184 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 187.1449 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2082.04 | 2082.04 | 0 | 1 | 28/9: complete |  |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5185 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 165.0798 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1836.56 | 1836.56 | 0 | 1 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5186 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 105.9658 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1178.9 | 1178.9 | 0 | 1 |  |  |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5185 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 69.4355 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 772.49 | 772.49 | 0 | 1 |  |  |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5183 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 363.1062 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 4039.66 | 4039.66 | 0 | 1 | 28/9: complete |  |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5185 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 51.6535 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 574.66 | 574.66 | 0 | 1 | 28/9: complete |  |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5186 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 361.5296 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 4022.12 | 4022.12 | 0 | 1 |  |  |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5185 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 116.7736 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1299.14 | 1299.14 | 0 | 1 |  |  |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45830787
YNE17 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5183 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 46.2056 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 514.05 | 514.05 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832009
YNE18 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5187 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 574.8617 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 6395.5 | 6395.5 | 0 | 1 |  |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45832009
YNE18 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5188 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | EB | 1091.67 |  | 1091.67 | 0 |  | Y | Clash Alan Hosty Scheme | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45831106
YNE18 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5187 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 80.42 |  | 80.42 | 0 |  | Y | Clash Alan Hosty Scheme | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45831106
YNE18 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5188 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | EB | 474.93 |  | 474.93 | 0 |  | Y | Clash Alan Hosty Scheme | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45831106
YNE18 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5187 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 420.07 |  | 420.07 | 0 |  | Y | Clash Alan Hosty Scheme | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45831106
YNE25 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5189 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | EB | 453.61 |  | 453.61 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5190 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | WB | 817.02 |  | 817.02 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5191 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 1357 | 1357 | 0 | 1 |  | N |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916355
YNE26 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5191 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 3468 | 3468 | 0 | 1 |  | N |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916355
YNE26 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5191 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 2575 | 2575 | 0 | 1 |  | N |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916355
YNE26 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5192 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 462 | 462 | 0 | 1 |  | N |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 6 |  |  | 6 times per year (Mar - Oct) |  |  | 45916355
YNE27 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5193 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 329 | 329 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45916350
YNE27 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5193 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 1346 | 1346 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45916350
YNE27 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5194 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 199 | 199 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45916350
YNE28 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5195 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 7727 | 7727 | 0 | 1 |  | N |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45925805
YNE28 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5195 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 2585 | 2585 | 0 | 1 |  | N |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45925805
YNE28 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5196 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 8327 | 8327 | 0 | 1 |  | N |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | Days | No |  | 6 times per year (Mar - Oct) |  |  | 45925805
YNE29 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5197 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 438 | 438 | 0 | 1 |  | N |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE29 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5197 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 3851 | 3851 | 0 | 1 |  | N |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE29 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5197 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 5971 | 5971 | 0 | 1 |  | N |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE29 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5198 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 6695 | 6695 | 0 | 1 |  | N |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 6 |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE29 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5198 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 401 | 401 | 0 | 1 |  | N |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 6 |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE29 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5198 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 1105 | 1105 | 0 | 1 |  | N |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 6 |  |  | 6 times per year (Mar - Oct) |  |  | 45925819
YNE32 Closure 1 CW OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5199 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | CW | 228.08 |  | 228.08 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE32 Closure 2 ACW OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5200 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | ACW | 265.02 |  | 265.02 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5201 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | CW | 3642.45 |  | 3642.45 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5201 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | CW | 3243.09 |  | 3243.09 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5202 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | CW | 146.02 |  | 146.02 | 0 |  |  |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5202 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 917.19 |  | 917.19 | 0 |  |  |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5203 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 660.54 |  | 660.54 | 0 |  |  |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5202 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 276 |  | 276 | 0 |  |  |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5203 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 104.56 |  | 104.56 | 0 |  |  |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5202 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 144.39 |  | 144.39 | 0 |  |  |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5203 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 587.82 |  | 587.82 | 0 |  |  |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5203 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 536.72 |  | 536.72 | 0 |  |  |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5202 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 18 |  | 18 | 0 |  |  |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE41 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5204 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | CW | 527 |  | 527 | 0 |  |  |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45929920
YNE41 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5205 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 68.765 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-09 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 4980 | 4980 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 58/3 & 0/0 R,Bout | 3/0 0/7 | 12013837 | 20:00 | 6:00 | Night Shift | Approved | 0
Cannot locate on map CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5206 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 50.7403 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 9744 | 3674.64 | 6069.36 | 0.37712 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/119 | YNE41: A64 Bramham - Headley | Cannot locate on map | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013838
YNE41 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5207 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 33.3106 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 370.59 | 370.59 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5207 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 49.0019 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 545.16 | 545.16 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5208 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 66.4675 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 739.47 | 739.47 | 0 | 1 |  | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5207 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 18.4121 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 204.84 | 204.84 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE42 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5209 | VRS - Check all Road Restraint System - ILM | 21.0752 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1638 | 1638 | 0 | 1 |  |  |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE42 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5210 | VRS - Check all Road Restraint System - ILM | 1.5791 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 122.73 | 122.73 | 0 | 1 |  |  |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE42 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5209 | VRS - Check all Road Restraint System - ILM | 15.5555 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1209 | 1209 | 0 | 1 |  |  |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE42 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5210 | VRS - Check all Road Restraint System - ILM | 0.51466 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 40 | 40 | 0 | 1 |  |  |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031905
YNE42 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5209 | VRS - Check all Road Restraint System - ILM | 8.7106 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 677 | 677 | 0 | 1 |  |  |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031905
YNE42 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5210 | VRS - Check all Road Restraint System - ILM | 1.441 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 112 | 112 | 0 | 1 |  |  |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031905
YNE42 Closure 2 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5211 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 644 |  | 644 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 1/7 | 5/7 | 52038224 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5212 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 107 |  | 107 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5211 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 18987 |  | 18987 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5213 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 1902 |  | 1902 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 1 WB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013871 and 12013872
YNE42 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5214 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 186.6065 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 2076.05 | 2076.05 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886200
YNE42 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5214 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 246.0971 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 2737.9 | 2737.9 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886200
YNE42 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5214 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 99.2289 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 1103.95 | 1103.95 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886200
YNE43 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5215 | VRS - Check all Road Restraint System - ILM | 3.3507 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 260.42 | 260.42 | 0 | 1 |  |  |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032334
YNE43 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5215 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 342 |  | 342 | 0 |  |  |  | 2700A64/138 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 66 |  | 66 | 0 |  |  |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 1.2094 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 94 | 94 | 0 | 1 |  |  |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032334
YNE43 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5215 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 1166 |  | 1166 | 0 |  |  |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 45 |  | 45 | 0 |  |  |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE43 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5215 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 1372 |  | 1372 | 0 |  |  |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 0.56612 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 44 | 44 | 0 | 1 |  |  |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032334
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 0.9718 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 75.53 | 75.53 | 0 | 1 |  |  |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032334
YNE43 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5216 | VRS - Check all Road Restraint System - ILM | 0.93346 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 72.55 | 72.55 | 0 | 1 |  |  |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032334
YNE43 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5217 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 53.0236 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 1280 | 1280 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE43 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5218 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 75.252 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 837.2 | 837.2 | 0 | 1 |  |  |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5219 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 66.2482 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 737.03 | 737.03 | 0 | 1 |  |  |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886201
YNE43 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5220 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5.7814 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 64.32 | 64.32 | 0 | 1 |  |  |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5218 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 128.9252 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1434.33 | 1434.33 | 0 | 1 |  |  |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5220 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4.4206 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 49.18 | 49.18 | 0 | 1 |  |  |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5219 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 159.6723 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1776.4 | 1776.4 | 0 | 1 |  |  |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886201
YNE44 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5221 | VRS - Check all Road Restraint System - ILM | 17.4726 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1358 | 1358 | 0 | 1 |  |  |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5222 | VRS - Check all Road Restraint System - ILM | 3.1523 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 245 | 245 | 0 | 1 |  |  |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5221 | VRS - Check all Road Restraint System - ILM | 17.91 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1392 | 1392 | 0 | 1 |  |  |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5222 | VRS - Check all Road Restraint System - ILM | 8.9422 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 695 | 695 | 0 | 1 |  |  |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5221 | VRS - Check all Road Restraint System - ILM | 1.5032 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 116.83 | 116.83 | 0 | 1 |  |  |  | 2700A64/169 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5221 | VRS - Check all Road Restraint System - ILM | 6.9607 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 541 | 541 | 0 | 1 |  |  |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5222 | VRS - Check all Road Restraint System - ILM | 6.9691 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 541.65 | 541.65 | 0 | 1 |  |  |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5222 | VRS - Check all Road Restraint System - ILM | 4.1724 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 324.29 | 324.29 | 0 | 1 |  |  |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031930
YNE44 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5223 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 26.3461 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 636 | 636 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5223 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 112.0538 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 2705 | 2705 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE44 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5224 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 121.0917 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1347.18 | 1347.18 | 0 | 1 |  |  |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5225 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 185.5269 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2064.04 | 2064.04 | 0 | 1 |  |  |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5224 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 140.347 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1561.4 | 1561.4 | 0 | 1 |  |  |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5225 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 85.2778 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 948.74 | 948.74 | 0 | 1 |  |  |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5224 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 68.1277 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 757.94 | 757.94 | 0 | 1 |  |  |  | 2700A64/169 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5224 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 49.8828 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 554.96 | 554.96 | 0 | 1 |  |  |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE44 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5225 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 93.7145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1042.6 | 1042.6 | 0 | 1 |  |  |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886203
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 10.9622 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 852 | 852 | 0 | 1 |  |  |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0.55326 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 43 | 43 | 0 | 1 |  |  |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 3.7313 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 290 | 290 | 0 | 1 |  |  |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 16.9708 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1319 | 1319 | 0 | 1 |  |  |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 5.5454 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 431 | 431 | 0 | 1 |  |  |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 4.0787 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 317 | 317 | 0 | 1 |  |  |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 4.3874 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 341 | 341 | 0 | 1 |  |  |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 0.8331 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 64.75 | 64.75 | 0 | 1 |  |  |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 1.1823 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 91.89 | 91.89 | 0 | 1 |  |  |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0.63045 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 49 | 49 | 0 | 1 |  |  |  | 2700A64/193 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032352
YNE45 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5228 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 81.2338 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 5883 | 5883 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE45 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5229 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 41.1762 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 2982 | 2982 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 60.0092 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 667.62 | 667.62 | 0 | 1 |  |  |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5231 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 32.6248 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 362.96 | 362.96 | 0 | 1 |  |  |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 67.8365 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 754.7 | 754.7 | 0 | 1 |  |  |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 68.9789 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 767.41 | 767.41 | 0 | 1 |  |  |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5231 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 148.3836 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1650.81 | 1650.81 | 0 | 1 |  |  |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 32.5628 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 362.27 | 362.27 | 0 | 1 |  |  |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 88.6764 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 986.55 | 986.55 | 0 | 1 |  |  |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5231 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 9.1359 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 101.64 | 101.64 | 0 | 1 |  |  |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5230 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 8.2623 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 91.92 | 91.92 | 0 | 1 |  |  |  | 2700A64/193 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886204
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 57.64 |  | 57.64 | 0 |  |  |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 14.46 |  | 14.46 | 0 |  |  |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 413.63 |  | 413.63 | 0 |  |  |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 322 |  | 322 | 0 |  |  |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 305.1 |  | 305.1 | 0 |  |  |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 632.13 |  | 632.13 | 0 |  |  |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 613.42 |  | 613.42 | 0 |  |  |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5227 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 357.21 |  | 357.21 | 0 |  |  |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE45 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5228 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 72.8108 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 5273 | 5273 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013836
YNE46 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5232 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 5316 |  | 5316 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE46 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5233 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 0 |  | 0 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE45 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5229 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 212.5502 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-16 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 15393 | 15393 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013839
YNE46 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5232 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 1924 |  | 1924 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE46 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5234 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 124.4112 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1384.11 | 1384.11 | 0 | 1 |  |  |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5235 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 177.4795 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1974.51 | 1974.51 | 0 | 1 |  |  |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5234 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 272.7247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 3034.14 | 3034.14 | 0 | 1 |  |  |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 111.9 |  | 111.9 | 0 |  |  |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5237 | VRS - Check all Road Restraint System - ILM | 0.83632 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 65 | 65 | 0 | 1 |  |  |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 713.82 |  | 713.82 | 0 |  |  |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5237 | VRS - Check all Road Restraint System - ILM | 0.88675 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 68.92 | 68.92 | 0 | 1 |  |  |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 845.96 |  | 845.96 | 0 |  |  |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5237 | VRS - Check all Road Restraint System - ILM | 1.3835 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 107.53 | 107.53 | 0 | 1 |  |  |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 835.34 |  | 835.34 | 0 |  |  |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5237 | VRS - Check all Road Restraint System - ILM | 0.84918 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 66 | 66 | 0 | 1 |  |  |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 750.16 |  | 750.16 | 0 |  |  |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031956
YNE47 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5238 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 3602 |  | 3602 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE47 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5238 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 9590 |  | 9590 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE47 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5239 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 11923 |  | 11923 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE47 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5240 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6.5526 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 72.9 | 72.9 | 0 | 1 |  |  |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5241 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 11.4109 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 126.95 | 126.95 | 0 | 1 |  |  |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5241 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 45.9269 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 510.95 | 510.95 | 0 | 1 |  |  |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5240 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 66.3713 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 738.4 | 738.4 | 0 | 1 |  |  |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5241 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 61.8986 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 688.64 | 688.64 | 0 | 1 |  |  |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5241 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 7.7427 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 86.14 | 86.14 | 0 | 1 |  |  |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5240 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 10.859 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 120.81 | 120.81 | 0 | 1 |  |  |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE47 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5240 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 21.6965 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 241.38 | 241.38 | 0 | 1 |  |  |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892434
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 1.5873 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 123.37 | 123.37 | 0 | 1 |  |  |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 8.0248 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 623.7 | 623.7 | 0 | 1 |  |  |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 0.53434 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 41.53 | 41.53 | 0 | 1 |  |  |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 12.6886 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 986.18 | 986.18 | 0 | 1 |  |  |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 0.88508 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 68.79 | 68.79 | 0 | 1 |  |  |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1592.84 |  | 1592.84 | 0 |  |  |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 61.71 |  | 61.71 | 0 |  |  |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1190.8 |  | 1190.8 | 0 |  |  |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 58.23 |  | 58.23 | 0 |  |  |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 351.16 |  | 351.16 | 0 |  |  |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 12.98 |  | 12.98 | 0 |  |  |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 670.74 |  | 670.74 | 0 |  |  |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 2.4474 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 190.22 | 190.22 | 0 | 1 |  |  |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5243 | VRS - Check all Road Restraint System - ILM | 1.4489 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 112.61 | 112.61 | 0 | 1 |  |  |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5242 | VRS - Check all Road Restraint System - ILM | 6.3038 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 489.94 | 489.94 | 0 | 1 |  |  |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031969
YNE48 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5244 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 346.13 |  | 346.13 | 0 |  |  |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5245 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 188.2476 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 274.33 | 274.33 | 0 | 1 |  |  |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5244 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 486.86 |  | 486.86 | 0 |  |  |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5244 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 1034.29 |  | 1034.29 | 0 |  |  |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5244 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 1169.14 |  | 1169.14 | 0 |  |  |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5244 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 539.2 |  | 539.2 | 0 |  |  |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928008
YNE48 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5246 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 3594 |  | 3594 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE48 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5247 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 4239 |  | 4239 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE48 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5246 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 1392 |  | 1392 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE48 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5247 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 7426 |  | 7426 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 2 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5248 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 8003 |  | 8003 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 2 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5249 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 6785 |  | 6785 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5246 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 6519 |  | 6519 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5247 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 12289 |  | 12289 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5246 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | CW | 7425 |  | 7425 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE48 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5250 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 22.3279 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 539 | 539 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5251 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 20.1324 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 486 | 486 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE48 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5252 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 220.6146 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2454.4 | 2454.4 | 0 | 1 |  |  |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892440
YNE48 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5252 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 132.002 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1468.56 | 1468.56 | 0 | 1 |  |  |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892440
YNE48 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5253 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 282.2435 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3140.04 | 3140.04 | 0 | 1 |  |  |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5253 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 215.3005 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2395.28 | 2395.28 | 0 | 1 |  |  |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5253 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 63.8689 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 710.56 | 710.56 | 0 | 1 |  |  |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5254 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 30.5008 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 339.33 | 339.33 | 0 | 1 |  |  |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5253 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 92.8947 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1033.48 | 1033.48 | 0 | 1 |  |  |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0.28551 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 22.19 | 22.19 | 0 | 1 |  |  |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5256 | VRS - Check all Road Restraint System - ILM | 7.357 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 571.8 | 571.8 | 0 | 1 |  |  |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 113.42 |  | 113.42 | 0 |  |  |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 1.5779 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 122.64 | 122.64 | 0 | 1 |  |  |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0.24858 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 19.32 | 19.32 | 0 | 1 |  |  |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 22.9813 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1786.15 | 1786.15 | 0 | 1 |  |  |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 49.92 |  | 49.92 | 0 |  |  |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 10.7365 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 834.46 | 834.46 | 0 | 1 |  |  |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 6.6194 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 514.47 | 514.47 | 0 | 1 |  |  |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 30.83 |  | 30.83 | 0 |  |  |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 0.74844 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 58.17 | 58.17 | 0 | 1 |  |  |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5255 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 176.04 |  | 176.04 | 0 |  |  |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE49 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5257 | VRS - Check all Road Restraint System - ILM | 6.944 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 539.7 | 539.7 | 0 | 1 |  |  |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52031985
YNE49 Closure 2 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5258 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 289.9574 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 422.55 | 422.55 | 0 | 1 |  |  |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5259 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 246.4655 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 359.17 | 359.17 | 0 | 1 |  |  |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 2 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5258 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 233.7638 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 340.66 | 340.66 | 0 | 1 |  |  |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5259 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 339.3096 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 494.47 | 494.47 | 0 | 1 |  |  |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 2 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5258 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 384.5582 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 560.41 | 560.41 | 0 | 1 |  |  |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5259 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 195.4734 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 284.86 | 284.86 | 0 | 1 |  |  |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5259 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 53.6409 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 78.17 | 78.17 | 0 | 1 |  |  |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5259 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 157.3751 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 229.34 | 229.34 | 0 | 1 |  |  |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928103
YNE49 Closure 2 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5260 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 4454 |  | 4454 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE48 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5247 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 38.1522 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 2763 | 2763 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013802
YNE49 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5261 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 7876 |  | 7876 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE49 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5262 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 45.222 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 3275 | 3275 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE49 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5263 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 26.144 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 290.86 | 290.86 | 0 | 1 |  |  |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892442
YNE49 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5264 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 41.9045 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 466.2 | 466.2 | 0 | 1 |  |  |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5263 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 252.8537 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 2813.07 | 2813.07 | 0 | 1 |  |  |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892442
YNE49 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5265 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 98.7247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1098.34 | 1098.34 | 0 | 1 |  |  |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892442
YNE50 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5266 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 46.75 |  | 46.75 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE50 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5267 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 11.27 |  | 11.27 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45902935
YNE50 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5268 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 237.48 |  | 237.48 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928118
YNE50 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5269 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 42.916 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1036 | 1036 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep) |  |  | 12014061
YNE50 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5269 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 33.8854 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 818 | 818 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep) |  |  | 12014061
YNE51 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5270 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1033.48 |  | 1033.48 | 0 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE51 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5270 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 734.61 |  | 734.61 | 0 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE51 Closure 1 EB NS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5271 | VRS - Check all Road Restraint System - ILM | 3.6247 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-20 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | EB | 281.72 | 281.72 | 0 | 1 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5272 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 647.67 |  | 647.67 | 0 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE51 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5272 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1040.62 |  | 1040.62 | 0 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE51 Closure 2 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5273 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 87.4 |  | 87.4 | 0 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE51 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5272 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 746.58 |  | 746.58 | 0 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032423
YNE51 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5272 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 718.13 |  | 718.13 | 0 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032423
YNE51 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5274 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 13.6563 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 21dys | WB | 989 | 989 | 0 | 1 |  | N |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE51 Closure 2 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5275 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 27.2575 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 658 | 658 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5276 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 51.5738 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1245 | 1245 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE51 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5277 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 326.1813 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 3628.86 | 3628.86 | 0 | 1 | Sched D |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | N/A
YNE51 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5278 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 65.9039 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 733.2 | 733.2 | 0 | 1 | Sched D |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | N/A
YNE51 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5278 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 151.4622 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1685.06 | 1685.06 | 0 | 1 | Sched D |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | N/A
YNE51 Closure CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5279 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 57.7441 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 642.42 | 642.42 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5280 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 346.401 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3853.81 | 3853.81 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5280 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 382.676 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 4257.38 | 4257.38 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5280 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 97.7314 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1087.29 | 1087.29 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5281 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 145.9621 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1623.87 | 1623.87 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5282 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 194 |  | 194 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE52 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5282 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 106.69 |  | 106.69 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE52 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5283 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 94.8073 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 6866 | 6866 | 0 | 1 | Quants differ to actuals due to Tim Haskell cancelling some plots | N |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE52 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5283 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 280.2243 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 20294 | 20294 | 0 | 1 | Quants differ to actuals due to Tim Haskell cancelling some plots | N |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE52 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5283 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 112.7166 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 8163 | 8163 | 0 | 1 | Quants differ to actuals due to Tim Haskell cancelling some plots | N |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE52 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5283 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 113.0342 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 8186 | 8186 | 0 | 1 | Quants differ to actuals due to Tim Haskell cancelling some plots | N |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE52 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5284 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 16.5285 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 399 | 399 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5284 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 32.4355 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 783 | 783 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5284 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 9.8591 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 238 | 238 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5284 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5.8823 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 142 | 142 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5285 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6.0709 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 67.54 | 67.54 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5286 | VRS - Check all Road Restraint System - ILM | 1.1102 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 86.29 | 86.29 | 0 | 1 |  |  |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 14.5047 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1127.33 | 1127.33 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5286 | VRS - Check all Road Restraint System - ILM | 1.2367 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 96.12 | 96.12 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 16.9142 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1314.6 | 1314.6 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 616.46 |  | 616.46 | 0 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 11.6499 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 905.45 | 905.45 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 3.1533 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 245.08 | 245.08 | 0 | 1 |  |  |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 678.39 |  | 678.39 | 0 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5286 | VRS - Check all Road Restraint System - ILM | 1.1739 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 91.24 | 91.24 | 0 | 1 | works cancelled 19/09/2023 due to Adverse weather |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5287 | VRS - Check all Road Restraint System - ILM | 2.3588 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 183.33 | 183.33 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032433
YNE53 Closure 1 WB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5288 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | WB | 78.12 |  | 78.12 | 0 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE53 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5289 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 8836 |  | 8836 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) | 50/5 | 50/7 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5289 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 238.1783 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-23 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 17249 | 17249 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 50/5 | 50/7 | 12013863 | 20:00 | 6:00 | Night Shift | Approved | 0
Cannot locate on map CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5206 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 16734 |  | 16734 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/725 | YNE53: A64 Musley - Pickering Int | Cannot locate on map | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013866
YNE53 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5289 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 126.4972 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-23 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 9161 | 9161 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) | 50/5 | 50/7 | 12013864 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5290 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 108.1875 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-23 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 7835 | 7835 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  | Nights | Annually (Sept, Oct) |  |  | 12013867
YNE53 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5291 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 31.3999 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 758 | 758 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep) |  |  | 12014073
YNE53 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5291 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 61.9299 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 1495 | 1495 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep) |  |  | 12014073
YNE53 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5292 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 155.7785 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1733.08 | 1733.08 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE53 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5293 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 233.576 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 2598.6 | 2598.6 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE53 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5292 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 46.4348 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 516.6 | 516.6 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE53 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5292 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 131.3288 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1461.07 | 1461.07 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE53 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5292 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 186.4222 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2074 | 2074 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE53 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5293 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 102.7614 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1143.25 | 1143.25 | 0 | 1 | works cancelled 19/09/2023 due to Adverse weather |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893633
YNE53 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5293 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 56.9253 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 633.31 | 633.31 | 0 | 1 | works cancelled 19/09/2023 due to Adverse weather |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893633
YNE53 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5292 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 26.7337 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 297.42 | 297.42 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893633
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 6.7224 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 522.48 | 522.48 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 1.7258 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 134.13 | 134.13 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 231.9 |  | 231.9 | 0 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 4.6759 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 363.42 | 363.42 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 8.5101 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 661.42 | 661.42 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 5.6087 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 435.92 | 435.92 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 3.2252 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 250.67 | 250.67 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 75.61 |  | 75.61 | 0 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 42.02 |  | 42.02 | 0 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 5.6001 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 435.25 | 435.25 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 0.11631 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 9.04 | 9.04 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 2.8894 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 224.57 | 224.57 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 2 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5294 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 141.01 |  | 141.01 | 0 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE54 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5295 | VRS - Check all Road Restraint System - ILM | 0.90451 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 70.3 | 70.3 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 52032443
YNE54 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5296 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 49.407 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 40 | 40 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45893724
YNE54 Closure 2 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5297 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 204 |  | 204 | 0 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45893724
YNE54 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5296 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 108.6954 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 88 | 88 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45893724
YNE54 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5296 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 77.8161 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 63 | 63 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45893724
YNE54 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5298 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 666.48 |  | 666.48 | 0 | 23/11 Cancelled due to high winds | N |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 55/5 | 58/3 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5299 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 107.022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 1190.65 | 1190.65 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 28.3723 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 315.65 | 315.65 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5299 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 12.2693 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 136.5 | 136.5 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 18.2917 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 203.5 | 203.5 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 38.9653 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 433.5 | 433.5 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 70.8926 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 788.7 | 788.7 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 78.0636 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 868.48 | 868.48 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE54 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5300 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 21.0386 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 234.06 | 234.06 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE55 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5301 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 28.27 |  | 28.27 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE55 Closure 1 WB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5302 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | WB | 341.07 |  | 341.07 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | No jobs
YNE55 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5303 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | WB | 20 |  | 20 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45931284
YNE55 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5304 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 63.7526 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1539 | 1539 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep) |  |  | 12014073
YNE55 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5304 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 86.1634 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 2080 | 2080 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5305 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 108.52 |  | 108.52 | 0 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5306 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 151 |  | 151 | 0 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45931265
YNE56 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 5307 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 82 |  | 82 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931265
YNE56 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5308 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 12.68 |  | 12.68 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 778.4 |  | 778.4 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 2962.98 |  | 2962.98 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 1843.26 |  | 1843.26 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 538.1 |  | 538.1 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 2093.24 |  | 2093.24 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 253.02 |  | 253.02 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5309 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 5423.6 |  | 5423.6 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5310 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5310 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 118 |  | 118 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5310 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 68 |  | 68 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5310 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 24 |  | 24 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5310 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 126 |  | 126 | 0 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45201 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 5311 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE56 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5312 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 135.7073 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 9828 | 9828 | 0 | 1 |  | N |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE56 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5312 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 76.7324 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 5557 | 5557 | 0 | 1 |  | N |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE56 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5312 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 24.6891 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 1788 | 1788 | 0 | 1 |  | N |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 49.9582 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1206 | 1206 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 16.5699 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 400 | 400 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 41.3419 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 998 | 998 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 302.4832 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 7302 | 7302 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 55.6748 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1344 | 1344 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 15.5757 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 376 | 376 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 18.2269 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 440 | 440 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 346.9319 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 8375 | 8375 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 138.9385 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 3354 | 3354 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 57.4146 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1386 | 1386 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 31.9799 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 772 | 772 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5313 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 98.9636 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 2389 | 2389 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE58 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5314 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | CW | 66 |  | 66 | 0 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45931379
YNE58 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5315 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 2723.2 |  | 2723.2 | 0 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5315 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 863.36 |  | 863.36 | 0 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5315 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 91.57 |  | 91.57 | 0 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5316 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE58 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5317 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3.0792 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 223 | 223 | 0 | 1 |  | N |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) |  |  | 12013829
YNE57 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5318 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 91.8386 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 2217 | 2217 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 48.674 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | NB | 1175 | 1175 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 33.6783 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 813 | 813 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 110.4383 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 2666 | 2666 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 62.6342 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 1512 | 1512 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 15.2443 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 368 | 368 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 21.0438 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 508 | 508 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 30.1572 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | CW | 728 | 728 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE58 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5320 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 81.67 |  | 81.67 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5314 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 77 |  | 77 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45931379
YNE58 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5321 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 114.11 |  | 114.11 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE58 Closure 1 EB NS Amey 45201 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5321 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-10-02 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 106dys | EB | 714.75 |  | 714.75 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE58 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5322 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 8847 |  | 8847 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE58 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5317 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | SB | 315 |  | 315 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE58 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5322 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | EB | 5427 |  | 5427 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE58 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5317 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 2713 |  | 2713 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct) |  |  | No jobs
YNE58 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5322 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | CW | 895 |  | 895 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE58 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5323 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 125.7654 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 3036 | 3036 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE58 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5324 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 64.5071 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 717.66 | 717.66 | 0 | 1 |  |  |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5325 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 58.7149 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 653.22 | 653.22 | 0 | 1 |  |  |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5326 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 428.39 |  | 428.39 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE59 Closure 1 WB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5327 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-10-31 | N/A | Removed following GC-898 | 22dys | WB | 250 |  | 250 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE59 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5328 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3.0378 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 220 | 220 | 0 | 1 |  | N |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE59 Closure 1 EB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5328 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3.9768 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 288 | 288 | 0 | 1 |  | N |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE59 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5329 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 19.5939 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 473 | 473 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5329 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 27.5474 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 665 | 665 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5329 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 83.098 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | CW | 2006 | 2006 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5330 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 197.0646 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2192.4 | 2192.4 | 0 | 1 |  |  |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5331 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | EB | 268.42 |  | 268.42 | 0 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE60 Closure 1 EB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5331 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Single carriageway no offside assets | 44dys | CW | 137.15 |  | 137.15 | 0 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE60 Closure 1 WB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5332 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5.0538 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | WB | 122 | 122 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5333 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 202.6497 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | EB | 4892 | 4892 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5333 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 14.6643 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-10-02 | 2023-10-31 | 2023-11-30 |  | 22dys | CW | 354 | 354 | 0 | 1 |  | N | Works ongiong for completion this week - inability to plot amenity jobs onto a map delayed progress with the amenity cuts on the A64 as we were unable to locate the plots | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | 3 time per year (Apr - Sep)
YNE68 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5334 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 913.61 |  | 913.61 | 0 |  |  |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45834423
YNE68 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5334 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 294.3 |  | 294.3 | 0 |  |  |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45834423
YNE69 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5335 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 221.0622 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2459.38 | 2459.38 | 0 | 1 | Including Litter pick under schedule D |  |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45833242
YNE69 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5335 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 603.9243 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 6718.83 | 6718.83 | 0 | 1 | Including Litter pick under schedule D |  |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45833242
YNE69 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5335 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 517.6488 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 5758.99 | 5758.99 | 0 | 1 | Including Litter pick under schedule D |  |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45833242
YNE69 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5335 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 132.9278 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 1478.86 | 1478.86 | 0 | 1 | Including Litter pick under schedule D |  |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45833242
YNE69 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5336 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 3983.04 |  | 3983.04 | 0 |  |  |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45898620
YNE70 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5337 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 866.0245 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 9634.77 | 9634.77 | 0 | 1 |  |  |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901638
YNE70 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5337 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 203.9175 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2268.64 | 2268.64 | 0 | 1 |  |  |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901638
YNE70 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5337 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 261.8576 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2913.24 | 2913.24 | 0 | 1 |  |  |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901638
YNE70 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5337 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 172.7623 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 1922.03 | 1922.03 | 0 | 1 |  |  |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901638
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 164.5872 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 1831.08 | 1831.08 | 0 | 1 |  |  |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5339 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 86.1308 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | SB | 958.23 | 958.23 | 0 | 1 |  |  |  | 4700M1/185 | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 788.6225 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 8773.65 | 8773.65 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 349.4787 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 3888.05 | 3888.05 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5339 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 99.0851 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | SB | 1102.35 | 1102.35 | 0 | 1 |  |  |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 128.9351 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 1434.44 | 1434.44 | 0 | 1 |  |  |  | 4700M1/2 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 68.729 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 764.63 | 764.63 | 0 | 1 |  |  |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 41.7562 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 464.55 | 464.55 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5338 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 233.9311 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2602.55 | 2602.55 | 0 | 1 |  |  |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" | 45837489 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE78 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5340 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.8446 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 28.24 | 28.24 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5340 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.683 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 79.76 | 79.76 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5340 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.912 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 46.12 | 46.12 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5340 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 15.3007 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 89.19 | 89.19 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5340 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.2575 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 7.33 | 7.33 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5341 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | CW | 25 | 0 | 25 | 0 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5342 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 143.2804 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 116 | 116 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5343 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | WB | 292 |  | 292 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5344 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 281.62 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 228 | 228 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5343 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | WB | 304 |  | 304 | 0 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5344 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 1019.0198 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 825 | 825 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5343 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | WB | 146 |  | 146 | 0 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5344 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 95.1085 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 77 | 77 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5343 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | WB | 51 |  | 51 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5344 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 82.7568 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 67 | 67 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5341 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | CW | 180 |  | 180 | 0 |  |  | Cancelled due to storm Babet | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 5342 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 37.0553 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 30 | 30 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5345 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 43.0574 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 557.75 | 557.75 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 3 times per year (ILM Entire Route) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE79 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5346 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 126.578 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 737.84 | 737.84 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908238 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5347 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 48.6419 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 283.54 | 283.54 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5347 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 103.3447 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 602.41 | 602.41 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5347 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0.45461 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2.65 | 2.65 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE81 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5348 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.7587 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 21.91 | 21.91 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52031466
YNE82 Closure 1 NB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5349 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 89.07 |  | 89.07 | 0 | 23/10 - not complete no tensionned barrier |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45908155 |  |  | Day Shift
YNE82 Closure 1 NB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5349 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 111.13 |  | 111.13 | 0 | 23/10 - not complete no tensionned barrier |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45908155 |  |  | Day Shift
YNE82 Closure 1 SB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5350 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 130.56 |  | 130.56 | 0 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45908155 |  |  | Day Shift
YNE82 Closure 1 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5351 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 145.7507 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | CW | 118 | 118 | 0 | 1 | 0 on OS |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years | [5 empty] | Day Shift
YNE82 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5352 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 66.6976 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 742.03 | 742.03 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925840 |  |  | Day Shift
YNE83 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5353 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 240.9 |  | 240.9 | 0 |  |  |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5353 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 5023.71 |  | 5023.71 | 0 |  |  |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5353 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1755.25 |  | 1755.25 | 0 |  |  |  | 4400M18/204 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5353 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 4987.78 |  | 4987.78 | 0 |  |  |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5353 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1952.63 |  | 1952.63 | 0 |  |  |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5354 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 15.2181 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-04 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 197.13 | 197.13 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45927429
YNE84 Closure 2 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5354 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5.9443 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-04 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 77 | 77 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45927429
YNE84 Closure 2 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5354 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1.3533 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-04 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 17.53 | 17.53 | 0 | 1 |  | N |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45927429
YNE84 Closure 2 SB OS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5355 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 83.3855 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 6 | 6 | 0 | 1 | No assets in OS closure | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 45927465
YNE84 Closure 2 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5356 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6.8295 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-04 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 75.98 | 75.98 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE84 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5357 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2105.68 |  | 2105.68 | 0 |  |  |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5358 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A |  | 44dys | NB | 2038.92 |  | 2038.92 | 0 |  | N | 3/11 Scheme clash on site works cancelled - intervention missed | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE84 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5358 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A |  | 44dys | NB | 4288.24 |  | 4288.24 | 0 |  | N | 3/11 Scheme clash on site works cancelled - intervention missed | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE84 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5358 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A |  | 44dys | NB | 406.76 |  | 406.76 | 0 |  | N | 3/11 Scheme clash on site works cancelled - intervention missed | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE84 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5358 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A |  | 44dys | NB | 1461.85 |  | 1461.85 | 0 |  | N | 3/11 Scheme clash on site works cancelled - intervention missed | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE84 Closure 3 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5359 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1323.69 |  | 1323.69 | 0 |  |  |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5359 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 4206.78 |  | 4206.78 | 0 |  |  |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5359 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2209.29 |  | 2209.29 | 0 |  |  |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5360 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 215 |  | 215 | 0 |  |  |  | 4400M18/217 | YNE84: M18 J1-2 | YNE85 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5360 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1163.69 |  | 1163.69 | 0 |  |  |  | 4400M18/218 | YNE84: M18 J1-2 | YNE85 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5361 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 77.8346 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-09 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 1008.24 | 1008.24 | 0 | 1 |  | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929798
YNE86 Closure 1 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5361 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 80.6654 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-09 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 1044.91 | 1044.91 | 0 | 1 |  | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929798
YNE86 Closure 1 NB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5362 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 27.617 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-09 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 357.74 | 357.74 | 0 | 1 |  | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929798
YNE86 Closure 3 NB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5363 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 47.5095 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-09 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 615.42 | 615.42 | 0 | 1 |  | N |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929798
YNE86 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5364 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 177.08 | 0 | 177.08 | 0 | 30/8: not completed |  |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5365 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1102.4 | 0 | 1102.4 | 0 | 30/8: not completed |  |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 3 NB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5363 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 57.7715 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-11 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 748.35 | 748.35 | 0 | 1 |  | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929857
YNE86 Closure 3 NB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5363 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 92.0978 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | completed | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 1193 | 1193 | 0 | 1 |  | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 45929857
YNE87 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5366 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 265.6 |  | 265.6 | 0 |  |  |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5367 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 117.15 |  | 117.15 | 0 |  |  |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5367 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 820.29 |  | 820.29 | 0 |  |  |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5367 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 1266.63 |  | 1266.63 | 0 |  |  |  | 4400M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5367 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 982.13 |  | 982.13 | 0 |  |  |  | 4400M18/103 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5367 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 220.71 |  | 220.71 | 0 |  |  |  | 4400M18/180 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5366 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2510.13 |  | 2510.13 | 0 |  |  |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5366 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1208.76 |  | 1208.76 | 0 |  |  |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5366 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 78.03 |  | 78.03 | 0 |  |  |  | 4400M18/280 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 58.6106 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 652.06 | 652.06 | 0 | 1 |  |  |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5369 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 10.8321 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | SB | 120.51 | 120.51 | 0 | 1 |  |  |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 70.3488 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 782.65 | 782.65 | 0 | 1 |  |  |  | 2000M18/136 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 25.2749 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 281.19 | 281.19 | 0 | 1 |  |  |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 119.9942 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 1334.97 | 1334.97 | 0 | 1 |  |  |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 207.2342 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2305.54 | 2305.54 | 0 | 1 |  |  |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE88 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5368 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 182.727 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 2032.89 | 2032.89 | 0 | 1 |  |  |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52032963
YNE89 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5370 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 156.2 |  | 156.2 | 0 |  |  |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5371 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1759.93 |  | 1759.93 | 0 |  |  |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 2 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5371 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1308.87 |  | 1308.87 | 0 |  |  |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5372 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 31.3758 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 406.43 | 406.43 | 0 | 1 | No v-channel in this location and no jobs rasied | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE90 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5373 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 218.4663 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2430.5 | 2430.5 | 0 | 1 | No grass WB EB cut |  |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871679
YNE90 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5373 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 89.8925 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1000.08 | 1000.08 | 0 | 1 | No grass WB EB cut |  |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871679
YNE90 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5373 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 23.4457 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 260.84 | 260.84 | 0 | 1 | No grass WB EB cut |  |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871679
YNE91 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5374 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1430.29 |  | 1430.29 | 0 |  |  |  | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5375 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 1189.22 |  | 1189.22 | 0 |  |  |  | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5376 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1287.1 |  | 1287.1 | 0 |  |  |  | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5374 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1604.09 |  | 1604.09 | 0 |  |  |  | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5374 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 3210.94 |  | 3210.94 | 0 |  |  |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5375 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 85.01 |  | 85.01 | 0 |  |  |  | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5374 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 3016.11 |  | 3016.11 | 0 |  |  |  | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5374 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1354.48 |  | 1354.48 | 0 |  |  |  | 2000M180/130 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5377 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 2098.48 |  | 2098.48 | 0 |  |  |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5378 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 2170.41 |  | 2170.41 | 0 |  |  |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5377 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 2883.42 |  | 2883.42 | 0 |  |  |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5377 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 565.44 |  | 565.44 | 0 |  |  |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5377 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 2220.03 |  | 2220.03 | 0 |  |  |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5378 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 1235.04 |  | 1235.04 | 0 |  |  |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5378 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 45.38 |  | 45.38 | 0 |  |  |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5378 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | EB | 1094.21 |  | 1094.21 | 0 |  |  |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5377 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 23.94 |  | 23.94 | 0 |  |  |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5379 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 483.68 |  | 483.68 | 0 |  |  |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB OS | Lane 3 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5380 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 172.2302 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 1916.11 | 1916.11 | 0 | 1 | 24/10 COMPLETE |  |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45870999
YNE93 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5381 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 174.1322 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 1937.27 | 1937.27 | 0 | 1 |  |  |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45870999
YNE93 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5382 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1196.54 |  | 1196.54 | 0 |  |  |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45870999
YNE93 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5380 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 35.0337 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 389.76 | 389.76 | 0 | 1 | 24/10 COMPLETE |  |  | 2000M180/165 | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45870999
YNE93 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5383 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 93.3477 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 1038.52 | 1038.52 | 0 | 1 | 24/10 COMPLETE |  |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45870999
YNE94 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5384 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 10.9085 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 121.36 | 121.36 | 0 | 1 |  |  |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5385 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 182.2156 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 2027.2 | 2027.2 | 0 | 1 |  |  |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5385 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 178.39 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 1984.64 | 1984.64 | 0 | 1 |  |  |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5386 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 6855.12 |  | 6855.12 | 0 | 26/10 - works cancelled fog. Yellow warning issued |  |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5386 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 3774.85 |  | 3774.85 | 0 | 26/10 - works cancelled fog. Yellow warning issued |  |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5387 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 273.077 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 3038.06 | 3038.06 | 0 | 1 |  |  |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5387 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 168.4757 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 1874.34 | 1874.34 | 0 | 1 |  |  |  | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45871700
YNE94 Closure 4 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5388 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 2291.18 |  | 2291.18 | 0 |  |  |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5388 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 779.34 |  | 779.34 | 0 |  |  |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5388 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 44dys | WB | 1831.5 |  | 1831.5 | 0 |  |  |  | 2000M180/197 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 5.0921 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 395.77 | 395.77 | 0 | 1 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5390 | VRS - Check all Road Restraint System - ILM | 3.3269 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 258.57 | 258.57 | 0 | 1 |  | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 6.3395 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 492.72 | 492.72 | 0 | 1 |  | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 1.4095 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 109.55 | 109.55 | 0 | 1 |  | N |  | 2000M181/133 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 4.0353 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 313.63 | 313.63 | 0 | 1 |  | N |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 15.7772 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 1226.23 | 1226.23 | 0 | 1 |  | N |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5390 | VRS - Check all Road Restraint System - ILM | 1.8022 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 140.07 | 140.07 | 0 | 1 |  | N |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 1.2928 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 100.48 | 100.48 | 0 | 1 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5389 | VRS - Check all Road Restraint System - ILM | 17.6284 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 1370.11 | 1370.11 | 0 | 1 |  | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5390 | VRS - Check all Road Restraint System - ILM | 1.6447 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | SB | 127.83 | 127.83 | 0 | 1 |  | N |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5391 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 298.65 |  | 298.65 | 0 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE95 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5392 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 976.8 |  | 976.8 | 0 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE95 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5392 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 1447.33 |  | 1447.33 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE95 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5392 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 1040.92 |  | 1040.92 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE95 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5391 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2462.59 |  | 2462.59 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE95 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5392 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 799.32 |  | 799.32 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised
YNE96 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5393 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 14.0771 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 182.35 | 182.35 | 0 | 1 | 0 aset OS |  |  | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5394 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0.25797 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 2.87 | 2.87 | 0 | 1 |  |  |  | 2000A180/101 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 | 45925810 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5395 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 3.084 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 34.31 | 34.31 | 0 | 1 |  |  |  | 2000A180/102 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 | 45925810 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5394 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 164.403 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 1829.03 | 1829.03 | 0 | 1 |  |  |  | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 | 45925810 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5395 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 56.0597 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 623.68 | 623.68 | 0 | 1 |  |  |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 | 45925810 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5395 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 161.9069 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | WB | 1801.26 | 1801.26 | 0 | 1 |  |  |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 | 45925810 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5396 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 392.48 |  | 392.48 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925810
YNE96 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5397 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 942.24 |  | 942.24 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925810
YNE96 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5397 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 2762.8 |  | 2762.8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925810
YNE96 Closure CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5398 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 141.6934 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1576.38 | 1576.38 | 0 | 1 |  |  |  | 2000A180/151 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5399 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 84.6234 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 941.46 | 941.46 | 0 | 1 |  |  |  | 2000A180/147 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5400 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 540.34 |  | 540.34 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5401 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 3926.45 |  | 3926.45 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5400 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 1280.1 |  | 1280.1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5401 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 940.18 |  | 940.18 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5400 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 314.51 |  | 314.51 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/160 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5401 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 482.67 |  | 482.67 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5402 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 33.11 |  | 33.11 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/164 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5403 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 4013.74 |  | 4013.74 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/168 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5403 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 2652.18 |  | 2652.18 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5402 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 369.2 |  | 369.2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5403 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1705.98 |  | 1705.98 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5403 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1803.25 |  | 1803.25 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/187 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5404 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 375.3737 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-07 | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | WB | 4176.14 | 4176.14 | 0 | 1 |  | N |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45928973
YNE100 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5405 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 51 | 51 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916347
YNE100 Closure 1 CW OS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5406 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 1085 | 1085 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW OS | Lane 2 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916347
YNE100 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5405 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 654 | 654 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916347
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 6653.51 | 6653.51 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 351.65 | 351.65 | 0 | 1 |  | N |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 233.14 | 233.14 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 389.64 | 389.64 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | EB | 2302.85 | 2302.85 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure 1 CW NS CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5408 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | CW | 1819 | 1819 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 9183.24 | 9183.24 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 3359.14 | 3359.14 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 869.31 | 869.31 | 0 | 1 |  | N |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 119.67 | 119.67 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE101 Closure CGS 45201 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 5407 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 6 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | WB | 1790.7 | 1790.7 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | Days |  |  | 6 times per year (Mar - Oct) |  |  | 45916348
YNE102 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5409 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 259.67 |  | 259.67 | 0 |  | Y | Clash with contraflow scheme works | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5410 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 2382.68 |  | 2382.68 | 0 |  | Y | Clash with contraflow scheme works | 4700A162/103 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5409 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 780.88 |  | 780.88 | 0 |  | Y | Clash with contraflow scheme works | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5411 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 184.32 |  | 184.32 | 0 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5412 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 120.11 |  | 120.11 | 0 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5413 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 66 | 0 | 66 | 0 | 06/09/2023 -TM Cancelled due to closurs not including rbts and so activities not being able to be completed |  |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 52032157
YNE104 Closure 3 CW OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5414 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | CW | 174 |  | 174 | 0 |  |  |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE106 Closure 2 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 5415 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 228.5075 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | NB | 185 | 185 | 0 | 1 | 0 in this TM layout |  |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB OS | Lane 2 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52031354
YNE107 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5416 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 3067.82 |  | 3067.82 | 0 |  |  |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925822
YNE107 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5416 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 2228.03 |  | 2228.03 | 0 |  |  |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925822
YNE107 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5416 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 1312.04 |  | 1312.04 | 0 |  |  |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925822
YNE108 Closure 1 SB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5417 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5.5135 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-10-31 | Complete |  | 22dys | SB | 71.42 | 71.42 | 0 | 1 | 0 in OS | N |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031356
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 61.3189 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 682.19 | 682.19 | 0 | 1 |  |  |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4.3145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 48 | 48 | 0 | 1 |  |  |  | 4400A1M/14 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 253.2474 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 2817.45 | 2817.45 | 0 | 1 |  |  |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 99.3952 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 1105.8 | 1105.8 | 0 | 1 |  |  |  | 4400A1M/16 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 93.9266 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 1044.96 | 1044.96 | 0 | 1 |  |  |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 338.6412 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 3767.48 | 3767.48 | 0 | 1 |  |  |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5418 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 205.0464 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 2281.2 | 2281.2 | 0 | 1 |  |  |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5419 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 23.23 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 258.44 | 258.44 | 0 | 1 |  |  |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5419 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 31.7547 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 353.28 | 353.28 | 0 | 1 |  |  |  | 4400A1M/35 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5419 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 22.5432 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 250.8 | 250.8 | 0 | 1 |  |  |  | 4400A1M/36 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE108 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5419 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 9.4991 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-28 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 105.68 | 105.68 | 0 | 1 |  |  |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45925823
YNE109 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5420 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 118.5156 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 1318.52 | 1318.52 | 0 | 1 |  |  |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5420 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 349.1542 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 3884.44 | 3884.44 | 0 | 1 |  |  |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5420 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 475.5294 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | NB | 5290.4 | 5290.4 | 0 | 1 |  |  |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5421 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 57.8322 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 643.4 | 643.4 | 0 | 1 |  |  |  | 4400A1M/26 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5421 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 131.833 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 1466.68 | 1466.68 | 0 | 1 |  |  |  | 4400A1M/27 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5421 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 29.5327 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | SB | 328.56 | 328.56 | 0 | 1 |  |  |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 | 45925820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 208.96 |  | 208.96 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 304.26 |  | 304.26 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 79.39 |  | 79.39 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 324.9 |  | 324.9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 433.56 |  | 433.56 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 101.36 |  | 101.36 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 253.12 |  | 253.12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 348.42 |  | 348.42 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 310.94 |  | 310.94 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 299.41 |  | 299.41 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 75.42 |  | 75.42 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 846.23 |  | 846.23 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 156.92 |  | 156.92 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 114.38 |  | 114.38 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 602.66 |  | 602.66 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5422 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 153.97 |  | 153.97 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/383 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 231.4 |  | 231.4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 848.4 |  | 848.4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 79.05 |  | 79.05 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 105.31 |  | 105.31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 93.18 |  | 93.18 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 38.16 |  | 38.16 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/643 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 82.21 |  | 82.21 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/658 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 91.53 |  | 91.53 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 229.56 |  | 229.56 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 147.93 |  | 147.93 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 214.87 |  | 214.87 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 443.74 |  | 443.74 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 96.19 |  | 96.19 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 133.05 |  | 133.05 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5423 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 82.07 |  | 82.07 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/694 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5424 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 50 |  | 50 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902856
YNE110 Closure 1 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5424 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 216 |  | 216 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902856
YNE110 Closure 1 NB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5424 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 183 |  | 183 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902856
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 50 |  | 50 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 165 |  | 165 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 60 |  | 60 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 45 |  | 45 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/633 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 90 |  | 90 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 204 |  | 204 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 123 |  | 123 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5425 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 30 |  | 30 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902902
YNE110 Closure 1 SB NS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5426 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | SB | 73.72 |  | 73.72 | 0 |  |  |  | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 2 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45903149 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5426 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-10-02 | 2023-11-30 | 2024-01-31 |  | 44dys | SB | 69.72 |  | 69.72 | 0 |  |  |  | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 2 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45903149 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45201 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5427 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Unable to complete | Unable to complete |  | 2023-10-02 | 2023-11-30 | 2023-11-30 |  | 44dys | NB | 402 |  | 0 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane Closures | Days |  | Days | Annually (Sept, Oct) | 285/8 | 289/4 | 12013791 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 685.29 |  | 685.29 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1350.44 |  | 1350.44 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2028.12 |  | 2028.12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 638.57 |  | 638.57 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1700.01 |  | 1700.01 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1790.99 |  | 1790.99 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1734.21 |  | 1734.21 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1317.58 |  | 1317.58 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 101.32 |  | 101.32 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 4579.61 |  | 4579.61 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1331.7 |  | 1331.7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 1464.06 |  | 1464.06 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 3912.87 |  | 3912.87 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5428 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 276.67 |  | 276.67 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/383 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5429 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 897.62 |  | 897.62 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5429 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 239.33 |  | 239.33 | 0 |  |  |  | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5429 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | NB | 325.55 |  | 325.55 | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 SB OS Bettamix 45201 VRS - Check all Road Restraint System - ILM | 5430 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 44dys | SB | 809.33 |  | 809.33 | 0 |  |  |  | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5431 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 2299.3 |  | 2299.3 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5431 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | NB | 732.27 |  | 732.27 | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5432 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | SB | 3524.45 |  | 3524.45 | 0 |  |  |  | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 1006 |  | 1006 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5434 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | ACW | 507 |  | 507 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5434 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | ACW | 914 |  | 914 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 416 |  | 416 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5434 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 648 |  | 648 | 0 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5434 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 554 |  | 554 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5434 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1625 |  | 1625 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 1084 |  | 1084 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45231 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 5433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-11-01 | 2023-11-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 374 |  | 374 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 5 | No | Days | 6 times per year (ILM Certain Sections)
YNE1 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5435 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 61.9749 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 361.26 | 361.26 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 3 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5436 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 28.373 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 165.39 | 165.39 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 3 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5436 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.9541 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 17.22 | 17.22 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 3 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5437 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 21.396 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 124.72 | 124.72 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 3 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5437 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 116.1974 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 677.33 | 677.33 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 3 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5437 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 181.1162 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1055.75 | 1055.75 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5438 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 51.6526 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 301.09 | 301.09 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5438 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.0981 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12.23 | 12.23 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910237
YNE1 Closure 1 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5439 | VRS - Re-tension Wire Rope safety barriers | 7.9789 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 46.51 | 46.51 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5439 | VRS - Re-tension Wire Rope safety barriers | 75.3131 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 439.01 | 439.01 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5439 | VRS - Re-tension Wire Rope safety barriers | 229.4287 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1337.37 | 1337.37 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5439 | VRS - Re-tension Wire Rope safety barriers | 280.4054 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1634.52 | 1634.52 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5440 | VRS - Re-tension Wire Rope safety barriers | 72.2046 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 420.89 | 420.89 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5440 | VRS - Re-tension Wire Rope safety barriers | 7.5689 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 44.12 | 44.12 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 3 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5441 | VRS - Re-tension Wire Rope safety barriers | 16.5634 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 96.55 | 96.55 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 3 EB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5441 | VRS - Re-tension Wire Rope safety barriers | 3.6609 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 21.34 | 21.34 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 3 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5442 | VRS - Re-tension Wire Rope safety barriers | 185.0121 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1078.46 | 1078.46 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 3 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5442 | VRS - Re-tension Wire Rope safety barriers | 175.0312 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1020.28 | 1020.28 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5443 | VRS - Re-tension Wire Rope safety barriers | 231.9814 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1352.25 | 1352.25 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5443 | VRS - Re-tension Wire Rope safety barriers | 42.8812 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 249.96 | 249.96 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5443 | VRS - Re-tension Wire Rope safety barriers | 190.9787 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1113.24 | 1113.24 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5444 | VRS - Re-tension Wire Rope safety barriers | 310.4253 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1809.51 | 1809.51 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5444 | VRS - Re-tension Wire Rope safety barriers | 319.262 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1861.02 | 1861.02 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5444 | VRS - Re-tension Wire Rope safety barriers | 104.6159 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 609.82 | 609.82 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 1 WB NS Bettamix 45261 VRS - Re-tension Wire Rope safety barriers | 5444 | VRS - Re-tension Wire Rope safety barriers | 10.4698 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 61.03 | 61.03 | 0 | 1 | 9/11 None in the NS | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Can jobs by route be cancelled and re-raised using op barrier layer
YNE1 Closure 2 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5445 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 634.8802 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 514 | 514 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902934
YNE1 Closure 2 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5446 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 789.2771 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 639 | 639 | 0 | 1 | 17/11 extra 761m KDU found | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902934
YNE1 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5447 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1147.7497 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 929.22 | 929.22 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903151
YNE1 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5447 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1436.2003 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1162.75 | 1162.75 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903151
YNE1 Closure 2 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5448 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 532.9412 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 431.47 | 431.47 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903151
YNE1 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5449 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 71.9613 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 932.16 | 932.16 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034394
YNE1 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5449 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 15.8813 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 205.72 | 205.72 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034393
YNE1 Closure 3 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 76.621 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 992.52 | 992.52 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034396
YNE1 Closure 3 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1.378 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 17.85 | 17.85 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034397
YNE1 Closure 3 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1.9724 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 25.55 | 25.55 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034400
YNE1 Closure 3 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5451 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 37.4189 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 484.71 | 484.71 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034399
YNE1 Closure 2 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5452 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 24.4874 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 317.2 | 317.2 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034403
YNE1 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5453 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 57.0528 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 739.04 | 739.04 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034402
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5454 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5454 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5454 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5454 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5454 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5455 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5455 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5455 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 12.7837 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5457 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5457 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5457 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5457 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5460 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5461 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5462 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5462 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5463 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5464 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5465 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5466 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5467 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5467 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5467 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5468 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5468 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5468 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5468 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5468 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5469 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5469 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5469 | Marker Posts - Clean all marker post faces and reference numbers | 7.9898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5469 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5470 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5470 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5470 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5471 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5472 | Bollards - Clean all illuminated and non-illuminated bollards | 59.2352 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5472 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5472 | Bollards - Clean all illuminated and non-illuminated bollards | 16.4542 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5472 | Bollards - Clean all illuminated and non-illuminated bollards | 46.0718 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5472 | Bollards - Clean all illuminated and non-illuminated bollards | 42.7809 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 13 | 13 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 2 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5473 | Bollards - Clean all illuminated and non-illuminated bollards | 6.5817 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 3 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5474 | Bollards - Clean all illuminated and non-illuminated bollards | 39.4901 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 2 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5475 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5476 | Bollards - Clean all illuminated and non-illuminated bollards | 49.3626 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5476 | Bollards - Clean all illuminated and non-illuminated bollards | 115.1795 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 35 | 35 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5476 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5476 | Bollards - Clean all illuminated and non-illuminated bollards | 59.2352 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE1 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5477 | Electrical Testing - Network cabling and electrical components | 153.4043 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 8 | 8 | 0 | 1 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years
YNE2 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5478 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 34 |  | 34 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE2 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5479 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE2 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5480 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 8 |  | 8 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE2 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE1 Closure Vaisala 45261 Meteorological sites - Clean fog sensors | 5481 | Meteorological sites - Clean fog sensors | 0 | 4.6.6 | ART009 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE1 Closure Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5482 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE1 Closure Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5483 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE1 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5484 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE1 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5485 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE1 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5486 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE1 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5487 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE1 Closure 3 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5488 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 15146 |  | 15146 | 0 |  |  |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 3 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5488 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 16530 |  | 16530 | 0 |  |  |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 3 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5488 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 960 |  | 960 | 0 |  |  |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 3 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5489 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 9438 |  | 9438 | 0 |  |  |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 3 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5489 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 24789 |  | 24789 | 0 |  |  |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 2 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5490 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 12019 |  | 12019 | 0 |  |  |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 2 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5490 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 22196 |  | 22196 | 0 |  |  |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 3 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5491 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 4288 |  | 4288 | 0 |  |  |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE1 Closure 3 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5492 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 1780 |  | 1780 | 0 |  |  |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE1 Closure 3 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5493 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 156 |  | 156 | 0 |  |  |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE1 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5494 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 70 |  | 70 | 0 |  |  |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5494 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 2813 |  | 2813 | 0 |  |  |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5495 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 2202 |  | 2202 | 0 |  |  |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5495 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 105 |  | 105 | 0 |  |  |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5496 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 180 |  | 180 | 0 |  |  |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5497 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 518 |  | 518 | 0 |  |  |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5498 | Sweeping - Paved non-running areas - Full Sweep 02 | 54.058 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE1 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5499 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.9161 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 605 | 605 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038271
YNE1 Closure 3 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5500 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.9629 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 685 | 685 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038280
YNE1 Closure 3 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.6171 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 735 | 735 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038279
YNE1 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5502 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.2563 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 631 | 631 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038260
YNE2 Closure 2 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5503 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.1531 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 82.5 | 82.5 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910850
YNE2 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5504 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.2938 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 19.2 | 19.2 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910850
YNE2 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5505 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 227.09 |  | 227.09 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910850
YNE2 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5505 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 885.01 |  | 885.01 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910850
YNE2 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5506 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5507 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5507 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5507 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 18.3766 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 23 | 23 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5507 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5507 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5508 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 |  | 5 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5508 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5508 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 |  | 6 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5508 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5508 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 |  | 4 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5509 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5510 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5511 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5512 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5513 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5513 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5513 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5513 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5513 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5514 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5514 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5514 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 |  | 5 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5514 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5514 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 |  | 11 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE2 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 5515 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 44.9427 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE2 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5516 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 134.828 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years
YNE2 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5517 | Electrical Testing - Network cabling and electrical components | 172.5798 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 9 | 9 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years
YNE2 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5478 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 10 |  | 10 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5479 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 23 |  | 23 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 5518 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 & 2 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE2 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5480 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 20 |  | 20 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE2 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5519 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE2 Closure 1 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5520 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 2533 |  | 2533 | 0 |  |  |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE2 Closure 2 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5521 | Sweeping - Paved non-running areas - Full Sweep 02 | 92.6707 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12442 | 12442 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | 52038326
YNE2 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5522 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.5853 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 809 | 809 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45820241
YNE2 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5523 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 921 |  | 921 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45820241
YNE3 Closure Amey 45261 Electrical Testing - Network cabling and electrical components | 5524 | Electrical Testing - Network cabling and electrical components | 383.5108 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | 2023-07-14 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys |  | 20 | 20 | 0 | 1 |  | N |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | 52038321
YNE3 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5525 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1165.8 |  | 1165.8 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | 45910924 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5525 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 845.76 |  | 845.76 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | 45910924 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5525 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 233.38 |  | 233.38 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | 45910924 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5525 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 307.77 |  | 307.77 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | 45910924 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5526 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 193.4 |  | 193.4 | 0 |  |  |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5526 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 185.47 |  | 185.47 | 0 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5526 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 810.75 |  | 810.75 | 0 |  |  |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5526 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 804.01 |  | 804.01 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 6 |  | 6 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 8 |  | 8 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 9 |  | 9 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 17 |  | 17 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 16 |  | 16 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5527 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 12 |  | 12 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 25 |  | 25 | 0 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5528 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5529 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5529 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5529 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5530 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5530 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5530 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5530 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5530 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5531 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 9 |  | 9 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 14 |  | 14 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 19 |  | 19 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 25 |  | 25 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5532 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 95/3 | 100/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 22 |  | 22 | 0 |  |  |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 18 |  | 18 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 13 |  | 13 | 0 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5533 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years
YNE3 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5534 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually
YNE3 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5535 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 19 |  | 19 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5536 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 23 |  | 23 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5537 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 20 |  | 20 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE3 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5538 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE3 Closure Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 5539 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE3 Closure Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5540 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5541 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5542 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE3 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5543 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5544 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5545 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE3 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5546 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 2140 |  | 2140 | 0 |  |  |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5546 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 3105 |  | 3105 | 0 |  |  |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5547 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 3768 |  | 3768 | 0 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE3 Closure 2 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5548 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 5689 |  | 5689 | 0 |  |  |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE3 Closure 2 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5548 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 7757 |  | 7757 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE3 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5547 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 1393 |  | 1393 | 0 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE3 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5549 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 442 |  | 442 | 0 |  |  |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5550 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 433 |  | 433 | 0 |  |  |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE3 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5551 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year | 95/3 | 100/9 | 52038340 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5552 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 1.9888 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 152 | 152 | 0 | 1 | 22/11 - cancelled strong winds | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 | 45820242 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5552 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.1986 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1238 | 1238 | 0 | 1 | 22/11 - cancelled strong winds | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 | 45820242 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5552 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.6227 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 659 | 659 | 0 | 1 | 22/11 - cancelled strong winds | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/326 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 | 45820242 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5552 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.3067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 482 | 482 | 0 | 1 | 22/11 - cancelled strong winds | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 | 45820242 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5553 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.0394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 538 | 538 | 0 | 1 |  |  |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | Days |  | Days | 2 times per year (ILM Certain Sections) |  |  | 45820310
YNE3 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5553 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 30.1466 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2304 | 2304 | 0 | 1 |  |  |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | Days |  | Days | 2 times per year (ILM Certain Sections) |  |  | 45820297
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 263.01 |  | 263.01 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 79.9 |  | 79.9 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 568.83 |  | 568.83 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 187.11 |  | 187.11 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 42.39 |  | 42.39 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5554 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 65.81 |  | 65.81 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 52032300
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 88.5878 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 516.39 | 516.39 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 28.6509 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 167.01 | 167.01 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 78.9123 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 459.99 | 459.99 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 73.0538 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 425.84 | 425.84 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 52.7231 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 307.33 | 307.33 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5555 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 54.6668 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 318.66 | 318.66 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031883
YNE4 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5556 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 144 |  | 144 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 45904439
YNE4 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5556 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 101 |  | 101 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5557 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 131 |  | 131 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5557 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 22 |  | 22 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/927 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5557 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 94 |  | 94 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5557 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 78 |  | 78 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5557 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 102 |  | 102 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45904439
YNE4 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5558 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 85.18 |  | 85.18 | 0 | 30/11 - icy conditions prevented completion. 18/10 - cancelled storm Babet | N |  | 4700M62/929 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903160
YNE4 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5559 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 443.21 |  | 443.21 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877333
YNE4 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5560 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 15.3061 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 198.27 | 198.27 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877333
YNE4 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5560 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 10.1717 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 131.76 | 131.76 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877333
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 6 |  | 6 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 13 |  | 13 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5561 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 13 |  | 13 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897586
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 5 | 5 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 12 | 12 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 6 | 6 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 8 | 8 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 12 | 12 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 5 | 5 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5562 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.1806 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 19 | 19 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897580
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5563 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898067
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 | 1 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 | 1 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 | 1 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 | 1 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5564 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898065
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5565 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45897997
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 179.7707 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 134.828 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 179.7707 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5566 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 | 1 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897943
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 5 |  | 5 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 7 |  | 7 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 7 |  | 7 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 8 |  | 8 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 13 |  | 13 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5567 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45899503
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 5 | 5 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 9 | 9 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 6 | 6 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 6 | 6 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5568 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899472
YNE4 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 5569 | Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Annually |  |  | 45898628
YNE4 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 5569 | Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Annually |  |  | 45898628
YNE4 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 5570 | Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 45898625
YNE4 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 5570 | Bollards - Clean all illuminated and non-illuminated bollards 2nd cut | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 | 3 | 0 | 1 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 45898625
YNE4 Closure Amey 45261 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 5571 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 44.9427 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE4: M62 J25-26 | YNE4 Closure | Lane 1 Closure | 4 |  | Nights | Every 2 years
YNE3 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5572 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 6 |  | 6 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - booked for January |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required | Nights | Every 6 years | 95/3 | 100/9 | 52038315 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5573 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 11 |  | 11 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - booked for January |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Nights | Every 3 years | 95/3 | 100/9 | 52038304 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 5574 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE4: M62 J25-26 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years |  |  | 52038305
YNE3 Closure 1 WB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5575 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 32 |  | 32 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE4: M62 J25-26 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 6 years |  |  | 52038302
YNE3 Closure 1 EB NS Amey 45261 Ramp Metering Traffic Light Signals - Check alignment and condition of site | 5576 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 0 | 4.6.11 | ART024 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5577 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 12 |  | 12 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5578 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5579 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 5580 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5581 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 10 |  | 10 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5582 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5583 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5584 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5585 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5586 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 640.49 |  | 640.49 | 0 | 22/11 - cancelled strong winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/652 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 95/3 | 100/9 | 12013773 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5586 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 494.3 |  | 494.3 | 0 | 22/11 - cancelled strong winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/656 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 95/3 | 100/9 | 12013774 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5586 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 862.79 |  | 862.79 | 0 | 22/11 - cancelled strong winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/657 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 95/3 | 100/9 | 12013775 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5587 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1061.5 |  | 1061.5 | 0 | 18/10 - cancelled storm Babet | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/960 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  | Nights | Annually (Sept, Oct) |  |  | 12013781
YNE3 Closure 1 WB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5587 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3559.45 |  | 3559.45 | 0 | 18/10 - cancelled storm Babet | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/961 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 4 |  | Nights | Annually (Sept, Oct) |  |  | 12013785
YNE4 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5588 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 811 |  | 811 | 0 |  |  |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE4 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5588 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 604 |  | 604 | 0 |  |  |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE4 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5588 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 3482 |  | 3482 | 0 |  |  |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE4 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5588 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 4866 |  | 4866 | 0 |  |  |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE4 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5588 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 3443 |  | 3443 | 0 |  |  |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE4 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5589 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 330 |  | 330 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52038290
YNE4 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5589 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 3665.28 |  | 3665.28 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52038290
YNE4 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5590 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 13188.75 |  | 13188.75 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | 2 times per year |  |  | 52038292
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 308 |  | 308 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1235 |  | 1235 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 814 |  | 814 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/653 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 590 |  | 590 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 727 |  | 727 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2291 |  | 2291 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 533 |  | 533 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 59 |  | 59 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 455 |  | 455 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038287
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-06 | 2023-12 | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 556 |  | 556 | 0 | 18/10 - cancelled storm Babet | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-06 | 2023-12 | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 662 |  | 662 | 0 |  | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/957 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-06 | 2023-12 | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1094 |  | 1094 | 0 |  | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.8058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 673 | 673 | 0 | 1 |  | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.604 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 734 | 734 | 0 | 1 |  | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE4 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-06 | 2023-12 | 2023-12-08 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2308 |  | 2308 | 0 |  | N | Unable to complete due to severe weather. Catch-up planned w/c 4th December | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | Days | Days |  | 2 times per year (ILM Certain Sections) |  |  | 45820204
YNE5 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5593 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 73.2047 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 426.72 | 426.72 | 0 | 1 |  |  |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52032407
YNE5 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5593 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.9541 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 17.22 | 17.22 | 0 | 1 |  |  |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52032407
YNE5 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5593 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 39.2614 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 228.86 | 228.86 | 0 | 1 |  |  |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52032407
YNE5 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5593 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0.66048 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3.85 | 3.85 | 0 | 1 |  |  |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52032407
YNE5 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5593 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 17.9169 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 104.44 | 104.44 | 0 | 1 |  |  |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52032407
YNE5 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5594 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 25.4738 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 148.49 | 148.49 | 0 | 1 |  |  |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 52032407 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5594 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 41.8484 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 243.94 | 243.94 | 0 | 1 |  |  |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 52032407 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5594 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.5339 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 84.72 | 84.72 | 0 | 1 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 52032407 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5594 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 36.4411 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 212.42 | 212.42 | 0 | 1 |  |  |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 52032407 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5594 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 69.633 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 405.9 | 405.9 | 0 | 1 |  |  |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 52032407 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5595 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 130 |  | 130 | 0 | No resources assigned Enviro | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | No jobs rasied
YNE5 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5595 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 258 |  | 258 | 0 | No resources assigned Enviro | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | No jobs rasied
YNE5 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5596 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 480 |  | 480 | 0 | No resources assigned Enviro | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | No jobs rasied | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5596 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 245 |  | 245 | 0 | No resources assigned Enviro | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | No jobs rasied | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5597 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 277 |  | 277 | 0 | No resource assigned | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | Every 2 years |  |  | 45897899
YNE5 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5598 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 3.2887 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 42.6 | 42.6 | 0 | 1 | No v-channel on EB |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52032011
YNE5 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5598 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2.9752 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 38.54 | 38.54 | 0 | 1 | No v-channel on EB |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52032011
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 8 | 8 | 0 | 1 |  |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5599 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897602
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 14 | 14 | 0 | 1 |  |  |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5600 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45792420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5601 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898130
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5601 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898130
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5601 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898130
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5601 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 3 |  | 3 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898130
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5601 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898130
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5602 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 |  | 2 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - booked for January | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898537 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5602 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 |  | 2 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898537 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5602 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 |  | 1 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898537 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5602 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 |  | 3 | 0 | 3/10 requires hoist | Y | Unable to access due to schemes - booked for January | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898537 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5603 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898008
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5603 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898008
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5603 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898008
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5603 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898008
YNE5 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5603 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45898008
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5604 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5604 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5604 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5604 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5604 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Every 2 years | 109/0 | 104/9 | 45898253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 9 | 9 | 0 | 1 |  |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 6.7913 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 17 | 17 | 0 | 1 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5605 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 11 | 11 | 0 | 1 |  |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45899834
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 6.7913 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 17 | 17 | 0 | 1 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 12 | 12 | 0 | 1 |  |  |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5606 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 9 | 9 | 0 | 1 |  |  |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 109/0 | 104/9 | 45900028 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5607 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | 45898612
YNE5 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5607 | Bollards - Clean all illuminated and non-illuminated bollards | 36.1993 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 11 | 11 | 0 | 1 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | 45898612
YNE5 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5608 | Bollards - Clean all illuminated and non-illuminated bollards | 36.1993 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1, 2 & 3 Closure | 4 |  |  | Annually | 109/0 | 104/9 | 45898639 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5608 | Bollards - Clean all illuminated and non-illuminated bollards | 19.7451 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1, 2 & 3 Closure | 4 |  |  | Annually | 109/0 | 104/9 | 45898639 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB OS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5609 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 50 |  | 50 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB OS | Lane 1 Closure | 4 | Yes | Nights | Every 6 years |  |  | 52038342
YNE4 Closure 1 EB OS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 5610 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 6 |  | 6 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB OS | Lane 1 Closure | 4 | Yes | Nights | Every 2 years |  |  | 52038345
YNE4 Closure 1 EB OS Amey 45261 Electrical Testing - Network cabling and electrical components | 5611 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 48 |  | 48 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB OS | Lane 1 Closure | 4 | Yes | Nights | Every 6 years |  |  | 52038344
YNE4 Closure 1 EB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 5612 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 21dys |  | 19 |  | 19 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Annually |  |  | On ServiceNow
YNE3 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5577 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5578 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5579 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 5580 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 95/3 | 100/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5613 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 8 |  | 8 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5614 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE4 Closure 1 EB NS Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5615 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5616 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 392.9414 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 | 1 | 1 | 0.5 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5617 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5618 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5619 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5620 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 749 |  | 749 | 0 | 22/11 - cancelled strong winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/619 | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013777
YNE4 Closure 1 WB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5621 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 174 |  | 174 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/955 | YNE5: M62 J26-27 | YNE4 Closure 1 WB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013776
YNE5 Closure 1 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5622 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 312 |  | 312 | 0 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years |  |  | 52038320
YNE5 Closure 1 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5623 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 78 |  | 78 | 0 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 109/0 | 104/9 | 52038320 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5624 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1666 |  | 1666 | 0 |  |  |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) |  |  | 52038267
YNE5 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5624 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1753 |  | 1753 | 0 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) |  |  | 52038267
YNE5 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5624 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 895 |  | 895 | 0 |  |  |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) |  |  | 52038267
YNE5 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5624 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 746 |  | 746 | 0 |  |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) |  |  | 52038267
YNE5 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5625 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 609.75 |  | 609.75 | 0 |  |  |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52038263
YNE5 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5626 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 1118 |  | 1118 | 0 |  |  |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52038263 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5626 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 157 |  | 157 | 0 |  |  |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52038263 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5627 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 15819 |  | 15819 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  | Nights | 2 times per year |  |  | 52038261
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 451 |  | 451 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 558 |  | 558 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/662 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 554 |  | 554 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1442 |  | 1442 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 1638 |  | 1638 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 2047 |  | 2047 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5628 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 479 |  | 479 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) |  |  | 52038274
YNE5 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5629 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | WB | 1179 |  | 1179 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) | 109/0 | 104/9 | 52038274 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5630 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.4555 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 37.63 | 37.63 | 0 | 1 |  | N |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 52032481 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5630 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 34.681 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 202.16 | 202.16 | 0 | 1 |  | N |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 52032481 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5630 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 19.6204 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 114.37 | 114.37 | 0 | 1 |  | N |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 52032481 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5630 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.6841 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 56.45 | 56.45 | 0 | 1 |  | N |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 52032481 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5631 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 95.5 |  | 95.5 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45922648
YNE6 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5631 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 169.22 |  | 169.22 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45922648
YNE6 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5631 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 122.92 |  | 122.92 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45922648
YNE6 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5632 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 923.9112 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 748 | 748 | 0 | 1 | 750m Completed Amey Sweeper cleaned Affected area. 100% full so slow going |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 52032101 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5632 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 2.4704 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 157 | 2 | 155 | 0.012739 | 750m Completed Amey Sweeper cleaned Affected area. 100% full so slow going | Y | Unable to access due to schemes | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45927431 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5632 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 59 | 0 | 59 | 0 | 750m Completed Amey Sweeper cleaned Affected area. 100% full so slow going | Y | Unable to access due to schemes | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45927431 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5633 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 88 |  | 88 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45927431
YNE6 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5633 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 92 |  | 92 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45927431
YNE6 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5633 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 476 |  | 476 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45927431
YNE6 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5633 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 161 |  | 161 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45927431
YNE6 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5634 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 112.66 | 0 | 112.66 | 0 | Ran out of time | Y | Unable to access due to schemes | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897865 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 2 | 1 | 1 | 0.5 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 9 | 4 | 5 | 0.44444 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 11 | 6 | 5 | 0.54545 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 3 | 1 | 2 | 0.33333 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 1 | 0 | 1 | 0 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 7 | 4 | 3 | 0.57143 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5635 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 12 | 6 | 6 | 0.5 | 50% completed evidence on Do Forms | Y | Unable to access due to schemes | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45897620 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 16 |  | 16 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 |  | 4 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 10 |  | 10 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5636 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12 |  | 12 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45897623
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5637 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 2 | 0 | 2 | 0 | Requires Hoist to Complete All signs | Y | Unable to access due to schemes | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5637 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 2 | 0 | 2 | 0 | Requires Hoist to Complete All signs | Y | Unable to access due to schemes | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5637 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 5 | 0 | 5 | 0 | Requires Hoist to Complete All signs | Y | Unable to access due to schemes | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5638 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898130
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5638 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898130
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5638 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898130
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5638 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898130
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 314.5987 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7 | 7 | 0 | 1 |  |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 134.828 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5639 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 134.828 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45898044 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5640 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45898116
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 5.1934 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 13 | 13 | 0 | 1 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 6.7913 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 17 | 17 | 0 | 1 |  |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5641 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7 | 7 | 0 | 1 |  |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years | 108/1 | 112/5 | 45899851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 19 |  | 19 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 |  | 9 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 |  | 8 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5642 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 |  | 5 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | 45927606
YNE6 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5643 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | 45898635 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5643 | Bollards - Clean all illuminated and non-illuminated bollards | 19.7451 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | 45898635 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5644 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 |  | 6 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | 45898658
YNE6 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5644 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | 45898658
YNE6 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5644 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | 45898658
YNE6 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5645 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys |  | 8 |  | 8 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required |  | Every 6 years | 108/1 | 112/5 | 52038542 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 5646 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 | LBS123 required |  | Every 2 years | 108/1 | 112/5 | 52038541 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5647 | Electrical Testing - Network cabling and electrical components | 1035.4791 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys |  | 74 | 54 | 20 | 0.72973 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required |  | Every 6 years | 108/1 | 112/5 | 52038540 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 5648 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5649 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5650 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5651 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 5652 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5653 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5654 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE6 Closure 1 WB NS Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 5655 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE6 Closure 1 WB NS Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5656 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 | 1 | 0 | 1 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE6 Closure 1 WB NS Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5657 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 | 1 | 0 | 1 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5658 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 6 years | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5659 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5660 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5661 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE6 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5662 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 24.5234 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1776 | 1776 | 0 | 1 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Annually (Sept, Oct) | 108/1 | 112/5 | 52038555 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5663 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 31.5271 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8614 | 2283.21 | 6330.79 | 0.26506 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/952 | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  | Nights | Annually (Sept, Oct) | 109/0 | 104/9 | 12013784 | 20:00 | 6:00 | Night Shift | Approved | 0
Cannot locate on map CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5664 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 314 |  | 314 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/962 | YNE6: M62 J27-28 | Cannot locate on map | Lane 1 Closure | 4 |  | Nights | Annually (Sept, Oct) |  |  | 12013780
YNE6 Closure 1 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5665 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 25 | 0 | 25 | 0 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 108/1 | 112/5 | 52038551 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 5666 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 2867 |  | 2867 | 0 |  |  |  | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE6 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5667 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 2021 |  | 2021 | 0 |  |  |  | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE6 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5667 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 248 |  | 248 | 0 |  |  |  | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE6 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5667 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 1589 |  | 1589 | 0 |  |  |  | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE6 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5668 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 339 | 0 | 339 | 0 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 108/1 | 112/5 | 52038547 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5668 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1666 | 0 | 1666 | 0 |  |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 108/1 | 112/5 | 52038547 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5669 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 1297 |  | 1297 | 0 |  |  |  | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE6 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5669 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 306 |  | 306 | 0 |  |  |  | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE6 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5669 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 118 |  | 118 | 0 |  |  |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE6 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5670 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 297.78 |  | 297.78 | 0 |  |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5671 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 15689.5 |  | 15689.5 | 0 |  | Y | Unable to access due to schemes | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5672 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 1287 |  | 1287 | 0 |  | Y | Unable to access due to schemes | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5672 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 861 |  | 861 | 0 |  | Y | Unable to access due to schemes | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Days | 2 times per year (ILM Certain Sections) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5673 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2089 |  | 2089 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820332
YNE6 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5673 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 572 |  | 572 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820332
YNE6 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5673 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 189 |  | 189 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820332
YNE6 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5673 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1348 |  | 1348 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820332
YNE7 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5674 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | CW | 56.82 |  | 56.82 | 0 |  |  |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5675 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 16.74 |  | 16.74 | 0 |  |  |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5675 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 164.64 |  | 164.64 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5676 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 149 |  | 149 | 0 |  |  |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5676 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 143 |  | 143 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5676 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 202 |  | 202 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5676 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 141 |  | 141 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5677 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 142 |  | 142 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5677 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 297 |  | 297 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5677 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 108 |  | 108 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931413
YNE7 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5678 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 407.71 |  | 407.71 | 0 |  |  |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5678 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1146.05 |  | 1146.05 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5678 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 559.79 |  | 559.79 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5678 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 319.57 |  | 319.57 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5679 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1465.34 |  | 1465.34 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5679 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 544.36 |  | 544.36 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5680 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 16 |  | 16 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5680 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 18 |  | 18 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5681 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 16 |  | 16 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5681 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 16 |  | 16 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45261 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 5682 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 6 |  | 6 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Enviroflow 45261 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 5682 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 12 |  | 12 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 6 |  | 6 | 0 |  |  |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | CW | 15 |  | 15 | 0 |  |  |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5684 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 10 |  | 10 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 13 |  | 13 | 0 |  |  |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5683 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5685 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5686 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5686 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5686 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5686 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5686 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5685 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5685 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5685 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5685 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5688 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5688 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5688 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5688 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5688 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5687 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5690 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 9 |  | 9 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5689 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 11 |  | 11 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 6 |  | 6 | 0 |  |  |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | CW | 10 |  | 10 | 0 |  |  |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5692 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5692 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5691 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5693 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required |  | Every 6 years |  |  | 52038533
YNE7 Closure 1 EB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 5694 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required |  | Every 2 years |  |  | 52038534
YNE7 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5695 | Electrical Testing - Network cabling and electrical components | 575.2661 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys |  | 30 | 30 | 0 | 1 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | 52038539
YNE7 Closure 1 EB NS Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5696 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5697 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5698 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 13 |  | 13 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5699 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5700 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV Masts - Check mast breaking system | 5701 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5702 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5703 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 5704 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 10 |  | 10 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5705 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE7 Closure 1 EB NS Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 5706 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 47.9388 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 6 | 3 | 3 | 0.5 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5707 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5708 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5709 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5710 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7190 |  | 7190 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013782
YNE7 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5711 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 11507 |  | 11507 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE7 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5712 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-02-29 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | EB | 5286 |  | 5286 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5713 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | WB | 46 |  | 46 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5714 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 11999.25 |  | 11999.25 | 0 |  |  |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE7 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 148 |  | 148 | 0 |  |  |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 352 |  | 352 | 0 |  |  |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 161 |  | 161 | 0 |  |  |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 15 |  | 15 | 0 |  |  |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 252 |  | 252 | 0 |  |  |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 157 |  | 157 | 0 |  |  |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 99 |  | 99 | 0 |  |  |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 203 |  | 203 | 0 |  |  |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 785 |  | 785 | 0 |  |  |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | EB | 1782 |  | 1782 | 0 |  |  |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 1021 |  | 1021 | 0 |  |  |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys | WB | 941 |  | 941 | 0 |  |  |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5717 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 138.49 |  | 138.49 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5717 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 537.9 |  | 537.9 | 0 |  |  |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5717 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 153.13 |  | 153.13 | 0 |  |  |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5717 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 789.27 |  | 789.27 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5717 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 285.42 |  | 285.42 | 0 |  |  |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5718 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 71.57 |  | 71.57 | 0 |  |  |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5718 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 620.02 |  | 620.02 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5718 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 643.35 |  | 643.35 | 0 |  |  |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 11 |  | 11 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 11 |  | 11 | 0 |  |  |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5719 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5720 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5720 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5720 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 12 |  | 12 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5720 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 11 |  | 11 | 0 |  |  |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5720 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5721 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5721 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5721 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5722 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5723 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 13 |  | 13 | 0 |  |  |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 16 |  | 16 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5724 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 17 |  | 17 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 17 |  | 17 | 0 |  |  |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 |  | 6 | 0 |  |  |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5725 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE8 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5726 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5727 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys |  | 38 |  | 38 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 6 years |  |  | 52038486
YNE8 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5728 | Electrical Testing - Network cabling and electrical components | 3068.0861 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys |  | 160 | 160 | 0 | 1 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | 52038489
YNE8 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5729 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 25 |  | 25 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5730 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5731 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV Masts - Check mast breaking system | 5732 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5733 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 15 |  | 15 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5734 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5735 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5736 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5737 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 EB NS CGS 45261 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 5710 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3347 |  | 3347 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/267 | YNE8: M62 J29-31 | YNE7 Closure 1 EB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013783
YNE8 Closure 1 EB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 5738 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Annually
YNE8 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5739 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | WB | 311 |  | 311 | 0 |  |  |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5740 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 85 |  | 85 | 0 |  |  |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5741 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 10275.25 |  | 10275.25 | 0 |  |  |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE8 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5742 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 976 |  | 976 | 0 |  |  |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5742 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 538 |  | 538 | 0 |  |  |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5743 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 626 |  | 626 | 0 |  |  |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5743 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 694 |  | 694 | 0 |  |  |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE9 Closure Amey 45261 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 5744 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | No assets | 41dys |  |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 223.97 |  | 223.97 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 501.79 |  | 501.79 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 792.72 |  | 792.72 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 805.26 |  | 805.26 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 473.78 |  | 473.78 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5745 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 180.36 |  | 180.36 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | 45910116 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5746 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 38.3676 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 223.65 | 223.65 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910116
YNE9 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5746 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 52.9461 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 308.63 | 308.63 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910116
YNE9 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5746 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 64.8347 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 377.93 | 377.93 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910116
YNE9 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5746 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 77.4095 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 451.23 | 451.23 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910116
YNE9 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5746 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 20.1162 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 117.26 | 117.26 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45910116
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 |  | 1 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 |  | 11 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 |  | 9 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 |  | 8 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5747 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 |  | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 13 | 13 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5748 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5749 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5749 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5750 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 59.9236 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5750 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5750 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5751 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 |  | 5 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 19 |  | 19 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 14 |  | 14 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 |  | 4 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5752 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 |  | 2 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 129/5 | 124/5 | No jobs raised | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5753 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE9 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5754 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 16 |  | 16 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE9 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5755 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 11 |  | 11 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE9 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5756 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 8 |  | 8 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE9 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5757 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE9 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5758 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE9 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5759 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE9 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5760 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 4275 |  | 4275 | 0 |  |  |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE9 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5761 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 502 |  | 502 | 0 |  |  |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5762 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | WB | 15 |  | 15 | 0 |  |  |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5763 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 710 |  | 710 | 0 |  |  |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5764 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 10946.25 |  | 10946.25 | 0 | 22/11 - cancelled strong winds | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year | 129/5 | 124/5 | 52038517 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5765 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 595 |  | 595 | 0 | 22/11 - cancelled strong winds | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) | 129/5 | 124/5 | 45820207 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5765 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 473 |  | 473 | 0 | 22/11 - cancelled strong winds | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) | 129/5 | 124/5 | 45820207 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5766 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.8114 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 597 | 597 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45820207
YNE9 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5766 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 558 | 558 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45820207
YNE10 Closure 1 WB NS Amey 45261 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5767 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years
YNE10 Closure 1 EB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 5768 | BC - Lamps (LED) for Illuminated Signs and Bollards | 119.8471 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 8 | 8 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE10 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 5769 | Electrical Testing - Network cabling and electrical components | 153.4043 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 8 | 8 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 21.9089 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 127.71 | 127.71 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 24.3261 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 141.8 | 141.8 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 65.7251 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 383.12 | 383.12 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 24.4187 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 142.34 | 142.34 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 46.8749 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 273.24 | 273.24 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 183.1353 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1067.52 | 1067.52 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 191.7919 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1117.98 | 1117.98 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0.80286 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4.68 | 4.68 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 88.7199 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 517.16 | 517.16 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 122.6907 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 715.18 | 715.18 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 116.0585 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 676.52 | 676.52 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 150.3363 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 876.33 | 876.33 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.7653 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 80.24 | 80.24 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 62.8773 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 366.52 | 366.52 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 41.2206 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 240.28 | 240.28 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 WB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 46.1441 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 268.98 | 268.98 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45909824
YNE10 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5772 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 86.4623 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 70 | 70 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902908
YNE10 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5773 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 203.804 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 165 | 165 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902908
YNE10 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5774 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2.7876 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 36.11 | 36.11 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52029175
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 75.9032 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 95 | 95 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5775 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5776 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5777 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5778 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5777 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 1 | 1 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5778 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5777 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5778 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5777 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5779 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5779 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 179.7707 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5779 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5779 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5780 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5779 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 2 | 2 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5782 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5781 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE10 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5783 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 25 |  | 25 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5784 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5785 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV Masts - Check mast breaking system | 5786 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5787 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 21 |  | 21 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5788 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 19 |  | 19 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5789 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5790 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5791 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE10 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5792 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 925 |  | 925 | 0 |  |  |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE10 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5792 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | CW | 3412 |  | 3412 | 0 |  |  |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE10 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5793 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1481 |  | 1481 | 0 |  |  |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE10 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5794 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 297 |  | 297 | 0 |  |  |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE10 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 5795 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 121 |  | 121 | 0 |  |  |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE10 Closure 1 WB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 5796 | Wildlife structures and tunnels - Remove all material that could impair operation | 13.8082 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 | No assets | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 52038497
YNE10 Closure 1 WB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 5796 | Wildlife structures and tunnels - Remove all material that could impair operation | 13.8082 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 | No assets | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 52038497
YNE10 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5797 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 119 |  | 119 | 0 |  |  |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5797 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 68 |  | 68 | 0 |  |  |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5797 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 271 |  | 271 | 0 |  |  |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5797 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 327 |  | 327 | 0 |  |  |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 5798 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 17.8995 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-22 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1368 | 1368 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 | No |  | 3 times per year (ILM Certain Sections) |  |  | 52038506
YNE10 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 5799 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 13.1891 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1008 | 1008 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 4 | No |  | 3 times per year (ILM Certain Sections) |  |  | 52038505
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 1.6345 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 127.04 | 127.04 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5801 | VRS - Check all Road Restraint System - ILM | 31.9074 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1953.82 | 2479.9 | -526.08 | 1.2693 |  | N |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5801 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 0 |  | 0 | 0 |  | N |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5802 | VRS - Check all Road Restraint System - ILM | 30.2668 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2352.39 | 2352.39 | 0 | 1 |  | N |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5802 | VRS - Check all Road Restraint System - ILM | 23.3245 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1812.82 | 1812.82 | 0 | 1 |  | N |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5802 | VRS - Check all Road Restraint System - ILM | 14.921 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1159.69 | 1159.69 | 0 | 1 |  | N |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5801 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 0 |  | 0 | 0 |  | N |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5801 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 0 |  | 0 | 0 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5801 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 0 |  | 0 | 0 |  | N |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 3.2143 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 249.82 | 249.82 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 4.0183 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 312.31 | 312.31 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 8.4395 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 655.93 | 655.93 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 14.942 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1161.32 | 1161.32 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5803 | VRS - Check all Road Restraint System - ILM | 23.3201 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1812.48 | 1812.48 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5803 | VRS - Check all Road Restraint System - ILM | 30.0113 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2332.53 | 2332.53 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905149
YNE11 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5800 | VRS - Check all Road Restraint System - ILM | 2.3749 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 184.58 | 184.58 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906270
YNE11 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5804 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 882.44 |  | 882.44 | 0 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE11 Closure 2 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5805 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1258.83 |  | 1258.83 | 0 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE11 Closure 2 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5805 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1666.74 |  | 1666.74 | 0 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE11 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5806 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1654.86 |  | 1654.86 | 0 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE11 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5806 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2817.78 |  | 2817.78 | 0 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE11 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5807 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 805.59 |  | 805.59 | 0 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 12016573
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5809 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5809 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5810 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5810 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5810 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5809 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5809 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5809 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5811 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5811 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5808 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9 | 9 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014624
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5812 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5812 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5813 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5813 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5814 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014640
YNE11 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5815 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5814 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014640
YNE11 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5816 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5817 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5817 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5817 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5820 | Marker Posts - Clean all marker post faces and reference numbers | 8.7888 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 22 | 22 | 0 | 1 |  | N |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5820 | Marker Posts - Clean all marker post faces and reference numbers | 6.3918 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5820 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-24 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5819 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 8 | 8 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5821 | Marker Posts - Clean all marker post faces and reference numbers | 6.7913 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5821 | Marker Posts - Clean all marker post faces and reference numbers | 9.1883 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-25 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 23 | 23 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE11 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5818 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014651
YNE11 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5822 | Bollards - Clean all illuminated and non-illuminated bollards | 29.6176 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs raised
YNE11 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5823 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 11 |  | 11 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE11 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5824 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE11 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5825 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 11 |  | 11 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE11 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5826 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE11 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5827 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE11 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5828 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE11 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 5829 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 8.0208 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 613 | 613 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 | No |  | 3 times per year (ILM Certain Sections) |  |  | 52038524
YNE11 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 5830 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 10.0489 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 768 | 768 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 | No | Days | 3 times per year (ILM Certain Sections) |  |  | 52037490, 52038527
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 2.6251 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 204.03 | 204.03 | 0 | 1 |  | N |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5832 | VRS - Check all Road Restraint System - ILM | 1.2812 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 99.58 | 99.58 | 0 | 1 |  | N |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 5.2001 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 404.16 | 404.16 | 0 | 1 |  | N |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5832 | VRS - Check all Road Restraint System - ILM | 16.6846 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1296.76 | 1296.76 | 0 | 1 |  | N |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 7.1313 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 554.26 | 554.26 | 0 | 1 |  | N |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5832 | VRS - Check all Road Restraint System - ILM | 5.9072 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 459.12 | 459.12 | 0 | 1 |  | N |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 5.8789 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 456.92 | 456.92 | 0 | 1 |  | N |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5833 | VRS - Check all Road Restraint System - ILM | 10.7444 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 835.07 | 835.07 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5833 | VRS - Check all Road Restraint System - ILM | 10.2917 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 799.89 | 799.89 | 0 | 1 |  | N |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5834 | VRS - Check all Road Restraint System - ILM | 9.3606 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 727.52 | 727.52 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5833 | VRS - Check all Road Restraint System - ILM | 8.3185 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 646.53 | 646.53 | 0 | 1 | 28/11 - no assets | N |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5834 | VRS - Check all Road Restraint System - ILM | 6.195 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 481.49 | 481.49 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5834 | VRS - Check all Road Restraint System - ILM | 25.4527 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1978.23 | 1978.23 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5835 | VRS - Check all Road Restraint System - ILM | 25.266 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 1963.72 | 1963.72 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5836 | VRS - Check all Road Restraint System - ILM | 23.9681 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1862.84 | 1862.84 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5835 | VRS - Check all Road Restraint System - ILM | 25.1607 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 1955.53 | 1955.53 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5836 | VRS - Check all Road Restraint System - ILM | 17.9737 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 1396.92 | 1396.95 | -0.03 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE12 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5832 | VRS - Check all Road Restraint System - ILM | 19.3562 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1504.4 | 1504.4 | 0 | 1 |  | N |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 4.3766 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 340.16 | 340.16 | 0 | 1 |  | N |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5832 | VRS - Check all Road Restraint System - ILM | 3.8473 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 299.02 | 299.02 | 0 | 1 |  | N |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5831 | VRS - Check all Road Restraint System - ILM | 17.6408 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1371.07 | 1371.07 | 0 | 1 |  | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906068
YNE12 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5837 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 205 |  | 0 | 1 | 27/11 no assets in closure | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902872
YNE12 Closure 3 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5838 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 233.42 |  | 233.42 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903005
YNE12 Closure 2 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5839 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5.3344 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 69.1 | 69.1 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031762
YNE12 Closure 1 WB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5840 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 27.7952 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 | No assets | N |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE12 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 5841 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 55.5903 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 | No assets | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs raised
YNE12 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5842 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 689.01 |  | 689.01 | 0 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5843 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 2181.81 |  | 2181.81 | 0 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5842 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 391.81 |  | 391.81 | 0 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5843 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 349.29 |  | 349.29 | 0 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 2 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5844 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1876.85 |  | 1876.85 | 0 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5845 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 994.67 |  | 994.67 | 0 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5845 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2091.9 |  | 2091.9 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5846 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 3518.56 |  | 3518.56 | 0 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 3 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5847 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2460.14 |  | 2460.14 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5846 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 3125.29 |  | 3125.29 | 0 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 3 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5847 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1938.45 |  | 1938.45 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5843 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 2392.22 |  | 2392.22 | 0 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5842 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1415.31 |  | 1415.31 | 0 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5843 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 784.91 |  | 784.91 | 0 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5842 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2977.44 |  | 2977.44 | 0 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5848 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5849 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5848 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5849 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5848 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5850 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5850 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5851 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5850 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5851 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5851 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 7 |  | 7 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5852 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 7 |  | 7 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5853 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 10 |  | 10 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5852 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 8 |  | 8 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5853 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 12 |  | 12 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5849 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5848 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5849 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5848 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 14.3817 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014669
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5854 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5855 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5854 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5854 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5856 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5857 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5854 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5855 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016077
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5859 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5859 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5859 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5860 | Marker Posts - Clean all marker post faces and reference numbers | 5.5929 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5860 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5861 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 11 |  | 11 | 0 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5860 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5861 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 |  | 6 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5861 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 20 |  | 20 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5862 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 17 |  | 17 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016081
YNE12 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5863 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 18 |  | 18 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5862 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 13 |  | 13 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016081
YNE12 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5863 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE12 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5859 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5859 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5858 | Marker Posts - Clean all marker post faces and reference numbers | 7.5903 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 19 | 19 | 0 | 1 |  | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12016093
YNE12 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5864 | Bollards - Clean all illuminated and non-illuminated bollards | 49.3626 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12014717
YNE12 Closure 2 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5865 | Bollards - Clean all illuminated and non-illuminated bollards | 52.6535 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 16 | 16 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12014717
YNE12 Closure 3 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5866 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12016097
YNE12 Closure 3 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5867 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5864 | Bollards - Clean all illuminated and non-illuminated bollards | 62.526 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 19 | 19 | 0 | 1 |  | N |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12014717
YNE12 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5868 | Bollards - Clean all illuminated and non-illuminated bollards | 69.1077 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 21 | 21 | 0 | 1 |  | N |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12014717
YNE12 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5869 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 16 |  | 16 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5870 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5871 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV Masts - Check mast breaking system | 5872 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5873 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 13 |  | 13 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5874 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 19 |  | 19 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE12 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5875 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE12 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5876 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5877 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5878 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5879 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE12 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5880 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 4158 |  | 4158 | 0 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1149 |  | 1149 | 0 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 2 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5882 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 6288 |  | 6288 | 0 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 2 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5882 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 2962 |  | 2962 | 0 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 2 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5883 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 753 |  | 753 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 3 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5884 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 3791 |  | 3791 | 0 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 3 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5885 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1692 |  | 1692 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5880 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 2045 |  | 2045 | 0 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE12 Closure 2 EB NS CGS 45261 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 5886 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 5552 |  | 5552 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5887 | Sweeping - Paved non-running areas - Full Sweep 02 | 36.2579 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-28 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4868 | 4868 | 0 | 1 |  | N |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | 52044039
YNE12 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5888 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2.6169 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 509 | 200 | 309 | 0.39293 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038464
YNE12 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5889 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2.6169 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 419 | 200 | 219 | 0.47733 | 29/11 not complete | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038465
YNE12 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5888 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.5049 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1959 | 650 | 1309 | 0.3318 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) |  |  | 52038488 |  |  |  |  | Langham ES Link
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 292.28 |  | 292.28 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5891 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 13.92 |  | 13.92 | 0 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5891 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1044.81 |  | 1044.81 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 528.16 |  | 528.16 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
WS Link Langham Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5892 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 503.32 |  | 503.32 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | WS Link Langham | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45912868
YNE13 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5891 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 272.65 |  | 272.65 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 77.58 |  | 77.58 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5891 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 625.02 |  | 625.02 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5891 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 56.75 |  | 56.75 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 16.54 |  | 16.54 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 6.6 |  | 6.6 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 50.36 |  | 50.36 | 0 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 94.06 |  | 94.06 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5890 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 159.53 |  | 159.53 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
WS Link Langham Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5893 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 51 |  | 51 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | WS Link Langham | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902859
YNE13 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5894 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 350 |  | 350 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902859
YNE13 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5895 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 496 |  | 496 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45902859
YNE13 Closure 1 WB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5896 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 216.03 |  | 216.03 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE13 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2928.97 |  | 2928.97 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 3127.36 |  | 3127.36 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1154.01 |  | 1154.01 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 951.91 |  | 951.91 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 413.49 |  | 413.49 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2176.74 |  | 2176.74 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 71.47 |  | 71.47 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 3163.57 |  | 3163.57 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5900 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9 |  | 9 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 10 |  | 10 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
WS Link Langham Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5901 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 17 |  | 17 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | WS Link Langham | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5900 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5900 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 14 |  | 14 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5900 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5899 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5902 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5903 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
WS Link Langham Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5904 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | WS Link Langham | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014738
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5902 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5902 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5903 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5906 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 16 |  | 16 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
WS Link Langham Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5907 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | WS Link Langham | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed. Use do forms
YNE13 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5906 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5906 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5905 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE13 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5908 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 17 |  | 17 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5909 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5909 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE13 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5910 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 9 |  | 9 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE13 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5911 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE13 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5912 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE13 Closure Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 5913 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE13 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5914 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 201 |  | 201 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE13 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5915 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 25088.25 |  | 25088.25 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year
WS Link Langham Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5916 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1427 |  | 1427 | 0 |  |  |  | 2000M62/134 | YNE83: M18 Link-J1 | WS Link Langham | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections) |  |  | 45820048
YNE13 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5917 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 642 |  | 642 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5918 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 203 |  | 203 | 0 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5918 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 124 |  | 124 | 0 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5918 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 213 |  | 213 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5918 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1249 |  | 1249 | 0 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 999.02 |  | 999.02 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 447.99 |  | 447.99 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 280 |  | 280 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 56.89 |  | 56.89 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 82.77 |  | 82.77 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 247.41 |  | 247.41 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1178.7 |  | 1178.7 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 18.66 |  | 18.66 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 77.41 |  | 77.41 | 0 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5919 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 406.96 |  | 406.96 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 20.45 |  | 20.45 | 0 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5920 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 372.34 |  | 372.34 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5921 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1941.96 |  | 1941.96 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE14 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5921 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 149.65 |  | 149.65 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE14 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5922 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 3361.96 |  | 3361.96 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE14 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5921 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 370.76 |  | 370.76 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5923 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 16 |  | 16 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5923 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5923 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 7 |  | 7 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 15 |  | 15 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5923 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5923 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 10 |  | 10 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5924 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5925 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5926 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5925 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5926 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5926 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5925 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5927 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 13 |  | 13 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5928 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5927 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5928 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5927 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5927 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3 |  | 3 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5928 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 13 |  | 13 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5928 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5927 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE14 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5928 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5929 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE14 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5930 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 8 |  | 8 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE14 Closure Vaisala 45261 Meteorological sites - Clean fog sensors | 5931 | Meteorological sites - Clean fog sensors | 0 | 4.6.6 | ART009 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE14 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5932 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9102 |  | 9102 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE14 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5933 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 513 |  | 513 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5934 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 671 |  | 671 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5934 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 392 |  | 392 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5933 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 548 |  | 548 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 150.75 |  | 150.75 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5936 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 114.17 |  | 114.17 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 178.58 |  | 178.58 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5936 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 761.86 |  | 761.86 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 17.43 |  | 17.43 | 0 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 274.07 |  | 274.07 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5936 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 77.14 |  | 77.14 | 0 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5936 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 575.78 |  | 575.78 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1218.65 |  | 1218.65 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1267.48 |  | 1267.48 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5938 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 807.51 |  | 807.51 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 172/6 | 168/2 | 45907245 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 735.52 |  | 735.52 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5939 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1790.16 |  | 1790.16 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 168/2 | 172/8 | 45907245 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5938 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1713.44 |  | 1713.44 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 172/6 | 168/2 | 45907245 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 229.47 |  | 229.47 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5939 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 1803.25 |  | 1803.25 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 168/2 | 172/8 | 45907245 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1589.64 |  | 1589.64 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 767.41 |  | 767.41 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 998.05 |  | 998.05 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 225.08 |  | 225.08 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 409.42 |  | 409.42 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 409.42 |  | 409.42 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5936 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 574.88 |  | 574.88 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5935 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 480.69 |  | 480.69 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 24.32 |  | 24.32 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5937 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 37.38 |  | 37.38 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 72.14 |  | 72.14 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 3 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 5940 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 31.57 |  | 31.57 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45907246
YNE15 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5941 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1564.32 |  | 1564.32 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903020
YNE15 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5942 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1605.23 |  | 1605.23 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903020
YNE15 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5941 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 1548.18 |  | 1548.18 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903020
YNE15 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5942 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 22.23 |  | 22.23 | 0 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903020
YNE15 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5942 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1496.77 |  | 1496.77 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903020
YNE15 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5943 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1566.5 |  | 1566.5 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5944 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 377.14 |  | 377.14 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5943 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2431.61 |  | 2431.61 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5944 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 2032.08 |  | 2032.08 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5943 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 3008.88 |  | 3008.88 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5944 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1682.23 |  | 1682.23 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5943 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2046.97 |  | 2046.97 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 3 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5945 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1195.5 |  | 1195.5 | 0 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 2 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5946 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 2860.41 |  | 2860.41 | 0 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 172/6 | 168/2 | TBC | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5947 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 1625.87 |  | 1625.87 | 0 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 168/2 | 172/8 | TBC | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5946 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1823.16 |  | 1823.16 | 0 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 172/6 | 168/2 | TBC | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5945 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 700.6 |  | 700.6 | 0 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 2 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5947 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 2007.01 |  | 2007.01 | 0 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 168/2 | 172/8 | TBC | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5948 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 1930.13 |  | 1930.13 | 0 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5948 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 962.63 |  | 962.63 | 0 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5948 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 957.93 |  | 957.93 | 0 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 3 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5948 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 245.71 |  | 245.71 | 0 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 3 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5945 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | EB | 377.45 |  | 377.45 | 0 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | TBC
YNE15 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 5944 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 41dys | WB | 410.82 |  | 410.82 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5949 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 7 |  | 7 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5950 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5949 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 |  | 6 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5950 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 10 |  | 10 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5949 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 7 |  | 7 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5950 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5950 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5949 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No jobs
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5951 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 4 |  | 4 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5952 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 10 |  | 10 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 172/6 | 168/2 | 12014782 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5951 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 7 |  | 7 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5953 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 6 |  | 6 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 168/2 | 172/8 | 12014782 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5952 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 5 |  | 5 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 172/6 | 168/2 | 12014782 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5953 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 8 |  | 8 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 168/2 | 172/8 | 12014782 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 9 |  | 9 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5951 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5950 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5949 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 22 |  | 22 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5951 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5951 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 8 |  | 8 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5954 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014782
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5955 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5955 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5956 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014807
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5957 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014807
YNE15 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5955 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5958 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 3 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5957 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014807
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5959 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014814
YNE15 Closure 3 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5959 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014814
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5961 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 5 |  | 5 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 14 |  | 14 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5961 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 15 |  | 15 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 6 |  | 6 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5961 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5961 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 11 |  | 11 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 20 |  | 20 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5962 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 9 |  | 9 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5963 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 21 |  | 21 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 172/6 | 168/2 | 12014830 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5962 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 3 |  | 3 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5964 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 16 |  | 16 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 168/2 | 172/8 | 12014830 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5963 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 19 |  | 19 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 172/6 | 168/2 | 12014830 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5964 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 17 |  | 17 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 168/2 | 172/8 | 12014830 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 19 |  | 19 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 8 |  | 8 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 6 |  | 6 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5962 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 5 |  | 5 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5961 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5960 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 2 |  | 2 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE15 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5962 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5962 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 2 |  | 2 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 3 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5965 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12014816
YNE15 Closure 2 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5966 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 5 |  | 5 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Annually | 168/2 | 172/8 | 12016106 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5967 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | WB | 7 |  | 7 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12014842
YNE15 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 5968 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 16 |  | 16 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE15 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5969 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 19 |  | 19 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE15 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 5970 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE15 Closure Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 5971 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE15 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 5972 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE15 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5973 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 342 |  | 342 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE15 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5974 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 959 |  | 959 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE15 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5973 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 1656 |  | 1656 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE15 Closure 3 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 5975 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | EB | 427 |  | 427 | 0 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE15 Closure 1 EB NS CGS 45261 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 5976 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 809 |  | 809 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept)
YNE15 Closure 2 EB NS CGS 45261 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 5977 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | EB | 160 |  | 160 | 0 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 4 |  | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 5978 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE15 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5979 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 544 |  | 544 | 0 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5980 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 828 |  | 828 | 0 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 WB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5980 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 590 |  | 590 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 EB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5979 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 432 |  | 432 | 0 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.1599 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 82.54 | 82.54 | 0 | 1 |  | N |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 NB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5982 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | NB | 116.34 |  | 116.34 | 0 | 22/9: Check and close jobs |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 420.66 |  | 420.66 | 0 |  | N |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 189.84 |  | 189.84 | 0 |  | N |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 229.5 |  | 229.5 | 0 | 22/9: Check and close jobs |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 412.28 |  | 412.28 | 0 |  | N |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 383.91 |  | 383.91 | 0 | 22/9: Check and close jobs |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 350.85 |  | 350.85 | 0 | 22/9: Check and close jobs |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 379.65 |  | 379.65 | 0 |  | N |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 560.63 |  | 560.63 | 0 | 22/9: Check and close jobs |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 269.11 |  | 269.11 | 0 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 48.05 |  | 48.05 | 0 | 22/9: Check and close jobs |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 170.45 |  | 170.45 | 0 | 22/9: Check and close jobs |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.9146 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 81.11 | 81.11 | 0 | 1 |  | N |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 116.6349 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 679.88 | 679.88 | 0 | 1 |  | N |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 NB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5982 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | NB | 591.62 |  | 591.62 | 0 | 22/9: Check and close jobs |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 50.939 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 296.93 | 296.93 | 0 | 1 |  | N |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45909650
YNE30 Closure 1 NB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5982 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | NB | 50.05 |  | 50.05 | 0 | 22/9: Check and close jobs |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031833
YNE30 Closure 1 SB OS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5985 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 188.9818 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | SB | 153 | 153 | 0 | 1 | 22/9 no assets found at this location |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031851
YNE30 Closure 1 SB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5986 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 21 |  | 21 | 0 |  | N |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45902911
YNE30 Closure 1 NB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5987 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 109.9306 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 89 | 89 | 0 | 1 |  | N |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45902911
YNE30 Closure 1 NB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5987 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 206.2743 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 167 | 167 | 0 | 1 |  | N |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45902911
YNE30 Closure 1 SB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5988 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 27.42 |  | 27.42 | 0 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031855
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 7 | 7 | 0 | 1 |  | N |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.1806 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 19 | 19 | 0 | 1 |  | N |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5990 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5989 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014845
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5991 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5992 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5992 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5992 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5991 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5992 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5992 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5991 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5991 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5991 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014860
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5994 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 5993 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014870 - 12014881
YNE30 Closure 1 NB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5995 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 89.8853 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | Rejected
YNE30 Closure 1 NB NS Amey 45261 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5996 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 11 | 11 | 0 | 1 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years |  |  | Not rasied as LED
YNE30 Closure 1 NB NS Amey 45261 BC - Lamps (LED) for Road Lighting | 5997 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 3 |  | 3 | 0 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038370
YNE30 Closure 1 NB OS Amey 45261 Electrical Testing - Network cabling and electrical components | 5998 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 5 |  | 5 | 0 |  | Y | LED upgrade scheme carried out testing. Confirmation on what assets were to be tested not received until 10/11/23 |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038371
YNE30 Closure Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5999 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 6000 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45261 CCTV Masts - Check mast breaking system | 6001 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6002 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 8 |  | 8 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6003 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6004 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 9 |  | 9 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE30 Closure Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 6005 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE30 Closure 1 SB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6006 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 1188 |  | 1188 | 0 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE30 Closure 1 SB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6006 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 808 |  | 808 | 0 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE30 Closure 1 SB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6006 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 1357 |  | 1357 | 0 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE30 Closure 1 SB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6006 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | WB | 1675 |  | 1675 | 0 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE30 Closure 1 SB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6007 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 314 |  | 314 | 0 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE30 Closure 1 NB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6008 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | NB | 80 |  | 80 | 0 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE30 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6009 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 11.8037 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | NB | 131.32 | 131.32 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6009 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 51.2679 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | NB | 570.37 | 570.37 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/14 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 SB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6010 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | SB | 510.93 |  | 510.93 | 0 | 22/9: Check and close jobs |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6009 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 79.5701 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | NB | 885.24 | 885.24 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/16 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 SB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6010 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 170.8855 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | WB | 1901.15 | 1901.15 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 SB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6010 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | WB | 893.84 |  | 893.84 | 0 | 22/9: Check and close jobs |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6009 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 116.3116 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | NB | 1294 | 1294 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6009 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | NB | 2722.5 |  | 2722.5 | 0 | 22/9: Check and close jobs |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893650
YNE30 Closure 1 SB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6011 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4.5011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 344 | 344 | 0 | 1 |  | N |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 | No |  | 4 times per year (ILM Certain Sections) |  |  | 52038352
YNE31 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6012 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 70.56 |  | 70.56 | 0 |  | N |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6013 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 151.96 |  | 151.96 | 0 | 22/9: Check and close jobs |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE31 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6012 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 59.32 |  | 59.32 | 0 |  | N |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6013 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 98.06 |  | 98.06 | 0 | 22/9: Check and close jobs |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE31 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6012 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 369.94 |  | 369.94 | 0 |  | N |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6013 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 357.32 |  | 357.32 | 0 | 22/9: Check and close jobs |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE31 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6012 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 130.73 |  | 130.73 | 0 |  | N |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 SB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6012 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 127.24 |  | 127.24 | 0 |  | N |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 SB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6013 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | SB | 305.68 |  | 305.68 | 0 | 22/9: Check and close jobs |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE31 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6014 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 147.9654 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 862.51 | 862.51 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 NB NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6014 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 42.7302 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 249.08 | 249.08 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45912544
YNE31 Closure 1 NB OS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6015 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | NB | 66.83 |  | 66.83 | 0 | 22/9: Check and close jobs |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE31 Closure 1 SB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6016 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 40.43 |  | 40.43 | 0 |  | N |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45903157
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 14 | 14 | 0 | 1 |  | N |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6017 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6018 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6018 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6018 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6018 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014882
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6019 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6019 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 SB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6019 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6020 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6020 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 NB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6020 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014892
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6021 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6022 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6022 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6022 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 NB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6022 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12014898 - 12014907
YNE31 Closure 1 SB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6023 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 12016170
YNE31 Closure 1 NB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6024 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 696.6114 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 31 | 31 | 0 | 1 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | REjected as LED
YNE31 Closure 1 NB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 6025 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | 2023-07-20 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 52038359
YNE31 Closure 1 NB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 6026 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038360
YNE31 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6027 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE31 Closure 1 SB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6028 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 1441 |  | 1441 | 0 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE31 Closure 1 NB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6029 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | NB | 6320 |  | 6320 | 0 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE31 Closure 1 NB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6029 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | NB | 80 |  | 80 | 0 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE31 Closure 1 SB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6030 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | SB | 493 |  | 493 | 0 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE31 Closure 1 SB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6031 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | SB | 2021.93 |  | 2021.93 | 0 | 22/9: Check and close jobs |  |  | 4700M606/12 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893658
YNE31 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6032 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | NB | 3672.48 |  | 3672.48 | 0 | 22/9: Check and close jobs |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893658
YNE31 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6032 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | NB | 955.48 |  | 955.48 | 0 | 22/9: Check and close jobs |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893658
YNE31 Closure 1 NB OS CGS 45261 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 6032 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to complete within ADAMr timescales due to access | 41dys | NB | 197.78 |  | 197.78 | 0 | 22/9: Check and close jobs |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45893658
YNE31 Closure 1 SB NS Amey 45261 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6033 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 5.7702 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-29 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | SB | 441 | 441 | 0 | 1 |  | N |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 | No |  | 4 times per year (ILM Certain Sections) |  |  | 52038788
YNE32 Closure 1 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6034 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 186.71 |  | 186.71 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6035 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 208.6 |  | 208.6 | 0 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6036 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 273.86 |  | 273.86 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6035 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 884.61 |  | 884.61 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6036 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 36.61 |  | 36.61 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6036 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 364.45 |  | 364.45 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6036 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 16.74 |  | 16.74 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6036 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 155.45 |  | 155.45 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6037 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 661.61 |  | 661.61 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6034 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 391.82 |  | 391.82 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6037 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 186.81 |  | 186.81 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6034 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 160.29 |  | 160.29 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6038 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 66 |  | 66 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | 45902921
YNE32 Closure 1 ACW OS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6039 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 71 |  | 71 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 6 |  |  | Every 2 years |  |  | 45902921
YNE32 Closure 1 CW OS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6040 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 45.82 |  | 45.82 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 6 |  |  | Every 2 years |  |  | 45903150
YNE32 Closure 1 CW OS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6041 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 228.08 |  | 228.08 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 6 |  |  | 3 times per year (ILM Entire Route)
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 20 |  | 20 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6043 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 3 |  | 3 | 0 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 7 |  | 7 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6043 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 5 |  | 5 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6043 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 7 |  | 7 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 5 |  | 5 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 7 |  | 7 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 13 |  | 13 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 8 |  | 8 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 9 |  | 9 | 0 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 6 |  | 6 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 8 |  | 8 | 0 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6044 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 9 |  | 9 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 7 |  | 7 | 0 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6045 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 5 |  | 5 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6045 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 7 |  | 7 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 12 |  | 12 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6045 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 4 |  | 4 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6042 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 12 |  | 12 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6046 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6047 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6048 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6048 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6047 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 4 |  | 4 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6047 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6046 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6049 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 2 |  | 2 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 2 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6049 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 4 |  | 4 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6046 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 2 |  | 2 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6046 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years |  |  | No jobs rasied
YNE32 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6050 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6051 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6051 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6053 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 5 |  | 5 | 0 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 5 |  | 5 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6053 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 12 |  | 12 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6053 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 14 |  | 14 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 6 |  | 6 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 9 |  | 9 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | ACW | 3 |  | 3 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 2 |  | 2 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6054 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | WB | 7 |  | 7 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 7 |  | 7 | 0 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 6 |  | 6 | 0 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6055 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 12 |  | 12 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6055 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 12 |  | 12 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 5 |  | 5 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 2 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6055 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 4 |  | 4 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6052 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure 1 CW NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6056 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Annually
YNE32 Closure 1 CW NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6057 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys |  | 17 |  | 17 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 6 years
YNE32 Closure 1 CW NS Amey 45261 BCC - UNSWITCHED lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6058 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys |  | 12 |  | 12 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 6 years
YNE32 Closure 1 CW NS Amey 45261 BCC - Lamps (LED) for Road Lighting | 6059 | BCC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 6 years
YNE32 Closure 1 CW NS Amey 45261 BCC - Lamps (LED) for Illuminated Signs and Bollards | 6060 | BCC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  |  | Every 2 years
YNE32 Closure Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 6061 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6062 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 9 |  | 9 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6063 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Every 6 years |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 6064 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 6065 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV Masts - Check mast breaking system | 6066 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6067 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 11 |  | 11 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE32 Closure Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6068 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 6 |  | 6 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV PTZ Cameras - Clean camera lens | 6069 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV PTZ Cameras - Check camera functionality | 6070 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 6071 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 6 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure 1 ACW NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6072 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | ACW | 490 |  | 490 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  | Days | Every 3 years (Sept - Feb)
YNE32 Closure 2 ACW NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6073 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | ACW | 799 |  | 799 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  | Days | Every 3 years (Sept - Feb)
YNE32 Closure 2 ACW NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6073 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | ACW | 1678 |  | 1678 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 6 |  | Days | Every 3 years (Sept - Feb)
YNE32 Closure 1 CW NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6074 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Removed following GC-898 | 41dys | CW | 130 |  | 130 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 6 |  | Days | Every 3 years (Sept - Feb)
YNE32 Closure 1 ACW NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 6075 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 6 |  |  | 2 times per year
YNE41 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6076 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 12793.73 |  | 12793.73 | 0 |  |  |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6077 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 19583.42 |  | 19583.42 | 0 |  |  |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 0.15247 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 11.85 | 11.85 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 2.9482 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 229.14 | 229.14 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6079 | VRS - Check all Road Restraint System - ILM | 8.3109 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 645.94 | 645.94 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 1.5549 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 120.85 | 120.85 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6079 | VRS - Check all Road Restraint System - ILM | 4.1575 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 323.13 | 323.13 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6079 | VRS - Check all Road Restraint System - ILM | 5.183 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 402.83 | 402.83 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 2.2067 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 171.51 | 171.51 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 3.5034 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 272.29 | 272.29 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6079 | VRS - Check all Road Restraint System - ILM | 1.9889 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 154.58 | 154.58 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6078 | VRS - Check all Road Restraint System - ILM | 0.08479 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6.59 | 6.59 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 2/6 | 0/0 | 45908820 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS - Bramham Rbt Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6080 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Unmaintainable - feedbakc loop used | Unmaintainable - feedbakc loop used |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 80 |  | 0 | 0 |  | N | Drainage driver took ill - rebooked for December | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS - Bramham Rbt | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45929920
YNE41 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6081 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 34.3562 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 65 | 43 | 22 | 0.66154 | 9/11 reachable assets cleaned | N | Part complete 9/11 - rebooked for December | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45929976 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6082 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 43.145 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 65 | 54 | 11 | 0.83077 | 9/11 reachable assets cleaned - jobs closed | N | Part complete 9/11 - rebooked for December | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45929976 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6083 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930366 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6084 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45930366 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6085 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N | Part complete 9/11 - rebooked for December | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930050 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6085 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N | Part complete 9/11 - rebooked for December | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930050 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6085 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 0 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 |  | 1 | 0 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N | Part complete 9/11 - rebooked for December | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930050 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6086 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6086 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 |  | 5 | 0 |  | N | Part complete 9/11 - rebooked for December | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6087 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 | 9/11 assets cleaned bult all jobs remain open. Daz to discuss with Jack | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45930357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6086 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 2/6 | 0/0 | 45930357 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6088 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 1 | 1 | 0 | 1 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually | 2/6 | 0/0 | 45929926 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6088 | Bollards - Clean all illuminated and non-illuminated bollards | 13.1634 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-09 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 | 9/11 reachable assets cleaned bult all jobs remain open. Daz to discuss with Jack | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually | 2/6 | 0/0 | 45929926 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6089 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 7486.51 |  | 7486.51 | 0 |  |  |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6089 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 821.57 |  | 821.57 | 0 |  |  |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6090 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 9667.82 |  | 9667.82 | 0 |  |  |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6089 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 2050.51 |  | 2050.51 | 0 |  |  |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6090 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 10156.02 |  | 10156.02 | 0 |  |  |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6091 | VRS - Check all Road Restraint System - ILM | 6.5177 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 506.57 | 506.57 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 1/7 | 5/7 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6092 | VRS - Check all Road Restraint System - ILM | 5.9719 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 464.15 | 464.15 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 5/5 | 2/3 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6091 | VRS - Check all Road Restraint System - ILM | 0.19557 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 15.2 | 15.2 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 1/7 | 5/7 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6092 | VRS - Check all Road Restraint System - ILM | 0.55158 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 42.87 | 42.87 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 5/5 | 2/3 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6091 | VRS - Check all Road Restraint System - ILM | 0.70315 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 54.65 | 54.65 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 1/7 | 5/7 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6092 | VRS - Check all Road Restraint System - ILM | 0.5777 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 44.9 | 44.9 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 5/5 | 2/3 | 45929906 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE43 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6093 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 13285.27 |  | 13285.27 | 0 |  |  |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6094 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 21448.42 |  | 21448.42 | 0 |  |  |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6095 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 1950.37 |  | 1950.37 | 0 |  |  |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6094 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 14865.67 |  | 14865.67 | 0 |  |  |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6096 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 12516.88 |  | 12516.88 | 0 |  |  |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6096 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 849.38 |  | 849.38 | 0 |  |  |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE43 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6097 | VRS - Check all Road Restraint System - ILM | 3.0268 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 235.25 | 235.25 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 2.4139 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 187.61 | 187.61 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6097 | VRS - Check all Road Restraint System - ILM | 3.1147 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 242.08 | 242.08 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 3.4335 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 266.86 | 266.86 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 0.76735 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 59.64 | 59.64 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 3.1137 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 242 | 242 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 1.544 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 120 | 120 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6098 | VRS - Check all Road Restraint System - ILM | 0.45032 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 35 | 35 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45908911
YNE43 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6099 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | EB | 386.01 |  | 386.01 | 0 |  |  |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45929671
YNE43 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6100 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | WB | 690.28 |  | 690.28 | 0 |  |  |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45929671
YNE43 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6101 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 25.5674 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 14.3817 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6101 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.1806 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6101 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6101 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.9847 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/157 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6102 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/174 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930156
YNE43 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6103 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930393
YNE43 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6104 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930393
YNE43 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6105 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930382
YNE43 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6106 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930382
YNE43 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6105 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930382
YNE43 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6105 | Marker Posts - Clean all marker post faces and reference numbers | 5.9924 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-11 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45930382
YNE43 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6107 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 4001 |  | 4001 | 0 |  |  |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE43 Closure 2 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6108 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 2219 |  | 2219 | 0 |  |  |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE44 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6109 | VRS - Check all Road Restraint System - ILM | 0.70598 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 54.87 | 54.87 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 9/1 | 15/6 | 45909123 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6110 | VRS - Check all Road Restraint System - ILM | 0.79 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 61.4 | 61.4 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909123
YNE44 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6110 | VRS - Check all Road Restraint System - ILM | 1.541 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 119.77 | 119.77 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909123
YNE44 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6109 | VRS - Check all Road Restraint System - ILM | 1.5972 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 124.14 | 124.14 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 9/1 | 15/6 | 45909123 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6111 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | EB | 188.47 |  | 188.47 | 0 |  |  |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 9/1 | 15/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6112 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | WB | 41.63 |  | 41.63 | 0 |  |  |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE44 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6113 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6114 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6114 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6113 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 14.3817 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6114 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6113 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6114 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6113 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6114 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6115 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6116 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6117 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  | 2023-12-13 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 | 13/11 cancelled due to bad weather | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6118 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6118 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6117 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 | 13/11 cancelled due to bad weather | N | 13/11 cancelled due bad weather, rebooked for December | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 9/1 | 15/6 | 12016225 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6118 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6118 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6118 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE44 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6119 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 |  | 8 | 0 | 13/11 cancelled due to bad weather | N | 13/11 cancelled due bad weather, rebooked for December | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually | 9/1 | 15/6 | 12014927 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6120 | Bollards - Clean all illuminated and non-illuminated bollards | 95.4344 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6120 | Bollards - Clean all illuminated and non-illuminated bollards | 19.7451 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE44 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6120 | Bollards - Clean all illuminated and non-illuminated bollards | 32.9084 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-14 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE44 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6121 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 42 |  | 42 | 0 |  |  |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE45 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6122 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1705.75 |  | 1705.75 | 0 |  |  |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE45 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6122 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | CW | 9909.22 |  | 9909.22 | 0 |  |  |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 3.3185 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 257.92 | 257.92 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 1.8219 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 141.6 | 141.6 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 5.8414 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 454 | 454 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 10.499 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 816 | 816 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 5.9829 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 465 | 465 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 7.5783 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 589 | 589 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 15.6584 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1217 | 1217 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 5.6226 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 437 | 437 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 0.4601 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 35.76 | 35.76 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 0.54682 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 42.5 | 42.5 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 1.5954 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 124 | 124 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 2.6161 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 203.33 | 203.33 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909135
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 19.9745 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 25 | 25 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.9847 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 15 | 15 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6127 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6128 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6128 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6128 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6130 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6130 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6131 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE45 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6132 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE45 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6133 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | On ServiceNow
YNE45 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6134 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 77 |  | 77 | 0 |  |  |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE46 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6135 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1362.81 |  | 1362.81 | 0 |  |  |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE46 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6136 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 5880.02 |  | 5880.02 | 0 |  |  |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE46 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6136 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 867.67 |  | 867.67 | 0 |  |  |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE46 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6135 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 2824.31 |  | 2824.31 | 0 |  |  |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 0.47168 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 36.66 | 36.66 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 0.15929 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 12.38 | 12.38 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 2.7137 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 210.91 | 210.91 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 7.061 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 548.79 | 548.79 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 8.1026 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 629.75 | 629.75 | 0 | 1 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 8.6144 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 669.53 | 669.53 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 0.21757 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 16.91 | 16.91 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6123 | VRS - Check all Road Restraint System - ILM | 0.71614 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 55.66 | 55.66 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 5.4367 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 422.55 | 422.55 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6124 | VRS - Check all Road Restraint System - ILM | 16.696 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1297.64 | 1297.64 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909370
YNE45 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6137 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 314.0365 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | EB | 457.64 | 457.64 | 0 | 1 |  |  |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE45 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6138 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | WB | 688.03 |  | 688.03 | 0 |  |  |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.1806 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6125 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 21.5725 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 27 | 27 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6126 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 17.5776 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 22 | 22 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6128 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6128 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 47.9388 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6127 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6127 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6130 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6130 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6129 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE45 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6139 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE46 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6140 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 64 |  | 64 | 0 |  |  |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE46 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6141 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | WB | 352 |  | 352 | 0 |  |  |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE47 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6142 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 3842.83 |  | 3842.83 | 0 |  |  |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 58.95 |  | 58.95 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 6.4929 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 504.64 | 504.64 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 1.226 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 95.29 | 95.29 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 3.9315 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 305.56 | 305.56 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 5.0341 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 391.26 | 391.26 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 1.1051 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 85.89 | 85.89 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 2.2245 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 172.89 | 172.89 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 5.5603 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 432.16 | 432.16 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 4.3954 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 341.62 | 341.62 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 0.72052 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 56 | 56 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 1.1778 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 91.54 | 91.54 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6144 | VRS - Check all Road Restraint System - ILM | 1.4997 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 116.56 | 116.56 | 0 | 1 |  | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6143 | VRS - Check all Road Restraint System - ILM | 0.80286 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 62.4 | 62.4 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45909460
YNE47 Closure 1 EB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6145 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 73.1704 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | EB | 106.63 | 106.63 | 0 | 1 |  |  |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE47 Closure 1 WB NS Amey 45261 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6146 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | N/A | Removed following updated instruction GC-928 | 19dys | WB | 270.19 |  | 270.19 | 0 |  |  |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 |  | 5 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 9 | 9 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 14.3817 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.9796 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 12 | 12 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6148 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6147 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6149 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6150 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6149 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6149 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | completed | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6151 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6151 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6151 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6151 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 11 | 11 | 0 | 1 |  | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE47 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6151 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 |  | 6 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6152 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 22dys | EB | 4679.98 |  | 4679.98 | 0 |  |  |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE48 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6152 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 22dys | EB | 18010.52 |  | 18010.52 | 0 |  |  |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE48 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6153 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 22dys | WB | 1441.08 |  | 1441.08 | 0 |  |  |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE48 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6152 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 22dys | CW | 9246.21 |  | 9246.21 | 0 |  |  |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.84121 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 65.38 | 65.38 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 1.4925 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 116 | 116 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 4.4807 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 348.25 | 348.25 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 5.3354 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 414.68 | 414.68 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.53138 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 41.3 | 41.3 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 0.2195 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 17.06 | 17.06 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 1.006 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 78.19 | 78.19 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 0.73737 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 57.31 | 57.31 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.38651 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 30.04 | 30.04 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 1.0314 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 80.16 | 80.16 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.82937 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 64.46 | 64.46 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 0.47091 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 36.6 | 36.6 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.64435 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 50.08 | 50.08 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6155 | VRS - Check all Road Restraint System - ILM | 2.1438 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 166.62 | 166.62 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 0.23983 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 18.64 | 18.64 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6154 | VRS - Check all Road Restraint System - ILM | 1.5626 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 121.45 | 121.45 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45910648
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 16.7786 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6157 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6156 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 59.9236 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 75 | 75 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6158 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6159 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6158 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6158 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6158 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 5.5929 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6161 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6161 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6161 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE48 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6160 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6162 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1260.61 |  | 1260.61 | 0 |  |  |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE49 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6162 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 2193.94 |  | 2193.94 | 0 |  |  |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 0.69196 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 53.78 | 53.78 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 0.8075 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 62.76 | 62.76 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 3.3535 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 260.64 | 260.64 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 3.4431 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 267.6 | 267.6 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 4.1327 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 321.2 | 321.2 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 6.2581 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 486.39 | 486.39 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 0.7294 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 56.69 | 56.69 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 3.1147 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 242.08 | 242.08 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 3.2113 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 249.59 | 249.59 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 2.4491 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 190.35 | 190.35 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6163 | VRS - Check all Road Restraint System - ILM | 3.5177 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 273.4 | 273.4 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6164 | VRS - Check all Road Restraint System - ILM | 3.5971 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 279.57 | 279.57 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45911449
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.1806 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/354 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 23.1704 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 29 | 29 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6165 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6166 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 22.3715 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 28 | 28 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6167 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6168 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6168 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/354 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6168 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6167 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6169 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 44.9427 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6169 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 89.8853 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6170 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 134.828 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6171 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6171 | Marker Posts - Clean all marker post faces and reference numbers | 3.9949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6172 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6171 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6172 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6172 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6171 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6171 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6172 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE49 Closure 2 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6173 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE49 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6174 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-18 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE50 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6175 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 3496.72 |  | 3496.72 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE50 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6175 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1418.7 |  | 1418.7 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE50 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6175 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 3144.55 |  | 3144.55 | 0 |  |  |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE50 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6176 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 140 |  | 140 | 0 |  |  |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931341
YNE50 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6176 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 228 |  | 228 | 0 |  |  |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931341
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 20 |  | 20 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/420 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 18 |  | 18 | 0 |  |  |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 44 |  | 44 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 8 |  | 8 | 0 |  |  |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 13 |  | 13 | 0 |  |  |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 29 |  | 29 | 0 |  |  |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6177 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 20 |  | 20 | 0 |  |  |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6178 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 9 |  | 9 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 7 |  | 7 | 0 |  |  |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6179 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 35 |  | 35 | 0 |  |  |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 12 |  | 12 | 0 |  |  |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 9 |  | 9 | 0 |  |  |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE50 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6180 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE51 Closure CGS 45261 Woodland - Thin / coppice | 6181 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 2204.29 |  | 2204.29 | 0 |  |  |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | Days |  | Days | Every 7 years
YNE51 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6182 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 752.25 |  | 752.25 | 0 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE51 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6183 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 104.75 |  | 104.75 | 0 |  | N |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6184 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 685 |  | 685 | 0 |  | N |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6185 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1190 |  | 1190 | 0 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6184 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1028 |  | 1028 | 0 |  | N |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6185 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 345 |  | 345 | 0 |  | N |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6185 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1009 |  | 1009 | 0 |  | N |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6184 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 714 |  | 714 | 0 |  | N |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6185 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 603 |  | 603 | 0 |  | N |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6184 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 696 |  | 696 | 0 |  | N |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912108
YNE51 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6186 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 183 |  | 183 | 0 | 20/11 TM did not cover | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45931409
YNE51 Closure 2 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6187 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 179 |  | 179 | 0 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45931409
YNE51 Closure 1 EB NS Enviroflow 45261 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6188 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 |  | 8 | 0 | 20/11 no jobs raised so no location info for these | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45903543
YNE51 Closure 2 EB NS Enviroflow 45261 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6189 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 16 |  | 16 | 0 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45903543
YNE51 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6190 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6191 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 18 |  | 18 | 0 |  | N |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6191 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 7 |  | 7 | 0 |  | N |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6192 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 26 |  | 26 | 0 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6193 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 19 |  | 19 | 0 |  | N |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6190 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 20.7735 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 26 | 26 | 0 | 1 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6193 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 23 |  | 23 | 0 |  | N |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6192 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 17 |  | 17 | 0 |  | N |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6192 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 35 |  | 35 | 0 |  | N |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6193 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 22 |  | 22 | 0 |  | N |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6192 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 23 |  | 23 | 0 |  | N |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6193 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 20 |  | 20 | 0 |  | N |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6194 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6195 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 |  | 4 | 0 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6196 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 |  | N |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6194 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6195 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 |  | N |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6196 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 |  | 1 | 0 |  | N |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6195 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 |  | N |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6196 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 |  | 1 | 0 |  | N |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6197 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6198 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 |  | N |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6198 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 |  | 5 | 0 |  | N |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6199 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6200 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 |  | N |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6197 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-20 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6200 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 |  | 6 | 0 |  | N |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6199 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 |  | 4 | 0 |  | N |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6199 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 |  | 4 | 0 |  | N |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6200 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 |  | N |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6199 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 |  | N |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6200 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 |  | 6 | 0 |  | N |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE51 Closure 2 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6201 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6202 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 |  | 1 | 0 |  | N |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE51 Closure 2 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6202 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 |  | N |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE51 Closure 1 WB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 6203 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 |  | N |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 52038435
YNE51 Closure 1 EB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 6204 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 |  | N |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 52038436
YNE52 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6205 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1406.01 |  | 1406.01 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE52 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6205 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1616.04 |  | 1616.04 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE52 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6205 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 2989.1 |  | 2989.1 | 0 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE52 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6206 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 4933.39 |  | 4933.39 | 0 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE52 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6207 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 22.79 |  | 22.79 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE52 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6207 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 414.57 |  | 414.57 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE52 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6207 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 208.56 |  | 208.56 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE52 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6208 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 193.13 |  | 193.13 | 0 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 24 |  | 24 | 0 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 40 |  | 40 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6209 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 15 |  | 15 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6210 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 5 |  | 5 | 0 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6211 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 7 |  | 7 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6212 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6213 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE52 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6213 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE52 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6213 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE52 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6213 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE52 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6214 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 53 |  | 53 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE52 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6214 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 158 |  | 158 | 0 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE53 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6215 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 4170.3 |  | 4170.3 | 0 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE53 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6215 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 3674.24 |  | 3674.24 | 0 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE53 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6216 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 961.22 |  | 961.22 | 0 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6215 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 7207.09 |  | 7207.09 | 0 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE53 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6215 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 4967.3 |  | 4967.3 | 0 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 5.4693 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 425.08 | 425.08 | 0 | 1 |  | N |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 5.1839 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 402.9 | 402.9 | 0 | 1 |  | N |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 1.4054 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 109.23 | 109.23 | 0 | 1 |  | N |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 1.6749 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 130.18 | 130.18 | 0 | 1 |  | N |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 0.80801 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 62.8 | 62.8 | 0 | 1 |  | N |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 1.1039 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 85.8 | 85.8 | 0 | 1 |  | N |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 1.5927 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 123.79 | 123.79 | 0 | 1 |  | N |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 0.74831 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 58.16 | 58.16 | 0 | 1 |  | N |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 0.96266 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 74.82 | 74.82 | 0 | 1 |  | N |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 0.64538 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 50.16 | 50.16 | 0 | 1 |  | N |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 2.178 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 169.28 | 169.28 | 0 | 1 |  | N |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 0.9772 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 75.95 | 75.95 | 0 | 1 |  | N |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6217 | VRS - Check all Road Restraint System - ILM | 2.9979 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 233 | 233 | 0 | 1 |  | N |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 50/5 | 50/7 | 45912270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6218 | VRS - Check all Road Restraint System - ILM | 2.9836 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 231.89 | 231.89 | 0 | 1 |  | N |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45912270
YNE53 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6219 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 23.85 |  | 23.85 | 0 | 22/11 - not completed - defective. Schedule D jobs required as full of tarmac | N |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45931369
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6220 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6221 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6222 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6222 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6223 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6223 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6223 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6224 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6225 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6224 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6224 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6224 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6225 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6225 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 50/5 | 50/7 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6224 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | No jobs raised
YNE53 Closure 1 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 6226 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 5361 |  | 5361 | 0 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 6226 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 3855 |  | 3855 | 0 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 6227 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | WB | 4437 |  | 4437 | 0 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE53 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6228 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | WB | 2773 |  | 2773 | 0 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE53 Closure 1 EB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 6229 | Wildlife structures and tunnels - Remove all material that could impair operation | 6.9041 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 | 1 | 0 | 1 | 11/22/2023 No assets - TH confirmed so unable to complete | N |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually | 50/5 | 50/7 | 52038413 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 6230 | Wildlife structures and tunnels - Remove all material that could impair operation | 6.9041 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-23 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Annually |  |  | 52038412
YNE54 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6231 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 5207.84 |  | 5207.84 | 0 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE54 Closure 2 WB NS CGS 45261 Woodland - Thin / coppice | 6232 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 23151.3 |  | 23151.3 | 0 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45261 Woodland - Thin / coppice | 6233 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 6948.59 |  | 6948.59 | 0 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE54 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6234 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 4429.48 |  | 4429.48 | 0 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6231 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | WB | 4799.55 |  | 4799.55 | 0 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE54 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6235 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 53.11 |  | 53.11 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 93.7 |  | 93.7 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 153.5 |  | 153.5 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 256.71 |  | 256.71 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 48.4 |  | 48.4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 434.34 |  | 434.34 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 31.55 |  | 31.55 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 425.26 |  | 425.26 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 516.03 |  | 516.03 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 46.53 |  | 46.53 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 21.82 |  | 21.82 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 54.11 |  | 54.11 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 87.13 |  | 87.13 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 47.45 |  | 47.45 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 56.35 |  | 56.35 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6237 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 401.96 |  | 401.96 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 58/3 | 55/0 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6236 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | NB | 79.62 |  | 79.62 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 55/5 | 58/3 | 45913553 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6238 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 87 |  | 87 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | 45893724 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6238 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 32 |  | 32 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | 45893724 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6238 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 52 |  | 52 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | 45893724 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6239 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 16 |  | 16 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | 45893724 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6238 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | NB | 31 |  | 31 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | 45893724 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6240 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 26.11 |  | 26.11 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | 45931371 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 6 |  | 6 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 12 |  | 12 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 5 |  | 5 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 7 |  | 7 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 5 |  | 5 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 13 |  | 13 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 7 |  | 7 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 13 |  | 13 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | CW | 11 |  | 11 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6242 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6241 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | NB | 2 |  | 2 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6243 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 2 |  | 2 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6243 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 1 |  | 1 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6244 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 1 |  | 1 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6244 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6245 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | EB | 2 |  | 2 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 55/5 | 58/3 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 4 |  | 4 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6246 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2023-12-29 | 2023-11-30 |  | 19dys | WB | 3 |  | 3 | 0 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 | 55/0 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6235 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE54 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6247 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | On ServiceNow
YNE54 Closure 2 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6248 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 221 |  | 221 | 0 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE55 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6249 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 137.74 |  | 137.74 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE55 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6249 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 113.15 |  | 113.15 | 0 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE55 Closure 1 WB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6250 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 136 |  | 136 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931284
YNE55 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6251 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 23.12 |  | 23.12 | 0 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931367
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/794 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6253 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 4 |  | 4 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 11 |  | 11 | 0 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 17 |  | 17 | 0 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 23 |  | 23 | 0 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6252 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 30 |  | 30 | 0 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6254 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6254 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6255 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 7 |  | 7 | 0 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6255 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6255 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6256 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE55 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6256 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 39 |  | 39 | 0 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE55 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6256 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE55 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6256 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE55 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6257 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 674 |  | 674 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE56 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6258 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 55.81 |  | 55.81 | 0 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6259 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 100 |  | 100 | 0 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931265
YNE56 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6260 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 93 |  | 93 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931265
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 186.46 |  | 186.46 | 0 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1531.22 |  | 1531.22 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3058.2 |  | 3058.2 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1898.82 |  | 1898.82 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1799.4 |  | 1799.4 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 954.48 |  | 954.48 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6261 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5064.4 |  | 5064.4 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6262 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 26 |  | 26 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6262 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 36 |  | 36 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6262 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6262 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 154 |  | 154 | 0 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45261 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6263 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 26 |  | 26 | 0 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 30 |  | 30 | 0 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 33 |  | 33 | 0 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 12 |  | 12 | 0 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 17 |  | 17 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 21 |  | 21 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 25 |  | 25 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 31 |  | 31 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 21 |  | 21 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 13 |  | 13 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 16 |  | 16 | 0 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6264 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 34 |  | 34 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6265 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6265 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6265 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6265 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6266 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 8 |  | 8 | 0 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 15 |  | 15 | 0 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 32 |  | 32 | 0 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 9 |  | 9 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6267 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE56 Closure Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6268 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure | Lane 1 & 2 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE56 Closure Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6269 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure | Lane 1 & 2 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE57 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6270 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 950 |  | 950 | 0 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE57 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6271 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 22 |  | 22 | 0 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931342
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 936.31 |  | 936.31 | 0 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 714.4 |  | 714.4 | 0 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1065.6 |  | 1065.6 | 0 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 309.96 |  | 309.96 | 0 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 367.84 |  | 367.84 | 0 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45261 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6272 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 279.94 |  | 279.94 | 0 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Enviroflow 45261 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6273 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 15 |  | 15 | 0 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6275 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 3 |  | 3 | 0 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 11 |  | 11 | 0 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 21 |  | 21 | 0 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 14 |  | 14 | 0 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 11 |  | 11 | 0 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 19 |  | 19 | 0 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 12 |  | 12 | 0 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 29 |  | 29 | 0 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6274 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 14 |  | 14 | 0 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6276 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6276 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | NB | 1 |  | 1 | 0 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 8 |  | 8 | 0 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 7 |  | 7 | 0 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6277 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6278 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 28 |  | 28 | 0 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6279 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 9 |  | 9 | 0 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6278 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | NB | 23 |  | 23 | 0 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6278 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6278 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 37 |  | 37 | 0 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6278 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 2 |  | 2 | 0 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE57 Closure Vaisala 45261 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6280 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE57 Closure Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6281 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2023-12-29 | 2023-12-31 |  | 19dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | On ServiceNow
YNE57 Closure 1 EB NS CGS 45261 Rock Scree - Removal of scrub encroachment | 6282 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 225 |  | 225 | 0 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE57 Closure 1 EB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6283 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | EB | 318 |  | 318 | 0 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE58 Closure 1 WB NS CGS 45261 Woodland - Thin / coppice | 6284 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | SB | 1378 |  | 1378 | 0 |  |  |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE58 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6285 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 66.87 |  | 66.87 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE58 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6285 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 51.92 |  | 51.92 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE58 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6286 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 75 |  | 75 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931379
YNE58 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6286 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 20 |  | 20 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931379
YNE58 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6286 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 66 |  | 66 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45931379
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6287 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6287 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 18 |  | 18 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6288 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | SB | 13 |  | 13 | 0 |  |  |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6287 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6287 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6288 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 8 |  | 8 | 0 |  |  |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6287 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 12 |  | 12 | 0 |  |  |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6289 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6289 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6289 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 1 |  | 1 | 0 |  |  |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6290 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6290 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 11 |  | 11 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6290 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6290 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6291 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 1 |  | 1 | 0 |  |  |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6292 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 18 |  | 18 | 0 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE58 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6292 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 24 |  | 24 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE58 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6293 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | SB | 7 |  | 7 | 0 |  |  |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually
YNE58 Closure 1 WB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6294 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | SB | 446 |  | 446 | 0 |  |  |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE58 Closure 1 WB NS CGS 45261 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6295 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | SB | 50 |  | 50 | 0 |  |  |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE58 Closure 1 EB NS CGS 45261 Wildlife structures and tunnels - Remove all material that could impair operation | 6296 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 5 |  | 5 | 0 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Annually
YNE59 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6297 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 1388.48 |  | 1388.48 | 0 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE59 Closure 1 EB NS CGS 45261 Woodland - Thin / coppice | 6297 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 21dys | EB | 3398.19 |  | 3398.19 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE59 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6298 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 135.01 |  | 135.01 | 0 |  |  |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE59 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6298 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 802.18 |  | 802.18 | 0 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE59 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6298 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 777.27 |  | 777.27 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6299 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 13 |  | 13 | 0 |  |  |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 WB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6300 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 14 |  | 14 | 0 |  |  |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6299 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 9 |  | 9 | 0 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6299 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 18 |  | 18 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6299 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 23 |  | 23 | 0 |  |  |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6301 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6302 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 3 |  | 3 | 0 |  |  |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 WB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6303 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 2 |  | 2 | 0 |  |  |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6302 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 10 |  | 10 | 0 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6302 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 11 |  | 11 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6304 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 9 |  | 9 | 0 |  |  |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE59 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6304 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE59 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6304 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE59 Closure 1 EB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6304 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 2 |  | 2 | 0 |  |  |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually
YNE60 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6305 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 293.8 |  | 293.8 | 0 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE60 Closure 1 EB NS Bettamix 45261 VRS - Check all Road Restraint System - ILM | 6305 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 54.41 |  | 54.41 | 0 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years
YNE60 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6306 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 1 |  | 1 | 0 |  |  |  | 2700A64/956 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6306 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 6 |  | 6 | 0 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6306 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | CW | 35 |  | 35 | 0 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6307 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 4 |  | 4 | 0 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB NS Amey 45261 Marker Posts - Clean all marker post faces and reference numbers | 6308 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | EB | 12 |  | 12 | 0 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 WB NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6309 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-12-01 | 2023-12-29 | 2024-02-29 |  | 19dys | WB | 1 |  | 1 | 0 |  |  |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually
YNE60 Closure 1 EB NS CGS 45261 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6310 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2023-12-29 | N/A | Removed following GC-898 | 19dys | CW | 970 |  | 970 | 0 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE114 Closure 1 CW NS Bettamix 45261 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6311 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 147.62 | 0 | 0 | 0 | 29/11 no assets for tension on NS | N |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45924216
YNE114 Closure 1 CW OS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6312 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | CW | 670 |  | 670 | 0 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW OS | Lane 2 Closure | 3 |  |  | Every 2 years |  |  | 52031739
YNE114 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6313 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 19.9745 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 25 | 25 | 0 | 1 |  | N |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12015334
YNE114 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6314 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 2 | 2 | 0 | 1 |  | N |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12015335
YNE114 Closure 1 CW NS Amey 45261 Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 6315 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 359.5413 | 4.4.1.3 | A40033 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 8 | 8 | 0 | 1 |  | N |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 12015336
YNE114 Closure 1 CW NS Amey 45261 Bollards - Clean all illuminated and non-illuminated bollards | 6316 | Bollards - Clean all illuminated and non-illuminated bollards | 26.3267 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-30 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | CW | 8 | 8 | 0 | 1 |  | N |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 12015337
YNE114 Closure Amey 45261 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6317 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE114 Closure Amey 45261 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6318 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
N/A Amey 45261 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 6319 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 6 |  | 6 | 0 |  |  |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | 2 times per year |  |  | On ServiceNow
YNE16 Closure 2 WB NS Amey 45293 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6320 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 22dys | WB | 202.06 |  | 202.06 | 0 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE16 Closure 1 WB NS Amey 45293 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6321 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 22dys | WB | 457 |  | 457 | 0 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 12.7837 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 16 | 16 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.1959 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A63/404 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 10 |  | 10 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 14 | 14 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 17 |  | 17 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 2 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6324 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 23 |  | 23 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 17 |  | 17 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 19.1755 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 24 | 24 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 2 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6325 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 5 |  | 5 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 11 |  | 11 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000A63/419 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 |  | 3 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/474 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6322 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 10.3867 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 13 | 13 | 0 | 1 |  |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6323 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 2 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6325 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 2 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6324 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015338
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6326 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015355
YNE16 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6327 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015355
YNE16 Closure 2 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6328 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015355
YNE16 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6326 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015355
YNE16 Closure 2 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6329 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015355
YNE16 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6330 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6331 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6331 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 18 |  | 18 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 2 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6332 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 26 |  | 26 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6331 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 19 |  | 19 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6330 | Marker Posts - Clean all marker post faces and reference numbers | 8.3893 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 21 | 21 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 2 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6333 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 4 |  | 4 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE16 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6334 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 27 |  | 27 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 2 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6335 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 13 |  | 13 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6334 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 26 |  | 26 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6336 | Bollards - Clean all illuminated and non-illuminated bollards | 65.8168 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 20 | 20 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6334 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 2 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6335 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015367
YNE16 Closure 2 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6337 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 457 |  | 457 | 0 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE16 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6338 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 1258 |  | 1258 | 0 |  |  |  | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 9.5878 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 2 |  | 2 | 0 |  |  |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 3 |  | 3 | 0 |  |  |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 28.7633 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 36 | 36 | 0 | 1 |  | N |  | 2000A63/418 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 10 |  | 10 | 0 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 14 |  | 14 | 0 |  |  |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 5 |  | 5 | 0 |  |  |  | 2000A63/428 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015373
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 8 |  | 8 | 0 |  |  |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6340 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 3 |  | 3 | 0 |  |  |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015373 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6341 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015387 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6341 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | 12015387 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6342 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015387
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE17 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6344 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 5 |  | 5 | 0 |  |  |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE17 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6344 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE17 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6344 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 5.9924 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE17 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6344 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 14 |  | 14 | 0 |  |  |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 5.9924 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE17 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6344 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 |  |  |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 189/5 | 184/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6345 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 24 |  | 24 | 0 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 189/5 | 184/5 | 12015400 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6346 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 26 |  | 0 | 0 | 6/12 no bollards within closure | N |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015400
YNE17 Closure Amey 45293 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6347 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE17 Closure Amey 45293 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6348 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No assets | 20dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE17 Closure 2 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6349 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 45 |  | 45 | 0 |  |  |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE17 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6350 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 833 |  | 833 | 0 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6350 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 92 |  | 92 | 0 |  |  |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6351 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 229 |  | 229 | 0 |  |  |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 200.3 |  | 200.3 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 47.36 |  | 47.36 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE17 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6354 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 392.89 | 0 | 0 | 1 | 6/12 no tensionning within closure |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1485.28 |  | 1485.28 | 0 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 428.26 |  | 428.26 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1223.13 |  | 1223.13 | 0 |  |  |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 547.51 |  | 547.51 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 191.27 |  | 191.27 | 0 |  |  |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 369.34 |  | 369.34 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1320.4 |  | 1320.4 | 0 |  |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1484.78 |  | 1484.78 | 0 |  |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 397.86 |  | 397.86 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905737
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 224.17 |  | 224.17 | 0 |  |  |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE17 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6357 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 310 | 0 | 0 | 0 | 11/30/2023: Non NH asset |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6358 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 48 |  | 48 | 0 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6359 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 658.28 |  | 658.28 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6358 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 433 |  | 433 | 0 |  |  |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6359 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | EB | 0 |  | 0 | 0 |  |  |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6358 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 75 |  | 75 | 0 |  |  |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6360 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | WB | 0 |  | 0 | 0 |  |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6360 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | WB | 0 |  | 0 | 0 |  |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45854302
YNE18 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6361 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 34 |  | 34 | 0 |  |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45854302
YNE18 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6360 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | WB | 0 |  | 0 | 0 |  |  |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6361 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 209 |  | 209 | 0 |  |  |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45854302
YNE18 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6362 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 119.03 |  | 119.03 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903015
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6363 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 52.8 |  | 52.8 | 0 |  |  |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45903015
YNE18 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6364 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 50.94 |  | 50.94 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903015
YNE17 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6365 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 269.88 | 0 | 0 | 1 | 6/12 no v-channel in closure |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854332
YNE18 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6366 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 365.79 |  | 365.79 | 0 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031508
YNE18 Closure 1 WB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6367 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 8.42 |  | 0 | 0 | 11/30/2023: non NH asset | N |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854332
YNE18 Closure 1 WB NS Enviroflow 45293 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6368 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45903168
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 |  | 12 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6339 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.9796 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 20 | 20 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 6 |  | 6 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 10 |  | 10 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 8 |  | 8 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 34 |  | 34 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 13 |  | 13 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015402
YNE17 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6342 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015411
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6371 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015411
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6372 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015411
YNE17 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6343 | Marker Posts - Clean all marker post faces and reference numbers | 4.7939 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-12-07 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6373 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 |  | 12 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6374 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 12 |  | 12 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6374 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 12 |  | 12 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6375 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 5 |  | 5 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015418
YNE18 Closure Amey 45293 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6376 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 0 | 0 | No jobs for MIDAS |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE18 Closure Amey 45293 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6377 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No assets | 20dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE17 Closure 1 EB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6378 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | EB | 862 |  | 862 | 0 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE18 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6379 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 331 |  | 331 | 0 |  |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 745.48 |  | 745.48 | 0 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 732.83 |  | 732.83 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 298.64 |  | 298.64 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1080.42 |  | 1080.42 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1626.21 |  | 1626.21 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 38.06 |  | 38.06 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 81.71 |  | 81.71 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 67.19 |  | 67.19 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 61.64 |  | 61.64 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 350.62 |  | 350.62 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 171.45 |  | 171.45 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 119.27 |  | 119.27 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6355 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 113.48 |  | 113.48 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6352 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 522 |  | 522 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/611 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 179.57 |  | 179.57 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 520.08 |  | 520.08 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6353 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 111.31 |  | 111.31 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45905839
YNE18 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 56.35 |  | 56.35 | 0 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6358 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 50 |  | 50 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45902833
YNE18 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6359 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | EB | 0 |  | 0 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854301
YNE18 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6358 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 32 |  | 32 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE18 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6360 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A |  | 22dys | WB | 0 |  | 0 | 0 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45854301
YNE18 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6361 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 38 |  | 38 | 0 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 7 |  | 7 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 25 |  | 25 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 18 |  | 18 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 12 |  | 12 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 7 |  | 7 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 6 |  | 6 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6369 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 8 |  | 8 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 6 |  | 6 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 16 |  | 16 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6370 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 3 |  | 3 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015419
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6371 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 |  | 3 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015430
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6372 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015430
YNE18 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6371 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 |  | 3 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015430
YNE18 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6372 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015430
YNE18 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6374 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 6 |  | 6 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6373 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 16 |  | 16 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6374 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6373 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 4 |  | 4 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6373 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 7 |  | 7 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE18 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6374 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 4 |  | 4 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE19 Closure Amey 45293 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 6380 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 126dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE19 Closure Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6381 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE19 Closure Amey 45293 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 6382 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE19 Closure Amey 45293 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6383 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE19 Closure Amey 45293 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6384 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE19 Closure Amey 45293 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6385 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No assets | 20dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE18 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6379 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 2329 |  | 2329 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 151.16 |  | 151.16 | 0 |  |  |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6387 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 262.99 |  | 262.99 | 0 |  |  |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 163.33 |  | 163.33 | 0 |  |  |  | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6389 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 140.83 |  | 140.83 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906249
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 452.27 |  | 452.27 | 0 |  |  |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 60.48 |  | 60.48 | 0 |  |  |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6389 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 678.18 |  | 678.18 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906249
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1114.08 |  | 1114.08 | 0 |  |  |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1585.98 |  | 1585.98 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6389 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 667.15 |  | 667.15 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906249
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1477.82 |  | 1477.82 | 0 |  |  |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 73.77 |  | 73.77 | 0 |  |  |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6387 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 218.47 |  | 218.47 | 0 |  |  |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6389 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 24.68 |  | 24.68 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906249
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 152.98 |  | 152.98 | 0 |  |  |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6386 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 72.24 |  | 72.24 | 0 |  |  |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 191/1 | 195/5 | 45906249 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6389 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 132.07 |  | 132.07 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years |  |  | 45906249
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1166.37 |  | 1166.37 | 0 |  |  |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6388 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 30.89 |  | 30.89 | 0 |  |  |  | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE20 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6390 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 166.1064 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 22dys | EB | 134.48 | 134.48 | 0 | 1 |  |  |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | No assets on Confirm | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6391 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 514.8 |  | 514.8 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 191/1 | 195/5 | 45854546 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6392 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 105.2601 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 22dys | EB | 1363.5 | 1363.5 | 0 | 1 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031553
YNE20 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6392 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 160.5836 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 22dys | EB | 2080.14 | 2080.14 | 0 | 1 |  |  |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031553
YNE20 Closure 1 WB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6393 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 18.2405 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 22dys | WB | 236.28 | 236.28 | 0 | 1 |  |  |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031553
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 13 |  | 13 | 0 |  |  |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 2 |  | 2 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 13 |  | 13 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 13 |  | 13 | 0 |  |  |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 7 |  | 7 | 0 |  |  |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 33 |  | 33 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 21 |  | 21 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 23 |  | 23 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 22 |  | 22 | 0 |  |  |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 35 |  | 35 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6394 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 9 |  | 9 | 0 |  |  |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015440 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 9 |  | 9 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6395 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 11 |  | 11 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015440
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6396 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015453 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6397 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 12015453
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6396 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015453 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6396 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | 12015453 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6398 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE20 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6399 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 3 |  | 3 | 0 |  |  |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6399 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 7 |  | 7 | 0 |  |  |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6398 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 10 |  | 10 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE20 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6399 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 14 |  | 14 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6398 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 13 |  | 13 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE20 Closure 1 EB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6399 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 191/1 | 195/5 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6398 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 20 |  | 20 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | Jobs already closed
YNE20 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6400 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-08 | 2023-12 | 2023-12-09 | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 191/1 | 195/5 | 12015465 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6401 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015465
YNE20 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6401 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-12-31 |  | 22dys | WB | 1 |  | 1 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 12015465
YNE20 Closure Amey 45293 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6402 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE20 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6403 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 742 |  | 742 | 0 |  |  |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE20 Closure 1 EB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6404 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | EB | 409 |  | 409 | 0 |  |  |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6403 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 868 |  | 868 | 0 |  |  |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE20 Closure 1 WB NS CGS 45293 Shrubs (Ornamental) - Maintain design requirements / amenity function | 6405 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 0 | 4.8.14 | A40090 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 7062 |  | 7062 | 0 |  |  |  | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Annually (Sept - Feb)
YNE20 Closure 1 WB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6406 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | WB | 318 |  | 318 | 0 |  |  |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE23 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6407 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 377.92 |  | 377.92 | 0 |  |  |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE23 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6407 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 95.28 |  | 95.28 | 0 |  |  |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE23 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6408 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 262.98 |  | 262.98 | 0 |  |  |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE23 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6409 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 42.6 |  | 42.6 | 0 |  |  |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6410 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 15 |  | 15 | 0 |  |  |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6410 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 6 |  | 6 | 0 |  |  |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6411 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 12 |  | 12 | 0 |  |  |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6410 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 9 |  | 9 | 0 |  |  |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6411 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 23 |  | 23 | 0 |  |  |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6411 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 9 |  | 9 | 0 |  |  |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6410 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 5 |  | 5 | 0 |  |  |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6410 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 29 |  | 29 | 0 |  |  |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6411 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 6 |  | 6 | 0 |  |  |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6411 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 21 |  | 21 | 0 |  |  |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6412 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6413 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6413 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6412 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Marker Posts - Clean all marker post faces and reference numbers | 6414 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 6 |  | 6 | 0 |  |  |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE23 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6415 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 10 |  | 10 | 0 |  |  |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE23 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6415 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE23 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6416 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE23 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6417 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE23 Closure 1 EB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6418 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | EB | 34 |  | 34 | 0 |  |  |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years
YNE24 Closure Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6419 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 355.21 |  | 355.21 | 0 |  |  |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE24 Closure Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6419 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 355.81 |  | 355.81 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 6 |  | 6 | 0 |  |  |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 74 |  | 74 | 0 |  |  |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 17 |  | 17 | 0 |  |  |  | 2000A63/355 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 84 |  | 84 | 0 |  |  |  | 2000A63/355 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 43 |  | 43 | 0 |  |  |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 48 |  | 48 | 0 |  |  |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6420 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 99 |  | 99 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6421 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 55.41 |  | 55.41 | 0 |  |  |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6422 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1243.98 |  | 1243.98 | 0 |  |  |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6421 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1005.09 |  | 1005.09 | 0 |  |  |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6423 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 491.07 |  | 491.07 | 0 |  |  |  | 2000A63/355 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6423 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1554.21 |  | 1554.21 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6423 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1409.37 |  | 1409.37 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6424 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 4 |  | 4 | 0 |  |  |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6424 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 39 |  | 39 | 0 |  |  |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6425 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 13 |  | 13 | 0 |  |  |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6425 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 3 |  | 3 | 0 |  |  |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6426 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 44 |  | 44 | 0 |  |  |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6425 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 22 |  | 22 | 0 |  |  |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6426 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 2 |  | 2 | 0 |  |  |  | 2000A63/382 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6425 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6425 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 20 |  | 20 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6427 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 3 |  | 3 | 0 |  |  |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6427 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 1 |  | 1 | 0 |  |  |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6427 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Every 2 years
YNE24 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6428 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 29 |  | 29 | 0 |  |  |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE24 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6429 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 6 |  | 6 | 0 |  |  |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE24 Closure Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6430 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Annually
YNE24 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6431 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE24 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6432 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE24 Closure CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6433 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | EB | 413 |  | 413 | 0 |  |  |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE25 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6434 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 60.81 |  | 60.81 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6435 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 392.51 |  | 392.51 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6434 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 804.47 |  | 804.47 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6435 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 927.64 |  | 927.64 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6434 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 52.07 |  | 52.07 | 0 |  |  |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6434 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 47 |  | 47 | 0 |  |  |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6436 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 308.33 |  | 308.33 | 0 |  |  |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6437 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 439.5 |  | 439.5 | 0 |  |  |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6436 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 613.08 |  | 613.08 | 0 |  |  |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6437 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 150.36 |  | 150.36 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB OS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6436 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 386.13 |  | 386.13 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6437 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 61 |  | 61 | 0 |  |  |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 WB NS Bettamix 45293 VRS - Check all Road Restraint System - ILM | 6437 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 257.09 |  | 257.09 | 0 |  |  |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 2 Closure | 4 |  |  | ILM Every 2 years
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6438 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 156 |  | 156 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6439 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 96 |  | 96 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6439 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 543 |  | 543 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6438 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 1772 |  | 1772 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6438 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 135 |  | 135 | 0 |  |  |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 131 |  | 131 | 0 |  |  |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 172 |  | 172 | 0 |  |  |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 275 |  | 275 | 0 |  |  |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6441 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 231 |  | 231 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 91 |  | 91 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 92 |  | 92 | 0 |  |  |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6441 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 119 |  | 119 | 0 |  |  |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6440 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 20 |  | 20 | 0 |  |  |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6438 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 120 |  | 120 | 0 |  |  |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6438 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 167 |  | 167 | 0 |  |  |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931228
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6442 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 48.48 |  | 48.48 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 EB OS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6443 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 68.08 |  | 68.08 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6442 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 1063.61 |  | 1063.61 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6444 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 160.58 |  | 160.58 | 0 |  |  |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6444 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 198.06 |  | 198.06 | 0 |  |  |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6444 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 116.63 |  | 116.63 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE25 Closure 1 WB NS Enviroflow 45293 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6445 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 24 |  | 24 | 0 |  |  |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6446 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6446 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 7 |  | 7 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6446 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 14 |  | 14 | 0 |  |  |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6446 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 12 |  | 12 | 0 |  |  |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 8 |  | 8 | 0 |  |  |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6447 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 3 |  | 3 | 0 |  |  |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6448 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6448 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6449 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6449 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | WB | 2 |  | 2 | 0 |  |  |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | No Jobs rasied
YNE25 Closure Amey 45293 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 6450 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 126dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE25 Closure Amey 45293 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 6451 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE25 Closure Amey 45293 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6452 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE25 Closure Amey 45293 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6453 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No assets | 20dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE26 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6454 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 74.39 |  | 74.39 | 0 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894795
YNE26 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6454 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 649.54 |  | 649.54 | 0 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894795
YNE26 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6454 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 55.98 |  | 55.98 | 0 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894795
YNE26 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6455 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 394.32 |  | 394.32 | 0 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894795
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 12 |  | 12 | 0 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895074
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 40 |  | 40 | 0 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895074
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6456 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 13 |  | 13 | 0 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895074
YNE26 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6457 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 29 |  | 29 | 0 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895074
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 1 |  | 1 | 0 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895068
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895068
YNE26 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6458 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 2 |  | 2 | 0 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895068
YNE26 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6459 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895068
YNE26 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6460 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 1 |  | 1 | 0 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually
YNE26 Closure 1 WB NS Amey 45293 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6461 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys |  | 11 |  | 11 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 7 | TBC - on Southcoates rbt |  | Every 3 years |  |  | 52038689
YNE26 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6462 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE26 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6463 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE27 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6464 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 253.53 |  | 253.53 | 0 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45902940
YNE27 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6464 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 175.54 |  | 175.54 | 0 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45902940
YNE27 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6465 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 207.34 |  | 207.34 | 0 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45902940
YNE27 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6466 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 26 |  | 26 | 0 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6466 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 17 |  | 17 | 0 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6467 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 17 |  | 17 | 0 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6468 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6468 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 1 |  | 1 | 0 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6469 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE27 Closure 1 EB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6470 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 10 |  | 10 | 0 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually
YNE27 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6471 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 7 |  | 7 | 0 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Annually
YNE27 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6472 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE27 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6473 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE27 Closure 1 EB NS CGS 45293 Shrubs (Ornamental) - Maintain design requirements / amenity function | 6474 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 0 | 4.8.14 | A40090 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | CW | 515 |  | 515 | 0 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually (Sept - Feb)
YNE28 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6475 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 248.42 |  | 248.42 | 0 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45902950
YNE28 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6476 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 740.52 |  | 740.52 | 0 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45902950
YNE28 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6477 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 98 |  | 98 | 0 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6477 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 14 |  | 14 | 0 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6478 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 34 |  | 34 | 0 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6479 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6479 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | CW | 4 |  | 4 | 0 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6480 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No Jobs rasied
YNE28 Closure 1 WB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6481 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | WB | 1 |  | 1 | 0 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Annually
YNE27 Closure 1 EB NS Amey 45293 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 6482 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 22.4713 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 22dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually
YNE27 Closure 1 WB NS Amey 45293 Electrical Testing - Network cabling and electrical components | 6483 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 7 | No TM required |  | Every 6 years |  |  | 52038619
YNE28 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6484 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE28 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6485 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE28 Closure 1 EB NS CGS 45293 Shrubs (Ornamental) - Maintain design requirements / amenity function | 6486 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 0 | 4.8.14 | A40090 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Removed following GC-898 | 22dys | EB | 213 |  | 213 | 0 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually (Sept - Feb)
YNE29 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6487 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 172.6 |  | 172.6 | 0 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6487 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 428.18 |  | 428.18 | 0 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6487 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 39.44 |  | 39.44 | 0 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6488 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1010.0647 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 1464.96 | 817.75 | 647.21 | 0.55821 | 26/10 Everthing on the tablet in this section completed. 2 at End of day due to other works at the location. |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB OS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6489 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 655.3841 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 530.6 | 530.6 | 0 | 1 | 26/10 No drainage on the O/S and no jobs on the tablet. |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6488 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No quants | 22dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6488 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No quants | 22dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6488 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | No quants | 22dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45893675
YNE29 Closure 1 WB NS Amey 45293 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6490 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | N/A | Removed following updated instruction GC-928 | 22dys | WB | 215.81 |  | 215.81 | 0 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45894774
YNE29 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6491 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 15 |  | 15 | 0 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895072
YNE29 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6491 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 33 |  | 33 | 0 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895072
YNE29 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6491 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 32 |  | 32 | 0 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895072
YNE29 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6492 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 14 | 0 | 14 | 0 | 26/10 - not resourced |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894894
YNE29 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6492 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 17 | 0 | 17 | 0 | 26/10 - not resourced |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894894
YNE29 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6492 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 14 | 0 | 14 | 0 | 26/10 - not resourced |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894894
YNE29 Closure 1 EB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6493 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 | Subject to roadspace | 22dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45895030
YNE29 Closure 1 WB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6494 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 22dys | WB | 1 | 0 | 1 | 0 | 26/10 - not resourced |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | 45894927
YNE29 Closure 1 WB NS Amey 45293 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 6495 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 44.9427 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | 2023-10-31 |  | 21dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Annually |  |  | 52038595
YNE29 Closure 1 WB NS Amey 45293 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6496 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 3 years
YNE29 Closure 1 WB NS Amey 45293 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6496 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 3 years
YNE29 Closure 1 WB NS Amey 45293 BC - Lamps (LED) for Illuminated Signs and Bollards | 6497 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-01-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years
YNE29 Closure Amey 45293 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6498 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE29 Closure Amey 45293 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6499 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | On ServiceNow
YNE32 Closure 1 CW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6500 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | CW | 1006 |  | 1006 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | ACW | 507 |  | 507 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | ACW | 914 |  | 914 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6500 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | CW | 416 |  | 416 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | WB | 648 |  | 648 | 0 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | WB | 554 |  | 554 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6501 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | WB | 1625 |  | 1625 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6500 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | CW | 1084 |  | 1084 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 6500 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 5 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 23dys | CW | 374 |  | 374 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 7 | No | Days | 6 times per year (ILM Certain Sections)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 186.46 |  | 186.46 | 0 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 1531.22 |  | 1531.22 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 778.4 |  | 778.4 | 0 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 3058.2 |  | 3058.2 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 2962.98 |  | 2962.98 | 0 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 1898.82 |  | 1898.82 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 1843.26 |  | 1843.26 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 538.1 |  | 538.1 | 0 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 1799.4 |  | 1799.4 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 2093.24 |  | 2093.24 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 954.48 |  | 954.48 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 253.02 |  | 253.02 | 0 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6502 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys | EB | 5064.4 |  | 5064.4 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 6503 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 3 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Single carriageway no offside assets | 43dys | EB | 5423.6 |  | 5423.6 | 0 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6504 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1000 |  | 1000 | 0 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6504 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 100 |  | 100 | 0 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6504 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 700 |  | 700 | 0 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 56.3549 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 730 | 730 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 50.951 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 660 | 660 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 30.1074 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 390 | 390 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 128.9214 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 1670 | 1670 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 14.6677 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 190 | 190 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 16.9837 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 220 | 220 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6505 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2.316 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 30 | 30 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031622
YNE61 Closure 1 NB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6506 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 10 |  | 10 | 0 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually
YNE61 Closure 1 SB NS Amey 45293 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6507 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-12 | 2024-1 | 2024-01-13 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 3 | Yes J31 SB entry verge |  | Every 6 years | 244/8 | 238/8 | 52038686 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE62 Closure 1 NB NS CGS 45293 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 6508 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-01-02 | 2024-02-29 | 2023-11-30 |  | 43dys | NB | 2868 |  | 2868 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M1/426 | YNE61: M1 J30-31 | YNE62 Closure 1 NB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013804
YNE61 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6509 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 4094 |  | 4094 | 0 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE61 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6510 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 2046 |  | 2046 | 0 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6510 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1809 |  | 1809 | 0 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6511 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 99 |  | 99 | 0 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE62 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6512 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 620 |  | 620 | 0 |  |  |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031629
YNE62 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6512 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 480 |  | 480 | 0 |  |  |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031629
YNE62 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6513 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 480 |  | 480 | 0 |  |  |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031629
YNE62 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6513 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 420 |  | 420 | 0 |  |  |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031629
YNE62 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6513 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 300 |  | 300 | 0 |  |  |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031629
YNE62 Closure 1 SB NS Amey 45293 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6514 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 3 | Yes J31 SB exit slip |  | Every 6 years |  |  | 52038602
YNE62 Closure 1 NB NS CGS 45293 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 6508 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-01-02 | 2024-02-29 | 2023-11-30 |  | 43dys | NB | 2996 |  | 2996 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013823
YNE62 Closure 1 SB NS CGS 45293 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 6515 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-01-02 | 2024-02-29 | 2023-11-30 |  | 43dys | SB | 2236.6328 |  | 2236.6328 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013803
YNE62 Closure 1 SB NS CGS 45293 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 6515 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-01-02 | 2024-02-29 | 2023-11-30 |  | 43dys | SB | 1752 |  | 1752 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013821
YNE62 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6516 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 6619 |  | 6619 | 0 |  |  |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE62 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6517 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1462 |  | 1462 | 0 |  |  |  | 4400M1/918 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE63 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6518 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 93.61 |  | 93.61 | 0 |  |  |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE63 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6519 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 724.87 |  | 724.87 | 0 |  |  |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE63 Closure 1 NB OS Enviroflow 45293 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6520 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 7 |  | 7 | 0 |  |  |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | Every 2 years
YNE63 Closure 1 NB OS Enviroflow 45293 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6520 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2 |  | 2 | 0 |  |  |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | Every 2 years
YNE63 Closure 1 SB OS Enviroflow 45293 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6521 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 |  | 1 | 0 |  |  |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | Every 2 years
YNE63 Closure 1 SB OS Enviroflow 45293 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 6521 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 |  | 5 | 0 |  |  |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | Every 2 years
YNE63 Closure 1 NB NS Amey 45293 BC - Lamps (LED) for Road Lighting | 6522 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 3 | Yes NB exit slip verge |  | Every 6 years |  |  | 52038606
YNE63 Closure 1 SB NS Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6523 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE63 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6524 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 5039 |  | 5039 | 0 |  |  |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE63 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6524 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 3542 |  | 3542 | 0 |  |  |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6525 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 150 |  | 150 | 0 |  |  |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6525 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1250 |  | 1250 | 0 |  |  |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6525 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 80 |  | 80 | 0 |  |  |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6525 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 500 |  | 500 | 0 |  |  |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6526 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 95.53 |  | 95.53 | 0 |  |  |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 SB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6527 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 4 |  | 4 | 0 |  |  |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually
YNE64 Closure 1 NB NS Amey 45293 BC - Lamps (LED) for Road Lighting | 6528 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 | Yes NE entry J33 verge |  | Every 6 years |  |  | 52038598
YNE64 Closure Amey 45293 BC - Lamps (LED) for Illuminated Signs and Bollards | 6529 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 Closure | 3 | No TM required |  | Every 2 years |  |  | 52038585
Unsure on location Amey 45293 Electrical Testing - Network cabling and electrical components | 6530 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 12 |  | 12 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | Unsure on location | Lane 1 Closure | 3 | Unsure of actual location |  | Every 6 years |  |  | 52038586
YNE64 Closure 1 SB NS Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6531 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE64 Closure 1 SB NS Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6532 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE64 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6533 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 10245 |  | 10245 | 0 |  |  |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6533 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 2582 |  | 2582 | 0 |  |  |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6533 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 12823 |  | 12823 | 0 |  |  |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6533 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 2442 |  | 2442 | 0 |  |  |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6534 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 4212 |  | 4212 | 0 |  |  |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6534 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 7936 |  | 7936 | 0 |  |  |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE64 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6535 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 250 |  | 250 | 0 |  |  |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE64 Closure 1 SB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6536 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 913 |  | 913 | 0 |  |  |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE65 Closure 1 NB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6537 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 20 |  | 20 | 0 |  |  |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931410
YNE65 Closure 1 SB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6538 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 54 |  | 54 | 0 |  |  |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931410
YNE66 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6539 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 120 |  | 120 | 0 |  |  |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6539 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 280 |  | 280 | 0 |  |  |  | 4400M1/502 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6540 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 892.27 |  | 892.27 | 0 |  |  |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6539 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 713.28 |  | 713.28 | 0 |  |  |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6541 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3162.04 |  | 3162.04 | 0 |  |  |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6541 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 804.67 |  | 804.67 | 0 |  |  |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6542 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 604.79 |  | 604.79 | 0 |  |  |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6543 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038663
YNE66 Closure 1 SB NS Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6544 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE66 Closure 1 SB NS Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6545 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE66 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6546 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 4098 |  | 4098 | 0 |  |  |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE66 Closure 2 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6547 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 3131 |  | 3131 | 0 |  |  |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE66 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6548 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 673 |  | 673 | 0 |  |  |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE66 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6549 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 182 |  | 182 | 0 |  |  |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE67 Closure 2 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6550 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 250 |  | 250 | 0 |  |  |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6551 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 420 |  | 420 | 0 |  |  |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 2 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6552 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 380 |  | 380 | 0 |  |  |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 2 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6552 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 783.6 |  | 783.6 | 0 |  |  |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 1 SB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6553 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1 |  | 1 | 0 |  |  |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45904962
YNE67 Closure Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6554 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE68 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6555 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 30 |  | 30 | 0 |  |  |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031653
YNE68 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6556 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038670
YNE68 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6557 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 932 |  | 932 | 0 |  |  |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE68 Closure 1 SB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6558 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 158 |  | 158 | 0 |  |  |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE69 Closure 1 SB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6559 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-18 | 2023-12 | 2023-12-19 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 16.59 |  | 16.59 | 0 |  |  |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS Amey 45293 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6560 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 | 0 | 3 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038634
YNE69 Closure 1 NB NS Amey 45293 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6561 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 | 0 | 2 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 3 | Yes |  | Every 3 years |  |  | 52038637
YNE69 Closure Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6562 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE69 Closure 1 SB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6563 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 4175 |  | 4175 | 0 |  |  |  | 4400M1/112 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6564 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1581 |  | 1581 | 0 |  |  |  | 4400M1/109 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6565 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1302 |  | 1302 | 0 |  |  |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6566 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 1114 |  | 1114 | 0 |  |  |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE69 Closure 1 SB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6567 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 226 |  | 226 | 0 |  |  |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6568 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 538 |  | 538 | 0 |  |  |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE69 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6568 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 334 |  | 334 | 0 |  |  |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE69 Closure 1 SB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6559 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-18 | 2023-12 | 2023-12-19 | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 1291.36 |  | 1291.36 | 0 |  |  |  | 4400M1/106 | YNE70: M1 J37-38 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 284/5 | 275/3 | 45901938 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE70 Closure 1 NB NS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6569 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6.1751 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | NB | 79.99 | 79.99 | 0 | 1 | 11/21/2023 No v-channel on NB NS withiin this closure | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6570 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 3.8553 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | NB | 49.94 | 49.94 | 0 | 1 |  |  |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031657
YNE70 Closure Amey 45293 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6571 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | No jobs raised
YNE70 Closure Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6572 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE70 Closure Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6573 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE70 Closure 1 SB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6574 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 6536 |  | 6536 | 0 |  |  |  | 4400M1/104 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE70 Closure 1 NB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6575 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 2542 |  | 2542 | 0 |  |  |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6575 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 6660 |  | 6660 | 0 |  |  |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6575 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 4172 |  | 4172 | 0 |  |  |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6576 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 3375 |  | 3375 | 0 |  |  |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE70 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6576 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 3224 |  | 3224 | 0 |  |  |  | 4400M1/104 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE70 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6576 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1814 |  | 1814 | 0 |  |  |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE70 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6577 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 2257 |  | 2257 | 0 |  |  |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE71 Closure Amey 45293 BC - Lamps (LED) for Illuminated Signs and Bollards | 6578 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 52038644
YNE71 Closure 1 SB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6579 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 3 |  | 3 | 0 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually
YNE71 Closure 1 NB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6580 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-11 | 2023-12 | 2023-12-12 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1 |  | 1 | 0 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 288/2 | 294/8 | 12015502 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6581 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure | Lane 1 Closure | 3 | Calder box bridge Access issues no TM required |  | Every 6 years |  |  | 52038620
YNE71 Closure 1 NB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6582 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 4000 |  | 4000 | 0 |  |  |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6583 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 380 |  | 380 | 0 |  |  |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE71 Closure 1 SB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6583 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1080 |  | 1080 | 0 |  |  |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE71 Closure 1 NB NS CGS 45293 Rock Scree - Removal of scrub encroachment | 6582 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 1594 |  | 1594 | 0 |  |  |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6584 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 938 |  | 938 | 0 |  |  |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE71 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6584 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 2768 |  | 2768 | 0 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE71 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6584 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 711 |  | 711 | 0 |  |  |  | 4700M1/196 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE71 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6585 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 6336 |  | 6336 | 0 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6586 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1103 |  | 1103 | 0 |  |  |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 3 | No |  | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 | No jobs raised emailed NH | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6587 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 765 |  | 765 | 0 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 3 | No | Days | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 SB NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6587 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 594 |  | 594 | 0 |  |  |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 3 | No | Days | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 NB NS Amey 45293 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6586 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 412 |  | 412 | 0 |  |  |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 3 | No |  | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 | No jobs raised emailed NH | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6588 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 31.6514 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | NB | 410 | 410 | 0 | 1 |  |  |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031658
YNE72 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6588 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 22.3876 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | NB | 290 | 290 | 0 | 1 |  |  |  | 4700M1/628 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031658
YNE72 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6589 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 32.8093 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys | SB | 425 | 425 | 0 | 1 |  |  |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | 52031658
YNE72 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6590 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure | Lane 1 Closure | 3 | Calder box bridge Access issues no TM required |  | Every 6 years |  |  | 52038671
YNE73 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6591 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1200 |  | 1200 | 0 |  |  |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6591 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1230 |  | 1230 | 0 |  |  |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6591 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 350 |  | 350 | 0 |  |  |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6592 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 395 |  | 395 | 0 |  |  |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6593 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 9 |  | 9 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038667
YNE73 Closure Vaisala 45293 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6594 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2024-01-02 | 2024-02-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE73 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6595 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 7485 |  | 7485 | 0 |  |  |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE73 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6596 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 6208 |  | 6208 | 0 |  |  |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE73 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6597 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 160 |  | 160 | 0 |  |  |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE74 Closure Amey 45293 BC - Lamps (LED) for Illuminated Signs and Bollards | 6598 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 3 |  |  | Every 2 years
YNE74 Closure 1 NB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6599 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 764.96 |  | 764.96 | 0 |  |  |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS | Lane 3 & 4 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6600 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 274.29 |  | 274.29 | 0 |  |  |  | 4700M1/703 | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 2 & 3 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure 1 SB OS Amey 45293 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6600 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1244.79 |  | 1244.79 | 0 |  |  |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 2 & 3 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure 1 NB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6601 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 |  | 1 | 0 |  |  |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually
YNE74 Closure 1 SB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6602 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 15 |  | 15 | 0 |  |  |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45293 Bollards - Clean all illuminated and non-illuminated bollards | 6602 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-01-02 | 2024-02-29 | 2023-12-31 |  | 43dys | SB | 2 |  | 2 | 0 |  |  |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6603 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 18 |  | 18 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE74 Closure Amey 45293 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6604 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE74 Closure 1 NB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6605 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 6471 |  | 6471 | 0 |  |  |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE74 Closure 1 SB NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6606 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 1982 |  | 1982 | 0 |  |  |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6607 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | NB | 866 |  | 866 | 0 |  |  |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years
YNE74 Closure 1 SB NS CGS 45293 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6608 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | SB | 588 |  | 588 | 0 |  |  |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE104 Closure 1 NB NS Enviroflow 45293 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6609 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 476 |  | 476 | 0 |  |  |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 2 CW NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6610 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 78 |  | 78 | 0 |  |  |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 1 NB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6611 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 |  | 5 | 0 |  |  |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 1 NB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6611 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 |  | 3 | 0 |  |  |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 1 SB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6612 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 |  | 4 | 0 |  |  |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 3 CW NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6613 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 73 |  | 73 | 0 |  |  |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 1 NB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6614 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 |  | 1 | 0 |  |  |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure 1 SB NS Amey 45293 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6615 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 |  | 1 | 0 |  |  |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure Amey 45293 BC - Lamps (LED) for Illuminated Signs and Bollards | 6616 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 3 |  |  | Every 2 years
YNE104 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 6617 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 154 |  | 154 | 0 |  |  |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE104 Closure 3 CW NS CGS 45293 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6618 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-02 | 2024-02-29 | N/A | Removed following GC-898 | 43dys | CW | 1132 |  | 1132 | 0 |  |  |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE76 Closure 1 EB NS Amey 45323 Electrical Testing - Network cabling and electrical components | 6619 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 4 | No TM required |  | Every 6 years | 0 | 0 | 52038748 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 27 |  | 27 | 0 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 24 |  | 24 | 0 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 22 |  | 22 | 0 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 2 |  | 2 | 0 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 5 |  | 5 | 0 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 25 |  | 25 | 0 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6620 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 29 |  | 29 | 0 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 12015505 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6621 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 7 |  | 7 | 0 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6621 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 21 |  | 21 | 0 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6621 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 17 |  | 17 | 0 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | Jobs already closed | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6622 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 2 |  | 2 | 0 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 12015515 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6622 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 32 |  | 32 | 0 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 12015515 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6622 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 9 |  | 9 | 0 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 12015515 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6622 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 6 |  | 6 | 0 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 12015515 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45323 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6623 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | EB | 105 |  | 105 | 0 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6624 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Single carriageway no offside assets | 21dys | EB | 456.67 |  | 456.67 | 0 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE77 Closure 1 EB OS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6624 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Single carriageway no offside assets | 21dys | EB | 1212.44 |  | 1212.44 | 0 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE77 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6625 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.3694 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 25.47 | 25.47 | 0 | 1 |  | N |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45847236 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6624 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Single carriageway no offside assets | 21dys | EB | 1463.31 |  | 1463.31 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE77 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6626 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.5012 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 14.58 | 14.58 | 0 | 1 |  | N |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45847253 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6627 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 112 |  | 112 | 0 |  | N |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45909974 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6627 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 51 |  | 51 | 0 |  | N |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45909974 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6627 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 40 |  | 40 | 0 |  | N |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45909974 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Enviroflow 45323 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6628 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Single carriageway no offside assets | 21dys | EB | 103.49 |  | 103.49 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years
YNE77 Closure 1 EB NS Amey 45323 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6629 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 111.7 |  | 111.7 | 0 |  | N |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 0 | 0 | 45909974 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6629 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-05 | 2023-12 | 2023-12-06 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 109.21 |  | 109.21 | 0 |  | N |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 0 | 0 | 45909974 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6630 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 35 |  | 35 | 0 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6630 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 34 |  | 34 | 0 |  |  |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6630 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 29 |  | 29 | 0 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6630 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 30 |  | 30 | 0 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6630 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 33 |  | 33 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6631 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 3 |  | 3 | 0 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6631 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 30 |  | 30 | 0 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6631 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 32 |  | 32 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6631 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 49 |  | 49 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45917240 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6632 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 1 |  | 1 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45923245 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6633 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 10 |  | 10 | 0 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6633 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 9 |  | 9 | 0 |  |  |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6633 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 19 |  | 19 | 0 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6633 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 14 |  | 14 | 0 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6633 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 16 |  | 16 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6634 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 5 |  | 5 | 0 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6634 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 22 |  | 22 | 0 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6634 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 10 |  | 10 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6634 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 34 |  | 34 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years | 0 | 0 | 45916368 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6635 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 1 |  | 1 | 0 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6635 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 43 |  | 43 | 0 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6635 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | EB | 21 |  | 21 | 0 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6636 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 25 |  | 25 | 0 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6636 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 20 |  | 20 | 0 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6636 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 65 |  | 65 | 0 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6636 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 1 |  | 1 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6636 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-06 | 2023-12 | 2023-12-31 | 2024-02-01 | 2024-02-29 | 2023-12-31 | Subject to roadspace - full closure was cancelled due to storm Babet | 21dys | WB | 83 |  | 83 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually | 0 | 0 | 45910317 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure Amey 45323 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6637 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-02-01 | 2024-02-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE77 Closure Vaisala 45323 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6638 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-02-01 | 2024-02-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE77 Closure 1 EB NS CGS 45323 Rock Scree - Removal of scrub encroachment | 6639 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | EB | 7920 |  | 7920 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45323 Rock Scree - Removal of scrub encroachment | 6640 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | WB | 1209 |  | 1209 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6641 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | WB | 1523 |  | 1523 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 1378.31 |  | 1378.31 | 0 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 596.03 |  | 596.03 | 0 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 1637 |  | 1637 | 0 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 10874.25 |  | 10874.25 | 0 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 11272.17 |  | 11272.17 | 0 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 8883.64 |  | 8883.64 | 0 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 3928.33 |  | 3928.33 | 0 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 1413.42 |  | 1413.42 | 0 |  |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6642 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 10400.31 |  | 10400.31 | 0 |  |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45323 Woodland - Thin / coppice | 6643 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | CW | 479.83 |  | 479.83 | 0 |  |  |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | Days | Yes | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 69.4546 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 404.86 | 404.86 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6645 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.6824 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 56.44 | 56.44 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031433 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 70.0344 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 408.24 | 408.24 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 64.2549 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 374.55 | 374.55 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 118.5717 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 691.17 | 691.17 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 16.5805 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 96.65 | 96.65 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.419 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 84.05 | 84.05 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 52.57 |  | 52.57 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 70.45 |  | 70.45 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6644 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 111.27 |  | 111.27 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 52031432 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6646 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 25 | 0 | 25 | 0 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6647 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 143.2804 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 116 | 116 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6648 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 292 |  | 292 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6649 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 281.62 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 228 | 228 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6648 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 304 |  | 304 | 0 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6649 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 1019.0198 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 825 | 825 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6648 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 146 |  | 146 | 0 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6649 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 95.1085 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 77 | 77 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6648 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 51 |  | 51 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6649 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 82.7568 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 67 | 67 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6646 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 180 |  | 180 | 0 |  |  | Cancelled due to storm Babet | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 | 45901521 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45323 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6647 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 37.0553 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 30 | 30 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 4 | Yes |  | 2 times per year (ILM Certain Sections) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6650 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 18.3766 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 23 | 23 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6650 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 5 | 5 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 14 | 14 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE81 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6652 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years |  |  | 45901151
YNE78 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6650 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 16.7786 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 21 | 21 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 10 |  | 10 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 9 |  | 9 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 17 |  | 17 | 0 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 5 |  | 5 | 0 |  |  | Cancelled due to storm Babet | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 32 |  | 32 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  | Cancelled due to storm Babet | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 23 |  | 23 | 0 |  |  | Cancelled due to storm Babet | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 9 |  | 9 | 0 |  |  | Cancelled due to storm Babet | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6651 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 40 |  | 40 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6650 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 11 |  | 11 | 0 |  |  | Cancelled due to storm Babet | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901151 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6653 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901818 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6653 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901818 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 8 | 8 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 8 | 8 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 2.7964 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 7 | 7 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 3.1959 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 8 | 8 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 4 |  | 4 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 10 |  | 10 | 0 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 3 |  | 3 | 0 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 20 |  | 20 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 4 |  | 4 | 0 |  |  | Cancelled due to storm Babet | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 3 |  | 3 | 0 |  |  | Cancelled due to storm Babet | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 5 |  | 5 | 0 |  |  | Cancelled due to storm Babet | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6654 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 2 years | 0 | 0 | 45901837 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 6.5817 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6656 | Bollards - Clean all illuminated and non-illuminated bollards | 6.5817 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6656 | Bollards - Clean all illuminated and non-illuminated bollards | 42.7809 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 13 | 13 | 0 | 1 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 36.1993 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6656 | Bollards - Clean all illuminated and non-illuminated bollards | 39.4901 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 12 | 12 | 0 | 1 |  |  |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 32.9084 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 14 |  | 14 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6655 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 8 |  | 8 | 0 |  |  | Cancelled due to storm Babet | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Annually | 0 | 0 | 45901369 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Amey 45323 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6657 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 876.382 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Not required | Not required | 2023-11-10 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 39 | 39 | 0 | 1 | 11/10/2023: works no longer required following upgrade for LED |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 4 | Yes |  | Every 6 years | 0 | 0 | 52038772 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Amey 45323 Electrical Testing - Network cabling and electrical components | 6658 | Electrical Testing - Network cabling and electrical components | 19.1755 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 4 | Yes |  | Every 6 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Vaisala 45323 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6659 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 4 | Yes |  | 2 times per year | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Amey 45323 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6660 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-17 | 2024-1 | 2024-01-18 | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 4 | Yes |  | Every 6 years | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6661 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 596 |  | 596 | 0 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 3 years (Sept - Feb) | 0 | 0 | 52038754 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45323 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6662 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 64 |  | 64 | 0 |  |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 3 years | 0 | 0 | 52038743 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE79 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6663 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 6797.53 |  | 6797.53 | 0 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45323 Woodland - Thin / coppice | 6664 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | EB | 1724.17 |  | 1724.17 | 0 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45323 Woodland - Thin / coppice | 6664 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | EB | 1280.15 |  | 1280.15 | 0 |  |  |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6665 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 111.4523 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 649.67 | 649.67 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908238 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6666 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.6235 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 32.78 | 32.78 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908238 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6665 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.2253 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 24.63 | 24.63 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908238 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6665 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.8669 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 28.37 | 28.37 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908238 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/105 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6668 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0.79898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/107 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6668 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 5.5929 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 13.5827 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 17 | 17 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6668 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6668 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6667 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4.7939 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901014 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6669 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901791 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6670 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901791 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6671 | Marker Posts - Clean all marker post faces and reference numbers | 5.9924 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 15 | 15 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901775 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6671 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901775 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6671 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901775 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6671 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901775 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6672 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901272 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6672 | Bollards - Clean all illuminated and non-illuminated bollards | 32.9084 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901272 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6673 | Bollards - Clean all illuminated and non-illuminated bollards | 39.4901 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 12 | 12 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901272 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6672 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901272 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure Amey 45323 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6674 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45323 Rock Scree - Removal of scrub encroachment | 6675 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 2501 |  | 2501 | 0 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years | 0 | 0 | 52036699 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6676 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 3062.82 |  | 3062.82 | 0 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6676 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | SB | 1321.2 |  | 1321.2 | 0 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45323 Woodland - Thin / coppice | 6677 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | CW | 831.79 |  | 831.79 | 0 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6676 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 6169.53 |  | 6169.53 | 0 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6676 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 6084.46 |  | 6084.46 | 0 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6676 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 11220.64 |  | 11220.64 | 0 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6678 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.751 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 56.84 | 56.84 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6679 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.4415 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 25.89 | 25.89 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6678 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 60.6351 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 353.45 | 353.45 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6679 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.07 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 52.87 | 52.87 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6678 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.232 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 82.96 | 82.96 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6678 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 27.0486 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 157.67 | 157.67 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45908230 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | SB | 9 | 9 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6681 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6681 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 13.5827 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 17 | 17 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 14.3817 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 18 | 18 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6681 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 13.5827 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 17 | 17 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 19.9745 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6680 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901005 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6682 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901768 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6682 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901768 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6683 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901758 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6683 | Marker Posts - Clean all marker post faces and reference numbers | 3.5954 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 9 | 9 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901758 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6683 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901758 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6683 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901758 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6683 | Marker Posts - Clean all marker post faces and reference numbers | 1.9975 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 0 | 0 | 45901758 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6684 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901208 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6684 | Bollards - Clean all illuminated and non-illuminated bollards | 16.4542 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901208 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6685 | Bollards - Clean all illuminated and non-illuminated bollards | 39.4901 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 12 | 12 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901208 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6684 | Bollards - Clean all illuminated and non-illuminated bollards | 32.9084 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901208 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6684 | Bollards - Clean all illuminated and non-illuminated bollards | 32.9084 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 0 | 0 | 45901208 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Amey 45323 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6686 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-16 | 2024-1 | 2024-01-17 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 17 |  | 17 | 0 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 4 | Yes |  | Every 6 years | 0 | 0 | 52038747 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure Amey 45323 BC - Lamps (LED) for Road Lighting | 6687 | BC - Lamps (LED) for Road Lighting | 629.1974 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 28 | 28 | 0 | 1 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | 4 |  |  | Every 6 years | 0 | 0 | Jobs rejected - Not in our maintenance | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure Amey 45323 Electrical Testing - Network cabling and electrical components | 6688 | Electrical Testing - Network cabling and electrical components | 1054.6546 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 55 | 55 | 0 | 1 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | 4 |  |  | Every 6 years | 0 | 0 | Jobs rejected - Not in our maintenance | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE81 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6689 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 992 |  | 992 | 0 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE81 Closure 1 EB NS CGS 45323 Woodland - Thin / coppice | 6690 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | EB | 1771.01 |  | 1771.01 | 0 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE81 Closure 1 WB NS CGS 45323 Woodland - Thin / coppice | 6689 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 43dys | WB | 30773.75 |  | 30773.75 | 0 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE81 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.9989 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 23.31 | 23.31 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031466
YNE81 Closure 1 EB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6692 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.2215 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 7.12 | 7.12 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031466
YNE81 Closure 1 WB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 103.6295 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 604.07 | 604.07 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 52031466
YNE81 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6693 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1.598 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901036
YNE81 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6652 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901491
YNE81 Closure 1 EB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6652 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 9 | 9 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901491
YNE81 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6693 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 43.145 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 54 | 54 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901036
YNE81 Closure 1 WB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6694 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 | No jobs raised |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE81 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6695 | Marker Posts - Clean all marker post faces and reference numbers | 1.1985 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901036
YNE81 Closure 1 EB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6696 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901755
YNE81 Closure 1 WB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6695 | Marker Posts - Clean all marker post faces and reference numbers | 5.9924 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 15 | 15 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45901036
YNE81 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6697 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 0 | 0 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 45901176
YNE81 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6698 | Bollards - Clean all illuminated and non-illuminated bollards | 59.2352 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 18 | 18 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 45901176
YNE81 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6697 | Bollards - Clean all illuminated and non-illuminated bollards | 69.1077 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 21 | 21 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | 45901176
YNE82 Closure 1 NB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6699 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 112.29 |  | 112.29 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6699 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 73.06 |  | 73.06 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6700 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | SB | 30.14 |  | 30.14 | 0 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Bettamix 45323 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6699 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 426.65 |  | 426.65 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6701 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 33 |  | 33 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6701 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 24 |  | 24 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6702 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | SB | 1 |  | 1 | 0 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6701 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 33 |  | 33 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6703 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 2 |  | 2 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6703 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 3 |  | 3 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6703 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | CW | 2 |  | 2 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6704 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 7 |  | 7 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6704 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 2 |  | 2 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6705 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | NB | 6 |  | 6 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS Amey 45323 Electrical Testing - Network cabling and electrical components | 6706 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-08 |  | 41dys |  | 15 |  | 15 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 3 | No TM required |  | Every 6 years | 0 | 0 | 52038758 | 0:00 | 0:00 |  | 0 | 0
YNE90 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6707 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 710.67 |  | 710.67 | 0 |  |  |  | 2000M180/103 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/3M18 SB J5 Exit Slip | 2/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6707 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 250.9 |  | 250.9 | 0 |  |  |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/3M18 SB J5 Exit Slip | 2/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6707 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 397.09 |  | 397.09 | 0 |  |  |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/3M18 SB J5 Exit Slip | 2/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6708 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 1393.06 |  | 1393.06 | 0 |  |  |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | TBC | Days | ILM Annually | 2/7 | 0/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6709 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 283/3M18 SB J5 Exit Slip | 2/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6710 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | WB | 1 |  | 1 | 0 |  |  |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually | 2/7 | 0/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6711 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | CW | 10 |  | 10 | 0 |  |  |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6711 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | EB | 33 |  | 33 | 0 |  |  |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6710 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M180/198 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6710 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | WB | 10 |  | 10 | 0 |  |  |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually | 2/7 | 0/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6712 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 2755 |  | 2755 | 0 |  |  |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6713 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys |  | 4097.5 |  | 4097.5 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 2 times per year | 283/3M18 SB J5 Exit Slip | 2/5 | 52037250 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 70 |  | 70 | 0 |  |  |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 603 |  | 603 | 0 |  |  |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 716 |  | 716 | 0 |  |  |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 495 |  | 495 | 0 |  |  |  | 2000M180/198 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE91 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6716 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 651.07 |  | 651.07 | 0 |  |  |  | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6716 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 869.87 |  | 869.87 | 0 |  |  |  | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6717 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 1481.08 |  | 1481.08 | 0 |  |  |  | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6718 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 857.47 |  | 857.47 | 0 |  |  |  | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6717 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 42.77 |  | 42.77 | 0 |  |  |  | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6719 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 757.09 |  | 757.09 | 0 |  |  |  | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6718 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 656.09 |  | 656.09 | 0 |  |  |  | 2000M180/119 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6717 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 456.57 |  | 456.57 | 0 |  |  |  | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6718 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 1022.29 |  | 1022.29 | 0 |  |  |  | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6719 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 608.1 |  | 608.1 | 0 |  |  |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6716 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 793.03 |  | 793.03 | 0 |  |  |  | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6719 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 787.93 |  | 787.93 | 0 |  |  |  | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6716 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 789.85 |  | 789.85 | 0 |  |  |  | 2000M180/128 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 2/3 | 10/5 | 45904476 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6719 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 616.12 |  | 616.12 | 0 |  |  |  | 2000M180/131 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45904476
YNE91 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6720 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6721 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE91 Closure 2 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6722 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6721 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE91 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6721 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE91 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6723 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE91 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6724 | Bollards - Clean all illuminated and non-illuminated bollards | 16.4542 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually | 2/3 | 10/5 | 45902639 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6725 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 4 |  | 4 | 0 |  |  |  | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45902675
YNE91 Closure 1 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6726 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 857.58 |  | 857.58 | 0 |  |  |  | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 2/3 | 10/5 | 52038761 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6727 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 5711.47 |  | 5711.47 | 0 |  |  |  | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE91 Closure 2 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6728 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 202.88 |  | 202.88 | 0 |  |  |  | 2000M180/119 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 2/3 | 10/5 | 52038752 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6728 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 899.69 |  | 899.69 | 0 |  |  |  | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 2/3 | 10/5 | 52038723 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6727 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 3849.31 |  | 3849.31 | 0 |  |  |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE91 Closure 1 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6726 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 5569.02 |  | 5569.02 | 0 |  |  |  | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 2/3 | 10/5 | 52038715 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6727 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 10743.87 |  | 10743.87 | 0 |  |  |  | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE91 Closure 2 EB NS CGS 45323 Wildlife structures and tunnels - Remove all material that could impair operation | 6729 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | 2023-12-18 | 2023-12 | 2023-12-19 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | EB | 1 |  | 1 | 0 |  |  |  | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  |  | Days | Annually | 2/3 | 10/5 | 52038718 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45323 Wildlife structures and tunnels - Remove all material that could impair operation | 6730 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | WB | 2 |  | 2 | 0 |  |  |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Annually |  |  | 52037260
YNE91 Closure 1 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6731 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  | 41dys | EB | 8878.25 |  | 8878.25 | 0 |  |  |  | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  |  |  | 2 times per year | 2/3 | 10/5 | 52038717 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6732 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 466 |  | 466 | 0 |  |  |  | 2000M180/128 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6733 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 589 |  | 589 | 0 |  |  |  | 2000M180/131 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038726
YNE92 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6734 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 752.84 |  | 752.84 | 0 |  |  |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 939.32 |  | 939.32 | 0 |  |  |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 969.31 |  | 969.31 | 0 |  |  |  | 2000M180/130 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6734 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 505.85 |  | 505.85 | 0 |  |  |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6734 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 802.46 |  | 802.46 | 0 |  |  |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 203.25 |  | 203.25 | 0 |  |  |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6734 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 1387.99 |  | 1387.99 | 0 |  |  |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 621.81 |  | 621.81 | 0 |  |  |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6734 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 475.66 |  | 475.66 | 0 |  |  |  | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 479.73 |  | 479.73 | 0 |  |  |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6735 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 911.93 |  | 911.93 | 0 |  |  |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903179
YNE92 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6736 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6737 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6736 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6737 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6736 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6736 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6737 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6738 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB |  |  |  | 0 |  |  |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE92 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6739 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE92 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6740 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 8 |  | 8 | 0 |  |  |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45902627
YNE92 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6739 | Bollards - Clean all illuminated and non-illuminated bollards | 26.3267 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE92 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6740 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 4 |  | 4 | 0 |  |  |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45902627
YNE92 Closure 1 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6740 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 15 |  | 15 | 0 |  |  |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45902627
YNE92 Closure 1 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6739 | Bollards - Clean all illuminated and non-illuminated bollards | 13.1634 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | No jobs raised
YNE92 Closure Vaisala 45323 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6741 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE92 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6742 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 1157 |  | 1157 | 0 |  |  |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 52038740
YNE92 Closure 1 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6743 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 3672 |  | 3672 | 0 |  |  |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE92 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6742 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 2578 |  | 2578 | 0 |  |  |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 52038786
YNE92 Closure 1 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6742 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 891 |  | 891 | 0 |  |  |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 52038785
YNE92 Closure 2 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6744 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 2094 |  | 2094 | 0 |  |  |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE92 Closure 1 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6745 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 9924.1667 |  | 9924.1667 | 0 |  |  |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6746 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 653 |  | 653 | 0 |  |  |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE92 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6747 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.2413 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 477 | 477 | 0 | 1 |  |  |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52037301
YNE92 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6747 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.1797 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 778 | 778 | 0 | 1 |  |  |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52037301
YNE92 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6746 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 846 |  | 846 | 0 |  |  |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE93 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6748 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 253.14 |  | 253.14 | 0 |  |  |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903214
YNE93 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6748 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 631.11 |  | 631.11 | 0 |  |  |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903214
YNE93 Closure 2 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6749 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 759.77 |  | 759.77 | 0 |  |  |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903214
YNE93 Closure 1 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6750 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 539.47 |  | 539.47 | 0 |  |  |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45903214
YNE93 Closure 2 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6751 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6752 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 2 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6751 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6753 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 3 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6754 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 3 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6755 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 3 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6754 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/155 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 3 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6755 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6756 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6756 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6756 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE93 Closure 2 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6757 | Bollards - Clean all illuminated and non-illuminated bollards | 46.0718 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 14 | 14 | 0 | 1 |  |  |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45902675
YNE93 Closure 3 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6758 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys | EB | 15 |  | 15 | 0 |  |  |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | Days |  |  | Annually |  |  | No jobs raised
YNE93 Closure 2 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6759 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 1416 |  | 1416 | 0 |  |  |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE93 Closure 2 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6759 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 530 |  | 530 | 0 |  |  |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE93 Closure 3 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6760 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 10402 |  | 10402 | 0 | 28/9: not complete. Rain canelled closure. 1/9: Not complete |  |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE93 Closure 2 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6761 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 6214.5 |  | 6214.5 | 0 |  |  |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6762 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 479 |  | 479 | 0 | 28/9: not complete. Rain canelled closure. 1/9: Not complete |  |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE93 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6763 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 635 |  | 635 | 0 |  |  |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE94 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6764 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 166.68 |  | 166.68 | 0 |  |  |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45897713
YNE94 Closure 2 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6765 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 31.58 | 0 | 31.58 | 0 |  |  |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45897713
YNE94 Closure 2 EB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6764 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 501.22 |  | 501.22 | 0 |  |  |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45897713
YNE94 Closure 3 WB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6766 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | WB | 88.84 | 0 | 88.84 | 0 |  |  |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45897713
YNE94 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6767 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 1 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6767 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6768 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 1 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6768 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6769 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 2 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6770 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 2 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6769 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 3 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6771 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 3 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6772 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 3 EB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6772 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | EB | TBC |  |  | 0 |  |  |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 4 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6773 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 4 WB NS Amey 45323 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6773 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | No assets | 41dys | WB | TBC |  |  | 0 |  |  |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE94 Closure 2 EB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6774 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 5 |  | 5 | 0 |  |  |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45898608
YNE94 Closure 3 WB NS Amey 45323 Bollards - Clean all illuminated and non-illuminated bollards | 6775 | Bollards - Clean all illuminated and non-illuminated bollards | 19.7451 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | Complete |  | 41dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | 45898629
YNE94 Closure 3 EB NS Amey 45323 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 6776 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE94 Closure 1 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6777 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 1344 |  | 1344 | 0 |  |  |  | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 45819769
YNE94 Closure 2 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6778 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 359 |  | 359 | 0 |  |  |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE94 Closure 3 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6779 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 1250 | 0 | 1250 | 0 |  |  |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 52038696
YNE94 Closure 3 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6779 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 367 | 0 | 367 | 0 |  |  |  | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) |  |  | 52038696
YNE94 Closure 3 EB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6780 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | EB | 351 |  | 351 | 0 |  |  |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE94 Closure 4 WB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6781 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Removed following GC-898 | 41dys | WB | 589 |  | 589 | 0 |  |  |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE94 Closure 1 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6782 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys | EB | 4946.6875 | 0 | 4946.6875 | 0 | 13/10 incomplete |  |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6783 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 418 |  | 418 | 0 |  |  |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819769
YNE94 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6784 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 426 |  | 426 | 0 |  |  |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE94 Closure 1 EB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6783 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | EB | 419 |  | 419 | 0 |  |  |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819769
YNE94 Closure 1 WB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6784 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 41dys | WB | 560 |  | 560 | 0 |  |  |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | 2 times per year (ILM Certain Sections)
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 2.4985 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 194.19 | 194.19 | 0 | 1 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6786 | VRS - Check all Road Restraint System - ILM | 29.5927 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 4675.54 | 2300 | 2375.54 | 0.49192 |  | N |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6786 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A |  | 21dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6786 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A |  | 21dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 4.5638 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 354.71 | 354.71 | 0 | 1 |  | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 1.4226 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 110.57 | 110.57 | 0 | 1 |  | N |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 4.041 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 314.07 | 314.07 | 0 | 1 |  | N |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 18.3281 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 1424.49 | 1424.49 | 0 | 1 |  | N |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6786 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A |  | 21dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 6.5095 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 505.93 | 505.93 | 0 | 1 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 NB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6785 | VRS - Check all Road Restraint System - ILM | 15.5729 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 1210.35 | 1210.35 | 0 | 1 |  | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Bettamix 45323 VRS - Check all Road Restraint System - ILM | 6786 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A |  | 21dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM Every 2 years |  |  | 45906051
YNE95 Closure 1 SB NS Enviroflow 45323 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 6787 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 2 |  | 2 | 0 | 28/11 not in closure | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45939238
YNE95 Closure 1 SB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6788 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 25.87 |  | 25.87 | 0 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 NB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6789 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1173.8 |  | 1173.8 | 0 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 SB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6788 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 663.5 |  | 663.5 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 NB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6789 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 794.66 |  | 794.66 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 SB NS Amey 45323 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6788 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-02-01 | 2024-02-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 803.68 |  | 803.68 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 42 | 0 | 42 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6791 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 17 |  | 17 | 0 |  | N |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6791 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 10 |  | 10 | 0 |  | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6791 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 10 |  | 10 | 0 |  | N |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures |  |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6791 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 6 |  | 6 | 0 |  | N |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6790 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6791 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 11 |  | 11 | 0 |  | N |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015535
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6792 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 1 |  | 1 | 0 |  | N |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015542
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6792 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 3 |  | 3 | 0 |  | N |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015542
YNE95 Closure 1 NB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6793 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 2 | 2 | 0 | 1 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015542
YNE95 Closure 1 SB NS Amey 45323 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6792 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 1 |  | 1 | 0 |  | N |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015542
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 1 | 1 | 0 | 1 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 SB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6795 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 3 |  | 3 | 0 |  | N |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 SB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6795 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 8 |  | 8 | 0 |  | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 SB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6795 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 1 |  | 1 | 0 |  | N |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 2 | 2 | 0 | 1 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 2 | 2 | 0 | 1 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 1.598 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 4 | 4 | 0 | 1 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0.39949 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 12 | 1 | 11 | 0.083333 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 SB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6795 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 13 |  | 13 | 0 |  | N |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 4 |  | 4 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6794 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 10 |  | 10 | 0 | 28/11 Cleaned signs 9/9 - 11/0 then required for winter. Evidence captured on do-forms, No confirm jobs for signs in closures | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 SB NS Amey 45323 Marker Posts - Clean all marker post faces and reference numbers | 6795 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 10 |  | 10 | 0 |  | N |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 12015543 - 12015550
YNE95 Closure 1 NB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6796 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | NB | 2081 |  | 2081 | 0 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 SB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6797 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | SB | 1465 |  | 1465 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 NB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6796 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | NB | 1366 |  | 1366 | 0 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 SB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6797 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | SB | 794 |  | 794 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 NB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6796 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | NB | 5697 |  | 5697 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 SB NS CGS 45323 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6797 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-02-29 | N/A | Removed following GC-898 | 21dys | SB | 7710 |  | 7710 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 3 |  | Days | Every 3 years (Sept - Feb)
YNE95 Closure 1 NB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 6798 | Sweeping - Paved non-running areas - Full Sweep 02 | 60.554 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-28 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 8130 | 8130 | 0 | 1 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | 2 times per year |  |  | 52038706
YNE95 Closure 1 SB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6799 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.9573 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | SB | 761 | 761 | 0 | 1 |  | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | 2 times per year (ILM Certain Sections) |  |  | 45819793
YNE95 Closure 1 NB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6800 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 1.3084 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 100 | 100 | 0 | 1 |  | N |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | 2 times per year (ILM Certain Sections) |  |  | 45819793
YNE95 Closure 1 NB NS Amey 45323 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6800 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.9534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2024-02-01 | 2024-02-29 | 2023-11-30 |  | 21dys | NB | 455 | 455 | 0 | 1 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | 2 times per year (ILM Certain Sections) |  |  | 45819793
YNE30 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6801 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2023-03-31 | Should thi be March because doing other pick 3 here | 20dys | SB | 344 |  | 344 | 0 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | 4 times per year (ILM Certain Sections)
YNE31 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6802 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2023-03-31 | Should thi be March because doing other pick 3 here | 20dys | SB | 441 |  | 441 | 0 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | 4 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6803 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1006 |  | 1006 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6804 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 507 |  | 507 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6804 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 914 |  | 914 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6803 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 416 |  | 416 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6804 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 648 |  | 648 | 0 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6804 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 554 |  | 554 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6804 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1625 |  | 1625 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6803 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1084 |  | 1084 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 6803 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 6 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 374 |  | 374 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 8 | No | Days | 6 times per year (ILM Certain Sections)
YNE71 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6805 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 | Subject to share with scheme works and clash management | 20dys | NB | 1103 |  | 1103 | 0 |  |  |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | Days | No | Days | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6806 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 765 |  | 765 | 0 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 4 | No | Days | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6806 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 594 |  | 594 | 0 |  |  |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 4 | No | Days | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 6805 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 | Subject to share with scheme works and clash management | 20dys | NB | 412 |  | 412 | 0 |  |  |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | Days | No | Days | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE83 Closure 1 SB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6807 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 117.36 |  | 117.36 | 0 |  |  |  | 4400M18/131 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6808 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 65.64 |  | 65.64 | 0 |  |  |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 & 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6809 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 10 |  | 10 | 0 |  |  |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6809 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45352 Electrical Testing - Network cabling and electrical components | 6810 | Electrical Testing - Network cabling and electrical components | 38.3511 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | Complete |  | 20dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 6 years | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6811 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2579 |  | 2579 | 0 |  |  |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6811 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 3487 |  | 3487 | 0 |  |  |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6812 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2586 |  | 2586 | 0 |  |  |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6812 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 9997 |  | 9997 | 0 |  |  |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6813 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 228 |  | 228 | 0 |  |  |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6813 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 6845 |  | 6845 | 0 |  |  |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6813 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 596 |  | 596 | 0 |  |  |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6813 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 5158 |  | 5158 | 0 |  |  |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6814 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 59 |  | 59 | 0 |  |  |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6815 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4400M18/129 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 3 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6816 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-30 | 2024-1 | 2024-01-31 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6816 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-30 | 2024-1 | 2024-01-31 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6817 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-26 | 2024-1 | 2024-01-27 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 3 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6816 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-30 | 2024-1 | 2024-01-31 | 2024-03-01 | 2024-03-29 | 2024-01-30 |  | 20dys | CW | 4 |  | 4 | 0 |  |  |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6818 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-31 | 2024-1 | 2024-02-01 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 9 |  | 9 | 0 |  |  |  | 4400M18/292 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6819 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys |  |  |  | 0 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE84 Closure 3 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6820 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2867 |  | 2867 | 0 |  |  |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6821 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1549 |  | 1549 | 0 |  |  |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6821 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 4520 |  | 4520 | 0 |  |  |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6821 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 789 |  | 789 | 0 |  |  |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6822 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 2236 |  | 2236 | 0 |  |  |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6823 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 5151 |  | 5151 | 0 |  |  |  | 4400M18/122 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6823 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 839 |  | 839 | 0 |  |  |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6824 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 793 |  | 793 | 0 |  |  |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6825 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 507 |  | 507 | 0 |  |  |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6826 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 77 |  | 77 | 0 |  |  |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6826 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 269 |  | 269 | 0 |  |  |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6827 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 187 |  | 187 | 0 |  |  |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6828 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-31 | 2024-1 | 2024-02-01 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 10 |  | 10 | 0 |  |  |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6829 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 282 |  | 282 | 0 |  |  |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6830 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1212 |  | 1212 | 0 |  |  |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45352 Wildlife structures and tunnels - Remove all material that could impair operation | 6831 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-31 | 2024-1 | 2024-02-01 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6832 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-05 | 2024-2 | 2024-02-06 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | SB | 78.75 |  | 78.75 | 0 |  |  |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6833 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-02 | 2024-2 | 2024-02-03 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Annually | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45352 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6834 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys |  | 5 | 5 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45352 Electrical Testing - Network cabling and electrical components | 6835 | Electrical Testing - Network cabling and electrical components | 19.1755 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 6 years | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6836 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2050 |  | 2050 | 0 |  |  |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6836 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1515 |  | 1515 | 0 |  |  |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6837 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1470 |  | 1470 | 0 |  |  |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6838 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 3545 |  | 3545 | 0 |  |  |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6839 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 2924 |  | 2924 | 0 |  |  |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6840 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 33 |  | 33 | 0 |  |  |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6841 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 46 |  | 46 | 0 |  |  |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6842 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6843 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6844 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-05 | 2024-2 | 2024-02-06 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6843 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | SB | 14 |  | 14 | 0 |  |  |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6843 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4400M18/160 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6842 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | NB | 8 |  | 8 | 0 |  |  |  | 4400M18/253 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6842 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-02-06 | 2024-2 | 2024-02-07 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | NB | 15 |  | 15 | 0 |  |  |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45352 Electrical Testing - Network cabling and electrical components | 6845 | Electrical Testing - Network cabling and electrical components | 268.4575 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys |  | 14 | 14 | 0 | 1 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 6 years | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure Vaisala 45352 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6846 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE87 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6847 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1755 |  | 1755 | 0 |  |  |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6848 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2432 |  | 2432 | 0 |  |  |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6849 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1978 |  | 1978 | 0 |  |  |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6849 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 838 |  | 838 | 0 |  |  |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6850 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 92 |  | 92 | 0 |  |  |  | 4400M18/104 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6851 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 78 |  | 78 | 0 |  |  |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6852 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6853 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6853 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 7 |  | 7 | 0 |  |  |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6854 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys |  |  |  | 0 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE88 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6855 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 3459 |  | 3459 | 0 |  |  |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6855 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 148 |  | 148 | 0 |  |  |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6856 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | NB | 505 | 0 | 505 | 0 | 17/8: No litter pickers |  |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Certain Sections) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6857 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 621 |  | 621 | 0 |  |  |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Certain Sections) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6858 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-12 | 2023-12 | 2023-12-13 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 3 | No |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6859 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2023-12-13 | 2023-12 | 2023-12-14 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 10 |  | 10 | 0 |  |  |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 3 | No |  | Annually | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6860 | Bollards - Clean all illuminated and non-illuminated bollards | 3.2908 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | 2023-11-03 | 2024-03-01 | 2023-10-31 | 2023-10-31 |  | 20dys | NB | 1 | 1 | 0 | 1 |  | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | Days | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | 45905032 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6861 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 2075 |  | 2075 | 0 |  |  |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6862 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1034 |  | 1034 | 0 |  |  |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6863 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-12 | 2023-12 | 2023-12-13 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | NB | 604 |  | 604 | 0 |  |  |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Certain Sections) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6864 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-13 | 2023-12 | 2023-12-14 | 2024-03-01 | 2024-03-29 | 2023-12-31 |  | 20dys | SB | 469 |  | 469 | 0 |  |  |  | 2000M18/150 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Certain Sections) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6865 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 327.87 |  | 327.87 | 0 |  |  |  | 2000A180/132 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE96 Closure 1 EB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6865 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 111.89 |  | 111.89 | 0 |  |  |  | 2000A180/139 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE96 Closure 1 WB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6866 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 391.35 |  | 391.35 | 0 |  |  |  | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | 0 |  |  | 0 |  |  |  | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6868 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB | 0 |  |  | 0 |  |  |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | 0 |  |  | 0 |  |  |  | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | 0 |  |  | 0 |  |  |  | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6868 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 711.99 |  |  | 0 |  |  |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 478.72 |  |  | 0 |  |  |  | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6869 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 131.17 |  |  | 0 |  |  |  | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6870 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 88 |  |  | 0 |  |  |  | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6870 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB | 0 |  |  | 0 |  |  |  | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6871 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 88.11 |  | 88.11 | 0 |  |  |  | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6872 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 478.72 |  | 478.72 | 0 |  |  |  | 2000A180/132 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6873 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 131.17 |  | 131.17 | 0 |  |  |  | 2000A180/133 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6874 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 711.99 |  | 711.99 | 0 |  |  |  | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | 0 |  |  | 0 |  |  |  | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE96 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6870 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | 0 |  |  | 0 |  |  |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6875 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB | TBC |  |  | 0 |  |  |  | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 5 years | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6875 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | TBC |  |  | 0 |  |  |  | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 5 years | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 WB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6876 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB | TBC |  |  | 0 |  |  |  | 2000A180/133 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 5 years |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6877 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6877 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6877 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 17 |  | 17 | 0 |  |  |  | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs
YNE96 Closure 2 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6878 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-22 | 2024-1 | 2024-01-23 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 25 |  | 25 | 0 |  |  |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Annually | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6878 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-22 | 2024-1 | 2024-01-23 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 13 |  | 13 | 0 |  |  |  | 2000A180/909 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Annually | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure Vaisala 45352 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6879 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE96 Closure 1 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6880 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 1331 |  | 1331 | 0 |  |  |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 3028 |  | 3028 | 0 |  |  |  | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 1388 |  | 1388 | 0 |  |  |  | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 2 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6882 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 1559 |  | 1559 | 0 |  |  |  | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6883 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 1254 |  | 1254 | 0 |  |  |  | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6883 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 3398 |  | 3398 | 0 |  |  |  | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 496 |  | 496 | 0 |  |  |  | 2000A180/139 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 855 |  | 855 | 0 |  |  |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6881 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 826 |  | 826 | 0 |  |  |  | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE96 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6883 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 492 |  | 492 | 0 |  |  |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6884 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 26 |  | 26 | 0 |  |  |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years
YNE97 Closure 2 EB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6885 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 508.35 |  | 508.35 | 0 |  |  |  | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE97 Closure 2 WB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6886 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 695.92 |  | 695.92 | 0 |  |  |  | 2000A180/149 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route)
YNE97 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6887 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 1441.75 |  | 1441.75 | 0 |  |  |  | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6887 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 1042.4 |  | 1042.4 | 0 |  |  |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6888 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 943.99 |  | 943.99 | 0 |  |  |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6888 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 277.14 |  | 277.14 | 0 |  |  |  | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6887 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 5 |  | 5 | 0 |  |  |  | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6888 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 229.03 |  | 229.03 | 0 |  |  |  | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6889 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB |  |  |  | 0 |  |  |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 5 years |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6889 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | WB |  |  |  | 0 |  |  |  | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 5 years
YNE97 Closure 2 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6890 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE97 Closure 2 WB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6891 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 4 |  | 4 | 0 |  |  |  | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Annually
YNE97 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6892 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 874 |  | 874 | 0 |  |  |  | 2000A180/145 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6892 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 1443 |  | 1443 | 0 |  |  |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6893 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 3690 |  | 3690 | 0 |  |  |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6892 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 390 |  | 390 | 0 |  |  |  | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6893 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 517 |  | 517 | 0 |  |  |  | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6892 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 3267 |  | 3267 | 0 |  |  |  | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6893 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 934 |  | 934 | 0 |  |  |  | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE97 Closure 2 EB NS CGS 45352 Wildlife structures and tunnels - Remove all material that could impair operation | 6894 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 1 |  | 1 | 0 |  |  |  | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE98 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6895 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 646.62 |  |  | 0 |  |  |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE98 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6896 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 1531.43 |  |  | 0 |  |  |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | Every 5 years (Sept - Feb) |  |  | No jobs
YNE98 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 824.27 |  | 824.27 | 0 |  |  |  | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 364.63 |  | 364.63 | 0 |  |  |  | 2000A180/175 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 290.84 |  | 290.84 | 0 |  |  |  | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6897 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 342.53 |  | 342.53 | 0 |  |  |  | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6898 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 355.78 |  | 355.78 | 0 |  |  |  | 2000A180/191 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 EB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6899 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | EB | TBC |  |  | 0 |  |  |  | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 5 years
YNE98 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6900 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually
YNE98 Closure Vaisala 45352 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6901 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE98: A180 Stallingborough - GreatCoates | YNE98 Closure | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | On ServiceNow
YNE98 Closure Amey 45352 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6902 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE98: A180 Stallingborough - GreatCoates | YNE98 Closure | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE98 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6903 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 1477 |  | 1477 | 0 |  |  |  | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE98 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6903 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 638 |  | 638 | 0 |  |  |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE98 Closure 1 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6904 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 1554 |  | 1554 | 0 |  |  |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE98 Closure 1 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6904 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 2531 |  | 2531 | 0 |  |  |  | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE98 Closure 1 WB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6904 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 3104 |  | 3104 | 0 |  |  |  | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb)
YNE99 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6905 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 265.4941 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | N/A | No Ditch assets on this route. LW confirmed 10/31/2023 | 20dys | EB | 386.9 | 386.9 | 0 | 1 | No Ditch assets on this route. LW confirmed 10/31/2023 |  |  | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE99 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6906 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 255.7774 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | N/A | No Ditch assets on this route. LW confirmed 10/31/2023 | 20dys | WB | 372.74 | 372.74 | 0 | 1 | No Ditch assets on this route. LW confirmed 10/31/2023 |  |  | 2000A180/192 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE99 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6906 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 313.9267 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | N/A | No Ditch assets on this route. LW confirmed 10/31/2023 | 20dys | WB | 457.48 | 457.48 | 0 | 1 | No Ditch assets on this route. LW confirmed 10/31/2023 |  |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE99 Closure Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6907 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys |  | TBC |  |  | 0 |  |  |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 4 |  |  | Every 5 years |  |  | No jobs
YNE99 Closure 1 WB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6908 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 5 |  | 5 | 0 |  |  |  | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs
YNE99 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6909 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | CW | 18 |  | 18 | 0 |  |  |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | No jobs
YNE99 Closure 1 EB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6910 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 783 |  | 783 | 0 |  |  |  | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years (Sept - Feb) |  |  | No jobs
YNE99 Closure 1 WB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6911 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 167 |  | 167 | 0 |  |  |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Every 3 years
YNE99 Closure 1 EB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6912 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 759 |  | 759 | 0 |  |  |  | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 3 years
YNE100 Closure 1 WB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6913 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | EB | 206.13 |  | 206.13 | 0 |  |  |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | 3 times per year (ILM Entire Route)
YNE100 Closure 1 EB OS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6914 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | EB | 866.59 |  | 866.59 | 0 |  |  |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 EB OS | Lane 2 Closure | 7 |  |  | 3 times per year (ILM Entire Route)
YNE100 Closure 1 EB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6915 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 3108.63 |  | 3108.63 | 0 |  |  |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | 3 times per year (ILM Entire Route)
YNE100 Closure 1 WB OS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6916 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1931.96 |  | 1931.96 | 0 |  |  |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 WB OS | Lane 2 Closure | 7 |  |  | 3 times per year (ILM Entire Route)
YNE100 Closure CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6917 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 3506 |  | 3506 | 0 |  |  |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 7 |  |  | Every 3 years (Sept - Feb)
YNE101 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6918 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | EB | 1517.47 |  | 1517.47 | 0 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE101 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation - ILM | 6919 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following updated instruction GC-928 | 20dys | WB | 295.11 |  | 295.11 | 0 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 WB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE101 Closure 1 EB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6920 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | EB | 2 |  | 2 | 0 |  |  |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Annually |  |  | No jobs
YNE101 Closure 1 EB NS Amey 45352 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 6921 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 89.8853 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | Complete |  | 20dys |  | 4 | 4 | 0 | 1 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure 1 EB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No jobs
YNE101 Closure 1 WB NS Amey 45352 BC - Lamps (LED) for Illuminated Signs and Bollards | 6922 | BC - Lamps (LED) for Illuminated Signs and Bollards | 149.8089 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2024-03-01 | 2024-03-29 | Complete |  | 20dys |  | 10 | 10 | 0 | 1 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure 1 WB NS | Lane 1 Closure | 7 |  |  | Every 2 years |  |  | No jobs
YNE101 Closure Amey 45352 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6923 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | No jobs
YNE101 Closure Amey 45352 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6924 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 7 |  |  | Annually |  |  | No jobs
YNE101 Closure CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6925 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | EB | 316 |  | 316 | 0 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 7 |  |  | Every 3 years (Sept - Feb)
YNE101 Closure CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6925 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | WB | 239 |  | 239 | 0 |  |  |  | 2000A160/317 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 7 |  |  | Every 3 years (Sept - Feb)
YNE106 Closure 2 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 6926 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-19 | 2024-1 | 2024-01-20 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 147 |  | 147 | 0 |  |  |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | 2 times per year (ILM Certain Sections) | 4/2 | 8/7 | 45931344 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6927 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 300 |  | 300 | 0 |  |  |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE106 Closure 2 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6928 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6929 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | SB | TBC |  |  | 0 |  |  |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6928 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6930 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually
YNE106 Closure 2 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6931 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-19 | 2024-1 | 2024-01-20 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Annually | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6930 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 16 |  | 16 | 0 |  |  |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually
YNE106 Closure 2 NB NS Amey 45352 Electrical Testing - Network cabling and electrical components | 6932 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2024-01-19 | 2024-1 | 2024-01-20 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 | No TM required |  | Every 6 years | 4/2 | 8/7 | 52038882 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure Vaisala 45352 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 6933 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE106 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6934 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 117 |  | 117 | 0 |  |  |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE106 Closure 3 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6935 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1307 |  | 1307 | 0 |  |  |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6936 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 563 |  | 563 | 0 |  |  |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6936 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 979 |  | 979 | 0 |  |  |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6937 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 776 |  | 776 | 0 |  |  |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6936 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 2239 |  | 2239 | 0 |  |  |  | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 2 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6938 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 394 |  | 394 | 0 |  |  |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6939 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1105 |  | 1105 | 0 |  |  |  | 4400A1M/45 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6939 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1296 |  | 1296 | 0 |  |  |  | 4400A1M/46 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6939 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 2627 |  | 2627 | 0 |  |  |  | 4400A1M/47 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6940 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 486 |  | 486 | 0 |  |  |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6940 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 607 |  | 607 | 0 |  |  |  | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6938 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1942 |  | 1942 | 0 |  |  |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6937 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1645 |  | 1645 | 0 |  |  |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6937 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 622 |  | 622 | 0 |  |  |  | 4400A1M/51 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6936 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 346 |  | 346 | 0 |  |  |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6937 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 384 |  | 384 | 0 |  |  |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE106 Closure 3 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6941 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 456 |  | 456 | 0 |  |  |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6941 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 2695 |  | 2695 | 0 |  |  |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6941 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 176 |  | 176 | 0 |  |  |  | 4400A1M/8 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45352 Wildlife structures and tunnels - Remove all material that could impair operation | 6942 | Wildlife structures and tunnels - Remove all material that could impair operation | 0 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-22 | 2024-1 | 2024-01-23 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 3 |  |  | Annually | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE107 Closure 1 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6943 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE107 Closure 1 SB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6944 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | SB | TBC |  |  | 0 |  |  |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 5 years
YNE107 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6945 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 15 |  | 15 | 0 |  |  |  | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually
YNE107 Closure Amey 45352 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 6946 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE107 Closure Amey 45352 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 6947 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE107 Closure Amey 45352 CCTV Masts - Check mast breaking system | 6948 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE107 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6949 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE107 Closure Amey 45352 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6950 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE107 Closure 1 NB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6951 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 598 |  | 598 | 0 |  |  |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6952 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 506 |  | 506 | 0 |  |  |  | 4400A1M/41 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6953 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 566 |  | 566 | 0 |  |  |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE107 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6954 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 458 |  | 458 | 0 |  |  |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb)
YNE107 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6955 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1256 |  | 1256 | 0 |  |  |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6956 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1369 |  | 1369 | 0 |  |  |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6955 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 114 |  | 114 | 0 |  |  |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6956 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 76 |  | 76 | 0 |  |  |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE107 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6955 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 167 |  | 167 | 0 |  |  |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years
YNE108 Closure 1 NB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6957 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 18.39 |  | 18.39 | 0 |  |  |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 14/7 | 20/4 | 52031356 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6958 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | SB | TBC |  |  | 0 |  |  |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6959 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6960 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6959 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6960 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45352 BC - Lamps (LED) for Illuminated Signs and Bollards | 6961 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 | No TM required |  | Every 2 years | 14/7 | 20/4 | 52038797 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6962 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE108 Closure Amey 45352 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 6963 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE108 Closure Amey 45352 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 6964 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE108 Closure Amey 45352 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 6965 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | On ServiceNow
YNE108 Closure Amey 45352 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6966 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE108 Closure 1 NB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6967 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 843 |  | 843 | 0 |  |  |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6967 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1526 |  | 1526 | 0 |  |  |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6968 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 1315 |  | 1315 | 0 |  |  |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6969 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1539 |  | 1539 | 0 |  |  |  | 4400A1M/19 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6970 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 625 |  | 625 | 0 |  |  |  | 4400A1M/32 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6969 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 287 |  | 287 | 0 |  |  |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6971 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 333 |  | 333 | 0 |  |  |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6971 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 684 |  | 684 | 0 |  |  |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6971 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 393 |  | 393 | 0 |  |  |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6972 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 222 |  | 222 | 0 |  |  |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6972 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 681 |  | 681 | 0 |  |  |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6972 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 324 |  | 324 | 0 |  |  |  | 4400A1M/39 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6972 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 106 |  | 106 | 0 |  |  |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6971 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 888 |  | 888 | 0 |  |  |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6972 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 899 |  | 899 | 0 |  |  |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 544 |  | 544 | 0 |  |  |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 3 | No |  | 3 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-24 | 2024-1 | 2024-01-25 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 547 |  | 547 | 0 |  |  |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 3 | No |  | 3 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6975 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | SB | TBC |  |  | 0 |  |  |  | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6976 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 5 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6977 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-25 | 2024-1 | 2024-01-26 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 6977 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-25 | 2024-1 | 2024-01-26 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
Unsure on location Amey 45352 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 6978 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys |  | 11 |  | 11 | 0 |  | Y |  |  | YNE109: A1M J37-38 | Unsure on location | Lane 1 Closure | 3 | Unsure on location |  | Every 3 years |  |  | 52038833
YNE109 Closure Amey 45352 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 6979 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 6980 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 CCTV Masts - Check mast breaking system | 6981 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6982 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE109 Closure Amey 45352 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6983 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 3 |  | 3 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 CCTV PTZ Cameras - Clean camera lens | 6984 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 CCTV PTZ Cameras - Check camera functionality | 6985 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure Amey 45352 CCTV PTZ Cameras - Check data and power supplies | 6986 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE109 Closure 1 NB NS CGS 45352 Rock Scree - Removal of scrub encroachment | 6987 | Rock Scree - Removal of scrub encroachment | 0 | 4.8.12 | A40088 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 1272 |  | 1272 | 0 |  |  |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6988 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 411 |  | 411 | 0 |  |  |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45352 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 6989 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 3532 |  | 3532 | 0 |  |  |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years (Sept - Feb) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6990 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 976 |  | 976 | 0 |  |  |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6990 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 824 |  | 824 | 0 |  |  |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6991 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 809 |  | 809 | 0 |  |  |  | 4400A1M/28 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6991 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 619 |  | 619 | 0 |  |  |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6991 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | SB | 499 |  | 499 | 0 |  |  |  | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6990 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 276 |  | 276 | 0 |  |  |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45352 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 6990 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Removed following GC-898 | 20dys | NB | 250 |  | 250 | 0 |  |  |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 3 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6992 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-25 | 2024-1 | 2024-01-26 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 375 |  | 375 | 0 |  |  |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 3 | No |  | 3 times per year (ILM Certain Sections) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45352 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 6993 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-25 | 2024-1 | 2024-01-26 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 343 |  | 343 | 0 |  |  |  | 4400A1M/64 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 3 | No |  | 3 times per year (ILM Certain Sections) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 300.5 |  | 300.5 | 0 |  |  |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 332.12 |  | 332.12 | 0 |  |  |  | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 471.27 |  | 471.27 | 0 |  |  |  | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 118.85 |  | 118.85 | 0 |  |  |  | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 837.64 |  | 837.64 | 0 |  |  |  | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 186.68 |  | 186.68 | 0 |  |  |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 152.8 |  | 152.8 | 0 |  |  |  | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 343.77 |  | 343.77 | 0 |  |  |  | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 324.08 |  | 324.08 | 0 |  |  |  | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 155.69 |  | 155.69 | 0 |  |  |  | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 74.43 |  | 74.43 | 0 |  |  |  | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 496.93 |  | 496.93 | 0 |  |  |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 118.04 |  | 118.04 | 0 |  |  |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 165.26 |  | 165.26 | 0 |  |  |  | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 551.48 |  | 551.48 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6994 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 73 |  | 73 | 0 |  |  |  | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 155.63 |  | 155.63 | 0 |  |  |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 462.89 |  | 462.89 | 0 |  |  |  | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 63.35 |  | 63.35 | 0 |  |  |  | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 178.07 |  | 178.07 | 0 |  |  |  | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 21.75 |  | 21.75 | 0 |  |  |  | 4700A1/633 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 165.35 |  | 165.35 | 0 |  |  |  | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 71.9 |  | 71.9 | 0 |  |  |  | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 129.27 |  | 129.27 | 0 |  |  |  | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 90.29 |  | 90.29 | 0 |  |  |  | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 426.96 |  | 426.96 | 0 |  |  |  | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 605.86 |  | 605.86 | 0 |  |  |  | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 326.17 |  | 326.17 | 0 |  |  |  | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 165.98 |  | 165.98 | 0 |  |  |  | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 736.56 |  | 736.56 | 0 |  |  |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 140.17 |  | 140.17 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 239.94 |  | 239.94 | 0 |  |  |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2.62 |  | 2.62 | 0 |  |  |  | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 610.86 |  | 610.86 | 0 |  |  |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 6995 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 339.16 |  | 339.16 | 0 |  |  |  | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 370 |  | 370 | 0 |  |  |  | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 130 |  | 130 | 0 |  |  |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 100 |  | 100 | 0 |  |  |  | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 93 |  | 93 | 0 |  |  |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 150 |  | 150 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6996 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 130 |  | 130 | 0 |  |  |  | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 | 45902850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 200 |  | 200 | 0 |  |  |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 519 |  | 519 | 0 |  |  |  | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 35 |  | 35 | 0 |  |  |  | 4700A1/633 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 35 |  | 35 | 0 |  |  |  | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 22 |  | 22 | 0 |  |  |  | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 115 |  | 115 | 0 |  |  |  | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 129 |  | 129 | 0 |  |  |  | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 70 |  | 70 | 0 |  |  |  | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 100 |  | 100 | 0 |  |  |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 50 |  | 50 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 60 |  | 60 | 0 |  |  |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45352 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 6997 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 205 |  | 205 | 0 |  |  |  | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 | 45902874 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6998 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 83.86 |  | 83.86 | 0 |  |  |  | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | 3 times per year (ILM Entire Route) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 6999 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 5 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 7000 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | SB | TBC |  |  | 0 |  |  |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 5 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 13 |  | 13 | 0 |  |  |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 8 |  | 8 | 0 |  |  |  | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 6 |  | 6 | 0 |  |  |  | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 6 |  | 6 | 0 |  |  |  | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 7 |  | 7 | 0 |  |  |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 6 |  | 6 | 0 |  |  |  | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7001 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 6 |  | 6 | 0 |  |  |  | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 8 |  | 8 | 0 |  |  |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 4 |  | 4 | 0 |  |  |  | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 4 |  | 4 | 0 |  |  |  | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 12 |  | 12 | 0 |  |  |  | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 3 |  | 3 | 0 |  |  |  | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 8 |  | 8 | 0 |  |  |  | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 7 |  | 7 | 0 |  |  |  | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 3 |  | 3 | 0 |  |  |  | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 3 |  | 3 | 0 |  |  |  | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 5 |  | 5 | 0 |  |  |  | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 4 |  | 4 | 0 |  |  |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 8 |  | 8 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 5 |  | 5 | 0 |  |  |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7002 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 10 |  | 10 | 0 |  |  |  | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7003 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7003 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7004 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7004 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7004 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7004 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 6 |  | 6 | 0 |  |  |  | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 8 |  | 8 | 0 |  |  |  | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 17 |  | 17 | 0 |  |  |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 16 |  | 16 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7005 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 15 |  | 15 | 0 |  |  |  | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 3 |  | 3 | 0 |  |  |  | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/643 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 5 |  | 5 | 0 |  |  |  | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/658 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7006 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 7007 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Annually | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45352 Bollards - Clean all illuminated and non-illuminated bollards | 7008 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | 2024-01-29 | 2024-1 | 2024-01-30 | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Annually | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE113 Closure 1 SB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 7009 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 90.8 |  | 90.8 | 0 |  |  |  | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 7010 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 386.46 |  | 386.46 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB NS Bettamix 45352 VRS - Check all Road Restraint System - ILM | 7010 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 500.13 |  | 500.13 | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | ILM Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 7011 | Culvert - Clean remove any blockage restricting the free flow of water through the culvert - Annex 20 | 0 | 4.3.9 | A40018 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | No assets | 20dys | NB | TBC |  |  | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 5 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 2 CW NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7013 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | CW | 7 |  | 7 | 0 |  |  |  | 4700A1/425 | YNE113: A1 Darrington - A162 | YNE113 Closure 2 CW NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 11 |  | 11 | 0 |  |  |  | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 6 |  | 6 | 0 |  |  |  | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/433 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/436 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7014 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 4 |  | 4 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7012 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7014 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 1 |  | 1 | 0 |  |  |  | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7014 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 5 |  | 5 | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7015 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7015 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7016 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 3 |  | 3 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7015 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 7016 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7017 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 2 |  | 2 | 0 |  |  |  | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7017 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/436 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7018 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 13 |  | 13 | 0 |  |  |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7017 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 1 |  | 1 | 0 |  |  |  | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 NB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7018 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | NB | 2 |  | 2 | 0 |  |  |  | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure 1 SB NS Amey 45352 Marker Posts - Clean all marker post faces and reference numbers | 7017 | Marker Posts - Clean all marker post faces and reference numbers | 0 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-03-01 | 2024-03-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 20dys | SB | 5 |  | 5 | 0 |  |  |  | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 4 |  |  | Every 2 years
YNE113 Closure Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7019 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure | Lane 1 Closure | Days | No |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE113 Closure Amey 45352 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7020 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure | Lane 1 Closure | Days | No |  | ILM Annual Network Wide |  |  | On ServiceNow
N/A Amey 45352 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7021 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys |  | 65 |  | 65 | 0 |  |  |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE2 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7022 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE7 Closure Amey N/A Ramp Metering Traffic Light Signals - Check alignment and condition of site | 7023 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 0 | 4.6.11 | ART024 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE7 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7024 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE8 Closure Amey N/A CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7025 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE8 Closure Amey N/A CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7025 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE10 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7026 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE11 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7027 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE13 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7028 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE14 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7029 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE29 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7030 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE32 Closure 1 CW OS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 7031 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW OS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 7032 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 7033 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 7034 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW OS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 7035 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW OS CGS N/A Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 7036 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | N/A |  | 830.75 |  | 830.75 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7037 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | N/A | N/A | 2024-02-29 | Subject to share with scheme works and clash management | N/A |  | 1 |  | 1 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE69 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7038 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE85 Closure 1 NB NS Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7039 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | N/A | N/A | 2024-01-31 |  | N/A |  | 1 |  | 1 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | N/A |  |  | Every 6 years | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7040 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | N/A | N/A | 2024-02-29 |  | N/A |  | 1 |  | 1 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | N/A |  |  | Every 6 years | 276/4 | 280/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7041 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE89 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7042 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE92 Closure 1 EB NS Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7043 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | N/A | N/A | 2024-01-31 |  | N/A |  | 1 |  | 1 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE93 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7044 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 | 0 |  |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE93 Closure Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7044 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | N/A | N/A | N/A | No assets | N/A |  | 0 |  | 0 | 0 | 0 |  |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | N/A |  |  | Every 6 years |  |  | On ServiceNow
YNE96 Closure 1 EB NS Amey N/A Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7045 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | N/A | N/A | 2024-01-31 |  | N/A |  | 1 |  | 1 | 0 | 0 | x |  | x | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | x |  |  | Every 6 years |  |  | x |  |  | x
YNE1 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7046 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7047 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS |  | 4 |  |  | 2 times per year
YNE1 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7048 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 2 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7049 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS |  | 4 |  |  | 2 times per year
YNE1 Closure 2 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7050 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 2 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7051 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS |  | 4 |  |  | 2 times per year
YNE1 Closure 2 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7052 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7053 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7054 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7055 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 01 | 7056 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS |  | 4 |  |  | 2 times per year
YNE10 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7057 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS |  | 1 |  |  | 2 times per year
YNE10 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7058 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE10 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7059 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 1 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7060 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7061 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE106 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7062 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 2 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7063 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS |  | 1 |  |  | 2 times per year | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 2 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7064 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 NB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 2 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7065 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS |  | 1 |  |  | 2 times per year | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 2 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7066 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 SB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 3 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7067 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 3 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7068 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB OS |  | 1 |  |  | 2 times per year
YNE106 Closure 3 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7069 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS |  | 1 |  |  | 2 times per year | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 3 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7070 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 SB OS |  | 1 |  |  | 2 times per year
YNE107 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7071 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 6924.75 |  | 6924.75 | 0 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE107 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7072 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 6924.75 | 6924.75 | 0 | 1 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB OS |  | 1 |  |  | 2 times per year |  |  | 52033905
YNE108 Closure 1 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7073 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 11670.75 | 4434.885 | 7235.865 | 0.38 | 7/8: Centres completed so 50% of 18 sections - 24 sections in total - 38% conplete roughly |  |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS |  | 1 |  |  | 2 times per year |  |  | 52037659
YNE108 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7074 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 11670.75 | 4434.885 | 7235.865 | 0.38 | 7/8: Centres completed so 50% of 18 sections - 24 sections in total - 38% conplete roughly |  |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS |  | 1 |  |  | 2 times per year | 20/3 | 15/9 | 52037659
YNE108 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7075 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 11670.75 | 4434.885 | 7235.865 | 0.38 | 7/8: Centres completed so 50% of 18 sections - 24 sections in total - 38% conplete roughly |  |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS |  | 1 |  |  | 2 times per year |  |  | 52037659
YNE109 Closure 1 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7076 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 8727 | 8727 | 0 | 1 | 8/8 centres completed. 31/7: NS completed from 20/5--24/4, 1 load. 3 slips left |  |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS |  | 1 |  |  | 2 times per year | 20/1 | 23/5
YNE109 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7077 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys |  | 8727 | 6981.6 | 1745.4 | 0.8 | 8/8 centres completed. 31/7: NS completed from 20/5--24/4, 1 load. 3 slips left |  |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS |  | 1 |  |  | 2 times per year | 285/8 | 19/9
YNE109 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7078 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 8727 | 8727 | 0 | 1 | 8/8 centres completed. 31/7: NS completed from 20/5--24/4, 1 load. 3 slips left |  |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS |  | 1 |  |  | 2 times per year | 23/8 | 20/2
YNE11 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7079 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  | 2023-07-31 | Complete |  | 43dys | EB | 11286.25 | 11286.25 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS |  | TBC |  |  | 2 times per year
YNE11 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7080 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  | 2023-07-31 | Complete |  | 43dys | EB | 11286.25 | 11286.25 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS |  | TBC |  |  | 2 times per year
YNE11 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7081 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  | 2023-07-31 | Complete |  | 43dys | EB | 11286.25 | 11286.25 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS |  | TBC |  |  | 2 times per year
YNE12 Closure 1 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7082 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE12 Closure 1 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7083 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE12 Closure 1 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7084 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE12 Closure 2 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7085 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS |  | 1 |  |  | 2 times per year
YNE12 Closure 2 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7086 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS |  | 1 |  |  | 2 times per year
YNE12 Closure 2 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7087 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS |  | 1 |  |  | 2 times per year
YNE12 Closure 2 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7088 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS |  | 1 |  |  | 2 times per year
YNE12 Closure 3 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7089 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS |  | 1 |  |  | 2 times per year
YNE12 Closure 3 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7090 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS |  | 1 |  |  | 2 times per year
YNE12 Closure 3 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7091 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS |  | 1 |  |  | 2 times per year
YNE12 Closure 3 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7092 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS |  | 1 |  |  | 2 times per year
YNE13 Closure 1 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7093 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 25088.25 | 25088.25 | 0 | 1 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS |  | 1 |  |  | 2 times per year
YNE13 Closure 1 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7094 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 25088.25 | 25088.25 | 0 | 1 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE13 Closure 1 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7095 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 25088.25 | 25088.25 | 0 | 1 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE14 Closure 1 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7096 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 9102 | 9102 | 0 | 1 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE14 Closure 1 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7097 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 9102 | 9102 | 0 | 1 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE14 Closure 1 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7098 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 9102 | 9102 | 0 | 1 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE15 Closure 1 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7099 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE15 Closure 1 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7100 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE15 Closure 2 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7101 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS |  | 1 |  |  | 2 times per year | 168/2 | 172/8
YNE15 Closure 2 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7102 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS |  | 1 |  |  | 2 times per year
YNE15 Closure 2 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7103 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS |  | 1 |  |  | 2 times per year | 172/6 | 168/2
YNE15 Closure 2 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7104 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS |  | 1 |  |  | 2 times per year
YNE15 Closure 3 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7105 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS |  | 1 |  |  | 2 times per year
YNE15 Closure 3 EB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7106 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS |  | 1 |  |  | 2 times per year
YNE15 Closure 3 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7107 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS |  | 1 |  |  | 2 times per year
YNE15 Closure 3 WB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7108 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS |  | 1 |  |  | 2 times per year
YNE30 Closure 1 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7109 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 7065.25 | 7065.25 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE30 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7110 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 7065.25 | 7065.25 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE30 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7111 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 7065.25 | 7065.25 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE31 Closure 1 NB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7112 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE31 Closure 1 SB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7113 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE31 Closure 1 SB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7114 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE32 Closure 1 AW OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7115 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 AW OS |  | 1 |  |  | 2 times per year
YNE32 Closure 1 CW NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7116 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS |  | 1 |  |  | 2 times per year
YNE32 Closure 1 CW OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7117 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS |  | 1 |  |  | 2 times per year
YNE32 Closure 2 AW NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7118 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 AW NS |  | 1 |  |  | 2 times per year
YNE32 Closure 2 AW OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7119 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 AW OS |  | 1 |  |  | 2 times per year
YNE32 Closure 2 CW NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7120 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS |  | 1 |  |  | 2 times per year
YNE32 Closure 2 CW OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7121 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS |  | 1 |  |  | 2 times per year
YNE4 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7122 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13188.75 | 13188.75 | 0 | 1 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE4 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7123 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13188.75 | 13188.75 | 0 | 1 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE4 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7124 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13188.75 | 13188.75 | 0 | 1 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE5 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7125 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15819 | 0 | 15819 | 0 |  | Y | 3/10 - Declined due to DBFO scheme |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS |  | 1 |  |  | 2 times per year | 104/3 | 108/6 | 52033914
YNE5 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7126 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15819 | 7909.5 | 7909.5 | 0.5 |  | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS |  | 1 |  |  | 2 times per year | 109/0 | 104/9 | 52033914
YNE5 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7127 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15819 | 0 | 15819 | 0 |  | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS |  | 1 |  |  | 2 times per year | 109/0 | 104/6 | 52033914
YNE2 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7128 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS |  | 1 |  |  | 2 times per year
YNE2 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7129 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE2 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7130 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE2 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7131 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE2 Closure 2 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7132 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 2 EB OS |  | 1 |  |  | 2 times per year
YNE2 Closure 2 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7133 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 12442 | 6221 | 6221 | 0.5 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 2 WB NS |  | 1 |  |  | 2 times per year
YNE3 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7134 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS |  | 1 |  |  | 2 times per year | 95/5 | 101/1
YNE3 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7135 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE3 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7136 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS |  | 1 |  |  | 2 times per year | 100/4 | 95/9
YNE3 Closure 2 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7137 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS |  | 1 |  |  | 2 times per year
YNE3 Closure 2 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7138 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS |  | 1 |  |  | 2 times per year
YNE3 Closure 2 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7139 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS |  | 1 |  |  | 2 times per year
YNE3 Closure 2 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7140 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS |  | 1 |  |  | 2 times per year
YNE6 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7141 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15689.5 |  | 15689.5 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS |  | 1 |  |  | 2 times per year | 108/1 | 112/6
YNE6 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7142 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15689.5 |  | 15689.5 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS |  | 1 |  |  | 2 times per year
YNE6 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7143 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | First intervention missed due to access | 21dys | EB | 15689.5 |  | 15689.5 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS |  | 1 |  |  | 2 times per year | 113/3 | 108/5
YNE61 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7144 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 22839 | 22839 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS |  | 1 |  |  | 2 times per year | 244/8 | 238/8
YNE61 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7145 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 22839 | 22839 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE62 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7146 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE62 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7147 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE62 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7148 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE63 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7149 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access |  |  | 11731.25 | 0 | 11731.25 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE63 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7150 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access |  |  | 11731.25 | 0 | 11731.25 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE63 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7151 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access |  |  | 11731.25 | 0 | 11731.25 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE64 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7152 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 10321.75 | 0 | 10321.75 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE64 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7153 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 10321.75 | 0 | 10321.75 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE64 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7154 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 10321.75 | 0 | 10321.75 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE66 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7155 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE66 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7156 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE66 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7157 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE66 Closure 2 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7158 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS |  | 1 |  |  | 2 times per year
YNE66 Closure 2 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7159 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS |  | 1 |  |  | 2 times per year
YNE66 Closure 2 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7160 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS |  | 1 |  |  | 2 times per year
YNE66 Closure 2 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7161 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB OS |  | 1 |  |  | 2 times per year
YNE67 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7162 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS |  | 1 |  |  | 2 times per year
YNE67 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7163 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE67 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7164 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE67 Closure 2 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7165 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS |  | 1 |  |  | 2 times per year
YNE67 Closure 2 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7166 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS |  | 1 |  |  | 2 times per year
YNE67 Closure 2 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7167 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS |  | 1 |  |  | 2 times per year
YNE68 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7168 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS |  | 1 |  |  | 2 times per year
YNE68 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7169 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS |  | 1 |  |  | 2 times per year |  |  | 52038013
YNE68 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7170 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS |  | 1 |  |  | 2 times per year
YNE68 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7171 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB OS |  | 1 |  |  | 2 times per year |  |  | 52038013
YNE68 Closure 2 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7172 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | First intervention missed due to access | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 2 SB OS |  | 1 |  |  | 2 times per year
YNE69 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7173 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS |  | 1 |  |  | 2 times per year
YNE69 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7174 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE69 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7175 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS |  | 1 |  |  | 2 times per year | 284/5 | 275/3
YNE69 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7176 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE69 Closure 2 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7177 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS |  | 1 |  |  | 2 times per year
YNE69 Closure 2 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7178 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 NB OS |  | 1 |  |  | 2 times per year
YNE69 Closure 2 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7179 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 SB OS |  | 1 |  |  | 2 times per year
YNE7 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7180 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 11999.25 | 11999.25 | 0 | 1 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS |  | 1 |  |  | 2 times per year
YNE7 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7181 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 11999.25 | 11999.25 | 0 | 1 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE7 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7182 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 11999.25 | 11999.25 | 0 | 1 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE70 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7183 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 13981.75 | 13981.75 | 0 | 1 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS |  | 1 |  |  | 2 times per year | 288/2 | 294/8
YNE70 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7184 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 13981.75 | 13981.75 | 0 | 1 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS |  | 1 |  |  | 2 times per year
YNE70 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7185 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 13981.75 | 13981.75 | 0 | 1 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS |  | 1 |  |  | 2 times per year
YNE71 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7186 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 14579.25 | 14579.25 | 0 | 1 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS |  | 1 |  |  | 2 times per year | 288/2 | 294/8
YNE71 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7187 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 14579.25 | 14579.25 | 0 | 1 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS |  | 1 |  |  | 2 times per year | 286/4" | 291/8"
YNE71 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7188 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 14579.25 | 14579.25 | 0 | 1 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS |  | 1 |  |  | 2 times per year | 292/2" | 286/7"
YNE72 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7189 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 10264.5 | 10264.5 | 0 | 1 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE72 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7190 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 10264.5 | 10264.5 | 0 | 1 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 300/6 116/8 M62 | 291/7 299/7 M1
YNE72 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7191 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 10264.5 | 10264.5 | 0 | 1 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE73 Closure 1 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7192 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 11572.5 | 11572.5 | 0 | 1 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE73 Closure 1 SB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7193 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 11572.5 | 11572.5 | 0 | 1 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS |  | TBC |  |  | 2 times per year
YNE73 Closure 1 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7194 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 11572.5 | 11572.5 | 0 | 1 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE74 Closure 1 NB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7195 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 6773 | 6773 | 0 | 1 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE74 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7196 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 6773 | 6773 | 0 | 1 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 300/6 116/8 M62 | 291/7 299/7 M1
YNE74 Closure 1 SB OS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 7197 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  |  |  | 6773 | 6773 | 0 | 1 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE8 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7198 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10275.25 | 10275.25 | 0 | 1 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS |  | 1 |  |  | 2 times per year
YNE8 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7199 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10275.25 | 10275.25 | 0 | 1 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS |  | 1 |  |  | 2 times per year
YNE8 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7200 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10275.25 | 10275.25 | 0 | 1 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS |  | 1 |  |  | 2 times per year
YNE83 Closure 1 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7201 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 15548 | 15548 | 0 | 1 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE83 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7202 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 15548 | 15548 | 0 | 1 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 253/0 | 257/0
YNE83 Closure 1 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7203 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 15548 | 15548 | 0 | 1 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE85 Closure 1 NB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7204 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 6297.25 | 6297.25 | 0 | 1 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS |  | TBC |  |  | 2 times per year | 264/4 | 268/8
YNE85 Closure 1 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7205 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 6297.25 | 6297.25 | 0 | 1 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE85 Closure 1 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7206 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 6297.25 | 6297.25 | 0 | 1 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 1 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7207 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | TBC |  |  | 2 times per year | 268/4 | 272/8
YNE86 Closure 1 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7208 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7209 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 273/6 | 268/8
YNE86 Closure 1 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7210 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 2 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7211 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS |  | TBC |  |  | 2 times per year | 272/4 | 276/8
YNE86 Closure 2 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7212 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 2 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7213 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | TBC |  |  | 2 times per year | 277/7 | 273/2
YNE86 Closure 2 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7214 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 3 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7215 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS |  | TBC |  |  | 2 times per year | 276/4 | 280/8
YNE86 Closure 3 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7216 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB OS |  | TBC |  |  | 2 times per year
YNE86 Closure 3 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7217 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB OS |  | TBC |  |  | 2 times per year
YNE87 Closure 1 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7218 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 13731.5 | 13731.5 | 0 | 1 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE87 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7219 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 13731.5 | 13731.5 | 0 | 1 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 283/1 | 281/0
YNE87 Closure 1 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7220 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 13731.5 | 13731.5 | 0 | 1 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE88 Closure 1 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7221 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7659.5 | 7659.5 | 0 | 1 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE88 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7222 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | First intervention missed due to access |  |  | 7659.5 | 3829.75 | 3829.75 | 0.5 |  | N/A |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 286/3 | 282/5
YNE88 Closure 1 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7223 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7659.5 | 7659.5 | 0 | 1 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 1 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7224 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7225 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 291/3 | 285/8
YNE89 Closure 1 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7226 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 2 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7227 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | TBC |  |  | 2 times per year | 291/3 | 293/0M18 M62 155/9 EB
YNE89 Closure 2 NB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7228 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 2 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7229 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS |  | TBC |  |  | 2 times per year | 153/0 | 155/7 291/6
YNE89 Closure 2 SB OS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 7230 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  |  |  | 7665 | 7665 | 0 | 1 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB OS |  | TBC |  |  | 2 times per year
YNE9 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7231 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10946.25 | 10946.25 | 0 | 1 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE9 Closure 1 EB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7232 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10946.25 | 10946.25 | 0 | 1 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS |  | 1 |  |  | 2 times per year |  |  | 52033918
YNE9 Closure 1 WB OS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 7233 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  |  |  | 10946.25 | 10946.25 | 0 | 1 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS |  | 1 |  |  | 2 times per year |  |  | 52033918
YNE90 Closure 1 EB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7234 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4097.5 | 4097.5 | 0 | 1 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037250
YNE90 Closure 1 WB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7235 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4097.5 |  | 4097.5 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS |  | TBC |  |  | 2 times per year | 2/7 | 0/0
YNE90 Closure 1 WB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7236 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4097.5 | 4097.5 | 0 | 1 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037250
YNE91 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7237 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7238 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS |  | TBC |  |  | 2 times per year
YNE91 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7239 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 2 EB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7240 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS |  | TBC |  |  | 2 times per year | 2/3 | 10/5
YNE91 Closure 2 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7241 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 EB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 2 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7242 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS |  | TBC |  |  | 2 times per year
YNE91 Closure 2 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7243 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 WB OS |  | TBC |  |  | 2 times per year
YNE92 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7244 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7245 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7246 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 2 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7247 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 2 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7248 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 2 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE93 Closure 1 EB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7249 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 | 28/9: complete |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7250 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | First intervention missed due to access | 43dys | EB | 6214.5 | 1491.48 | 4723.02 | 0.24 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7251 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7252 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | First intervention missed due to access | 43dys | EB | 6214.5 | 1491.48 | 4723.02 | 0.24 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 2 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7253 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | First intervention missed due to access | 43dys | EB | 6214.5 | 1491.48 | 4723.02 | 0.24 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 2 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7254 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 2 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7255 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | First intervention missed due to access | 43dys | EB | 6214.5 | 1491.48 | 4723.02 | 0.24 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 3 EB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7256 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 3 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7257 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 3 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7258 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 | 28/9: complete |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 3 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7259 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  | 43dys | EB | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037272
YNE94 Closure 1 EB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7260 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 1 WB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7261 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 1 WB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7262 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 2 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7263 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 2 EB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7264 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 2 WB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7265 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 2 WB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7266 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 3 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7267 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 3 EB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7268 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 3 WB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7269 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 3 WB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7270 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 4 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7271 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 4 EB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7272 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 4 WB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7273 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 4 WB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 7274 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access |  |  | 4946.6875 | 742.0031 | 4204.6844 | 0.15 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037164
YNE95 Closure 1 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7275 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037205
YNE95 Closure 1 SB NS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7276 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB NS |  | TBC |  |  | 2 times per year
YNE95 Closure 1 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 01 | 7277 | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | No assets |  |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037205
YNE1 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7278 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 | 18/9: cancelled heavy rain |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038260
YNE1 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7279 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-18 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038262
YNE1 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7280 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 | 18/9: cancelled heavy rain |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038260
YNE1 Closure 2 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7281 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS |  | 4 |  |  | 2 times per year |  |  | 52038262
YNE1 Closure 2 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7282 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 2 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7283 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-17 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038262
YNE1 Closure 2 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7284 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7285 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7257.85 | 7258 | -0.15 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS |  | 4 |  |  | 2 times per year |  |  | 52038262
YNE1 Closure 3 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7286 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7257.85 | 0 | 1 | 13/9: Didnt get into EB with sweeper. Full after WB. |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS |  | 4 |  |  | 2 times per year
YNE1 Closure 3 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7287 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-16 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 7257.85 | 7258 | -0.15 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038262
YNE1 Closure 3 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7288 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 7257.85 | 7258 | -0.15 | 1 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS |  | 4 |  |  | 2 times per year
YNE10 Closure 1 EB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7289 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-25 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS |  | 4 |  |  | 2 times per year |  |  | 52037831
YNE10 Closure 1 EB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7290 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52037831
YNE10 Closure 1 WB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7291 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS |  | 4 |  |  | 2 times per year |  |  | 52037831
YNE106 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7292 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE106 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7293 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 6991 |  | 6991 | 0 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE106 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7294 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE106 Closure 2 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7295 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-19 | 2024-1 | 2024-01-20 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 6991 |  | 6991 | 0 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS |  | 2 |  |  | 2 times per year | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 2 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7296 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 NB OS |  | 2 |  |  | 2 times per year
YNE106 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7297 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-19 | 2024-1 | 2024-01-20 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 6991 |  | 6991 | 0 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS |  | 2 |  |  | 2 times per year | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7298 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 2 SB OS |  | 2 |  |  | 2 times per year
YNE106 Closure 3 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7299 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-22 | 2024-1 | 2024-01-23 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 6991 |  | 6991 | 0 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 3 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7300 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB OS |  | 2 |  |  | 2 times per year
YNE106 Closure 3 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7301 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-22 | 2024-1 | 2024-01-23 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 6991 |  | 6991 | 0 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS |  | 2 |  |  | 2 times per year | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE106 Closure 3 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7302 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2024-03-31 |  | 21dys | NB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on centre sweep | N |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 SB OS |  | 2 |  |  | 2 times per year
YNE107 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7303 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-09-01 | 2023-09-30 | 2024-01-31 |  | 43dys | NB | 6924.75 |  | 6924.75 | 0 |  | N |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS |  | 2 |  |  | 2 times per year |  |  | 52033905
|  | Sweeping - Paved non-running areas - Full Sweep 01 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete |  | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 6924.75 | 6924.75 | 0 | 1 |  | N |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS |  | 2 |  |  | 2 times per year |  |  | 52033905
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction |  | Cancelled following NH instruction | 2023-09-01 | 2023-09-30 | 2023-10-31 |  | 43dys | NB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction | N |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS |  | 2 |  |  | 2 times per year |  |  | 52033905
YNE107 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7305 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-30 | 2023-10-31 |  | 43dys | NB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction | N |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB OS |  | 2 |  |  | 2 times per year |  |  | 52033905
YNE108 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7306 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 11670.75 | 11670.75 | 0 | 1 |  | N |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE108 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7307 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 11670.75 | 11670.75 | 0 | 1 |  | N |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS |  | 2 |  |  | 2 times per year | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved
YNE108 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7308 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 11670.75 | 11670.75 | 0 | 1 |  | N |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE109 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7309 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 8727 | 8727 | 0 | 1 |  | N |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS |  | 2 |  |  | 2 times per year | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE109 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7310 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 8727 | 8727 | 0 | 1 |  | N |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS |  | 2 |  |  | 2 times per year | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved
YNE109 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7311 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 8727 | 8727 | 0 | 1 |  | N |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS |  | 2 |  |  | 2 times per year | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved
YNE11 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7312 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 11286.25 | 11286.25 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52037416
YNE11 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7313 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 11286.25 | 11286.25 | 0 | 1 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS |  | TBC |  |  | 2 times per year |  |  | No job for 2nd sweep
YNE11 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7314 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 11286.25 | 11286.25 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52037416
YNE12 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7315 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 0 |  | 0 | 0 |  | N | 2/10 cancelled rain |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE12 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7316 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 0 |  | 0 | 0 |  | N | 2/10 cancelled rain |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE12 Closure 2 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7317 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  | 2024-12-06 |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4868 |  | 4868 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS |  | Days |  |  | 2 times per year |  |  | 52044039
YNE12 Closure 2 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7318 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-03-31 |  | 41dys | EB | 0 |  | 0 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE12 Closure 2 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7319 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 4868 | 2000 | 2868 | 0.41085 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS |  | Days |  |  | 2 times per year |  |  | 52044039
YNE12 Closure 2 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7320 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-03-31 |  | 41dys | EB | 0 |  | 0 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE12 Closure 3 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7321 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  | 2024-12-06 |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4868 |  | 4868 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS |  | Days |  |  | 2 times per year |  |  | 52044039
YNE12 Closure 3 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7322 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE12 Closure 3 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7323 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  | 2024-12-06 |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 4868 |  | 4868 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS |  | Days |  |  | 2 times per year |  |  | 52044039
YNE12 Closure 3 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7324 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 4868 | 4868 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038467
YNE13 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7325 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 25088.25 |  | 25088.25 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS |  | 4 |  |  | 2 times per year
YNE13 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7326 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on sweeping |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE13 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7327 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | WB | 0 |  | 0 | 0 | 6/11 cancelled following NH instruction on sweeping |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE14 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7328 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9102 |  | 9102 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE14 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7329 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9102 |  | 9102 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS |  | 4 |  |  | 2 times per year
YNE14 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7330 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 9102 |  | 9102 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE15 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7331 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038429
YNE15 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7332 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS |  | 4 |  |  | 2 times per year
YNE15 Closure 2 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7333 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS |  | 4 |  |  | 2 times per year | 168/2 | 172/8 | Jobs already closed - use Do Forms | 20:00 | 6:00 | Night Shift | Approved
YNE15 Closure 2 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7334 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038429
YNE15 Closure 2 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7335 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS |  | 4 |  |  | 2 times per year | 172/6 | 168/2 | Jobs already closed - use Do Forms | 20:00 | 6:00 | Night Shift | Approved
YNE15 Closure 2 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7336 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038429
YNE15 Closure 3 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7337 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS |  | 4 |  |  | 2 times per year |  |  | Jobs already closed - use Do Forms
YNE15 Closure 3 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7338 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS |  | 4 |  |  | 2 times per year
YNE15 Closure 3 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7339 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS |  | 4 |  |  | 2 times per year |  |  | Jobs already closed - use Do Forms
YNE15 Closure 3 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7340 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys | EB | 3326.9091 |  | 3326.9091 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS |  | 4 |  |  | 2 times per year
YNE2 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7341 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-21 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12442 | 12442 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS |  | 4 |  |  | 2 times per year |  |  | 52038326
YNE2 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7342 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 12442 | 12442 | 0 | 1 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE2 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7343 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12442 |  | 12442 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038326
YNE2 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7344 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 12442 | 12442 | 0 | 1 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE2 Closure 2 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7345 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 12442 | 12442 | 0 | 1 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 2 EB OS |  | 4 |  |  | 2 times per year
YNE2 Closure 2 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7346 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 12442 |  | 12442 | 0 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 2 WB NS |  | 4 |  |  | 2 times per year
YNE3 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7347 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  | Y | Unable to access due to schemes - booked for January |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS |  | 4 |  |  | 2 times per year | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved
YNE3 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7348 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS |  | 4 |  |  | 2 times per year
YNE3 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7349 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  | Y | Unable to access due to schemes - booked for January |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS |  | 4 |  |  | 2 times per year | 100/4 | 95/9 | 52038340 | 20:00 | 6:00 | Night Shift | Approved
YNE3 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7347 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  | Y | Unable to access due to schemes - booked for January |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS |  | 4 |  |  | 2 times per year | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved
YNE3 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7348 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS |  | 4 |  |  | 2 times per year
YNE3 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7347 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-12-01 | 2024-01-31 | 2023-12-31 |  | 41dys | EB | 2766.75 |  | 2766.75 | 0 |  | Y | Unable to access due to schemes - booked for January |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS |  | 4 |  |  | 2 times per year | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved
YNE30 Closure 1 NB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7350 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 7065.25 | 7065.25 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS |  | 4 |  |  | 2 times per year |  |  | 52037347
YNE30 Closure 1 SB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7351 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 7065.25 |  | 7065.25 | 0 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS |  | 4 |  |  | 2 times per year |  |  | 52037347
YNE30 Closure 1 SB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7352 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 7065.25 | 7064.25 | 7064.25 | 0.99986 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS |  | 4 |  |  | 2 times per year |  |  | 52037347
YNE31 Closure 1 NB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7353 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS |  | 2 |  |  | 2 times per year |  |  | 52037350
YNE31 Closure 1 SB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7354 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 4684.75 |  | 4684.75 | 0 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS |  | 2 |  |  | 2 times per year |  |  | 52037350
YNE31 Closure 1 SB OS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 7355 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS |  | 2 |  |  | 2 times per year |  |  | 52037350
YNE32 Closure 1 ACW OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7356 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS |  | 6 |  |  | 2 times per year
YNE32 Closure 1 CW NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7357 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS |  | 6 |  |  | 2 times per year
YNE32 Closure 1 CW OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7358 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS |  | 6 |  |  | 2 times per year
YNE32 Closure 2 ACW NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7359 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS |  | 6 |  |  | 2 times per year
YNE32 Closure 1 ACW OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7356 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS |  | 6 |  |  | 2 times per year
YNE32 Closure 2 CW NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7360 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS |  | 6 |  |  | 2 times per year
YNE32 Closure 1 CW OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7358 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-12-01 | 2024-01-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 6938.25 |  | 6938.25 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS |  | 6 |  |  | 2 times per year
YNE4 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7361 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 13188.75 | 13188.75 | 0 | 1 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038292
YNE4 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7362 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 13188.75 | 13188.75 | 0 | 1 | 18/10 - cancelled storm Babet | N |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038292
YNE4 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7363 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | Complete |  | 41dys | EB | 13188.75 | 13188.75 | 0 | 1 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS |  | 4 |  |  | 2 times per year |  |  | 52033913
YNE5 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7364 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS |  | 4 |  |  | 2 times per year | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved
YNE5 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7365 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 15819 |  | 15819 | 0 |  | Y | Unable to access due to schemes - booked for January |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS |  | 4 |  |  | 2 times per year | 109/0 | 104/9 | 52038261 | 20:00 | 6:00 | Night Shift | Approved
YNE5 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7366 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys | EB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS |  | 4 |  |  | 2 times per year | 109/0 | 104/6 | 52038261 | 20:00 | 6:00 | Night Shift | Approved
YNE6 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7367 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep | N |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS |  | 4 |  |  | 2 times per year | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved
YNE6 Closure 1 WB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7368 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys | EB | 15689.5 |  | 15689.5 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS |  | 4 |  |  | 2 times per year |  |  | 52038556
YNE6 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7369 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 41dys | EB | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep | N |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS |  | 4 |  |  | 2 times per year | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE61 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7370 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22839 | 22839 | 0 | 1 |  | N |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS |  | 2 |  |  | 2 times per year | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE61 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7371 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22839 | 22839 | 0 | 1 |  | N |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS |  | 2 |  |  | 2 times per year |  |  | 52038116
YNE62 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7372 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE62 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7373 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE62 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7374 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE63 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7375 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 11731.25 | 11731.25 | 0 | 1 |  | N |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE63 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7376 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 11731.25 | 11731.25 | 0 | 1 |  | N |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE63 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7377 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 11731.25 | 11731.25 | 0 | 1 |  | N |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE64 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7378 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 10321.75 | 10321.75 | 0 | 1 |  | N |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE64 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7379 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 10321.75 | 10321.75 | 0 | 1 |  | N |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE64 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7380 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 10321.75 | 10321.75 | 0 | 1 |  | N |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE66 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7381 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE66 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7382 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE66 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7383 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE66 Closure 2 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7384 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS |  | 2 |  |  | 2 times per year
YNE66 Closure 2 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7385 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS |  | 2 |  |  | 2 times per year
YNE66 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7386 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS |  | 2 |  |  | 2 times per year
YNE66 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7387 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB OS |  | 2 |  |  | 2 times per year
YNE67 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7388 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS |  | 2 |  |  | 2 times per year
YNE67 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7389 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE67 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7390 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE67 Closure 2 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7391 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS |  | 2 |  |  | 2 times per year
YNE67 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7392 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS |  | 2 |  |  | 2 times per year
YNE67 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7393 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS |  | 2 |  |  | 2 times per year
YNE68 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7394 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS |  | 2 |  |  | 2 times per year
YNE68 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7395 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE68 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7396 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS |  | 2 |  |  | 2 times per year
YNE68 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7397 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE68 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7398 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 2 SB OS |  | 2 |  |  | 2 times per year
YNE69 Closure 1 NB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7399 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-07 |  |  | 2023-12-31 |  |  |  | 6994 | 6994 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS |  | TBC |  |  | 2 times per year |  |  | 52044415
YNE69 Closure 1 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7400 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 6994 | 6994 | 0 | 1 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52038025
YNE69 Closure 1 SB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7401 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 |  |  | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 6994 |  | 6994 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved
YNE69 Closure 1 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7402 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete |  |  | Complete |  |  |  | 6994 | 6994 | 0 | 1 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52038025
YNE69 Closure 2 NB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7403 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-19 | 2023-12 | 2023-12-20 |  |  | 2023-12-31 |  |  |  | 6994 |  | 6994 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS |  | Days |  |  | 2 times per year |  |  | 52044415
YNE69 Closure 2 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7404 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 6994 |  | 6994 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 NB OS |  | TBC |  |  | 2 times per year |  |  | No jobs raised
YNE69 Closure 2 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7405 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 6994 |  | 6994 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 SB OS |  | TBC |  |  | 2 times per year |  |  | No jobs raised
YNE7 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7406 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures |  |  | 11999.25 |  | 11999.25 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS |  | 4 |  |  | 2 times per year
YNE7 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7407 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE7 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7408 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE70 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7409 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 13981.75 |  | 13981.75 | 0 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS |  | 2 |  |  | 2 times per year | 288/2 | 294/8 | 52037989 | 20:00 | 6:00 | Night Shift | Approved
YNE70 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7410 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 13981.75 | 13981.75 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS |  | 2 |  |  | 2 times per year
YNE70 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7411 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 13981.75 | 13981.75 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS |  | 2 |  |  | 2 times per year
YNE71 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7412 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14579.25 |  | 14579.25 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS |  | 2 |  |  | 2 times per year | 288/2 | 294/8 | No job emailed NH | 20:00 | 6:00 | Night Shift | Approved
YNE71 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7413 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14579.25 | 14579.25 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS |  | 2 |  |  | 2 times per year | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved
YNE71 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7414 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14579.25 | 14579.25 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS |  | 2 |  |  | 2 times per year | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved
YNE72 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7415 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 10264.5 | 10264.5 | 0 | 1 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52042557
YNE72 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7416 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-09-01 | 2023-09-29 | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 10264.5 |  | 10264.5 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 300/6 116/8 M62 | 291/7 299/7 M1 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved
YNE72 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7417 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 10264.5 | 10264.5 | 0 | 1 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52042557
YNE73 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7418 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 11572.5 |  | 11572.5 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE73 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7419 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-09-01 | 2023-09-29 | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 11572.5 |  | 11572.5 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS |  | TBC |  |  | 2 times per year
YNE73 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7420 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 11572.5 |  | 11572.5 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE74 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7421 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 6773 |  | 6773 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE74 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7422 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  |  |  | 6773 |  | 6773 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved
YNE74 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7423 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 6773 |  | 6773 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE8 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7424 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval |  |  | 10275.25 |  | 10275.25 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS |  | 4 |  |  | 2 times per year
YNE8 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7425 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS |  | 4 |  |  | 2 times per year
YNE8 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7426 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS |  | 4 |  |  | 2 times per year
YNE83 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7427 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 15548 |  | 15548 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE83 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7428 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 15548 |  | 15548 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved
YNE83 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7429 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 15548 |  | 15548 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE85 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7430 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 6297.25 |  | 6297.25 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS |  | TBC |  |  | 2 times per year | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE85 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7431 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037591
YNE85 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7432 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037591
YNE86 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7433 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-01 | 2024-2 | 2024-02-02 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 5863.4167 |  | 5863.4167 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | TBC |  |  | 2 times per year | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE86 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7434 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE86 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7435 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-01 | 2024-2 | 2024-02-02 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 5863.4167 |  | 5863.4167 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE86 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7436 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE86 Closure 2 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7437 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-02 | 2024-2 | 2024-02-03 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 5863.4167 |  | 5863.4167 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS |  | TBC |  |  | 2 times per year | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE86 Closure 2 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7438 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following instruction from NH | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE86 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7439 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-02 | 2024-2 | 2024-02-03 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 5863.4167 |  | 5863.4167 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | TBC |  |  | 2 times per year | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved
YNE86 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7440 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE86 Closure 3 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7441 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 5863.4167 |  | 5863.4167 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS |  | TBC |  |  | 2 times per year | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE86 Closure 3 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7442 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE86 Closure 3 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7443 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037383
YNE87 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7444 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 13731.5 | 13731.5 | 0 | 1 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037377
YNE87 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7445 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  |  |  | 13731.5 |  | 13731.5 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved
YNE87 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7446 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | completed | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 13731.5 | 13731.5 | 0 | 1 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037377
YNE88 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7447 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 7659.5 | 7659.5 | 0 | 1 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS |  | TBC |  |  | 2 times per year |  |  | 52037088
YNE88 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7448 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  |  |  | 7659.5 |  | 7659.5 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved
YNE88 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7449 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 7659.5 | 7659.5 | 0 | 1 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS |  | TBC |  |  | 2 times per year |  |  | 52037088
YNE89 Closure 1 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7450 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7451 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS |  | TBC |  |  | 2 times per year | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved
YNE89 Closure 1 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7452 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 2 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7453 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | TBC |  |  | 2 times per year | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved
YNE89 Closure 2 NB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7454 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS |  | TBC |  |  | 2 times per year
YNE89 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7455 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS |  | TBC |  |  | 2 times per year | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved
YNE89 Closure 2 SB OS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 7456 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. |  |  | 7665 |  | 7665 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB OS |  | TBC |  |  | 2 times per year
YNE9 Closure 1 EB NS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7457 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  |  |  | 10946.25 | 5473.125 | 5473.125 | 0.5 | 23/11 Sweeper didn't arrive until 01:45 once the A64 had been cancelled. 123/8 - 125/8 inc slips complete. Evidence captured on confirm, Job Paused. 125/8 - 128/5 to complete, Can be done under IPV | N |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 2 times per year |  |  | 52038517
YNE9 Closure 1 EB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7458 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS |  | 4 |  |  | 2 times per year |  |  | 52038517
YNE9 Closure 1 WB OS Amey 45261 Sweeping - Paved non-running areas - Full Sweep 02 | 7459 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval |  |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction on centre sweep |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS |  | 4 |  |  | 2 times per year |  |  | 52038517
YNE90 Closure 1 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7460 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 4097.5 |  | 4097.5 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038770
YNE90 Closure 1 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7461 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2024-02-01 | 2024-03-29 | 2023-12-31 |  |  |  | 4097.5 |  | 4097.5 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS |  | 2 |  |  | 2 times per year | 2/7 | 0/0 | 52037250 | 20:00 | 6:00 | Night Shift | Approved
YNE90 Closure 1 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7462 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 4097.5 |  | 4097.5 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038770
YNE91 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7463 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7464 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 |  |  | 2024-01-31 |  |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS |  | Days |  |  | 2 times per year |  |  | 52038717
YNE91 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7465 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 2 EB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7466 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 |  |  | 2023-12-31 |  |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS |  |  |  |  | 2 times per year | 2/3 | 10/5 | 52038717 | 20:00 | 6:00 | Night Shift | Approved
YNE91 Closure 2 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7467 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 EB OS |  | TBC |  |  | 2 times per year
YNE91 Closure 2 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7468 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 |  |  | 2024-01-31 |  |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS |  | Days |  |  | 2 times per year |  |  | 52038717
YNE91 Closure 2 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7469 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 8878.25 |  | 8878.25 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 2 WB OS |  | TBC |  |  | 2 times per year
YNE92 Closure 1 EB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7470 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 9924.1667 |  | 9924.1667 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7471 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 |  |  | 2024-01-31 |  |  |  | 9924.1667 |  | 9924.1667 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS |  | Days |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7472 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 9924.1667 |  | 9924.1667 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 2 WB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7473 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 |  |  | 2024-03-31 |  |  |  | 9924.1667 |  | 9924.1667 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS |  | Days |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 2 WB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7474 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP |  |  | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 9924.1667 |  | 9924.1667 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 2 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038750
YNE93 Closure 1 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7475 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 6214.5 |  | 6214.5 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS |  | Days |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 1 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7476 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2023-10-31 |  | 41dys |  | 6214.5 | 6214.5 | 0 | 1 | 24/10 COMPLETE |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 1 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7477 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 6214.5 |  | 6214.5 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS |  | Days |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 1 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7478 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2023-10-31 |  | 41dys |  | 6214.5 | 6214.5 | 0 | 1 | 24/10 COMPLETE |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 2 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7479 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2023-10-31 |  | 41dys |  | 6214.5 | 6214.5 | 0 | 1 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 2 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7480 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 6214.5 |  | 6214.5 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS |  | Days |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 2 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7481 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2024-02-01 | 2024-03-29 | 2023-10-31 |  | 41dys |  | 0 |  | 0 | 0 | 6/11 Cancelled following NH instruction |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 3 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7482 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-03-31 |  | 41dys |  | 6214.5 |  | 6214.5 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS |  | Days |  |  | 2 times per year |  |  | 52038757
YNE93 Closure 3 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7483 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  | 41dys |  | 6214.5 |  | 6214.5 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS |  | Days |  |  | 2 times per year |  |  | 52038757
YNE94 Closure 1 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7484 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 1 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7485 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 1 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7486 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 2 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7487 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 2 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7488 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 | 26/10 - works cancelled fog. Yellow warning issued |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB OS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 2 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7489 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 2 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7490 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 | 26/10 - works cancelled fog. Yellow warning issued |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7491 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 | 18/10 cancelled high winds. |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7492 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-10-28 | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7493 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7494 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-10-28 | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS |  | TBC |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 4 EB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7495 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 EB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7492 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-10-28 | 2024-02-01 | 2024-03-29 | 2023-10-31 |  |  |  | 4946.6875 | 4946.6875 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB OS |  | TBC |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 4 WB NS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7496 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2024-01-12 | 2024-02-01 | 2024-03-29 | 2024-01-31 |  |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS |  | Days |  |  | 2 times per year |  |  | 52038700
YNE94 Closure 3 WB OS Amey 45323 Sweeping - Paved non-running areas - Full Sweep 02 | 7497 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-02-01 | 2024-03-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works |  |  | 4946.6875 |  | 4946.6875 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS |  | TBC |  |  | 2 times per year
YNE95 Closure 1 NB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7498 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following Nh instruction |  |  | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following Nh instruiction on centre sweep | N |  |  | YNE95: M181 | YNE95 Closure 1 NB OS |  | Days |  | Days | 2 times per year |  |  | 52038706
YNE95 Closure 1 SB NS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7499 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | [5 empty] | 2023-11-30 |  |  |  | 8130 | 2000 | 6130 | 0.246 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December |  | YNE95: M181 | YNE95 Closure 1 SB NS |  | Days |  | Days | 2 times per year |  |  | 52038706
YNE95 Closure 1 SB OS Amey Sweeping - Paved non-running areas - Full Sweep 02 | 7500 | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following Nh instruction |  |  | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following Nh instruiction on centre sweep | N |  |  | YNE95: M181 | YNE95 Closure 1 SB OS |  | Days |  | Days | 2 times per year |  |  | 52038706
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  |  |  |  | 2 times per year | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  |  |  |  | 2 times per year | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 3397.6818 | 3397.6818 | 0 | 1 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB OS |  |  |  |  | 2 times per year
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS |  |  |  |  | 2 times per year | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS |  |  |  |  | 2 times per year | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  |  |  | 3397.6818 | 3397.6818 | 0 | 1 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB OS |  |  |  |  | 2 times per year
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS |  |  |  |  | 2 times per year | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS |  |  |  |  | 2 times per year | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-03 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 3397.6818 | 3397.6818 | 0 | 1 |  | N |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-30 | 2024-1 | 2024-01-31 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  |  |  |  | 2 times per year | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-30 | 2024-1 | 2024-01-31 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  |  |  |  | 2 times per year | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS |  |  |  |  | 2 times per year | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS |  |  |  |  | 2 times per year | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  |  |  | 3397.6818 |  | 3397.6818 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  |  |  |  | 2 times per year | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Sweeping - Paved non-running areas - Full Sweep 02 |  | 4.9.2 | A40095 |  |  | Amey | 4000 - Sweeping and Cleaning | Cancelled following NH instruction | Cancelled following NH instruction | Cancelled following NH instruction | 2023-09-01 | 2023-09-29 | 2023-11-30 |  |  |  | 0 |  | 0 | 0 | 6/11 cancelled following instruction from NH on centre sweeping | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB OS |  |  |  |  | 2 times per year |  |  | 52037612
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | 1916.11 | 1916.11 |  |  | 24/10 COMPLETE |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut | 1937.27 | [6 empty] | YNE93: M180 J3-4 | YNE93 Closure 2 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | 389.76 | 389.76 |  |  | 24/10 COMPLETE |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | 1038.52 | 1038.52 |  |  | 24/10 COMPLETE |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut |  |  | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut |  |  | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut |  |  | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut |  |  |  | 26/10 - works cancelled fog. Yellow warning issued |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | additional | additional | Schedule D |  |  |  | Per grass cut |  |  |  | 26/10 - works cancelled fog. Yellow warning issued |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-10-28 | additional | additional | Schedule D |  |  |  | 3038.06 | 3038.06 | [6 empty] | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres M180 J3-5 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-10-28 | additional | additional | Schedule D |  |  |  | 1874.34 | 1874.34 | [6 empty] | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | [7 empty] | 52042603
|  | Litter Sched D - centres A1M J35-38 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning |  |  |  | additional | additional | Schedule D |  |  |  | Per grass cut | [7 empty] | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | [7 empty] | 52042738
|  | Litter Sched D - centres A1M J35-38 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning |  |  |  | additional | additional | Schedule D |  |  |  | Per grass cut |  |  |  | 26/10 - works cancelled fog. Yellow warning issued |  |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB OS | [7 empty] | 52042738
|  | Litter Sched D - centres A1M J35-38 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete |  | 2023-10-28 | additional | additional | Schedule D |  |  |  | Per grass cut | Per grass cut | [6 empty] | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | [7 empty] | 52042738
|  | Litter Sched D - centres A1M J35-38 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete |  | 2023-10-28 | additional | additional | Schedule D |  |  |  | Per grass cut | Per grass cut | [6 empty] | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | [7 empty] | 52042738
|  | Litter Sched D - centres A1M J35-38 - please leave job open as covers whole area |  | 4.9.5 |  |  |  |  | 4000 - Sweeping and Cleaning | Complete |  | 2023-10-31 | additional | additional | Schedule D |  |  |  | Per grass cut | [7 empty] | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | [7 empty] | 52042738
|  | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System |  | 4.3.2.1 | A40007 |  |  | Enviroflow | 0500 - Drainage & Service Ducts | Complete |  | Complete | additional | additional | 2023-10-31 |  |  |  | 560 | 687.78 | -127.78 | 1.2282 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | [7 empty] | 45924777
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2657 |  | 2657 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 286/3 | 282/5 | 12013630 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3737 |  | 3737 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013631 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 148 |  | 148 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013632 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 6829 |  | 6829 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013633 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3229 |  | 3229 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013634 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2283 |  | 2283 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013635 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2154 |  | 2154 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013636 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 9998 |  | 9998 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013637 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4261 |  | 4261 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 286/3 | 282/5 | 12013638 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3689 |  | 3689 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 286/3 | 282/5 | 12013639 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1424 |  | 1424 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 291/3 | 285/8 | 12013640 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1447 |  | 1447 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013641 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1555 |  | 1555 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013642 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4699 |  | 4699 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 282/8 | 288/6 | 12013643 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 898 |  | 898 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 154/7 | 154/2 | 12013644 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1177 |  | 1177 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 154/7 | 154/2 | 12013645 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4024 |  | 4024 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013646 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4024 |  | 4024 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013647 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5491 |  | 5491 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013648 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 6156 |  | 6156 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013649 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4840 |  | 4840 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013650 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5676 |  | 5676 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013651 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1573 |  | 1573 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013652 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2986 |  | 2986 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 291/3 | 293/0M18 M62 155/9 EB | 12013653 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 205 |  | 205 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 283/1 | 281/0 | 12013654 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 708 |  | 708 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 281/4 | 277/3 | 12013655 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1350 |  | 1350 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 281/4 | 277/3 | 12013656 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 684 |  | 684 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 281/4 | 277/3 | 12013657 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 885 |  | 885 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 281/4 | 277/3 | 12013658 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3406 |  | 3406 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013659 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1035 |  | 1035 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013660 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2266 |  | 2266 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013661 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2016 |  | 2016 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013662 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 13347 |  | 13347 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013663 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 6533 |  | 6533 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013664 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 984 |  | 984 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013665 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 216 |  | 216 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013666 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 646 |  | 646 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013667 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1595 |  | 1595 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013668 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1595 |  | 1595 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013669 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 12722 |  | 12722 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013670 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3373 |  | 3373 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 273/6 | 268/8 | 12013671 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 6726 |  | 6726 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013672 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3356 |  | 3356 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013673 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5661 |  | 5661 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013674 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9259 |  | 9259 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013675 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5151 |  | 5151 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013676 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5082 |  | 5082 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013677 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 449 |  | 449 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013678 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5335 |  | 5335 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013679 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2615 |  | 2615 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013680 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2201 |  | 2201 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 261/2 | 257/0 | 12013681 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 6127 |  | 6127 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 261/2 | 257/0 | 12013682 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 15466 |  | 15466 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013683 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 6374 |  | 6374 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013684 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5208 |  | 5208 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013685 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2477 |  | 2477 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013686 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4968 |  | 4968 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013687 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1326 |  | 1326 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013688 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 935 |  | 935 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013689 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4060 |  | 4060 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013690 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1856 |  | 1856 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013691 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 683 |  | 683 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013692 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1391 |  | 1391 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013693 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 6987 |  | 6987 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013694 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4631 |  | 4631 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013695 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1221 |  | 1221 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013696 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1136 |  | 1136 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013697 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2955 |  | 2955 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013698 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9061 |  | 9061 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013699 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3149 |  | 3149 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013700 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9061 |  | 9061 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013701 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 479 |  | 479 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 283/1 | 281/0 | 12013702 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2923 |  | 2923 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 281/4 | 277/3 | 12013703 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1426 |  | 1426 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013704 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 7613 |  | 7613 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013705 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2059 |  | 2059 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS |  | Days |  | Days | Every 7 years | 277/7 | 273/2 | 12013706 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2601 |  | 2601 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013707 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3404 |  | 3404 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013708 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 376 |  | 376 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013709 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5305 |  | 5305 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS |  | Days |  | Days | Every 7 years | 264/5 | 260/6 | 12013710 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9192 |  | 9192 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013711 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9192 |  | 9192 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013712 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 6367 |  | 6367 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013713 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 8445 |  | 8445 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE85 Closure 1 SB NS |  | Days |  | Days | Every 7 years | 269/2 | 264/0 | 12013714 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 9997 |  | 9997 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE63 Closure 1 NB NS |  | Days |  | Days | Every 7 years |  |  | 12013715
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5542 |  | 5542 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE62 Closure 1 SB NS |  | Days |  | Days | Every 7 years |  |  | 12013716
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5812 |  | 5812 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE63 Closure 1 SB NS |  | Days |  | Days | Every 7 years |  |  | 12013717
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2373 |  | 2373 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE62 Closure 1 SB NS |  | Days |  | Days | Every 7 years |  |  | 12013718
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5614 |  | 5614 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013719 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5995 |  | 5995 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013720 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4546 |  | 4546 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013721 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1189 |  | 1189 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE83 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013722 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4806 |  | 4806 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013723 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 7227 |  | 7227 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 256/4 | 260/6 | 12013724 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2083 |  | 2083 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013725 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3098 |  | 3098 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013726 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1487 |  | 1487 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013727 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1376 |  | 1376 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013728 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1238 |  | 1238 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013729 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 22031 |  | 22031 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013730 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3649 |  | 3649 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013731 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 5861 |  | 5861 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 260/0 | 264/8 | 12013732 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 8009 |  | 8009 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013733 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 8473 |  | 8473 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013734 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1470 |  | 1470 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013735 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1625 |  | 1625 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013736 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 5860 |  | 5860 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013737 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 8180 |  | 8180 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013738 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 7933 |  | 7933 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013739 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 509 |  | 509 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013740 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3109 |  | 3109 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013741 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 509 |  | 509 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013742 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1572 |  | 1572 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013743 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 12317 |  | 12317 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 268/4 | 272/8 | 12013744 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1751 |  | 1751 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 272/4 | 276/8 | 12013745 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3282 |  | 3282 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS |  | Days |  | Days | Every 7 years | 272/4 | 276/8 | 12013746 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1923 |  | 1923 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 276/4 | 280/8 | 12013747 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 537 |  | 537 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 276/4 | 280/8 | 12013748 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2718 |  | 2718 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 276/4 | 280/8 | 12013749 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 1008 |  | 1008 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 276/4 | 280/8 | 12013750 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 838 |  | 838 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 280/4 | 283/4 | 12013751 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 205 |  | 205 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 280/4 | 283/4 | 12013752 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 234 |  | 234 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 280/4 | 283/4 | 12013753 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 213 |  | 213 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 280/4 | 283/4 | 12013754 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 14796 |  | 14796 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013755 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3444 |  | 3444 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013756 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 6845 |  | 6845 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013757 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 4188 |  | 4188 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013758 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3661 |  | 3661 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013759 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3661 |  | 3661 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013760 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 3411 |  | 3411 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013761 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 13282 |  | 13282 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013762 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 852 |  | 852 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 253/0 | 257/0 | 12013763 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 21508 |  | 21508 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 264/4 | 268/8 | 12013764 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3422 |  | 3422 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 264/4 | 268/8 | 12013765 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 517 |  | 517 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE85 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 264/4 | 268/8 | 12013766 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 2680 |  | 2680 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS |  | Days |  | Days | Every 7 years | 276/4 | 280/8 | 12013767 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-02-29 |  |  |  | 3172 |  | 3172 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 280/4 | 283/4 | 12013768 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 2631 |  | 2631 | 0 |  |  |  |  | YNE83: M18 Link-J1 | YNE63 Closure 1 SB NS |  | Days |  | Days | Every 7 years |  |  | 12013769
|  | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 1212 |  | 1212 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS |  | Days |  | Days | Every 7 years | 264/4 | 268/8 | 12013770 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5804 |  | 5804 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | [7 empty] | 12012650
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3426 |  | 3426 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012662
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 8974 |  | 8974 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012661
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5273 |  | 5273 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012649
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 346 |  | 346 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012652
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4295 |  | 4295 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012653
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-12-07 |  |  | 2023-12-31 |  |  |  | 8063 | 8063 | 0 | 1 |  |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012672
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4020 |  | 4020 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | [7 empty] | 12012663
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-12-07 |  |  | 2023-12-31 |  |  |  | 5307 | 5307 | 0 | 1 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | [7 empty] | 12012656
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-12-07 |  |  | 2023-12-31 |  |  |  | 13254 | 13254 | 0 | 1 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | [7 empty] | 12012657
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 241 |  | 241 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012654
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1550 |  | 1550 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012664
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 441 |  | 441 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012660
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 7852 |  | 7852 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012655
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 888 |  | 888 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012674
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 9300 |  | 9300 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012671
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 178 |  | 178 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012684
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5971 |  | 5971 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012668
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 9971 |  | 9971 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012670
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3957 |  | 3957 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012667
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 8264 |  | 8264 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | [7 empty] | 12012669
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 9758 |  | 9758 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | [5 empty] | 189/5 | 184/5 | 12012675 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 676 |  | 676 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | [5 empty] | 189/5 | 184/5 | 12012685 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1800 |  | 1800 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012665
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 4438 |  | 4438 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012666
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 2170 |  | 2170 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012698 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 7900 |  | 7900 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | [5 empty] | 189/5 | 184/5 | 12012673 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5634 |  | 5634 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012706
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 645 |  | 645 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012701 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 1595 |  | 1595 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012702 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 892 |  | 892 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012707 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 2073 |  | 2073 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012709 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 1367 |  | 1367 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012719 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 837 |  | 837 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012704 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 3052 |  | 3052 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012705 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 7507 |  | 7507 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012699 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 2454 |  | 2454 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012700 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 822 |  | 822 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012723 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 5679 |  | 5679 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012708 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 10577 |  | 10577 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012710 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 1078 |  | 1078 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012711 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-08 |  | 2023-12-09 |  |  | 2023-12-31 |  |  |  | 1183 |  | 1183 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | [5 empty] | 191/1 | 195/5 | 12012712 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 1363 |  | 1363 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012713
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 3350 |  | 3350 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012720
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 256 |  | 256 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012721
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 46 |  | 46 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012722
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 1196 |  | 1196 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012714
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 468 |  | 468 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012716
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2023-12-31 |  |  |  | 750 |  | 750 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012718
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 894 |  | 894 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012717
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 689 |  | 689 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012715
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 2243 |  | 2243 | 0 |  | Y | Unable to complete Major Projects |  | YNE21: A63 Priory Way - Brighton St | YNE21 Closure 1 EB NS | [7 empty] | 12012724
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 879 |  | 879 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012725
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2527 |  | 2527 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012689
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2233 |  | 2233 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012683
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 376 |  | 376 | 0 | 6/12 one plot completed - ran out of time. Heavy rain delayed |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | [7 empty] | 12012687
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1764 |  | 1764 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012682
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3683 |  | 3683 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012676
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 497 |  | 497 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012678
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 500 |  | 500 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012694
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3275 |  | 3275 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012691
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 871 |  | 871 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012696
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3078 |  | 3078 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | [7 empty] | 12012703
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2383 |  | 2383 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012693
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 590 |  | 590 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012679
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2339 |  | 2339 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012688
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 37 |  | 37 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012686
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 291 |  | 291 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012695
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2046 |  | 2046 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012690
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2588 |  | 2588 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012697
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 127 |  | 127 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012692
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3161 |  | 3161 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012680
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1630 |  | 1630 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012681
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1118 |  | 1118 | 0 | 4/12 - closure cancelled rain |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | [7 empty] | 12012677
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 3436 |  | 3436 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012658
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 790 |  | 790 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012659
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1046 |  | 1046 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | [7 empty] | 12012651
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 122 |  | 122 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | [7 empty] | 12012745
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 136 |  | 136 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | [7 empty] | 12012749
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 73 |  | 73 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | [7 empty] | 12012747
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 132 |  | 132 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | [7 empty] | 12012748
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A |  |  |  | 468 |  | 468 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | [7 empty] | 12012741
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A |  |  |  | 1585 |  | 1585 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | [7 empty] | 12012743
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A |  |  |  | 753 |  | 753 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | [7 empty] | 12012742
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 170 |  | 170 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | [7 empty] | 12012737
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 53 |  | 53 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | [7 empty] | 12012738
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 170 |  | 170 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | [7 empty] | 12012739
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 5164 |  | 5164 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012727
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 21488 |  | 21488 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012728
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 4965 |  | 4965 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012729
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 892 |  | 892 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012726
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 188 |  | 188 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012736
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 1192 |  | 1192 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012735
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 5758 |  | 5758 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012730
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 1814 |  | 1814 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012731
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 704 |  | 704 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012734
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 344 |  | 344 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure 1 EB NS | [7 empty] | 12012733
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete major works |  |  |  |  | 2024-03-31 |  |  |  | 373 |  | 373 | 0 |  | Y | Unable to complete Major Projects |  | YNE22: A63 Brighton St - Daltry St | YNE22 Closure WB NS | [7 empty] | 12012732
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-03-31 |  |  |  | 148 |  | 148 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | [7 empty] | 12012746
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A |  |  |  | 784 |  | 784 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | [7 empty] | 12012744
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A |  |  |  | 173 |  | 173 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | [7 empty] | 12012740
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 2096 | 2096 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | [5 empty] | 2/6 | 0/0 | 12012936 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 9436 | 9436 | 0 | 1 | 06/11 Unable to complete - woodland plot | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | [5 empty] | 2/6 | 0/0 | 12012937 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 873 | 873 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | [5 empty] | 2/6 | 0/0 | 12012942 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 4852 | 4852 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | [5 empty] | 2/6 | 0/0 | 12012943 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 17230 | 17230 | 0 | 1 | 06/11 Unable to complete - woodland plot | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | [5 empty] | 58/3 & 0/0 R,Bout | 3/0 0/7 | 12012935 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 219 | 219 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | [5 empty] | 58/3 & 0/0 R,Bout | 3/0 0/7 | 12012939 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 23 | 23 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | [5 empty] | 58/3 & 0/0 R,Bout | 3/0 0/7 | 12012940 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 3259 |  | 3259 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE42: A64 Headley - A162 | YNE42 Closure 1 WB NS | [7 empty] | 12012944
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 611 |  | 611 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE42: A64 Headley - A162 | YNE42 Closure 1 WB NS | [7 empty] | 12012771
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 74 |  | 74 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12012757 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 966 |  | 966 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12012768 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 16 |  | 16 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12012769 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 658 | 658 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012756
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 248 | 248 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012752
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 60 | 60 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012753
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 518 | 518 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012754
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 1689 | 1689 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012767
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 511 | 511 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012765
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 168 | 168 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012804
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 149 | 149 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012805
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 982 | 982 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012806
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1002 | 1002 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012803
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 49 | 49 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012802
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 14433 | 14433 | 0 | 1 | 6/11 unable to complete - this is a woodland plot | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012810
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 10414 | 10414 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012770
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 63 | 63 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012813
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 96 | 96 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012814
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 753 | 753 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012808
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 186 | 186 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012809
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 411 | 411 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012811
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 118 | 118 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12012812
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 882 | 882 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012815
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 4463 | 4463 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012786
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1549 |  | 1549 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | Off Network Plot | [7 empty] | 12012789
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 3331 |  | 3331 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012790
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 1933 | 1933 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12012787
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 3849 | 3849 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | [7 empty] | 12012794
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1427 | 1427 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | [7 empty] | 12012795
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 353 | 353 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | [7 empty] | 12012797
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1215 |  | 1215 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012793
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 168 | 168 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012800
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 308 | 308 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | [7 empty] | 12012799
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 282 | 282 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012782
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 150 | 150 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | [7 empty] | 12012801
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1390 | 1390 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012798
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 2199 | 2199 | 0 | 1 | 6/11 Not NH to maintain. TH updating Envis | N | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012796
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 3361 |  | 3361 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012784
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2952 |  | 2952 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012785
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 579 | 579 | 0 | 1 | 6/11 unable to complete this is a woodland plot | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | [7 empty] | 12012779
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2344 |  | 2344 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | [7 empty] | 12012781
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 2079 | 2079 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | [7 empty] | 12012778
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 5838 | 5838 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | [7 empty] | 12012776
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-16 |  |  | 2023-11-30 |  |  |  | 639 | 639 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | [7 empty] | 12012777
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 3941 | 3941 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | [7 empty] | 12012774
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 458 | 458 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | [7 empty] | 12012775
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 2840 | 2840 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | [7 empty] | 12012875
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 5108 | 5108 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | [7 empty] | 12012884
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 1884 | 1884 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | [7 empty] | 12012886
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 3795 | 3795 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | [7 empty] | 12012878
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 1275 | 1275 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | [7 empty] | 12012879
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-17 |  |  | 2023-11-30 |  |  |  | 9176 | 9176 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | [7 empty] | 12012885
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 32 | 32 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | [7 empty] | 12012877
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 2235 | 2235 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | [7 empty] | 12012873
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 67 | 67 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | [7 empty] | 12012874
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2024-02-29 |  |  |  | 791 | 791 | 0 | 1 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 WB NS |  | Days | [5 empty] | 12012863
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 5075 |  | 5075 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012893
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 291 |  | 291 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012889
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 385 |  | 385 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012844
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 283 |  | 283 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012828
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2163 |  | 2163 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012830
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2126 |  | 2126 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012831
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 471 |  | 471 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS |  | Days | [5 empty] | 12012832
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 1020 | 1020 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012833
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 1371 | 1371 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012845
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 646 | 646 | 0 | 1 |  | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012846
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 1951 | 1951 | 0 | 1 |  | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012836
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 3085 | 3085 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012837
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 816 | 816 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012834
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 1827 | 1827 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012835
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 1850 | 1850 | 0 | 1 | c res plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | [7 empty] | 12012841
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-20 |  |  | 2023-11-30 |  |  |  | 1400 | 1400 | 0 | 1 | 20/11 cres plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | [7 empty] | 12012838
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 2525 | 2525 | 0 | 1 | c res plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | [7 empty] | 12012823
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 540 | 540 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | [7 empty] | 12012822
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 3987 | 3987 | 0 | 1 | 11/21/2023 Cres grass cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | [7 empty] | 12012824
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 234 | 234 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012825
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 506 | 506 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012826
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 552 |  | 552 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | [7 empty] | 12012852
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 5406 | 5406 | 0 | 1 | 11/21/2023; Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012821
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1852 | 1852 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012818
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1125 | 1125 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012820
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1626 | 1626 | 0 | 1 | 11/21/2023: Centre res cut | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | [7 empty] | 12012817
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 67 |  | 67 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS |  | Days | [5 empty] | 12012861
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 42 |  | 42 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS |  | Days | [5 empty] | 12012862
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1792 |  | 1792 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS |  | Days | [5 empty] | 12012855
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2690 |  | 2690 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS |  | Days | [5 empty] | 12012859
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-22 |  |  | 2023-11-30 |  |  |  | 9430 | 9430 | 0 | 1 | 22/11 plot not found | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12012911 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 1407 |  | 1407 | 0 | 22/11 needs slip closure | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Requires EB Exit @Musley Closing |  |  |  |  | 50/5 | 50/7 | 12012912 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 1173 | 1173 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | [7 empty] | 12012915
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 770 | 770 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12012919 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 2707 |  | 2707 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012921 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 97 | 97 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12012922 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 869 | 869 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12012918 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 43 | 43 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | [7 empty] | 12012920
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 4960 | 4960 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | [7 empty] | 12012916
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 5422 |  | 5422 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12012932 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 4674 |  | 4674 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012931 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 2562 |  | 2562 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012929 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 2977 |  | 2977 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12012928 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 111 |  | 111 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12012933
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 2092 |  | 2092 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012925 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 3604 |  | 3604 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012924 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 9423 |  | 9423 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12012923 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 3129 |  | 3129 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012926 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 1259 |  | 1259 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012927 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 371 |  | 371 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012766 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 1373 |  | 1373 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12012930 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 111 |  | 111 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12012934
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2413 |  | 2413 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012750
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-15 |  | 2023-12-16 |  |  | 2023-12-31 |  |  |  | 3018 |  | 3018 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | [5 empty] | 283/3M18 SB J5 Exit Slip | 2/5 | 12013404 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-15 |  | 2023-12-16 |  |  | 2023-12-31 |  |  |  | 3996 |  | 3996 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | [5 empty] | 283/3M18 SB J5 Exit Slip | 2/5 | 12013405 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-15 |  | 2023-12-16 |  |  | 2023-12-31 |  |  |  | 7171 |  | 7171 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | [5 empty] | 283/3M18 SB J5 Exit Slip | 2/5 | 12013358 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 207 |  | 207 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013366 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 2420 |  | 2420 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013363 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 4402 |  | 4402 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013360 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1401 |  | 1401 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013361 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1309 |  | 1309 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013362 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 1481 |  | 1481 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013367 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1163 |  | 1163 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013368 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 208 |  | 208 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013365 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 395 |  | 395 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013364 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 943 |  | 943 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013378 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 545 |  | 545 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013369 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 6009 |  | 6009 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013371 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 1486 |  | 1486 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013377 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 4188 |  | 4188 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013370 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 1017 |  | 1017 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013374 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 7447 |  | 7447 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013375 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 2756 |  | 2756 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013376 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 92 |  | 92 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013372 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 672 | 672 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | [5 empty] | 58/3 & 0/0 R,Bout | 3/0 0/7 | 12012951 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 2063 | 2063 | 0 | 1 | 6/11 unable to complete no location info | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | [5 empty] | 2/6 | 0/0 | 12012948 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 3067 |  | 3067 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE42: A64 Headley - A162 | YNE42 Closure 1 WB NS | [7 empty] | 12012954
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 4637 | 4637 | 0 | 1 | 6/11 unable to compete no location info | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | [5 empty] | 1/7 | 5/7 | 12012960 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1635 | 1635 | 0 | 1 | 6/11 unable to location no location details on map | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | [5 empty] | 1/7 | 5/7 | 12012956 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-11 |  |  | 2023-11-30 |  |  |  | 661 | 661 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | [7 empty] | 12012964
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-11 |  |  | 2023-11-30 |  |  |  | 3724 | 3724 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | [7 empty] | 12012961
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-11 |  |  | 2023-11-30 |  |  |  | 1226 | 1226 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | [7 empty] | 12013269
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 891 |  | 891 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013271 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 3561 | 3561 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | [7 empty] | 12013268
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 796 | 796 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013265
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 7456 | 7456 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013267
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 284 | 284 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012969
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 125 | 125 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12012971
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 144 |  | 144 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013257 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 282 | 282 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013258 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 60 |  | 60 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013260 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 629 | 629 | 0 | 1 | 6/11 unable to complete - unmaintainable this is a planted hedge/woodland | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013262
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1932 | 1932 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013263 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 958 | 958 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013264
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1201 | 1201 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013259
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 3624 | 3624 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013274
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 2198 | 2198 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013254
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 1149 | 1149 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013255
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 133 | 133 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013256
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 3127 | 3127 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013275 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 382 |  | 382 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013279 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 2655 |  | 2655 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013277 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 2187 | 2187 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013276 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 1911 | 1911 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013251
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 715 | 715 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013252 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1694 |  | 1694 | 0 | 14/11 not complete due to banking access | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013253
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 335 | 335 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013247
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 1635 | 1635 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013248 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 3768 | 3768 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013249
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-14 |  |  | 2023-11-30 |  |  |  | 1588 | 1588 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013250
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 112 |  | 112 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013280 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1980 | 1980 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013281 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 2089 |  | 2089 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013282 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 2972 |  | 2972 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013283 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 440 |  | 440 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013284 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 771 |  | 771 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013285 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 902 | 902 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013243 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 1767 | 1767 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013244
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 3138 | 3138 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013245
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 1843 | 1843 | 0 | 1 | 6/11 unable to complete - this is a centre res grass cut | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013246 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 394 |  | 394 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013238 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 202 | 202 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013231
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 1328 | 1328 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013228
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 48 |  | 48 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013236 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 160 |  | 160 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013240 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-06 |  |  | 2023-11-30 |  |  |  | 39 | 39 | 0 | 1 | 6/11 Unable to complete - Nothing in this area apart from tarmac and stones. | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013242 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 17 | 17 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013227
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1382 | 1382 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12013232
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 348 |  | 348 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013233 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 543 | 543 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12013230
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 26 |  | 26 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013239 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-11-30 |  |  |  | 27 |  | 27 | 0 | 13/11 cancelled due to bad weather | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | [5 empty] | 9/1 | 15/6 | 12013234 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 47 | 47 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | [7 empty] | 12013235
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-15 |  |  | 2023-11-30 |  |  |  | 3359 | 3359 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | [7 empty] | 12013229
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1040 | 1040 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12013286
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 1438 | 1438 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | [7 empty] | 12013291
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | Complete |  |  | 2023-11-30 |  |  |  | 882 | 882 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | [7 empty] | 12013288
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 1598 | 1598 | 0 | 1 | c res plot | N |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | [7 empty] | 12013223
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 4695 | 4695 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12013210 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 3932 |  | 3932 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12013218 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 3071 | 3071 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | [5 empty] | 50/5 | 50/7 | 12013219 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 1967 |  | 1967 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Pickering EB Entry closing |  |  |  |  | 55/5 | 58/3 | 12013220 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-23 |  |  | 2023-11-30 |  |  |  | 526 | 526 | 0 | 1 |  | N |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | [7 empty] | 12013217
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 458 |  | 458 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12013222 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 3755 |  | 3755 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12013221 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 288 |  | 288 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12013293 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-09 |  | 2024-01-10 |  |  | 2023-11-30 |  |  |  | 455 |  | 455 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | [5 empty] | 58/3 | 55/0 | 12013294 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 233 |  | 233 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12013295 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-15 |  | 2024-01-16 |  |  | 2023-11-30 |  |  |  | 425 |  | 425 | 0 | 23/11 Cancelled due to high winds | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | [5 empty] | 55/5 | 58/3 | 12013292 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 356 |  | 356 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013179
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1729 |  | 1729 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013207
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 203 |  | 203 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013208
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 424 |  | 424 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013209
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 785 |  | 785 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013184
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1890 |  | 1890 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS |  | Days | [5 empty] | 12013185
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 246 |  | 246 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS |  | Days | [5 empty] | 12013186
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 778 |  | 778 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013203
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 525 |  | 525 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013204
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1297 |  | 1297 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013205
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 592 |  | 592 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013206
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1952 |  | 1952 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013201
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1387 |  | 1387 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS |  | Days | [5 empty] | 12013202
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 38 |  | 38 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013190
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 63 |  | 63 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013191
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 49 |  | 49 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013192
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 75 |  | 75 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013193
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 93 |  | 93 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013194
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 45 |  | 45 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013195
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 76 |  | 76 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013196
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 65 |  | 65 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013197
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 96 |  | 96 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013198
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 45 |  | 45 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013199
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 21 |  | 21 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013200
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 45 |  | 45 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013138
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 99 |  | 99 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013139
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 63 |  | 63 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013140
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 86 |  | 86 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013141
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 54 |  | 54 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013142
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 32 |  | 32 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013143
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 37 |  | 37 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013144
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 51 |  | 51 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013145
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 32 |  | 32 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013146
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 23 |  | 23 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013147
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 11 |  | 11 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013148
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 37 |  | 37 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013149
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 46 |  | 46 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013150
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 31 |  | 31 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013151
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 22 |  | 22 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013152
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 15 |  | 15 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013153
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 24 |  | 24 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013154
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 7 |  | 7 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013155
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 17 |  | 17 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013156
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 8 |  | 8 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013157
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 15 |  | 15 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013158
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 35 |  | 35 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013159
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3381 |  | 3381 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013162
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 5118 |  | 5118 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013165
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 283 |  | 283 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013166
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 584 |  | 584 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013131
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3150 |  | 3150 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013132
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1273 |  | 1273 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013134
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 170 |  | 170 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013136
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2022 |  | 2022 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013137
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1226 |  | 1226 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013133
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2147 |  | 2147 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013039
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 832 |  | 832 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013040
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3272 |  | 3272 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013041
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 246 |  | 246 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013043
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 771 |  | 771 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013044
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 962 |  | 962 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013045
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1041 |  | 1041 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013046
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 324 |  | 324 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013047
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 770 |  | 770 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013050
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1755 |  | 1755 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013051
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1932 |  | 1932 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013052
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 173 |  | 173 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013053
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 504 |  | 504 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013054
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 506 |  | 506 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013048
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 366 |  | 366 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013049
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 29 |  | 29 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013062
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 721 |  | 721 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013058
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1836 |  | 1836 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013059
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2098 |  | 2098 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013060
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 901 |  | 901 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013061
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 198 |  | 198 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013055
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 51 |  | 51 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013030
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 82 |  | 82 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013056
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 126 |  | 126 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013057
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 199 |  | 199 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013071
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3271 |  | 3271 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013074
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1089 |  | 1089 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013075
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1470 |  | 1470 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013076
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 621 |  | 621 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013077
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1279 |  | 1279 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013078
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1297 |  | 1297 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013079
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1341 |  | 1341 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013080
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 917 |  | 917 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013081
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 34 |  | 34 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013082
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 230 |  | 230 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013083
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 111 |  | 111 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013084
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2935 |  | 2935 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013085
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 400 |  | 400 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013086
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1524 |  | 1524 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013072
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 796 |  | 796 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013073
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 299 |  | 299 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013065
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 496 |  | 496 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013066
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 802 |  | 802 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013067
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1785 |  | 1785 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013068
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 183 |  | 183 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013069
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 498 |  | 498 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013070
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 437 |  | 437 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013127
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 992 |  | 992 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013101
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 494 |  | 494 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013063
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1290 |  | 1290 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013064
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 258 |  | 258 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013095
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 229 |  | 229 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS |  | Days | [5 empty] | 12013096
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 45 |  | 45 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013097
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 458 |  | 458 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013098
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 274 |  | 274 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013099
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 4669 |  | 4669 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013100
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2001 |  | 2001 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013087
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 492 |  | 492 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013088
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1983 |  | 1983 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013089
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1009 |  | 1009 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013090
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 893 |  | 893 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013091
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 439 |  | 439 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013092
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1223 |  | 1223 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013093
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 774 |  | 774 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013094
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1588 |  | 1588 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013112
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2593 |  | 2593 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013113
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 562 |  | 562 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013000
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 384 |  | 384 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013001
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 586 |  | 586 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS |  | Days | [5 empty] | 12013002
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1992 |  | 1992 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013003
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3988 |  | 3988 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012946
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 36 |  | 36 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013004
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 39 |  | 39 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013005
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1975 |  | 1975 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013111
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 693 |  | 693 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013123
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 25 |  | 25 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013124
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 23 |  | 23 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013125
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 15 |  | 15 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013126
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 420 |  | 420 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013122
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 284 |  | 284 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013106
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 269 |  | 269 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013107
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 310 |  | 310 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013108
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 62 |  | 62 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013109
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1211 |  | 1211 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013110
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 513 |  | 513 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013116
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 643 |  | 643 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013117
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 520 |  | 520 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013118
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 459 |  | 459 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013119
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1097 |  | 1097 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013120
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 235 |  | 235 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013121
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 577 |  | 577 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013006
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 239 |  | 239 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013007
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 73 |  | 73 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013008
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 276 |  | 276 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013009
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2585 |  | 2585 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013102
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1657 |  | 1657 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013104
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 782 |  | 782 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013105
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 84 |  | 84 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013103
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 252 |  | 252 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013010
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1755 |  | 1755 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013011
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1544 |  | 1544 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12012988
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 3183 |  | 3183 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12012989
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2636 |  | 2636 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013012
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1466 |  | 1466 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013013
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 812 |  | 812 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013014
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 122 |  | 122 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013015
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 24 |  | 24 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013016
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 56 |  | 56 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013017
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 433 |  | 433 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013018
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 99 |  | 99 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12013019
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2191 |  | 2191 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013020
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 124 |  | 124 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013021
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1544 |  | 1544 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013022
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 44 |  | 44 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS |  | Days | [5 empty] | 12012990
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2277 |  | 2277 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012991
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1059 |  | 1059 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012992
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1346 |  | 1346 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012993
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1533 |  | 1533 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012994
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1598 |  | 1598 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012995
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 383 |  | 383 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012996
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 498 |  | 498 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012997
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1965 |  | 1965 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS |  | Days | [5 empty] | 12012998
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 4145 |  | 4145 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013023
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 364 |  | 364 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013024
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 311 |  | 311 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12013026
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 390 |  | 390 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012986
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 871 |  | 871 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS |  | Days | [5 empty] | 12012985
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 148 |  | 148 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12012983
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 149 |  | 149 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12012984
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2695 |  | 2695 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12012987
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 1518 |  | 1518 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12012999
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 9992 |  | 9992 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013034
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 188 |  | 188 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS |  | Days | [5 empty] | 12013036
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 782 |  | 782 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013114
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 458 |  | 458 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013115
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 2098 |  | 2098 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013035
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 789 |  | 789 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013031
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 4139 |  | 4139 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013032
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 5268 |  | 5268 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS |  | Days | [5 empty] | 12013033
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 200 |  | 200 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS |  | Days | [5 empty] | 12013029
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 609 |  | 609 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS |  | Days | [5 empty] | 12013027
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 865 |  | 865 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS |  | Days | [5 empty] | 12013028
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 320 |  | 320 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS |  | Days | [5 empty] | 12012976
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 530 |  | 530 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS |  | Days | [5 empty] | 12012977
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 271 |  | 271 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS |  | Days | [5 empty] | 12012978
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 672 |  | 672 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS |  | Days | [5 empty] | 12012979
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-29 |  |  | 2024-02-29 |  |  |  | 646 |  | 646 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS |  | Days | [5 empty] | 12012980
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 26 |  | 26 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013373 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 976 |  | 976 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013355 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2587 |  | 2587 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013350 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2066 |  | 2066 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013403 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 501 |  | 501 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013399 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 72 |  | 72 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013400 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1397 |  | 1397 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013401 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 6517 |  | 6517 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013347 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1155 |  | 1155 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013341 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 2511 |  | 2511 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013343 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 254 |  | 254 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013398 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1772 |  | 1772 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013338 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-02-29 |  |  |  | 1306 |  | 1306 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013335 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 7835 |  | 7835 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | [5 empty] | 260/0 | 264/8 | 12013327 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 7886 |  | 7886 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013324 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 24 |  | 24 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013326 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 95 |  | 95 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013323 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 1194 |  | 1194 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013396 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 5255 |  | 5255 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013397 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 33 |  | 33 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013392 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 598 |  | 598 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013393 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 1320 |  | 1320 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | [5 empty] | 264/5 | 260/6 | 12013394 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 1115 |  | 1115 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013388 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 3044 |  | 3044 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013389 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 4816 |  | 4816 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013390 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 591 |  | 591 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013387 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 4693 |  | 4693 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013320 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1227 |  | 1227 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013321 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2509 |  | 2509 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013317 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 4077 |  | 4077 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013314 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 7137 |  | 7137 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013310 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 4440 |  | 4440 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | [5 empty] | 253/0 | 257/0 | 12013307 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 5458 |  | 5458 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | [5 empty] | 253/0 | 257/0 | 12013308 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 4099 |  | 4099 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | [5 empty] | 253/0 | 257/0 | 12013305 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 861 |  | 861 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013304 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 1744 |  | 1744 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013357 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2417 |  | 2417 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013352 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-02-29 |  |  |  | 1594 |  | 1594 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013333 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1062 |  | 1062 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013332 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2182 |  | 2182 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013328 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 719 |  | 719 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013318 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2526 |  | 2526 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013312 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 4790 |  | 4790 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013313 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 3113 |  | 3113 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013406 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 797 |  | 797 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | [7 empty] | 12013302
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 5336 |  | 5336 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | 12013303
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 3875 |  | 3875 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013309 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 3486 |  | 3486 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013380 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 1132 |  | 1132 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013381 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 9034 |  | 9034 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013383 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 3354 |  | 3354 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013315 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 38 |  | 38 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013384 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 3350 |  | 3350 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013386 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 3029 |  | 3029 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013385 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 43 |  | 43 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | [5 empty] | 260/0 | 264/8 | 12013322 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 377 |  | 377 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | [5 empty] | 256/4 | 260/6 | 12013391 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1705 |  | 1705 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013339 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1136 |  | 1136 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013340 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 2457 |  | 2457 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013344 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 2034 |  | 2034 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013342 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 1468 |  | 1468 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013348 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 5150 |  | 5150 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013349 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 2462 |  | 2462 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013345 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1813 |  | 1813 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013346 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 89 |  | 89 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013351 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 537 |  | 537 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013402 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 1650 |  | 1650 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013356 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 12448 |  | 12448 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | [5 empty] | 253/0 | 257/0 | 12013306 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 1571 |  | 1571 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013311 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 5352 |  | 5352 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013382 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 286 |  | 286 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013316 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-22 |  | 2024-01-23 |  |  | 2024-01-31 |  |  |  | 4155 |  | 4155 | 0 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | [5 empty] | 8/3 | 12/2 | 12013296 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2229 |  | 2229 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | [7 empty] | 12013297
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1992 |  | 1992 | 0 |  |  |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | [7 empty] | 12013298
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-22 |  | 2024-01-23 |  |  | 2024-01-31 |  |  |  | 3319 |  | 3319 | 0 |  |  |  |  | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | [5 empty] | 8/3 | 12/2 | 12013299 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1418 |  | 1418 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013334 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2238 |  | 2238 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013336 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2406 |  | 2406 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013353 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 1529 |  | 1529 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013354 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-29 |  |  |  | 2341 |  | 2341 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | [5 empty] | 280/4 | 283/4 | 12013407 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 11102 |  | 11102 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | 12013300
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1704 |  | 1704 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | 12013301
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 616 |  | 616 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013329 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 5765 |  | 5765 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013330 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1457 |  | 1457 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013331 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1535 |  | 1535 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013440 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 21 |  | 21 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013447 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1183 |  | 1183 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013442 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 858 |  | 858 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013444 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 9184 |  | 9184 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013445 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 2335 |  | 2335 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013443 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1359 |  | 1359 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | [5 empty] | 286/3 | 282/5 | 12013441 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 4958 |  | 4958 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013436 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 44 |  | 44 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013437 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 1176 |  | 1176 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013438 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 18506 |  | 18506 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013432 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 1217 |  | 1217 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013435 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 2784 |  | 2784 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013423 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 18085 |  | 18085 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013424 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 2176 |  | 2176 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013426 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 7641 |  | 7641 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013427 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-14 |  | 2023-12-15 |  |  | 2023-12-31 |  |  |  | 5520 |  | 5520 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | [5 empty] | 282/8 | 288/6 | 12013449 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-12 |  | 2023-12-13 |  |  | 2023-12-31 |  |  |  | 7977 |  | 7977 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | [5 empty] | 154/7 | 154/2 | 12013422 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 26 |  | 26 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013433 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 14391 |  | 14391 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013434 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 10034 |  | 10034 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013439 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 14186 |  | 14186 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013425 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 15 |  | 15 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013428 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 669 |  | 669 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013429 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 2668 |  | 2668 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013430 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-12-31 |  |  |  | 7122 |  | 7122 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | [5 empty] | 291/3 | 285/8 | 12013431 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 187 |  | 187 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013496 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 1464 |  | 1464 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013497 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 11778 |  | 11778 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013498
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 5440 |  | 5440 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013499
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 2801 |  | 2801 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013420 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 2449 |  | 2449 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | [5 empty] | 291/3 | 293/0M18 M62 155/9 EB | 12013421 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2142 |  | 2142 | 0 | 27/11 TM on slips removed following lining so not completed | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013586
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1215 |  | 1215 | 0 | 29/11 plot not accessible as high metal fence preventing access | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013587
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2023-11-30 |  |  |  | 4548 | 4548 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013502
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2023-11-30 |  |  |  | 684 | 684 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013560
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2023-11-30 |  |  |  | 4100 | 4100 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013561
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 7442 | 7442 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013605
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1492 |  | 1492 | 0 | 27/11 TM on slips removed following lining so not completed | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013589
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 1540 | 1540 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013588
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2023-11-30 |  |  |  | 2249 | 2249 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013608
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Unable ot complete |  |  |  |  | 2023-11-30 |  |  |  | 3680 | 3680 | 0 | 1 |  | Y | Unable to complete this FY due to scheme restricting access |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013609
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2023-11-30 |  |  |  | 1349 | 1349 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013501
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 3845 | 3845 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013610
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 1200 | 1200 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013571
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-29 |  |  | 2023-11-30 |  |  |  | 6767 | 6767 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | [7 empty] | 12013572
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-29 |  |  | 2023-11-30 |  |  |  | 22683 | 22683 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | [7 empty] | 12013534
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 6763 |  | 6763 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013539
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 7864 |  | 7864 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013540
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2141 |  | 2141 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013541
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1862 |  | 1862 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013573
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 349 |  | 349 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | [7 empty] | 12013581
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 4015 |  | 4015 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | [7 empty] | 12013538
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-29 |  |  | 2023-11-30 |  |  |  | 214 | 214 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | [7 empty] | 12013500
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 364 |  | 364 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | [7 empty] | 12013579
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 3100 |  | 3100 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | [7 empty] | 12013580
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 502 |  | 502 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | [7 empty] | 12013578
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 7954 |  | 7954 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | [7 empty] | 12013603
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1149 |  | 1149 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | [7 empty] | 12013604
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 18131 |  | 18131 | 0 |  | N | 27/11 TM not established due to TM vehicle breakdown |  | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | [7 empty] | 12013537
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 4670 |  | 4670 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | [7 empty] | 12013629
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 5669 |  | 5669 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013536
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1722 |  | 1722 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | [7 empty] | 12013542
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 5989 |  | 5989 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | [7 empty] | 12013625
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 9481 |  | 9481 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013624 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 13992 |  | 13992 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013551 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-11 |  | 2023-12-12 |  |  | 2023-12-31 |  |  |  | 5260 |  | 5260 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | [5 empty] | 153/0 | 155/7 291/6 | 12013552 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 4853 |  | 4853 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | [7 empty] | 12013612
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2724 |  | 2724 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | [7 empty] | 12013544
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1199 |  | 1199 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013562
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1403 |  | 1403 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013563
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2067 |  | 2067 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013547
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1741 |  | 1741 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013535
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 5986 |  | 5986 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013611
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 4374 |  | 4374 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | [7 empty] | 12013626
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1378 |  | 1378 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013545
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 542 |  | 542 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013613
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 4355 |  | 4355 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013574
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 671 |  | 671 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013546
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2307 |  | 2307 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013549
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 260 |  | 260 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013615
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1692 |  | 1692 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013614
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 889 |  | 889 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | [7 empty] | 12013550
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2530 |  | 2530 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013616
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 9364 |  | 9364 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013543
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1712 |  | 1712 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013593
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1471 |  | 1471 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013600
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1527 |  | 1527 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013599
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 7738 |  | 7738 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013595
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 2836 |  | 2836 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013592
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 5778 |  | 5778 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013598
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 601 |  | 601 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013596
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 998 |  | 998 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013597
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 380 |  | 380 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013594
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 761 |  | 761 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013564
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1575 |  | 1575 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013590
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 2461 |  | 2461 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013601
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1285 |  | 1285 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013529
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1616 |  | 1616 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013591
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 920 |  | 920 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013602
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 633 |  | 633 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013531
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 332 |  | 332 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013530
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 931 |  | 931 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013528
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 1655 |  | 1655 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013533 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1155 |  | 1155 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013565
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 2161 |  | 2161 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013566
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 1503 |  | 1503 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013567 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 3871 |  | 3871 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013568
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 2441 |  | 2441 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013569 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 6362 |  | 6362 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013570 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 328 |  | 328 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013504 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1218 |  | 1218 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013507
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1544 |  | 1544 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | [7 empty] | 12013575
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 3214 |  | 3214 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013607 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1109 |  | 1109 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013617
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2431 |  | 2431 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013554
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 25931 |  | 25931 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | [5 empty] | 172/6 | 168/2 | 12013606 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1238 |  | 1238 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013505
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1134 |  | 1134 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013506
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 1336 |  | 1336 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013532
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 1970 |  | 1970 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | [5 empty] | 172/6 | 168/2 | 12013526 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 | Subject to roadspace approval |  |  | 440 |  | 440 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | [7 empty] | 12013527
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 6130 |  | 6130 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013503
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 479 |  | 479 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013619 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 651 |  | 651 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013620 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 1736 |  | 1736 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013621 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 9530 |  | 9530 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | [5 empty] | 168/2 | 172/8 | 12013577 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-13 |  | 2023-12-14 |  |  | 2023-11-30 |  |  |  | 8839 |  | 8839 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | [5 empty] | 172/6 | 168/2 | 12013576 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1970 |  | 1970 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013553
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 693 |  | 693 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013622
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 6416 |  | 6416 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013623
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 47 |  | 47 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013628
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 931 |  | 931 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013555
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-30 |  |  |  | 1428 |  | 1428 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013618
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 559 |  | 559 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013627
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 2457 |  | 2457 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013524
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 1285 |  | 1285 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | [7 empty] | 12013522
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5105 |  | 5105 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013523
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-12-31 |  |  |  | 5305 |  | 5305 | 0 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | [7 empty] | 12013525
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 7594 |  | 7594 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | [7 empty] | 12013548
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-29 |  |  |  | 22 |  | 22 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | [5 empty] | 283/1 | 281/0 | 12013454 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 18634 |  | 18634 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013458 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 3465 |  | 3465 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013457 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 1819 |  | 1819 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013413 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 1076 |  | 1076 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013414 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 9999 |  | 9999 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | [5 empty] | 281/4 | 277/3 | 12013462 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2836 |  | 2836 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013463 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 906 |  | 906 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013466 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 6854 |  | 6854 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | [5 empty] | 277/7 | 273/2 | 12013469 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 3791 |  | 3791 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013472 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1315 |  | 1315 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | [5 empty] | 273/6 | 268/8 | 12013473 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 6930 |  | 6930 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013483 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 607 |  | 607 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013484 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 108 |  | 108 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013487 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 56 |  | 56 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013488 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 620 |  | 620 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013489 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2154 |  | 2154 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013490 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-29 |  | 2024-01-30 |  |  | 2024-01-31 |  |  |  | 3680 |  | 3680 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | [5 empty] | 261/2 | 257/0 | 12013495 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 16738 |  | 16738 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | [5 empty] | 269/2 | 264/0 | 12013481 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-26 |  | 2024-01-27 |  |  | 2024-01-31 |  |  |  | 2971 |  | 2971 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | [5 empty] | 253/0 | 257/0 | 12013494 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 814 |  | 814 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013475 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 59 |  | 59 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013476 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-01 |  | 2024-02-02 |  |  | 2024-02-29 |  |  |  | 1530 |  | 1530 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | [5 empty] | 268/4 | 272/8 | 12013474 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 2580 |  | 2580 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013467 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 7757 |  | 7757 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013468 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 3001 |  | 3001 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013471 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 873 |  | 873 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013464 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 4659 |  | 4659 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013465 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 42 |  | 42 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013418 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 1715 |  | 1715 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013448 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 1390 |  | 1390 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013461 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 5079 |  | 5079 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013459 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 3768 |  | 3768 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013411 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 2730 |  | 2730 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013412 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 11654 |  | 11654 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013460 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-29 |  |  |  | 2442 |  | 2442 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | [5 empty] | 280/4 | 283/4 | 12013452 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-29 |  |  |  | 7107 |  | 7107 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | [5 empty] | 280/4 | 283/4 | 12013453 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 651 |  | 651 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013470 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-02 |  | 2024-02-03 |  |  | 2024-02-29 |  |  |  | 20 |  | 20 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | [5 empty] | 272/4 | 276/8 | 12013419 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 49 |  | 49 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013415 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 15 |  | 15 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013416 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-29 |  |  |  | 7857 |  | 7857 | 0 |  |  |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | [5 empty] | 276/4 | 280/8 | 12013417 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-29 |  |  |  | 2017 |  | 2017 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | [5 empty] | 280/4 | 283/4 | 12013450 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2023-12-15 |  | 2023-12-16 |  |  | 2024-02-29 |  |  |  | 4927 |  | 4927 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS |  | 2 |  |  |  | 2/7 | 0/0 | 12013451 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-30 |  | 2024-01-31 |  |  | 2024-01-31 |  |  |  | 1264 |  | 1264 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | [5 empty] | 260/0 | 264/8 | 12013478 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1677 |  | 1677 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013485 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 5325 |  | 5325 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013486 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 1459 |  | 1459 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013479 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | 2024-01-31 |  | 2024-02-01 |  |  | 2024-01-31 |  |  |  | 2991 |  | 2991 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | [5 empty] | 264/4 | 268/8 | 12013480 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 1333 | 1333 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013516
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 1220 | 1220 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013512
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-30 |  |  | 2023-11-30 |  |  |  | 1316 | 1316 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | [7 empty] | 12013513
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 4188 |  | 4188 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013514
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 2282 |  | 2282 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013515
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 148 |  | 148 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013584
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 8758 |  | 8758 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013585
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2086 |  | 2086 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013583
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 487 |  | 487 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | [7 empty] | 12013556
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 3366 | 3366 | 0 | 1 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | [7 empty] | 12013557
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 1830 | 1830 | 0 | 1 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | [7 empty] | 12013517
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-21 |  |  | 2023-11-30 |  |  |  | 2621 | 2621 | 0 | 1 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | [7 empty] | 12013519
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2024-01-31 |  |  |  | 1236 | 1236 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | [7 empty] | 12013520
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-28 |  |  | 2024-01-31 |  |  |  | 6083 | 6083 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | [7 empty] | 12013518
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 3766 |  | 3766 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013521
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1716 |  | 1716 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013582
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 355 |  | 355 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013558
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1983 |  | 1983 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013559
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 209 |  | 209 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013509
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2024-01-31 |  |  |  | 1425 |  | 1425 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | [7 empty] | 12013510
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2857 |  | 2857 | 0 | 27/11 TM on slips removed following lining so not completed | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013511
|  | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment |  | 4.8.9 | A40085 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 2139 |  | 2139 | 0 | 27/11 TM on slips removed following lining so not completed | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | [7 empty] | 12013508
|  | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species |  | 4.8.11 | A40087 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 1552.8639 |  | 1552.8639 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS |  |  |  | Nights |  |  |  | 12013790
|  | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species |  | 4.8.11 | A40087 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete |  |  |  |  | 2023-11-30 |  |  |  | 2204.3316 |  | 0 | 0 | Unable to access wentbride | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE111: A1 Barnsdale-Wentbridge | YNE111 Closure 1 NB NS |  | Days |  | Days |  |  |  | 52042424
|  | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species |  | 4.8.11 | A40087 |  |  | CGS | 3000 - Landscape and Ecology | Unable to complete |  |  |  |  | 2023-11-30 |  |  |  | 23.8204 |  | 0 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE112: A1 Wentbridge-Darrington | YNE112 Closure 1 SB NS |  | Days |  | Days |  |  |  | 12013792
|  | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species |  | 4.8.11 | A40087 |  |  | CGS | 3000 - Landscape and Ecology | Complete |  | 2023-11-09 |  |  | 2023-11-30 |  |  |  | 18986.7626 | 18986.7626 | 0 | 1 |  | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS |  |  |  | Nights |  |  |  | 12013801 | 20:00 | 6:00 | Night Shift | Approved | 0
|  | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species |  | 4.8.11 | A40087 |  |  | CGS | 3000 - Landscape and Ecology | [5 empty] | 2023-11-30 |  |  |  | 106.7461 |  | 106.7461 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report |  | YNE42: A64 Headley - A162 | YNE42 Closure 1 WB NS | off site on Moor lane doesn’t need a closure |  |  | Days |  |  |  | 12013873
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 33 |  | 33 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 10 |  | 10 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 10 |  | 10 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 10 |  | 10 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices |  | 4.6.10.1 | ART023A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] |  | 4.6.10.2 | ART023B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices |  | 4.6.10.1 | ART023A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 |  | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] |  | 4.6.10.2 | ART023B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 |  | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 5 |  | 5 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE65: M1 Tinsley | YNE65 Closure | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 23 |  | 23 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 6 |  | 6 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 12 |  | 12 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 |  | 0 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 3 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 | [7 empty] | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets | [10 empty] | YNE69: M1 J36-37 | YNE69 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets | [10 empty] | YNE69: M1 J36-37 | YNE69 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets | [10 empty] | YNE69: M1 J36-37 | YNE69 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS |  |  | Yes |  |  |  |  | On ServiceNow
|  | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices |  | 4.6.10.1 | ART023A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 | 1 | 1 | 0.5 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] |  | 4.6.10.2 | ART023B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 | 1 | 1 | 0.5 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices |  | 4.6.10.1 | ART023A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] |  | 4.6.10.2 | ART023B |  |  | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP |  | Removed from Rebaselined SP |  |  | N/A | No assets |  |  | 0 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices |  | 4.6.10.1 | ART023A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] |  | 4.6.10.2 | ART023B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | Ramp Metering Traffic Light Signals - Check alignment and condition of site |  | 4.6.11 | ART024 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 |  | 4.6.5 | ART008 |  |  | Vaisala | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 |  | 4.6.5 | ART008 |  |  | Vaisala | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management | [10 empty] | YNE73: M1 J40-41 | YNE73 Closure | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | 2024-01-12 |  | 2024-01-13 |  |  | 2024-01-31 |  |  |  | 16 |  | 16 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings |  | 4.6.2.1 | ART005A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Greasing of winch assembly to manufacturers recommendations |  | 4.6.2.2 | ART005B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV Masts - Check mast breaking system |  | 4.6.2.3 | ART005C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 2 |  | 2 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance |  | 4.6.4 | ART007 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Clean camera lens |  | 4.6.13.1 | ART029A |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check camera functionality |  | 4.6.13.2 | ART029B |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | CCTV PTZ Cameras - Check data and power supplies |  | 4.6.13.3 | ART029C |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 4 |  | 4 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 1 |  | 1 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 16 | 5 | 11 | 0.3125 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2023-12-31 |  |  |  | 3 | 1 | 2 | 0.33333 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 |  | 4.6.12.1 | ART027 |  |  | Amey | 1500 - Roadside Technology | 2023-12-11 |  | 2023-12-12 |  |  | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 1 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | [7 empty] | On ServiceNow
|  | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations |  | 4.6.12.2 | ART028 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 19 | [7 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
|  | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] |  | 4.6.9 | ART030 |  |  | Amey | 1500 - Roadside Technology | [5 empty] | 2024-02-29 | Subject to share with scheme works and clash management |  |  | 7 | 0 | [6 empty] | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS |  |  | No |  |  |  |  | On ServiceNow
YNE96 Closure 1 WB NS Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7501 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 17 |  | 17 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52037832
Unsure on location Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4693 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 108 |  | 108 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure | Lane 1 Closure | 3 | TBC |  | Every 6 years |  |  | 52037850
YNE30 Closure 1 SB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7502 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 89.8853 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | Rejected
YNE30 Closure 1 SB NS Amey 45261 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7503 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 11 | 11 | 0 | 1 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 3 years |  |  | Not rasied as LED
YNE30 Closure 1 SB NS Amey 45261 BC - Lamps (LED) for Road Lighting | 7504 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 3 |  | 3 | 0 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038370
YNE30 Closure 1 SB OS Amey 45261 Electrical Testing - Network cabling and electrical components | 7505 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | LED upgrade scheme carried out testing. Confirmation on what assets were to be tested not received until 10/11/23 |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038371
YNE31 Closure 1 SB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7506 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 696.6114 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 31 | 31 | 0 | 1 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 6 years |  |  | REjected as LED
YNE31 Closure 1 SB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 7507 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | 2023-07-20 | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 52038359
YNE31 Closure 1 SB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 7508 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038360
YNE82 Closure 1 SB NS Amey 45323 Electrical Testing - Network cabling and electrical components | 7509 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2024-01-08 | 2024-1 | 2024-01-08 | 2024-02-01 | 2024-03-29 | 2024-01-08 |  | 41dys |  | 14 |  | 14 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 3 | No TM required |  | Every 6 years | 0 | 0 | 52038758 | 0:00 | 0:00 |  | 0 | 0
YNE25 Closure 1 EB NS Enviroflow 45293 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6442 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2024-01-02 | 2024-01-31 | 2024-03-31 |  | 22dys | EB | 160.58 |  | 160.58 | 0 |  |  |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 2 years |  |  | 45931236
YNE85 Closure 1 NB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7510 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7511 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | YNE85 Closure 1 SB NS | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 CCTV Masts - Check mast breaking system | 7512 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 7513 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 7514 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4434 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 17 |  | 17 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7515 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 15 |  | 15 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4361 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE84: M18 J1-2 | YNE84 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE85 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 7516 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 7517 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 7518 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4414 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 369.1632 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 26735 | 26735 | 21983.94 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 260/0 | 264/8 | 12013870 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4413 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 621.4258 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 45004.35 | 45004 | 0.35 | 0.99999 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 256/4 | 260/6 | 12013810 | 20:00 | 6:00 | Night Shift | Approved | 0
Cannot locate on map CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 7519 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  | Complete |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 1180.4 |  | 1180.4 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/210 | YNE84: M18 J1-2 | Cannot locate on map | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013853
YNE107 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4412 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1551.623 |  | 1551.623 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/149 | YNE84: M18 J1-2 | YNE107 Closure 1 SB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013799
Doesn't exist no shape file CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 7520 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 74.9104 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 43dys | EB | 5425.05 | 5425.05 | 0 | 1 | Unable to complete as no shape file and cannot locate plot | N | Unable to complete as no shape file and cannot locate plot | 2000M62/117 | YNE12: M62 J34-35 | Doesn't exist no shape file | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013860
Cannot locate on map CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 7519 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 710.7 |  | 710.7 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/44 | YNE106: A1M J34-35 | Cannot locate on map | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013793
Cannot locate on map CGS 45293 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 7521 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2024-01-02 | 2024-02-29 | 2023-11-30 |  | 43dys | SB | 2865.67 |  | 2865.67 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M1/924 | YNE62: M1 J31-32 | Cannot locate on map | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013822
|  | Litter schedule D job |  | 4.9.5 | A40098 |  |  | Amey | 4000 - Sweeping and Cleaning | Complete |  | 2023-11-04 |  |  | additional |  |  |  | 75.98 | 75.98 | 0 | 1 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | [7 empty] | 52043230
|  | Litter schedule D job |  | 4.9.6 |  |  |  |  | 4001 - Sweeping and Cleaning | [5 empty] | additional |  |  |  | 8195.77 |  | 8195.77 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | [7 empty] | 52043230
YNE4 Closure 1 EB NS Amey 45261 BC - Lamps (LED) for Illuminated Signs and Bollards | 7522 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 7 |  | 7 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Nights | Every 2 years |  |  | 52038345
YNE4 Closure 1 EB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 7523 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 22 |  | 22 | 0 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Nights | Every 6 years |  |  | 52038344
YNE4 Closure 1 EB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7524 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 134.828 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 41dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 4 | Yes | Nights | Every 6 years |  |  | 52038342
|  | v-channel schedule D |  | 4.3.2.3 |  |  |  | Amey | 3000 - Landscape and Ecology | Complete |  | Complete | [6 empty] | TBC | [7 empty] | YNE86: M18 J3-4 | YNE86 Closure 2 NB OS | [7 empty] | 52043407
|  | v-channel schedule D |  | 4.3.2.3 |  |  |  | Amey | 3000 - Landscape and Ecology | Complete |  | Complete | [6 empty] | TBC | [7 empty] | YNE86: M18 J3-4 | YNE86 Closure 2 SB OS | [7 empty] | 52043407
YNE84 Closure 2 SB NS Enviroflow 45201 G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 7525 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 0 | 4.3.3.1 | A40010 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-10-02 | 2023-11-30 |  |  | 44dys | SB | 6 |  | 6 | 0 |  |  |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 2 Closure | 3 |  |  | Every 2 years | 261/2 | 257/0 | 45927465 | 20:00 | 6:00 | Night Shift | Approved | 0
Unsure on location
YNE3 Closure 1 EB OS Amey 45261 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7526 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to access via scheme shares | 41dys |  | 122 |  | 122 | 0 |  | Y | TM cancelled due to scheme works |  | YNE4: M62 J25-26 | YNE3 Closure 1 EB OS | Lane 1 Closure | 4 | Yes | Nights | Every 3 years | 95/5 | 101/1 | 52038304 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE31 Closure 1 NB OS Amey 45261 Electrical Testing - Network cabling and electrical components | 7527 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | LED upgrade scheme carried out testing. Confirmation on what assets were to be tested not received until 10/11/23 |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038360
YNE31 Closure 1 SB OS Amey 45261 Electrical Testing - Network cabling and electrical components | 7528 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | LED upgrade scheme carried out testing. Confirmation on what assets were to be tested not received until 10/11/23 |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038360
YNE18 Closure 1 EB NS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2760 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 22 | 0 | 22 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036817
YNE18 Closure 1 EB OS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7529 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 28 | 0 | 28 | 0 |  | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036817
YNE20 Closure 1 EB NS Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7530 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 19 | 0 | 19 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years | 191/1 | 195/5 | 52036720 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45110 Electrical Testing - Network cabling and electrical components | 2777 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 22 | 0 | 22 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years | 191/1 | 195/5 | 52036726 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB OS Amey 45110 Electrical Testing - Network cabling and electrical components | 7531 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 36 | 0 | 36 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 WB OS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036726
YNE18 Closure 1 WB NS Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7532 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 6 | 0 | 6 | 0 | 4/12 - closure cancelled rain | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036818
YNE18 Closure 1 EB OS Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7533 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 64 | 0 | 64 | 0 |  | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036818
YNE18 Closure 1 EB OS Amey 45110 Electrical Testing - Network cabling and electrical components | 7534 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 94 | 0 | 94 | 0 |  | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036824
YNE18 Closure 1 EB OS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7529 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 36 | 0 | 36 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036719
YNE7 Closure 1 WB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7535 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace - full closures | 41dys |  | 10 |  | 10 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 | Yes - on WB entry slip |  | Every 6 years |  |  | 52038533
YNE8 Closure 1 WB NS Amey 45261 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7536 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 | Subject to roadspace approval | 41dys |  | 45 |  | 45 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 4 | Yes |  | Every 6 years |  |  | 52038486
YNE110 Closure 1 NB NS Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7537 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 44 |  | 44 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years | 285/8 | 289/4 | 52037779 | 20:00 | 6:00 | Night Shift | Approved | 0
TBC Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5029 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 12 |  | 12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | TBC | Lane 1 Closure | 3 | Yes on exit slip |  | Every 3 years |  |  | 52037776
YNE110 Closure 1 SB OS Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7538 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 1 Closure | 3 | Yes |  | Every 3 years |  |  | 52037776
YNE110 Closure 1 SB OS Amey 45170 Electrical Testing - Network cabling and electrical components | 7539 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52037728
YNE64 Closure Amey 45293 Electrical Testing - Network cabling and electrical components | 7540 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 Closure | 3 | No TM required |  | Every 6 years |  |  | 52038586
YNE69 Closure 1 SB NS Amey 45293 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7541 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2023-12-18 | 2023-12 | 2023-12-19 | 2024-01-02 | 2024-02-29 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years | 284/5 | 275/3 | 52038634 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE25 Closure 1 EB OS Amey 45110 Electrical Testing - Network cabling and electrical components | 7542 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 |  | 21dys |  | 70 | 0 | 70 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036953
YNE25 Closure 1 WB OS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 7543 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 |  | 21dys |  | 81 | 0 | 81 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036971
YNE30 Closure 1 NB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 7544 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038371
YNE30 Closure 1 SB NS Amey 45261 Electrical Testing - Network cabling and electrical components | 7545 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 |  | 41dys |  | 7 |  | 7 | 0 |  | N |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52038371
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2547.53 |  | 2547.53 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 590.22 |  | 590.22 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1195.58 |  | 1195.58 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 902.24 |  | 902.24 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 568.67 |  | 568.67 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1814.56 |  | 1814.56 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 839.91 |  | 839.91 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 583.33 |  | 583.33 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 29.88 |  | 29.88 | 0 |  |  |  |  | YNE106: A1M J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 369.92 |  | 369.92 | 0 |  |  |  |  | YNE11: M62 J33-34 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1612.53 |  | 1612.53 | 0 |  |  |  |  | YNE11: M62 J33-34 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1778.09 |  | 1778.09 | 0 |  |  |  |  | YNE11: M62 J33-34 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1966.86 |  | 1966.86 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 4284.76 |  | 4284.76 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 1307.85 |  | 1307.85 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 2708.74 |  | 2708.74 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 3510.14 |  | 3510.14 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 3484.91 |  | 3484.91 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 910.74 |  | 910.74 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 651.41 |  | 651.41 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 305.3 |  | 305.3 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 2246.91 |  | 2246.91 | 0 |  |  |  |  | YNE12: M62 J34-35 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 65.12 |  | 65.12 | 0 |  |  |  |  | YNE13: M62 J35-36 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 742.87 |  | 742.87 | 0 |  |  |  |  | YNE13: M62 J35-36 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 18.1 |  | 18.1 | 0 |  |  |  |  | YNE13: M62 J35-36 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 660.28 |  | 660.28 | 0 |  |  |  |  | YNE13: M62 J35-36 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 890.34 |  | 890.34 | 0 |  |  |  |  | YNE13: M62 J35-36 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 28.43 |  | 28.43 | 0 |  |  |  |  | YNE14: M62 J36-37 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 161.62 |  | 161.62 | 0 |  |  |  |  | YNE14: M62 J36-37 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 425.16 |  | 425.16 | 0 |  |  |  |  | YNE14: M62 J36-37 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-01-31 |  | 20dys | WB | 862.64 |  | 862.64 | 0 |  |  |  |  | YNE14: M62 J36-37 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 933.15 |  | 933.15 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 996.94 |  | 996.94 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 467.29 |  | 467.29 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1053.79 |  | 1053.79 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 220.74 |  | 220.74 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 547.63 |  | 547.63 | 0 |  |  |  |  | YNE15: M62 J37-38 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 139.47 |  | 139.47 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 56.73 |  | 56.73 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 421.14 |  | 421.14 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 378.58 |  | 378.58 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 3038.48 |  | 3038.48 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 218.76 |  | 218.76 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 490.66 |  | 490.66 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 905.79 |  | 905.79 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 593.9 |  | 593.9 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 41.63 |  | 41.63 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 218.73 |  | 218.73 | 0 |  |  |  |  | YNE45: A64 Bilbrough-Askham |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 229.9 |  | 229.9 | 0 |  |  |  |  | YNE45: A64 Bilbrough-Askham |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 3043.76 |  | 3043.76 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 517.34 |  | 517.34 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1707.59 |  | 1707.59 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 288.13 |  | 288.13 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 410.67 |  | 410.67 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 367.25 |  | 367.25 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1348.79 |  | 1348.79 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1140.77 |  | 1140.77 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE50 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7547 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 237.48 |  | 237.48 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE50 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7547 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 399.64 |  | 399.64 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE53 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7548 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 687.17 |  | 687.17 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE53 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7548 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 484.73 |  | 484.73 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE54 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7549 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2477.84 |  | 2477.84 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE54 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7549 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 571.44 |  | 571.44 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE58 Closure Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7550 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-02-01 |  | 2024-02-29 | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1695.18 |  | 1695.18 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1050.51 |  | 1050.51 | 0 |  |  |  |  | YNE85: M18 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1445.43 |  | 1445.43 | 0 |  |  |  |  | YNE85: M18 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 593.61 |  | 593.61 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 3394.32 |  | 3394.32 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1937.12 |  | 1937.12 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2569.83 |  | 2569.83 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2744.03 |  | 2744.03 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 139.72 |  | 139.72 | 0 |  |  |  |  | YNE86: M18 J3-4 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2634.93 |  | 2634.93 | 0 |  |  |  |  | YNE87: M18 J4-5 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2689.49 |  | 2689.49 | 0 |  |  |  |  | YNE87: M18 J4-5 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1242.48 |  | 1242.48 | 0 |  |  |  |  | YNE87: M18 J4-5 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 855.7 |  | 855.7 | 0 |  |  |  |  | YNE87: M18 J4-5 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2193.26 |  | 2193.26 | 0 |  |  |  |  | YNE88: M18 J5-6 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 2060.58 |  | 2060.58 | 0 |  |  |  |  | YNE88: M18 J5-6 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 571.86 |  | 571.86 | 0 |  |  |  |  | YNE88: M18 J5-6 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 52.95 |  | 52.95 | 0 |  |  |  |  | YNE89: M18 J6-7 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 5287.86 |  | 5287.86 | 0 |  |  |  |  | YNE89: M18 J6-7 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 4985.5 |  | 4985.5 | 0 |  |  |  |  | YNE89: M18 J6-7 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 6909.26 |  | 6909.26 | 0 |  |  |  |  | YNE89: M18 J6-7 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-02-29 |  | 20dys | WB | 1631.27 |  | 1631.27 | 0 |  |  |  |  | YNE89: M18 J6-7 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1667.24 |  | 1667.24 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1920.83 |  | 1920.83 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1555.79 |  | 1555.79 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2899.68 |  | 2899.68 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 4108.24 |  | 4108.24 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 4418.08 |  | 4418.08 | 0 |  |  |  |  | YNE91: M180 J1-2 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 343.06 |  | 343.06 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2267.39 |  | 2267.39 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2226.93 |  | 2226.93 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2733.37 |  | 2733.37 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1006.31 |  | 1006.31 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7546 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 620.27 |  | 620.27 | 0 |  |  |  |  | YNE92: M180 J2-3 |  |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7551 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 883.05 |  | 883.05 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7552 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2648.57 |  | 2648.57 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7553 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 570.97 |  | 570.97 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 2 EB NSc Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7554 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 3039.12 |  | 3039.12 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 EB NSc |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7555 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 4727.19 |  | 4727.19 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 3 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7556 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 195.41 |  | 195.41 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE93 Closure 3 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7557 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 821.51 |  | 821.51 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7558 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1032.41 |  | 1032.41 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE94 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7559 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1334.72 |  | 1334.72 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE94 Closure 1 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7558 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1889.61 |  | 1889.61 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7559 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1134.11 |  | 1134.11 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7560 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1483.98 |  | 1483.98 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7561 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 962.84 |  | 962.84 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 3 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7562 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 385.52 |  | 385.52 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 3 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7563 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1137.92 |  | 1137.92 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 4 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7564 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 90.93 |  | 90.93 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 4 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7565 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 329.76 |  | 329.76 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE95 Closure 1 SB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7566 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 41.66 |  | 41.66 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE100 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7567 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 47.01 |  | 47.01 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE100 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 4 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7564 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 27.51 |  | 27.51 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE94 Closure 4 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE94 Closure 4 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7565 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 29.6 |  | 29.6 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE94 Closure 4 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6867 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1832.88 |  | 1832.88 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 1 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6868 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1436.93 |  | 1436.93 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6870 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 571.83 |  | 571.83 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS |  | Days | TBC | Days | ILM Annually | 44/4 | 49/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6869 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 1109.73 |  | 1109.73 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE100 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7567 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 104.4 |  | 104.4 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE100 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE96 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6869 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 5 |  | 5 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE96 Closure 2 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7568 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 2006.69 |  | 2006.69 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE97 Closure 2 WB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 7569 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 839.74 |  | 839.74 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE98 Closure 1 EB NS Amey 45352 Ditches - Clean ditches by removing all material that could impair operation | 6895 | Ditches - Clean ditches by removing all material that could impair operation | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2024-03-01 | 2024-03-29 | 2024-03-31 |  | 20dys | WB | 5 |  | 5 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE98 Closure 1 EB NS |  | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE4 Closure 1 WB NS Amey 45261 Ramp Metering Traffic Light Signals - Check alignment and condition of site | 7570 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 0 | 4.6.11 | ART024 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7571 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 17 |  | 17 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7572 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7573 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV Masts - Check mast breaking system | 7574 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7575 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 39.5495 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 14 | 1 | 13 | 0.071429 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7576 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 7577 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 7578 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 7579 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 5648 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  | Nights | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7580 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2023-11-30 | Subject to access via scheme shares | 21dys |  | 30 |  | 30 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  | Nights | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7581 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 13 |  | 13 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5649 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7582 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 12 |  | 12 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7583 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7584 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE4 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 7585 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5650 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5651 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 5652 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7586 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7587 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Check mast breaking system | 7588 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 5653 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7589 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 10 |  | 10 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 5654 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7590 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 7 |  | 7 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 7591 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Every 6 years |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 5659 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 5660 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 5661 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 7592 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 7593 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 7594 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7580 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7595 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 19 |  | 19 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7596 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 24 |  | 24 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7582 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7597 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 52.7327 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 8 | 2 | 6 | 0.25 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7598 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 15 | 5 | 10 | 0.33333 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7586 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7599 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7600 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7587 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7601 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7602 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV Masts - Check mast breaking system | 7588 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV Masts - Check mast breaking system | 7603 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 CCTV Masts - Check mast breaking system | 7604 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7589 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7605 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 39.5495 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 | 1 | 4 | 0.2 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7606 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 79.0991 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 | 2 | 3 | 0.4 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7590 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | ILM Annual Network Wide | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7607 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 4 |  |  | ILM Annual Network Wide | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7608 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 4 |  | 4 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 7592 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 7593 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 7594 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE5 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually | 109/0 | 104/9 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 7609 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 7610 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 7611 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | Annually | 108/1 | 112/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Clean camera lens | 7612 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE6 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check camera functionality | 7613 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE6 Closure 1 WB NS Amey 45261 CCTV PTZ Cameras - Check data and power supplies | 7614 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | Y | Unable to access due to schemes |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 7615 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 13 |  | 13 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7616 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 9 |  | 9 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7617 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 41dys |  | 8 |  | 8 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE7 Closure 1 WB NS Amey 45261 CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 7618 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 0 | 4.6.1.1 | ART001A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-12-01 | 2024-01-31 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | Annually |  |  | On ServiceNow
YNE69 Closure 2 SB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7619 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-06-01 | 2023-07-31 | New |  | 43dys | SB | 86 |  | 86 | 0 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE41 Closure 1 EB NS Enviroflow 45261 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 7620 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-12-01 | 2023-12-29 | Addition |  | 19dys | CW | 80 |  | 0 | 0 |  | N | Drainage driver took ill - rebooked for December | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | Awaiting schedule D job from NH | 20:00 | 6:00 | Night Shift | Approved | 0