YNE104 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2489 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1452.29 | 0 | 1452.29 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818684
YNE104 Closure 3 CW NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2490 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 590.5 | 0 | 590.5 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2491 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 548 | 0 | 548 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2492 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 903 | 0 | 903 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819440
YNE104 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2492 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 897 | 0 | 897 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819440
YNE104 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2493 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 900 | 0 | 900 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819440
YNE104 Closure 3 CW NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2494 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 490 | 0 | 490 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 1 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2495 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 610 | 0 | 610 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 SB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2496 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 136 | 0 | 136 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2497 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 459 | 0 | 459 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  |  | YNE105: A638 Redhouse | YNE105 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2498 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  |  | 0 | 0 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2499 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  |  | 0 | 0 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2500 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  |  | 0 | 0 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2501 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1 | 0 | 1 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 2 | 0 | 2 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 1 | 0 | 1 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/12 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2503 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 1 | 0 | 1 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2501 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1 | 0 | 1 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 101.65 | 0 | 101.65 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 224.78 | 0 | 224.78 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/11 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 67.9 | 0 | 67.9 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/12 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 462.66 | 0 | 462.66 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 675.35 | 0 | 675.35 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2505 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | WB | 119.73 | 0 | 119.73 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/16 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | EB | 58.31 | 0 | 58.31 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  | 4400A638/9 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2506 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 2813 | 0 | 2813 | 0 |  | Y |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2507 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2508 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2509 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2511 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2511 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 636.78 | 0 | 636.78 | 0 |  | Y |  | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 89.44 | 0 | 89.44 | 0 |  | Y |  | 4700A1/309 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 136.42 | 0 | 136.42 | 0 |  | Y |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 55.3 | 0 | 55.3 | 0 |  | Y |  | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 348.12 | 0 | 348.12 | 0 |  | Y |  | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 22.77 | 0 | 22.77 | 0 |  | Y |  | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 89.64 | 0 | 89.64 | 0 |  | Y |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 84.77 | 0 | 84.77 | 0 |  | Y |  | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 35.04 | 0 | 35.04 | 0 |  | Y |  | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 196.31 | 0 | 196.31 | 0 |  | Y |  | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 50.53 | 0 | 50.53 | 0 |  | Y |  | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 64.87 | 0 | 64.87 | 0 |  | Y |  | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 27.86 | 0 | 27.86 | 0 |  | Y |  | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 220.06 | 0 | 220.06 | 0 |  | Y |  | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 134.97 | 0 | 134.97 | 0 |  | Y |  | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 109.62 | 0 | 109.62 | 0 |  | Y |  | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1093.02 | 0 | 1093.02 | 0 |  | Y |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1336.02 | 0 | 1336.02 | 0 |  | Y |  | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE113 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2514 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1041 | 0 | 1041 | 0 |  | Y |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2515 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2516 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2517 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2518 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2519 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2520 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 77.59 | 0 | 77.59 | 0 |  | Y |  | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2520 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 628.32 | 0 | 628.32 | 0 |  | Y |  | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2521 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 418.82 | 0 | 418.82 | 0 |  | Y |  | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2520 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 9.62 | 0 | 9.62 | 0 |  | Y |  | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2522 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2523 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 | 18/9: cancelled heavy rain | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037063
YNE1 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2524 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2525 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 | 18/9: cancelled heavy rain | N |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037063
YNE1 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2526 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 5276 | 0 | 5276 | 0 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 14 | 0 | 14 | 0 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 2 | 0 | 2 | 0 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 7 | 0 | 7 | 0 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 5 | 0 | 5 | 0 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 21 | 0 | 21 | 0 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 11 | 0 | 11 | 0 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 12 | 0 | 12 | 0 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 2 | 0 | 2 | 0 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 4 | 0 | 4 | 0 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2529 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 4 | 0 | 4 | 0 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2529 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 16 | 0 | 16 | 0 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2529 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 4 | 0 | 4 | 0 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2529 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 8 | 0 | 8 | 0 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2530 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 1 | 0 | 1 | 0 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2530 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 5 | 0 | 5 | 0 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2531 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 8 | 0 | 8 | 0 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2532 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 6 | 0 | 6 | 0 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2533 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 29.45 | 0 | 29.45 | 0 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2534 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 14.08 | 0 | 14.08 | 0 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2535 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2536 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037084
YNE2 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2537 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2538 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037084
YNE2 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2539 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 1284 | 0 | 1284 | 0 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2540 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 11 | 0 | 11 | 0 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2541 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 2 | 0 | 2 | 0 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2541 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 16 | 0 | 16 | 0 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2542 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 27.64 | 0 | 27.64 | 0 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2543 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 22.09 | 0 | 22.09 | 0 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2544 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 757.15 | 0 | 757.15 | 0 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2544 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 27.78 | 0 | 27.78 | 0 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2544 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 107.04 | 0 | 107.04 | 0 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2545 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2546 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2547 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 95/5 | 101/1 | 52037023 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2548 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | 52037023 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2549 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 3188 | 0 | 3188 | 0 |  | N |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 10 | 0 | 10 | 0 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 7 | 0 | 7 | 0 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 5 | 0 | 5 | 0 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 18 | 0 | 18 | 0 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 19 | 0 | 19 | 0 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2551 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 19 | 0 | 19 | 0 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2550 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 14 | 0 | 14 | 0 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2551 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 2 | 0 | 2 | 0 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2552 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 14.48 | 0 | 14.48 | 0 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2552 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 18.47 | 0 | 18.47 | 0 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2553 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 30.16 | 0 | 30.16 | 0 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2554 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 54.94 | 0 | 54.94 | 0 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2553 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 18.56 | 0 | 18.56 | 0 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2553 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 9.65 | 0 | 9.65 | 0 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE4 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2555 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 3747 | 0 | 3747 | 0 |  | N |  |  | YNE4: M62 J25-26 | YNE4 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2555 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 3747 | 0 | 3747 | 0 |  | N |  |  | YNE4: M62 J25-26 | YNE4 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2556 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2557 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2558 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2559 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 6 | 0 | 6 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 6 | 0 | 6 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 9 | 0 | 9 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 10 | 0 | 10 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 6 | 0 | 6 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 9 | 0 | 9 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 19 | 0 | 19 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039158
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2561 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 3 | 0 | 3 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45792063
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 20.11 | 0 | 20.11 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 43.43 | 0 | 43.43 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 40.07 | 0 | 40.07 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 224.29 | 0 | 224.29 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 265.92 | 0 | 265.92 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 21.47 | 0 | 21.47 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 484.93 | 0 | 484.93 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45792061
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 20.08 | 0 | 20.08 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 42.6 | 0 | 42.6 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 38.02 | 0 | 38.02 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 189.76 | 0 | 189.76 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 6.72 | 0 | 6.72 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE4 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2563 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 46.2 | 0 | 46.2 | 0 | 18/10 - cancelled storm Babet | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2564 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 3718 | 0 | 3718 | 0 | 3/10 slips not comlete | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45813669
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2565 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE5 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2566 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2567 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1, 2 & 3 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2568 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 75 | 1 | 74 | 0.013333 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 22 | 0 | 22 | 0 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2569 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2570 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2570 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 11 | 7 | 4 | 0.63636 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2570 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 49 | 0 | 49 | 0 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2570 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | 3/10 Not all Completed due to the amount of Barrier to Strim | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 56.8 | 0 | 56.8 | 0 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 390.46 | 0 | 390.46 | 0 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 16.7 | 0 | 16.7 | 0 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 235.02 | 0 | 235.02 | 0 |  | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 109.01 | 0 | 109.01 | 0 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 70.62 | 0 | 70.62 | 0 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2571 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 295.66 | 0 | 295.66 | 0 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039183
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2572 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 59.63 | 0 | 59.63 | 0 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2572 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 43.33 | 0 | 43.33 | 0 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2572 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 34.35 | 0 | 34.35 | 0 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039183 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2573 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 2848 | 0 | 2848 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2574 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2575 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2576 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE6 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2577 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 21 | 0 | 21 | 0 |  | Y |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 |  | Y |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 38 | 0 | 38 | 0 |  | Y |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2578 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 22 | 0 | 22 | 0 |  | Y |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 3 | 0 | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 1 | 0 | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 48 | 0 | 48 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 51 | 0 | 51 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 25 | 0 | 25 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2579 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 1 | 0 | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2580 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 255.9 | 0 | 255.9 | 0 |  | Y |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2580 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 292.77 | 0 | 292.77 | 0 |  | Y |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2580 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 65.17 | 0 | 65.17 | 0 |  | Y |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2580 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 66.27 | 0 | 66.27 | 0 |  | Y |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2581 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 185.55 | 0 | 185.55 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45813682
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2581 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 98.25 | 0 | 98.25 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45813682
YNE6 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2581 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-07-03 | 2023-07-31 | 2023-11-30 |  | 21dys | WB | 44.48 | 0 | 44.48 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45813682
YNE7 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2582 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 2621 | 0 | 2621 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2583 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2584 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2585 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2586 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 23 | 0 | 23 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 16 | 0 | 16 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2588 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2587 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2589 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 27.09 | 0 | 27.09 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2589 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 84.24 | 0 | 84.24 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2589 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 51.58 | 0 | 51.58 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2590 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 131.28 | 0 | 131.28 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2590 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 295.44 | 0 | 295.44 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2590 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 56.86 | 0 | 56.86 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2591 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 2645 | 0 | 2645 | 0 |  | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2592 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2593 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2594 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2595 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 7 | 0 | 7 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 13 | 0 | 13 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 10 | 0 | 10 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 10 | 0 | 10 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2597 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 20 | 0 | 20 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2597 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2597 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2597 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2597 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2598 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 20.16 | 0 | 20.16 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2598 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 23.17 | 0 | 23.17 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2599 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 10.55 | 0 | 10.55 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2599 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 62.4 | 0 | 62.4 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2599 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 10.11 | 0 | 10.11 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2599 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 19.09 | 0 | 19.09 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE9 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2600 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 108.7253 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 2268 | 2268 | 0 | 1 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2601 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2602 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037046
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2603 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2604 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037046
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2605 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2605 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2606 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2606 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2606 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2606 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2606 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2607 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.26781 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 12.93 | 12.93 | 0 | 1 |  |  |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2607 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.7299 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 83.52 | 83.52 | 0 | 1 |  |  |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2607 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.19987 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 9.65 | 9.65 | 0 | 1 |  |  |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2607 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.7452 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 132.54 | 132.54 | 0 | 1 |  |  |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2608 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8747 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 90.51 | 90.51 | 0 | 1 |  |  |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2608 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2108 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 58.46 | 58.46 | 0 | 1 |  |  |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2609 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 139.8376 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 2917 | 2917 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2610 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2611 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037035
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2612 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2613 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037035
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 5 | 5 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 101.5164 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 23 | 23 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2616 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.86785 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 41.9 | 41.9 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2616 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.71603 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 34.57 | 34.57 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2617 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 185.7853 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4484.89 | 4484.89 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 339.6733 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 44 | 44 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 285.6343 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 93 | 37 | 56 | 0.39785 | 6/12 37 assets completed all nearly 100% full, then ran out of time | N |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2620 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 | 28/9: complete |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 1003.5801 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 252 | 130 | 122 | 0.51587 | 4/12 - closure cancelled rain |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2621 | Gullies - Emptying / clear covers | 988.1404 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 128 | 128 | 0 | 1 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 2 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2622 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 | 28/9: complete |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2623 | Gullies - Emptying / clear covers | 208.4359 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-28 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 27 | 27 | 0 | 1 |  | N |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB OS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 2 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2624 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 28 | 0 | 28 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2623 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 | 28/9: complete |  |  | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/419 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/474 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2620 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 | 28/9: complete |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2618 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2625 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 | 28/9: complete |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2624 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 2 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2623 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  |  |  | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2621 | Gullies - Emptying / clear covers | 1358.693 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 252 | 176 | 76 | 0.69841 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 2 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2622 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 | 28/9: complete |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2620 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 | 28/9: complete |  |  | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852441
YNE16 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2619 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000A63/908 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2626 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 134.8999 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 2814 | 2814 | 0 | 1 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2627 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2628 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2629 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 17 | 17 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000A63/404 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 151.0074 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 63 | 63 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 151.0074 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 63 | 63 | 0 | 1 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 148.6104 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 62 | 62 | 0 | 1 |  |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 158.1982 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 66 | 66 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2633 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  |  |  | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000A63/419 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/474 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2630 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2633 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2635 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 143.8165 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 24 | 24 | 0 | 1 |  |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2635 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2635 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2635 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2000A63/474 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2636 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2637 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2638 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2637 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2638 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2638 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2638 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2638 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2639 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.4376 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 165.97 | 165.97 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2639 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9343 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 141.67 | 141.67 | 0 | 1 |  |  |  | 2000A63/404 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2640 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.55882 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 26.98 | 26.98 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2640 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 23.9445 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1156.05 | 1156.05 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2640 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 11.5925 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 559.69 | 559.69 | 0 | 1 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2640 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.5702 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 220.65 | 220.65 | 0 | 1 |  |  |  | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2640 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.9455 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 238.77 | 238.77 | 0 | 1 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2641 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.2671 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 447.42 | 447.42 | 0 | 1 |  |  |  | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2642 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.1822 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 250.2 | 250.2 | 0 | 1 |  |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2639 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.0457 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 195.33 | 195.33 | 0 | 1 |  |  |  | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2639 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.2686 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 302.65 | 302.65 | 0 | 1 |  |  |  | 2000A63/908 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2643 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 56.85 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1372.37 | 1372.37 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2644 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 9.6358 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 232.61 | 232.61 | 0 | 1 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2644 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 62.7564 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1514.95 | 1514.95 | 0 | 1 |  |  |  | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2643 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 36.3241 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 876.87 | 876.87 | 0 | 1 |  |  |  | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2643 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 44.2437 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1068.05 | 1068.05 | 0 | 1 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2644 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 26.2686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 634.13 | 634.13 | 0 | 1 |  |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.7945 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 238 | 238 | 0 | 1 |  |  |  | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.6232 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 232 | 232 | 0 | 1 |  |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9062 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 347 | 347 | 0 | 1 |  |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5653 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 265 | 265 | 0 | 1 |  |  |  | 2000A63/404 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.8876 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1152 | 1152 | 0 | 1 |  |  |  | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.695 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 830 | 830 | 0 | 1 |  |  |  | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.2718 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1831 | 1831 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2647 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 60.6364 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2124 | 2124 | 0 | 1 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2647 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.1134 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 39 | 39 | 0 | 1 |  |  |  | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 57.8102 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2025 | 2025 | 0 | 1 |  |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 56.6682 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1985 | 1985 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2648 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.907 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 312 | 312 | 0 | 1 |  |  |  | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 324 | 324 | 0 | 1 |  |  |  | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.3328 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 432 | 432 | 0 | 1 |  |  |  | 2000A63/419 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.168 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 146 | 146 | 0 | 1 |  |  |  | 2000A63/474 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.1518 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 846 | 846 | 0 | 1 |  |  |  | 2000A63/486 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.1314 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 495 | 495 | 0 | 1 |  |  |  | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2646 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.5033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 473 | 473 | 0 | 1 |  |  |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2648 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7023 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 515 | 515 | 0 | 1 |  |  |  | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2647 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.3312 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 502 | 502 | 0 | 1 |  |  |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.531 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 509 | 509 | 0 | 1 |  |  |  | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2645 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.9315 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 488 | 488 | 0 | 1 |  |  |  | 2000A63/908 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE16 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2649 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 18.9379 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 210.69 | 210.69 | 0 | 1 |  |  |  | 2000A63/402 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2650 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4.7594 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 52.95 | 52.95 | 0 | 1 |  |  |  | 2000A63/403 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2650 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 169.219 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1882.61 | 1882.61 | 0 | 1 |  |  |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2651 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 491.2845 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5465.68 | 5465.68 | 0 | 1 |  |  |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2651 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 16.1578 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 179.76 | 179.76 | 0 | 1 |  |  |  | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2650 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 165.8897 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1845.57 | 1845.57 | 0 | 1 |  |  |  | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2649 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 211.6872 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2355.08 | 2355.08 | 0 | 1 |  |  |  | 2000A63/413 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2652 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 17.6715 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 196.6 | 196.6 | 0 | 1 |  |  |  | 2000A63/415 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure Amey 45110 BC - Lamps (LED) for Illuminated Signs and Bollards | 2653 | BC - Lamps (LED) for Illuminated Signs and Bollards | 119.8471 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 8 | 8 | 0 | 1 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE16 Closure Amey 45110 Electrical Testing - Network cabling and electrical components | 2654 | Electrical Testing - Network cabling and electrical components | 19.1755 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE16: A63 North Cave - South Cave | YNE16 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE17 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2655 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2812 | 0 | 2812 | 0 |  | Y |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2656 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2657 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2658 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2659 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 24 | 0 | 24 | 0 |  | Y |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2660 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2660 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2659 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 36 | 0 | 36 | 0 |  | Y |  | 2000A63/418 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2659 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107.8624 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 45 | 45 | 0 | 1 |  | N |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2662 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 |  | Y |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2662 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 |  | Y |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2659 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 23 | 0 | 23 | 0 |  | Y |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000A63/428 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2662 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 51 | 0 | 51 | 0 |  | Y |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2661 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2663 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 2000A63/418 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2663 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2664 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2665 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000A63/428 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2666 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2667 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2666 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2668 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2669 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2670 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.70091 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 33.84 | 33.84 | 0 | 1 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2671 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 157.04 | 0 | 157.04 | 0 |  | Y |  | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2672 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.647 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 176.08 | 176.08 | 0 | 1 |  | N |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2673 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 59.5853 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1438.4 | 1438.4 | 0 | 1 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2674 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2955.53 | 0 | 2955.53 | 0 |  | Y |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2674 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 515.12 | 0 | 515.12 | 0 |  | Y |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2674 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 731.03 | 0 | 731.03 | 0 |  | Y |  | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2675 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 32.4264 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 782.78 | 782.78 | 0 | 1 |  | N |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2676 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.5735 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1141 | 1141 | 0 | 1 |  | Y |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 2 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2677 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3606 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 468 | 468 | 0 | 1 |  | N |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 2 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2677 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.8451 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 520 | 520 | 0 | 1 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2676 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.3182 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1062 | 1062 | 0 | 1 |  | Y |  | 2000A63/418 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2676 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.4201 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 365 | 365 | 0 | 1 |  | Y |  | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.1739 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1127 | 1127 | 0 | 1 |  | N |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2679 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.4756 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 437 | 437 | 0 | 1 |  | Y |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.677 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 374 | 374 | 0 | 1 |  | N |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2679 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.4788 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 297 | 297 | 0 | 1 |  | Y |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2676 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.7693 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1323 | 1323 | 0 | 1 |  | Y |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.5719 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1211 | 1211 | 0 | 1 |  | N |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.168 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 146 | 146 | 0 | 1 |  | N |  | 2000A63/428 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2679 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.5727 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1176 | 1176 | 0 | 1 |  | Y |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.058 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1193 | 1193 | 0 | 1 |  | N |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2679 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.7301 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 551 | 551 | 0 | 1 |  | Y |  | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2678 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9894 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 455 | 455 | 0 | 1 |  | N |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2680 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 271.9031 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3025 | 3025 | 0 | 1 |  | Y |  | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2681 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 187.1449 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2082.04 | 2082.04 | 0 | 1 |  | N |  | 2000A63/414 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2682 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 165.0798 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1836.56 | 1836.56 | 0 | 1 |  | N |  | 2000A63/421 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2683 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 105.9658 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1178.9 | 1178.9 | 0 | 1 |  | Y |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2682 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 69.4355 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 772.49 | 772.49 | 0 | 1 |  | N |  | 2000A63/423 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2680 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 363.1062 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4039.66 | 4039.66 | 0 | 1 |  | Y |  | 2000A63/426 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2682 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 51.6535 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 574.66 | 574.66 | 0 | 1 |  | N |  | 2000A63/427 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2683 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 361.5296 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4022.12 | 4022.12 | 0 | 1 |  | Y |  | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2682 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 116.7736 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1299.14 | 1299.14 | 0 | 1 |  | N |  | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2684 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2269.6047 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 101 | 101 | 0 | 1 |  | Y |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE17 Closure Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2685 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 52 | 52 | 0 | 1 |  | Y |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 1 Closure | 2 |  |  | Every 3 years
YNE17 Closure Amey 45110 Electrical Testing - Network cabling and electrical components | 2686 | Electrical Testing - Network cabling and electrical components | 2799.6286 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 146 | 146 | 0 | 1 |  | Y |  |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE17 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2687 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 67.4011 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-07 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 392.89 | 392.89 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE17 Closure 1 EB OS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2688 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 168.4453 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 981.89 | 981.89 | 0 | 1 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2689 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 3.26 | 0 | 3.26 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2689 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 547.51 | 0 | 547.51 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 EB OS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2690 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 161.23 | 0 | 161.23 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 WB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 361.88 | 0 | 361.88 | 0 | 4/12 - closure cancelled rain | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 WB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 1218.69 | 0 | 1218.69 | 0 | 4/12 - closure cancelled rain | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 WB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 200.46 | 0 | 200.46 | 0 | 4/12 - closure cancelled rain | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855418
YNE18 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2692 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 81 | 0 | 81 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 748.8251 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 163 | 97 | 66 | 0.59509 | 4/12 - closure cancelled rain | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2694 | Gullies - Emptying / clear covers | 231.5954 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36 | 30 | 6 | 0.83333 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE17 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2695 | Gullies - Emptying / clear covers | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-07 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 34 | 34 | 0 | 1 |  |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2696 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 2 | 4 | 0.33333 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2692 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2692 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2696 | Gullies - Emptying / clear covers | 301.074 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 105 | 39 | 66 | 0.37143 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2694 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2694 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852831
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE17 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2697 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 843.57 | 0 | 843.57 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE17 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2698 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 48.41 | 0 | 48.41 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45854031
YNE18 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2699 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 946.73 | 0 | 946.73 | 0 |  | Y |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2700 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 424.79 | 0 | 424.79 | 0 |  | Y |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45854031
YNE18 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2699 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2743.38 | 0 | 2743.38 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2700 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 86.2 | 0 | 86.2 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45854031
YNE18 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2701 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1028.7 | 0 | 1028.7 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2702 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 446.75 | 0 | 446.75 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45854031
YNE18 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2701 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 615.61 | 0 | 615.61 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2701 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 3671.27 | 0 | 3671.27 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2702 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 369.22 | 0 | 369.22 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45854031
YNE18 Closure 1 WB NS Enviroflow 45110 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 2703 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 430.42 | 0 | 430.42 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45854302
YNE18 Closure 1 WB OS Enviroflow 45110 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 2704 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 34 | 0 | 34 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45854301
YNE17 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2705 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-07 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 269.88 | 0 | 0 | 1 | 6/12 no v-channel in closure |  |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854458
YNE17 Closure 1 EB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2706 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 365.79 | 0 | 365.79 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854330
YNE18 Closure 1 WB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2707 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 8.42 | 0 | 0 | 0 | 11/30/2023: non NH asset | N |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854458
YNE18 Closure Amey 45110 BC - Lamps (LED) for Illuminated Signs and Bollards | 2708 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2709 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1455 | 0 | 1455 | 0 |  | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2710 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2711 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2712 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2713 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 11 | 0 | 11 | 0 |  | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2659 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 35 | 0 | 35 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2713 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 18 | 0 | 18 | 0 |  | Y |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2713 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 11 | 0 | 11 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 21 | 0 | 21 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 51 | 0 | 51 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 14 | 0 | 14 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2715 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2716 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2716 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 8 | 0 | 8 | 0 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2663 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 11 | 0 | 11 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2715 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2716 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2717 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2666 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2717 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2718 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2719 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 608.61 | 0 | 608.61 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2720 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 437.6 | 0 | 437.6 | 0 |  | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2720 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 167.37 | 0 | 167.37 | 0 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2721 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2281.69 | 0 | 2281.69 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2719 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 932.81 | 0 | 932.81 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2720 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2330.38 | 0 | 2330.38 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2720 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 778.58 | 0 | 778.58 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2722 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 613.37 | 0 | 613.37 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2723 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1858.52 | 0 | 1858.52 | 0 |  | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2724 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7375.37 | 0 | 7375.37 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2723 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 10480.38 | 0 | 10480.38 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2723 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 229.77 | 0 | 229.77 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2725 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 621 | 0 | 621 | 0 |  | Y |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 459 | 0 | 459 | 0 |  | Y |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 144 | 0 | 144 | 0 |  | Y |  | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2676 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1344 | 0 | 1344 | 0 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2725 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1091 | 0 | 1091 | 0 |  | Y |  | 2000A63/603 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2725 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 437 | 0 | 437 | 0 |  | Y |  | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1180 | 0 | 1180 | 0 |  | Y |  | 2000A63/622 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1364 | 0 | 1364 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 523 | 0 | 523 | 0 |  | Y |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE17 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2680 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 46.2056 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 514.05 | 514.05 | 0 | 1 |  | Y |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2727 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6395.5 | 0 | 6395.5 | 0 |  | Y |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2728 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 5 | 0 | 5 | 0 | 6/12 no lighting resource? |  |  |  | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 2 | Yes EB entry slip verge |  | Every 6 years |  |  | 52036818
YNE18 Closure 1 WB NS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2729 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 41 | 0 | 41 | 0 | 4/12 - closure cancelled rain | Y |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036817
YNE18 Closure 1 EB NS Amey 45110 Electrical Testing - Network cabling and electrical components | 2730 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 4 | 0 | 4 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036824
YNE18 Closure 1 WB OS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2731 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 32.09 | 0 | 32.09 | 0 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2689 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 217.73 | 0 | 217.73 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855631
YNE18 Closure 1 WB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 1080.42 | 0 | 1080.42 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855631
YNE18 Closure 1 WB OS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2731 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1009.46 | 0 | 1009.46 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45855411
YNE18 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2689 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 19.16 | 0 | 19.16 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855631
YNE18 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2689 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 120.11 | 0 | 120.11 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855631
YNE18 Closure 1 WB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2691 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 179.57 | 0 | 179.57 | 0 | 4/12 - closure cancelled rain |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45855631
YNE18 Closure 1 WB OS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2731 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 211.72 | 0 | 211.72 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45855411
YNE19 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2732 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE19 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2733 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE18 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2692 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2696 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852852
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2734 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE19 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2735 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2736 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2735 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2737 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2696 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852852
YNE19 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2735 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2736 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/611 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2693 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE18 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2694 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45852852
YNE19 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2737 | Gullies - Emptying / clear covers | 92.6382 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2737 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2738 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE19 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2739 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.5077 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 101.78 | 101.78 | 0 | 1 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2740 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 60 | 0 | 60 | 0 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2741 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 242 | 0 | 242 | 0 |  |  |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2741 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 242.47 | 0 | 242.47 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2699 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 30 | 0 | 30 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE18 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2700 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 51.33 | 0 | 51.33 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45853671
YNE19 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2741 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 293.04 | 0 | 293.04 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2742 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 217.12 | 0 | 217.12 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2741 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 739 | 0 | 739 | 0 |  |  |  | 2000A63/611 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2742 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 302 | 0 | 302 | 0 |  |  |  | 2000A63/611 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2739 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.1287 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 492.27 | 492.27 | 0 | 1 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2740 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 62.07 | 0 | 62.07 | 0 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE19 Closure Amey 45110 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2743 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2 | 0 | 2 | 0 |  | Y |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE19 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2744 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1633 | 0 | 1633 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2745 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2746 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2747 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2713 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 44 | 0 | 44 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 30 | 0 | 30 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2749 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  |  |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2749 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2713 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 13 | 0 | 13 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2749 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 9 | 0 | 9 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2714 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 11 | 0 | 11 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2750 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2751 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2752 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2717 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2718 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2752 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2717 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2753 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2718 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2752 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2719 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 220.39 | 0 | 220.39 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2754 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 428.67 | 0 | 428.67 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2722 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 304 | 0 | 304 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4413 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 681 | 681 | 0 | 1 |  |  |  | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2725 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1629 | 0 | 1629 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1472 | 0 | 1472 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 506 | 0 | 506 | 0 |  |  |  | 2000A63/442 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 674 | 0 | 674 | 0 |  |  |  | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.0204 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 351 | 351 | 0 | 1 |  |  |  | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2725 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 504 | 0 | 504 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 131 | 0 | 131 | 0 |  |  |  | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 947 | 0 | 947 | 0 |  |  |  | 2000A63/611 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2726 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 467 | 0 | 467 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.3614 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 433 | 433 | 0 | 1 |  |  |  | 2000A63/626 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE19 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.4274 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 50 | 50 | 0 | 1 |  |  |  | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE18 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2757 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1091.67 | 0 | 1091.67 | 0 |  |  |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2727 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 80.42 | 0 | 80.42 | 0 |  |  |  | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2757 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 474.93 | 0 | 474.93 | 0 |  |  |  | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2727 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 420.07 | 0 | 420.07 | 0 |  |  |  | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
Unsure on location Amey 45110 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 2758 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 16 | 0 | 16 | 0 |  | Y |  |  | YNE19: A63 Melton - WesternInt | Unsure on location | Lane 1 Closure | 2 | Unsure on location |  | Every 2 years |  |  | 52036717
YNE20 Closure 1 WB NS Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2759 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 16 | 0 | 16 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036720
YNE18 Closure 1 EB NS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2760 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 18 | 0 | 18 | 0 | 7/12 closure cancelled due to heavy rain and fog | N |  |  | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036719
YNE20 Closure 1 WB NS Amey 45110 Electrical Testing - Network cabling and electrical components | 2761 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 21 | 0 | 21 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality |  | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036726
YNE20 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2762 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 218.47 | 0 | 218.47 | 0 |  | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 2 Closure | 1 |  |  | Every 2 years | 191/1 | 195/5 | 45855443 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2763 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 191/1 | 195/5 | 45853062 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2764 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2765 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 8 | 0 | 8 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45853062
YNE20 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2764 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2763 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 191/1 | 195/5 | 45853062 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2766 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | Y |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2763 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 191/1 | 195/5 | 45853062 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2766 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2767 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 9 | 0 | 9 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45853062
YNE20 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2768 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 34 | 34 | 0 | 1 |  | Y |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45853032
YNE20 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2769 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 191/1 | 195/5 | 45853062 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2770 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 609.8679 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 79 | 79 | 0 | 1 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45853032
YNE20 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2767 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | WB | 15 | 0 | 15 | 0 | 5/12 Cancelled following NH instruction - A64 Fatality | Y | Cancelled following NH instruction - A64 Fatality | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45853062
YNE20 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2768 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45853032
YNE20 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2766 | Gullies - Emptying / clear covers | 331.9534 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 43 | 43 | 0 | 1 |  | Y |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2764 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 22 | 22 | 0 | 1 |  | Y |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45853032
YNE20 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2771 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 475 | 0 | 475 | 0 |  | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2772 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 411 | 0 | 411 | 0 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE20 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2773 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 125 | 0 | 125 | 0 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45853731
YNE20 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2771 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 180.75 | 0 | 180.75 | 0 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2772 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 302 | 0 | 302 | 0 |  | Y |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE20 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2773 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.9668 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 161 | 161 | 0 | 1 |  | Y |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45853731
YNE20 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2771 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 171 | 0 | 171 | 0 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2774 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys | EB | 514.8 | 0 | 514.8 | 0 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 191/1 | 195/5 | 45854546 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2775 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 105.2601 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1363.5 | 1363.5 | 0 | 1 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854408
YNE20 Closure 1 EB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2775 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 160.5836 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2080.14 | 2080.14 | 0 | 1 |  | Y |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854408
YNE20 Closure 1 WB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2776 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 18.2405 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 236.28 | 236.28 | 0 | 1 |  | Y |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) |  |  | 45854408
YNE20 Closure 1 EB NS Amey 45110 Electrical Testing - Network cabling and electrical components | 2777 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-07-03 | 2023-07-31 | 2023-12-31 |  | 21dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 | No TM required |  | Every 6 years | 191/1 | 195/5 | 52036734 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2778 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2057 | 0 | 2057 | 0 |  | Y |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2779 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2780 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2781 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 13 | 0 | 13 | 0 |  | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 13 | 0 | 13 | 0 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 16 | 0 | 16 | 0 |  | Y |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 44 | 0 | 44 | 0 |  | Y |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 36 | 0 | 36 | 0 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36 | 0 | 36 | 0 |  | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 26 | 0 | 26 | 0 |  | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36 | 0 | 36 | 0 |  | Y |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 10 | 0 | 10 | 0 |  | Y |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 29 | 0 | 29 | 0 |  | Y |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2784 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2785 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2784 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2784 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2785 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2786 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2787 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2786 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 | Missed? | Y |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2786 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2787 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 | 0 | 5 | 0 | Missed? | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2786 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2787 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2788 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 80.24 | 0 | 80.24 | 0 | Missed? | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2788 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 52.49 | 0 | 52.49 | 0 | Missed? | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2789 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 299.59 | 0 | 299.59 | 0 | Missed? | Y |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2790 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 960.67 | 0 | 960.67 | 0 |  | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 680 | 0 | 680 | 0 |  | Y |  | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 143 | 0 | 143 | 0 |  | Y |  | 2000A63/445 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 352 | 0 | 352 | 0 |  | Y |  | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 496 | 0 | 496 | 0 |  | Y |  | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 648 | 0 | 648 | 0 |  | Y |  | 2000A63/449 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1013 | 0 | 1013 | 0 |  | Y |  | 2000A63/450 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1487 | 0 | 1487 | 0 |  | Y |  | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1341 | 0 | 1341 | 0 |  | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 450 | 0 | 450 | 0 |  | Y |  | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 283 | 0 | 283 | 0 |  | Y |  | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2791 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 998 | 0 | 998 | 0 |  | Y |  | 2000A63/455 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1056 | 0 | 1056 | 0 |  | Y |  | 2000A63/456 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE20 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2792 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 900 | 0 | 900 | 0 |  | Y |  | 2000A63/459 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2793 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 69 | 0 | 69 | 0 |  | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2794 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE23 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 44 | 0 | 44 | 0 |  | Y |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2793 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2793 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2796 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2793 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2797 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2798 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 262.98 | 0 | 262.98 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE23 Closure 1 EB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2799 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 42.6 | 0 | 42.6 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE23 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2800 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 638 | 0 | 638 | 0 |  | Y |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2801 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2802 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2803 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2804 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 21 | 0 | 21 | 0 |  | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2804 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2805 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 28 | 0 | 28 | 0 |  | Y |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2804 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 17 | 0 | 17 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2805 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 24 | 0 | 24 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2805 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 11 | 0 | 11 | 0 |  | Y |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2804 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 |  | Y |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2804 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 73 | 0 | 73 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2805 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2805 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 26 | 0 | 26 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2806 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2806 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 13 | 0 | 13 | 0 |  | Y |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2807 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 14 | 0 | 14 | 0 |  | Y |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2806 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 9 | 0 | 9 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2807 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 15 | 0 | 15 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2807 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2806 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2806 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2807 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2807 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2808 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2808 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2808 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2808 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2809 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2810 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5269.96 | 0 | 5269.96 | 0 | Missed? | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2810 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1408.52 | 0 | 1408.52 | 0 | Missed? | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2811 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1394.61 | 0 | 1394.61 | 0 | Missed? | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2811 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1640.23 | 0 | 1640.23 | 0 | Missed? | Y |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2810 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 917.21 | 0 | 917.21 | 0 | Missed? | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2811 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 265.81 | 0 | 265.81 | 0 | Missed? | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2812 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3211.09 | 0 | 3211.09 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2813 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1579.72 | 0 | 1579.72 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2812 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2029.91 | 0 | 2029.91 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2813 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1091.46 | 0 | 1091.46 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2813 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 566.02 | 0 | 566.02 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 644 | 0 | 644 | 0 |  | Y |  | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 358 | 0 | 358 | 0 |  | Y |  | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 360 | 0 | 360 | 0 |  | Y |  | 2000A63/303 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 374 | 0 | 374 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 463 | 0 | 463 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 673 | 0 | 673 | 0 |  | Y |  | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 166 | 0 | 166 | 0 |  | Y |  | 2000A63/308 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 250 | 0 | 250 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 74 | 0 | 74 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 169 | 0 | 169 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE23 Closure Amey 45110 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 2816 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE23 Closure Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2817 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 117 | 0 | 117 | 0 |  | Y |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE23 Closure Amey 45110 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 2818 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 4 | 0 | 4 | 0 |  | Y |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE23 Closure Amey 45110 Electrical Testing - Network cabling and electrical components | 2819 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 42 | 0 | 42 | 0 |  | Y |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE24 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2820 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 49 | 0 | 49 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE24 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2821 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 22 | 0 | 22 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE24 Closure Enviroflow 45110 Gullies - Emptying / clear covers | 2822 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE24 Closure Enviroflow 45110 Gullies - Emptying / clear covers | 2822 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE24 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2823 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 47 | 0 | 47 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE24 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 2824 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 23 | 0 | 23 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE24 Closure Enviroflow 45110 Gullies - Emptying / clear covers | 2822 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE24 Closure Enviroflow 45110 Gullies - Emptying / clear covers | 2822 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 2 |  |  | Every 2 years
YNE24 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2825 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 55.41 | 0 | 55.41 | 0 |  | Y |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure 1 EB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2826 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1243.98 | 0 | 1243.98 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2825 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1005.09 | 0 | 1005.09 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2827 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 491.07 | 0 | 491.07 | 0 |  | Y |  | 2000A63/355 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2827 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1554.21 | 0 | 1554.21 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2827 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1409.37 | 0 | 1409.37 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2828 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 659 | 0 | 659 | 0 |  | Y |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2829 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2830 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2831 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2832 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2832 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 95 | 0 | 95 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 14 | 0 | 14 | 0 |  | Y |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 |  | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 60 | 0 | 60 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 29 | 0 | 29 | 0 |  | Y |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 2000A63/382 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 25 | 0 | 25 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2835 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 58 | 0 | 58 | 0 |  | Y |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2835 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2836 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2837 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2837 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 | Missed? | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2838 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2839 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2840 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2320.12 | 0 | 2320.12 | 0 | Missed? | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2841 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1884.32 | 0 | 1884.32 | 0 | Missed? | Y |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2841 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 531.72 | 0 | 531.72 | 0 | Missed? | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2842 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1824.44 | 0 | 1824.44 | 0 | Missed? | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2841 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 407.89 | 0 | 407.89 | 0 | Missed? | Y |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2841 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 509.9 | 0 | 509.9 | 0 | Missed? | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2843 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 866.38 | 0 | 866.38 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2844 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 198.76 | 0 | 198.76 | 0 |  | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2845 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 517.05 | 0 | 517.05 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2844 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 671.53 | 0 | 671.53 | 0 |  | Y |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2844 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 838.2 | 0 | 838.2 | 0 |  | Y |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2844 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 977.47 | 0 | 977.47 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2846 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 61 | 0 | 61 | 0 |  | Y |  | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2846 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 556 | 0 | 556 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 462 | 0 | 462 | 0 |  | Y |  | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 257 | 0 | 257 | 0 |  | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 45 | 0 | 45 | 0 |  | Y |  | 2000A63/355 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2848 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 537 | 0 | 537 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 405 | 0 | 405 | 0 |  | Y |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2848 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 76 | 0 | 76 | 0 |  | Y |  | 2000A63/382 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 45 | 0 | 45 | 0 |  | Y |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2847 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 725 | 0 | 725 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE24 Closure Amey 45110 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2849 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 23 | 0 | 23 | 0 |  | Y |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE24 Closure Amey 45110 Electrical Testing - Network cabling and electrical components | 2850 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE25 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2851 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 |  | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE25 Closure Enviroflow 45110 Gullies - Emptying / clear covers | 2852 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE25 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2853 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 90 | 0 | 90 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2854 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 108 | 0 | 108 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2853 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 58 | 0 | 58 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2855 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 564 | 0 | 564 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2856 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 44 | 0 | 44 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2855 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 492 | 0 | 492 | 0 |  | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2855 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 147 | 0 | 147 | 0 |  | Y |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2855 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 350 | 0 | 350 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2856 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 109 | 0 | 109 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2857 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 134 | 0 | 134 | 0 |  | Y |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2857 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 83 | 0 | 83 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE25 Closure Amey 45110 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2858 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2 | 0 | 2 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE25 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2859 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 842 | 0 | 842 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2860 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2861 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2862 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 |  | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2865 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2865 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2865 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2865 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2865 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 8 | 0 | 8 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2866 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2867 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3 | 0 | 3 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2868 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | Missed? | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2868 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2869 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 | Missed? | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2870 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1424.44 | 0 | 1424.44 | 0 | Missed? | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2871 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1285.7 | 0 | 1285.7 | 0 | Missed? | Y |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2872 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1122.09 | 0 | 1122.09 | 0 | Missed? | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2871 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 939.16 | 0 | 939.16 | 0 | Missed? | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2873 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7638 | 0 | 7638 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2873 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3142 | 0 | 3142 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2873 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1338 | 0 | 1338 | 0 |  | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2874 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 602 | 0 | 602 | 0 |  | Y |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2875 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 11496 | 0 | 11496 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2875 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1800 | 0 | 1800 | 0 |  | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2875 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4509 | 0 | 4509 | 0 |  | Y |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2875 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3244 | 0 | 3244 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2874 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 153 | 0 | 153 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2876 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 351 | 0 | 351 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2876 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 835 | 0 | 835 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2876 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 311 | 0 | 311 | 0 |  | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2877 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 268 | 0 | 268 | 0 |  | Y |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2878 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 283 | 0 | 283 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2878 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 553 | 0 | 553 | 0 |  | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2878 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 347 | 0 | 347 | 0 |  | Y |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2878 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 427 | 0 | 427 | 0 |  | Y |  | 2000A63/509 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2878 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 689 | 0 | 689 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2877 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 127 | 0 | 127 | 0 |  | Y |  | 2000A63/513 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2877 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 156 | 0 | 156 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE25 Closure 1 EB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2879 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 453.61 | 0 | 453.61 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 2880 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 817.02 | 0 | 817.02 | 0 |  | Y |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS Amey 45110 Electrical Testing - Network cabling and electrical components | 2881 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 |  | 21dys |  | 35 | 0 | 35 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 6 years |  |  | 52036953
YNE25 Closure 1 WB NS Amey 45110 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2882 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 |  | 21dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 3 years |  |  | 52036971
YNE26 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2883 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE26 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2883 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE26 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2884 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.6754 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 68 | 68 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE26 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2884 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.6481 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 351 | 351 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE26 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2884 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.5088 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 183 | 183 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE26 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2885 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 22.5934 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 917 | 917 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept) |  |  | 45853422
YNE26 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2886 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE26 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2887 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE26 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2886 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 16 | 16 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE26 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2887 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE26 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2888 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years |  |  | 45853399
YNE26 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2889 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE26 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2890 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 21.4766 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 448 | 448 | 0 | 1 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2891 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2892 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2893 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2894 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 18 | 18 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2894 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129.4349 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 54 | 54 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2894 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 19 | 19 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2895 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 30 | 30 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) |  |  | 45822659
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2896 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 107.8624 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 18 | 18 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2896 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 179.7707 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2896 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 89.8853 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 15 | 15 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2897 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) |  |  | 52036939
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2898 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2898 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2898 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2899 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.65492 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 31.62 | 31.62 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2899 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 77.6931 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3751.05 | 3751.05 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2899 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 26.5305 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1280.9 | 1280.9 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2900 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.6836 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 467.53 | 467.53 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2901 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1357 | 1357 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2901 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3468 | 3468 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2901 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 2575 | 2575 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2902 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 462 | 462 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2903 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.509 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 228 | 228 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2903 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.4683 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 752 | 752 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2903 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5367 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 264 | 264 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE26 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2904 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.0678 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 773 | 773 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) |  |  | 45830862
YNE27 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2905 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 | Subject to roadspace | 21dys | EB | 1 | 0 | 1 | 0 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE27 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 | Subject to roadspace | 21dys | WB | 2 | 0 | 2 | 0 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE27 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2907 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE27 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2907 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE27 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2908 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE27 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2909 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE27 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2910 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 12.9914 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 271 | 271 | 0 | 1 |  | N |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2911 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2912 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2913 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2914 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107.8624 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 45 | 45 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2914 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 21 | 21 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2915 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 26 | 26 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2916 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 53.9312 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2916 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 179.7707 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 30 | 30 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2917 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2917 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2918 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 91.9927 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4441.44 | 4441.44 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2918 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.7847 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 424.13 | 424.13 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2919 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 28.6638 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1383.9 | 1383.9 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2920 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 329 | 329 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2920 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1346 | 1346 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2921 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 199 | 199 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2922 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.531 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 509 | 509 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2922 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.8524 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 205 | 205 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2923 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.3883 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 504 | 504 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE27 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2924 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 30.5162 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 442 | 442 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2925 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 | Subject to roadspace | 21dys | EB | 14 | 0 | 14 | 0 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE28 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2926 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 | Subject to roadspace | 21dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE28 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2927 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 30.527 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1239 | 1239 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE28 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2927 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.1307 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 330 | 330 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE28 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2928 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.3845 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 665 | 665 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE28 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2929 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471.7684 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2930 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2929 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 257.3282 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 12 | 12 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2930 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2931 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2932 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE28 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2933 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 31.8314 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 664 | 664 | 0 | 1 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2934 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2935 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2936 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2937 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 297.2208 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 124 | 124 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2937 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 21 | 21 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2938 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 37 | 37 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2939 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2939 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 161.7936 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 27 | 27 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2940 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2941 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 203.1182 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9806.62 | 9806.62 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2941 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 14.1432 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 682.84 | 682.84 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2942 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 25.2121 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1217.25 | 1217.25 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2943 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 7727 | 7727 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2943 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 2585 | 2585 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2944 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 8327 | 8327 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2945 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3395 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1378 | 1378 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2945 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5946 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 231 | 231 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE28 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2946 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1377 | 1377 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS Bettamix 45110 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2947 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.7052 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9.94 | 9.94 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE29 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2948 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-07-03 | 2023-07-31 | 2024-03-31 | Subject to roadspace | 21dys | EB | 2 | 0 | 2 | 0 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE29 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2949 | Gullies - Emptying / clear covers | 162.1168 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 21 | 21 | 0 | 1 | 26/10 - gullies complete |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45853613
YNE29 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2949 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45853613
YNE29 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 2949 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years |  |  | 45853613
YNE29 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2950 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.519 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 224 | 224 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2950 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.474 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 141 | 141 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2950 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.1334 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 46 | 46 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2951 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 21.0658 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 855 | 855 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2951 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.6508 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 67 | 67 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2951 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.0032 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 406 | 406 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2951 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.587 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 105 | 105 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE29 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2952 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2953 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2952 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278.7722 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2953 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2952 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 364.5483 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2953 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2954 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514.6564 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 24 | 24 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2955 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 385.9923 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 18 | 18 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 45853514
YNE29 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2954 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2955 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 45853514
YNE29 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2954 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 192.9962 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2955 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 45853514
YNE29 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2954 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE29 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2955 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years |  |  | 45853514
YNE29 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2956 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 33.4134 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 697 | 697 | 0 | 1 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2957 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2958 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2959 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 46 | 46 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 86.2899 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 36 | 36 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 17 | 17 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 53.9312 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 359.5413 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 60 | 60 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2963 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2964 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2964 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2964 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2965 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2966 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 41.5778 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2007.39 | 2007.39 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2966 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 52.9623 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2557.04 | 2557.04 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2966 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.6186 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 319.55 | 319.55 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.1547 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 248.87 | 248.87 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.2029 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 396.04 | 396.04 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2968 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 438 | 438 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2968 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3851 | 3851 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2968 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5971 | 5971 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2969 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 6695 | 6695 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2969 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2969 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1105 | 1105 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2970 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6778 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 339 | 339 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2970 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 680 | 680 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2970 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.8491 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 345 | 345 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2971 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.6967 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 760 | 760 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2971 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.4788 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 297 | 297 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2971 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.7627 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 377 | 377 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2971 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6493 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 338 | 338 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE29 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2972 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 245.1652 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3551 | 3551 | 0 | 1 |  |  |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2973 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2216 |  | 2216 | 0 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2974 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2975 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2975 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2975 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2976 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 2 |  | 2 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2976 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 3 |  | 3 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2976 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1 |  | 1 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2977 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1 |  | 1 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2976 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2976 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3 |  | 3 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2974 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 7 |  | 7 | 0 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2974 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 8 |  | 8 | 0 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2978 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 3 |  | 3 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2978 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 4 |  | 4 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2974 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 10 |  | 10 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2974 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 5 |  | 5 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2979 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 38.76 |  | 38.76 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2980 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 8.77 |  | 8.77 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2979 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 17.14 |  | 17.14 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2979 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 23.88 |  | 23.88 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2979 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 151.7 |  | 151.7 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2979 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 237.64 |  | 237.64 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2981 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 118.6 |  | 118.6 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2981 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 80.4 |  | 80.4 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1006 |  | 1006 | 0 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2983 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 565 |  | 565 | 0 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 507 |  | 507 | 0 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2983 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1093 |  | 1093 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2983 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1521 |  | 1521 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 552 |  | 552 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 883 |  | 883 | 0 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 914 |  | 914 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 473 |  | 473 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 464 |  | 464 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 457 |  | 457 | 0 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 416 |  | 416 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 603 |  | 603 | 0 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 648 |  | 648 | 0 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 554 |  | 554 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1625 |  | 1625 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2984 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 477 |  | 477 | 0 |  |  |  | 4700M621/204 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 709 |  | 709 | 0 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 540 |  | 540 | 0 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2985 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 4894 |  | 4894 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2985 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 4330 |  | 4330 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1084 |  | 1084 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2985 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 569 |  | 569 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 2 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2982 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 374 |  | 374 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 2 | No | Days | 6 times per year (ILM Certain Sections)
YNE41 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2986 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 74.449 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1553 | 1553 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2987 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2988 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2989 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2990 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2991 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 2992 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2993 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.8785 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 621.78 | 621.78 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2994 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 13.3845 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 646.21 | 646.21 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2993 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8987 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 91.67 | 91.67 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2994 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 16.5703 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 800.02 | 800.02 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2994 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.7748 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 327.09 | 327.09 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2993 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.2758 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 592.68 | 592.68 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2993 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1073 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 53.46 | 53.46 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2994 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 13.1907 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 636.85 | 636.85 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2993 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1607 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 56.04 | 56.04 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2995 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 70.3742 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1468 | 1468 | 0 | 1 |  | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days | No |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2996 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2997 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036915
YNE42 Closure 2 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2998 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036915
YNE42 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 2999 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3000 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3000 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3001 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.7808 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 327.38 | 327.38 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3001 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.9339 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 141.65 | 141.65 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE43 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3002 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 84.66 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1766 | 1766 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3003 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3004 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3005 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3006 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036920
YNE43 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3007 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3008 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3009 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.99419 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 48 | 48 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3010 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.3637 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 258.96 | 258.96 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3011 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.9608 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 432.63 | 432.63 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3012 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.5314 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 363.62 | 363.62 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3009 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 15.9152 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 768.39 | 768.39 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3009 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.6706 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 225.5 | 225.5 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3009 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.082849 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3013 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 53.0236 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1280 | 1280 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3014 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Unable to complete within ADAMR window | Unable to complete within ADAMR window |  | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1712 | 0 | 1712 | 0 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3015 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3016 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52041716
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3017 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3018 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52041716
YNE44 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3019 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 79.8182 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1665 | 1665 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3020 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 52.3061 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2525.36 | 2525.36 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 24.9832 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1206.2 | 1206.2 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 22.19 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1071.34 | 1071.34 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 13.2658 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 640.48 | 640.48 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 58.6421 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2831.26 | 2831.26 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 33.1215 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1599.12 | 1599.12 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.2514 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 301.82 | 301.82 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.2717 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 351.08 | 351.08 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 29.2786 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1413.58 | 1413.58 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 45.1716 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 2180.9 | 2180.9 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3023 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 26.3461 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 636 | 636 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3023 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 112.0538 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 2705 | 2705 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3024 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3025 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3026 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036857
YNE45 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3027 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036857
YNE45 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3028 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 61.2179 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1277 | 1277 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3029 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3029 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3029 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.693 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 467.98 | 467.98 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.3094 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 256.34 | 256.34 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 21.9224 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1058.42 | 1058.42 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 35.3079 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1704.68 | 1704.68 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 21.1792 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1022.54 | 1022.54 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 25.2919 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1221.1 | 1221.1 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 53.5259 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2584.25 | 2584.25 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.51698 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 24.96 | 24.96 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.8771 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 332.03 | 332.03 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3031 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.9208 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 430.7 | 430.7 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.3719 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 404.2 | 404.2 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3030 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 31.1918 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 1505.95 | 1505.95 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3032 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Missed intervention | Missed intervention |  | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 127 | 0 | 127 | 0 |  | N | Should have been N/A'd in rebaselined programme | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3033 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3034 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3035 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3036 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3037 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 77.4692 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1616 | 1616 | 0 | 1 |  | N |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure | Lane 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3038 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3038 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3039 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 15.654 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 755.78 | 755.78 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3040 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.71913 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 34.72 | 34.72 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3039 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.0105 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 338.47 | 338.47 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3039 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 28.1282 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1358.04 | 1358.04 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3040 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 14.4021 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 695.34 | 695.34 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3040 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0253 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 49.5 | 49.5 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3039 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.93081 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 44.94 | 44.94 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3040 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.3686 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 259.2 | 259.2 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3040 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.1089 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 150.1 | 150.1 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3041 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 13 | 0 | 13 | 0 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3042 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3043 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3044 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036885
YNE47 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3045 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036885
YNE47 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3046 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 85.7626 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1789 | 1789 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3047 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3048 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.7057 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 82.35 | 82.35 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3050 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.82435 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 39.8 | 39.8 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3050 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.5476 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 123 | 123 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.020091 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 0.97 | 0.97 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3050 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.4977 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 120.59 | 120.59 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.025 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 97.77 | 97.77 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.8053 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 38.88 | 38.88 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3050 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.2322 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 107.77 | 107.77 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.7605 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 519.52 | 519.52 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3049 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.68144 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 32.9 | 32.9 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3051 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3052 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3053 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036890
YNE48 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3054 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036890
YNE48 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3055 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 139.4541 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 2909 | 2909 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3056 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3056 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3057 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3056 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.69801 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 33.7 | 33.7 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.26926 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 11.1263 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 537.18 | 537.18 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.944 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 190.42 | 190.42 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.6466 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 224.34 | 224.34 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.9768 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 143.72 | 143.72 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.0329 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 146.43 | 146.43 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3060 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.0665 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 148.05 | 148.05 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3061 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.4559 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 118.57 | 118.57 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3060 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.3743 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 66.35 | 66.35 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.62406 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 30.13 | 30.13 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.2416 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 591.03 | 591.03 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3062 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 22.3279 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 539 | 539 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3063 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 20.1324 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 486 | 486 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE49 Closure Amey 45110 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3064 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 2 | No |  | Annually |  |  | On ServiceNow
YNE49 Closure Amey 45110 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3065 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 2 | No |  | Annually |  |  | On ServiceNow
YNE49 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3066 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3067 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3068 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3069 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3070 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 101.918 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 2126 | 2126 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3071 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3072 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3072 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 2 | 2 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.89125 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 43.03 | 43.03 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.1884 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 491.9 | 491.9 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.1093 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 150.12 | 150.12 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 23.1707 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1118.69 | 1118.69 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.9212 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 285.88 | 285.88 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.0915 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 197.54 | 197.54 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 19.6318 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 947.83 | 947.83 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 11.9852 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 578.65 | 578.65 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.735 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | CW | 373.45 | 373.45 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.8757 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | WB | 187.12 | 187.12 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3075 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3076 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3077 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 91.2756 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys |  | 1904 | 1904 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3078 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3078 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3078 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3078 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.1559 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 200.65 | 200.65 | 0 | 1 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.3695 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 210.96 | 210.96 | 0 | 1 |  | N |  | 2700A64/420 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.38214 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 18.45 | 18.45 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 82.5099 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 3983.61 | 3983.61 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 16.7099 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 806.76 | 806.76 | 0 | 1 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2013 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 58 | 58 | 0 | 1 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.1219 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 488.69 | 488.69 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3079 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.42191 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 20.37 | 20.37 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3080 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 42.916 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 1036 | 1036 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3080 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 33.8854 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | 2023-10-31 |  | 21dys | EB | 818 | 818 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE51 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3081 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3082 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3083 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 | Sched D |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | N/A
YNE51 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3084 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 | Sched D |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | N/A
YNE51 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3085 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 104.9861 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys |  | 2190 | 2190 | 0 | 1 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.6128 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 512.39 | 512.39 | 0 | 1 |  |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3087 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 41.7733 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 2016.83 | 2016.83 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3087 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 28.0104 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1352.35 | 1352.35 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3088 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 38.0925 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1839.12 | 1839.12 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 28.7943 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1390.2 | 1390.2 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3088 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 42.6571 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 2059.5 | 2059.5 | 0 | 1 |  |  |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 45.9976 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 2220.78 | 2220.78 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.8823 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 621.96 | 621.96 | 0 | 1 |  |  |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 38.478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1857.73 | 1857.73 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 28.6624 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1383.83 | 1383.83 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 18.8893 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 911.98 | 911.98 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 37.1072 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1791.55 | 1791.55 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3091 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 27.2575 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 658 | 658 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3092 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 51.5738 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1245 | 1245 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3093 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3094 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3095 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3096 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE52Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3097 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 59.3483 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 1238 | 1238 | 0 | 1 |  |  |  |  | YNE52: A64 South Musley Single | YNE52Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 41.7472 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2015.57 | 2015.57 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 37.9378 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1831.65 | 1831.65 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.413 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 68.22 | 68.22 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.2816 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 496.4 | 496.4 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.3885 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 405 | 405 | 0 | 1 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3098 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.6156 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 78 | 78 | 0 | 1 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3099 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.3562 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 500 | 500 | 0 | 1 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3100 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.5285 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 399 | 399 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3100 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 32.4355 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 783 | 783 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3100 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 9.8591 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 238 | 238 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3100 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 5.8823 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 142 | 142 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3101 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3102 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 | works cancelled 19/09/2023 due to Adverse weather |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037004
YNE53 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3103 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037004
YNE53 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3104 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3105 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.6093 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys |  | 2203 | 2203 | 0 | 1 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3106 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3106 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3106 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3107 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3108 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.7226 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | EB | 83.17 | 83.17 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3109 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.8504 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 137.62 | 137.62 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3110 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 31.3999 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 758 | 758 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE53 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3110 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 61.9299 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys | WB | 1495 | 1495 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE54 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3111 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3112 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3113 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys |  |  |  | 0 | 1 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037009
YNE54 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3114 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3115 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 74.0655 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 1545 | 1545 | 0 | 1 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3116 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3117 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3118 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3119 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3116 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3120 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.92936 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 44.87 | 44.87 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3120 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1156 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 53.86 | 53.86 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3121 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.01802 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 0.87 | 0.87 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3121 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.1184 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 247.12 | 247.12 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3122 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3123 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3124 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3125 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE55Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3126 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 43.9599 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 917 | 917 | 0 | 1 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3127 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3127 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3127 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 167.92 | 167.92 | 0 | 1 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3129 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 14.3046 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 690.63 | 690.63 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3129 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 20.5222 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 990.82 | 990.82 | 0 | 1 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3129 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 42.7878 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2065.81 | 2065.81 | 0 | 1 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3129 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 24.9984 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1206.93 | 1206.93 | 0 | 1 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3129 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 48.1394 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2324.19 | 2324.19 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3130 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 63.7526 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1539 | 1539 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3130 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 86.1634 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2080 | 2080 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3131 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3132 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3131 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3132 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3133 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 111.2661 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2321 | 2321 | 0 | 1 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3134 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3134 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3134 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 41.3402 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1995.92 | 1995.92 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 18.2436 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 880.81 | 880.81 | 0 | 1 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 23.3668 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1128.16 | 1128.16 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.1938 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 154.2 | 154.2 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 24.0823 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1162.7 | 1162.7 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 45.2894 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2186.59 | 2186.59 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 27.0754 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1307.21 | 1307.21 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 11.1702 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 539.3 | 539.3 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 11.7217 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 565.93 | 565.93 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.0446 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 581.52 | 581.52 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 18.0162 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 869.83 | 869.83 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 29.7313 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1435.44 | 1435.44 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 20.2896 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 979.59 | 979.59 | 0 | 1 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 44.7946 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2162.7 | 2162.7 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 49.9582 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1206 | 1206 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.5699 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 400 | 400 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 41.3419 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 998 | 998 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 302.4832 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 7302 | 7302 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 55.6748 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1344 | 1344 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 15.5757 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 376 | 376 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 18.2269 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 440 | 440 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 346.9319 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 8375 | 8375 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 138.9385 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 3354 | 3354 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 57.4146 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1386 | 1386 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 31.9799 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 772 | 772 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3136 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 98.9636 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2389 | 2389 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45110 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 3137 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 906.58 |  | 906.58 | 0 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45110 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 3137 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 12064.95 |  | 12064.95 | 0 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3138 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3139 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3140 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3141 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE57Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3142 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 72.3877 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 1510 | 1510 | 0 | 1 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3143 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | NB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3143 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3143 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3143 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 51.9228 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2506.85 | 2506.85 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3145 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.99544 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 48.06 | 48.06 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.7504 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | NB | 132.79 | 132.79 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 13.3294 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 643.55 | 643.55 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 15.6523 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 755.7 | 755.7 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 14.9713 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 722.82 | 722.82 | 0 | 1 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 33.8697 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1635.24 | 1635.24 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.8481 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 523.75 | 523.75 | 0 | 1 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.8688 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 379.91 | 379.91 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.7775 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 134.1 | 134.1 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8434 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 89 | 89 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 19.5632 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 944.52 | 944.52 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3144 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.6628 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 32 | 32 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3146 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 91.8386 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 2217 | 2217 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 48.674 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | NB | 1175 | 1175 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 33.6783 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 813 | 813 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 110.4383 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2666 | 2666 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 62.6342 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1512 | 1512 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 15.2443 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 368 | 368 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 21.0438 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 508 | 508 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3147 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 30.1572 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 728 | 728 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45110 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 3148 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 795 |  | 795 | 0 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3149 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3150 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3151 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3152 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3153 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 26.6061 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 555 | 555 | 0 | 1 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3154 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 26.1266 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1261.4 | 1261.4 | 0 | 1 |  |  |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3154 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 47.6094 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2298.6 | 2298.6 | 0 | 1 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3154 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.5186 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 363 | 363 | 0 | 1 |  |  |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3154 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.4339 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 455.47 | 455.47 | 0 | 1 |  |  |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3155 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.6814 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 467.42 | 467.42 | 0 | 1 |  |  |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3154 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.193 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 57.6 | 57.6 | 0 | 1 |  |  |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3156 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 125.7654 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 3036 | 3036 | 0 | 1 |  |  |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3157 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3158 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3159 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3160 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3161 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 25.839 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 539 | 539 | 0 | 1 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3162 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3163 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.72493 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 35 | 35 | 0 | 1 |  |  |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3165 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 19.2702 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 930.37 | 930.37 | 0 | 1 |  |  |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 41.3522 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1996.5 | 1996.5 | 0 | 1 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 54.5804 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 2635.16 | 2635.16 | 0 | 1 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.91134 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 44 | 44 | 0 | 1 |  |  |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3166 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 19.5939 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 473 | 473 | 0 | 1 |  |  |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3166 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 27.5474 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 665 | 665 | 0 | 1 |  |  |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3166 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 83.098 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 2006 | 2006 | 0 | 1 |  |  |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3167 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3168 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3169 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3170 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3171 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 14.4296 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys |  | 301 | 301 | 0 | 1 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3172 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3172 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 3 | 3 | 0 | 1 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3173 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.67605 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 32.64 | 32.64 | 0 | 1 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3173 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.6052 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 318.9 | 318.9 | 0 | 1 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3174 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 5.0538 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | WB | 122 | 122 | 0 | 1 |  |  |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3175 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 202.6497 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | EB | 4892 | 4892 | 0 | 1 |  |  |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3175 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 14.6643 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | CW | 354 | 354 | 0 | 1 |  |  |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 2 | No | Days | 3 time per year (Apr - Sep)
YNE73 Closure Amey 45110 Ramp Metering Traffic Light Signals - Check alignment and condition of site | 3176 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 0 | 4.6.11 | ART024 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE76 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3177 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 242.21 |  | 242.21 | 0 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE76 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3177 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 247.28 |  | 247.28 | 0 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3178 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3179 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3178 | Gullies - Emptying / clear covers | 247.0351 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 32 | 32 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3179 | Gullies - Emptying / clear covers | 231.5954 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 30 | 30 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3178 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3179 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3180 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE76 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3182 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 1000A628/115 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3180 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 9 | 9 | 0 | 1 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3180 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 308.7939 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 40 | 40 | 0 | 1 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE76 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3180 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 19 | 19 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE76 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3183 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.24638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure Amey 45110 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3184 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE76 Closure Amey 45110 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3185 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE76 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3186 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 81.8316 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1707 | 1707 | 0 | 1 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3187 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3188 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3189 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 33 | 33 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 153.4043 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 64 | 64 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 30 | 30 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 21 | 21 | 0 | 1 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 124.641 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 52 | 52 | 0 | 1 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 46 | 46 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3191 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 161.7936 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 27 | 27 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3191 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 137.8242 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 23 | 23 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3191 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 37.908 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1830.21 | 1830.21 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 58.9933 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2848.22 | 2848.22 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 39.5517 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1909.57 | 1909.57 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.0855 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 438.65 | 438.65 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3194 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.1025 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 342.91 | 342.91 | 0 | 1 |  |  |  | 1000A628/115 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 30.7411 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1484.19 | 1484.19 | 0 | 1 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 72.0693 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 3479.53 | 3479.53 | 0 | 1 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3193 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 55.3235 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2671.04 | 2671.04 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3195 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.7666 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 404.75 | 404.75 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.4569 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1242 | 1242 | 0 | 1 |  |  |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.2636 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1445.4 | 1445.4 | 0 | 1 |  |  |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.6984 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1425.6 | 1425.6 | 0 | 1 |  |  |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6607 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 338.4 | 338.4 | 0 | 1 |  |  |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3197 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.8622 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 275.4 | 275.4 | 0 | 1 |  |  |  | 1000A628/115 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 56.8338 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1990.8 | 1990.8 | 0 | 1 |  |  |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 110.4816 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 3870 | 3870 | 0 | 1 |  |  |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3196 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 80.7801 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2829.6 | 2829.6 | 0 | 1 |  |  |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3198 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 306.74 |  | 306.74 | 0 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3198 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 456.67 |  | 456.67 | 0 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3198 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 1212.44 |  | 1212.44 | 0 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3199 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Subject to roadspace full closure cancelled due to storm Babet | 43dys | EB | 25.47 |  | 25.47 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3198 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | EB | 1598.3 |  | 1598.3 | 0 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3200 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | WB | 51.61 |  | 51.61 | 0 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3201 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Subject to roadspace full closure cancelled due to storm Babet | 43dys | WB | 100.34 |  | 100.34 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3200 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | Single carriageway no offside assets | 43dys | WB | 160.6 |  | 160.6 | 0 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE77 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3202 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 9 | 9 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3203 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3202 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3203 | Gullies - Emptying / clear covers | 92.6382 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 12 | 12 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3204 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3205 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3204 | Gullies - Emptying / clear covers | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 34 | 34 | 0 | 1 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3205 | Gullies - Emptying / clear covers | 331.9534 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 43 | 43 | 0 | 1 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3204 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3205 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3204 | Gullies - Emptying / clear covers | 192.9962 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3205 | Gullies - Emptying / clear covers | 192.9962 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE77 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3206 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.6117 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 106 | 106 | 0 | 1 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3207 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.6261 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 66 | 66 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept)
YNE77 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3208 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 8.6231 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 111.7 | 111.7 | 0 | 1 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3208 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 8.4308 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 109.21 | 109.21 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure Amey 45110 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3209 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE77 Closure Vaisala 45110 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3210 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE77 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3211 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 135.5711 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2828 | 2828 | 0 | 1 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3212 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3213 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3214 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3215 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 46 | 46 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3215 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 103.0685 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 43 | 43 | 0 | 1 |  |  |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3215 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 218.1217 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 91 | 91 | 0 | 1 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3215 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 155.8012 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 65 | 65 | 0 | 1 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3215 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 117.4502 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 49 | 49 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3216 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 28 | 28 | 0 | 1 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3216 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3216 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 280.4422 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 117 | 117 | 0 | 1 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3216 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 112.6563 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 47 | 47 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3216 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 397.8924 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 166 | 166 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3217 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3217 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3218 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3218 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3219 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 43.5763 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2103.88 | 2103.88 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3219 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 27.7229 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1338.47 | 1338.47 | 0 | 1 |  |  |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3219 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 23.7815 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1148.18 | 1148.18 | 0 | 1 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3219 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.66777 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 32.24 | 32.24 | 0 | 1 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3219 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.0414 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 98.56 | 98.56 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3220 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.8862 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 332.47 | 332.47 | 0 | 1 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3220 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.6095 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 512.23 | 512.23 | 0 | 1 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3220 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.8941 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 429.41 | 429.41 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3220 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.3713 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 211.05 | 211.05 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3221 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.4145 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1836 | 1836 | 0 | 1 |  |  |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3221 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.8966 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1747.8 | 1747.8 | 0 | 1 |  |  |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3221 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 108.4262 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 3798 | 3798 | 0 | 1 |  |  |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3221 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 71.5304 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2505.6 | 2505.6 | 0 | 1 |  |  |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3221 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 82.8355 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2901.6 | 2901.6 | 0 | 1 |  |  |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3222 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.0286 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 491.4 | 491.4 | 0 | 1 |  |  |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3222 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.5474 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1035 | 1035 | 0 | 1 |  |  |  | 4405A628/16 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3222 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 132.8349 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4653 | 4653 | 0 | 1 |  |  |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3222 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 50.1021 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1755 | 1755 | 0 | 1 |  |  |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3222 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 134.8904 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4725 | 4725 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 3223 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 7.8017 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 113 | 113 | 0 | 1 |  |  |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE78 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3224 | VRS - Check all Road Restraint System - ILM | 0.68102 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 52.93 | 52.93 | 0 | 1 |  |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.5989 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 124.27 | 124.27 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0.28512 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 22.16 | 22.16 | 0 | 1 |  |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0.24189 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 18.8 | 18.8 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 0.36335 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 28.24 | 28.24 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 5.2091 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 404.86 | 404.86 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.0262 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 79.76 | 79.76 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3224 | VRS - Check all Road Restraint System - ILM | 0.72618 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 56.44 | 56.44 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 8.6402 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 671.53 | 671.53 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 0.95096 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 73.91 | 73.91 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 8.3995 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 652.82 | 652.82 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 0.54579 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 42.42 | 42.42 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 8.8929 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 691.17 | 691.17 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.8238 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 141.75 | 141.75 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 1.2435 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 96.65 | 96.65 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 1.0814 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 84.05 | 84.05 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.1476 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 89.19 | 89.19 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 52.57 |  | 52.57 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45860090 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.213 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 94.28 | 94.28 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 70.45 |  | 70.45 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45860090 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 0.33118 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25.74 | 25.74 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 61.7 |  | 61.7 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45860090 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3226 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 171.08 |  | 171.08 | 0 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45860090 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3225 | VRS - Check all Road Restraint System - ILM | 1.0925 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 84.91 | 84.91 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3227 | Gullies - Emptying / clear covers | 856.903 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | EB | 146 | 111 | 35 | 0.76027 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852377 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 16 | 16 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3227 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 | 0 | 0 | 0 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852377 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3230 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Annually for ILM Sections Within the Route | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3231 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3227 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852377 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3232 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 833.7434 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 198 | 108 | 90 | 0.54545 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3232 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852374 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 385.9923 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 50 | 50 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 | No jobs in Confirm |  |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 | No jobs in Confirm |  |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3230 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 | No jobs in Confirm |  |  | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3231 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Annually for ILM Sections Within the Route | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3229 | Gullies - Emptying / clear covers | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 15 | 15 | 0 | 1 | No jobs in Confirm |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3228 | Gullies - Emptying / clear covers | 162.1168 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 21 | 21 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3227 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 |  | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | Every 2 years | 0 | 0 | 45852377 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3233 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.2003 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 414 | 414 | 0 | 1 | 16/10 CGS did not resource will do on days this week |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 | 45862769 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3234 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.8205 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 358 | 358 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3235 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.1334 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 46 | 46 | 0 | 1 | 16/10 CGS did not resource will catch up on days this week |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 | 45862283 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3236 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.3117 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 175 | 175 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3233 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 100 | 100 | 0 | 1 | 16/10 CGS did not resource will do on days this week |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 | 45862769 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3234 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.0075 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 325 | 325 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3233 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.4494 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 140 | 140 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 | 45862769 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3234 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.8827 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 117 | 117 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3234 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4885 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 101 | 101 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Amey 45110 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3237 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 43.0574 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 557.75 | 557.75 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | 3 times per year (ILM Entire Route) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856693 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 364.5483 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 17 | 17 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 | 0 | 0 | 0 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856693 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3241 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 1 | 1 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 16/10 - vvehicle breakdown prevented completion |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856693 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856693 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 |  | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 |  | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3239 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 |  | 0 | 0 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 | 45856694 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3240 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 | There are no assets on the OS on this route, it is single carriageway route. |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Amey 45110 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3242 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys |  | 7 |  | 7 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 2 | Yes |  | ILM Annual Network Wide | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure Vaisala 45110 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3243 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | 2024-01-17 | 2024-1 | 2024-01-18 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys |  | 1 |  | 1 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 2 | Yes |  | 2 times per year | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3244 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 21.3199 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1544 | 1544 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes |  | Annually (Sept, Oct) | 0 | 0 | 52036755 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3244 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 68.3646 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4951 | 4951 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes |  | Annually (Sept, Oct) | 0 | 0 | 52036768 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3244 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 138.4276 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 10025 | 10025 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes |  | Annually (Sept, Oct) | 0 | 0 | 52036769 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3244 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 51.1733 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3706 | 3706 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | Days | Yes |  | Annually (Sept, Oct) | 0 | 0 | 52036766 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3245 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3246 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3247 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 | There are no assets on the OS on this route, it is single carriageway route. |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 2 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3248 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 | There are no assets on the OS on this route, it is single carriageway route. |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 2 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3249 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 112.896 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2355 | 2355 | 0 | 1 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 2 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 35 | 35 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 7 | 7 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 24 | 24 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 16 | 16 | 0 | 1 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 16 | 16 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 15 | 15 | 0 | 1 |  |  |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 29 | 29 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 18 | 18 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 158.1982 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 66 | 66 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 26 | 26 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 119.8471 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 50 | 50 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862265 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 11 | 11 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3250 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 45862348 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3252 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65.9159 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 | 52036712 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3253 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 14 | 14 | 0 | 1 | Only 2 quantity raised and job completed |  |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3254 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3254 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3254 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3254 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.873 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 90.43 | 90.43 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45588 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 22.01 | 22.01 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3256 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.6267 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 223.38 | 223.38 | 0 | 1 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862524 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.46499 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 22.45 | 22.45 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3256 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.9045 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 236.79 | 236.79 | 0 | 1 |  |  |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862524 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.8556 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 475.83 | 475.83 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.1072 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 343.14 | 343.14 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 58.0646 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2803.38 | 2803.38 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 27.7258 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1338.61 | 1338.61 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.414 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 116.55 | 116.55 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.1667 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 249.45 | 249.45 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.39561 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 19.1 | 19.1 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 12.451 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 601.14 | 601.14 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.4678 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 312.27 | 312.27 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862437 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3256 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.1174 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 150.51 | 150.51 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862524 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3256 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.4163 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 164.94 | 164.94 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862524 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3257 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 22.3329 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 539.12 | 539.12 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862467 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 28.0077 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 676.11 | 676.11 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 10.3164 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 249.04 | 249.04 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 55.348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1336.11 | 1336.11 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3257 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2.0348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 49.12 | 49.12 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862467 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 63.024 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1521.41 | 1521.41 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 12.4606 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 300.8 | 300.8 | 0 | 1 |  |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 10.6507 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 257.11 | 257.11 | 0 | 1 |  |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 27.5984 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 666.23 | 666.23 | 0 | 1 |  |  |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3258 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3.3629 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 81.18 | 81.18 | 0 | 1 |  |  |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.2806 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 220 | 220 | 0 | 1 |  |  |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.1069 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 319 | 319 | 0 | 1 |  |  |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.1371 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 250 | 250 | 0 | 1 |  |  |  | 4405A616/48 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.7121 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 95 | 95 | 0 | 1 |  |  |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3868 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1800 | 1800 | 0 | 1 |  |  |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.0547 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 107 | 107 | 0 | 1 |  |  |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.2726 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1796 | 1796 | 0 | 1 |  |  |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 38.797 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1359 | 1359 | 0 | 1 |  |  |  | 4405A616/57 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 324 | 324 | 0 | 1 |  |  |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.1925 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 322 | 322 | 0 | 1 |  |  |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.3924 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 329 | 329 | 0 | 1 |  |  |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.1054 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1615 | 1615 | 0 | 1 |  |  |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.1925 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 322 | 322 | 0 | 1 |  |  |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7602 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 482 | 482 | 0 | 1 |  |  |  | 4405A616/70 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1909 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 392 | 392 | 0 | 1 |  |  |  | 4405A616/72 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.0686 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 738 | 738 | 0 | 1 |  |  |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.9357 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1539 | 1539 | 0 | 1 |  |  |  | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.7872 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 553 | 553 | 0 | 1 |  |  |  | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.8222 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 274 | 274 | 0 | 1 |  |  |  | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 100.661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3526 | 3526 | 0 | 1 |  |  |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.5254 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 754 | 754 | 0 | 1 |  |  |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 581 | 581 | 0 | 1 |  |  |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.6616 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1039 | 1039 | 0 | 1 |  |  |  | 4405A616/87 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3260 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.5328 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1665 | 1665 | 0 | 1 |  |  |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9633 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 349 | 349 | 0 | 1 |  |  |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3259 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.7121 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 340.2 | 340.2 | 0 | 1 |  |  |  | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 2 | Yes |  | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3261 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 1.7951 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 26 | 26 | 0 | 1 |  |  | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 2 | Yes | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 52036706 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE79 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3262 | VRS - Check all Road Restraint System - ILM | 8.3589 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 649.67 | 649.67 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033217 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3263 | VRS - Check all Road Restraint System - ILM | 9.7445 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 757.36 | 757.36 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033218 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3264 | VRS - Check all Road Restraint System - ILM | 0.42176 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 32.78 | 32.78 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033219 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3262 | VRS - Check all Road Restraint System - ILM | 0.3169 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 24.63 | 24.63 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033217 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3263 | VRS - Check all Road Restraint System - ILM | 0.39204 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 30.47 | 30.47 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033218 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3264 | VRS - Check all Road Restraint System - ILM | 0.28332 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 22.02 | 22.02 | 0 | 1 |  |  |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033219 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3262 | VRS - Check all Road Restraint System - ILM | 0.36502 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 28.37 | 28.37 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033217 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3263 | VRS - Check all Road Restraint System - ILM | 1.1612 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 90.25 | 90.25 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 52033218 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 30 | 0 | 30 | 0 | 13/10: No time to complete |  |  | 4405A616/105 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3266 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | EB | 30 | 0 | 30 | 0 | 13/10: No time to complete |  |  | 4405A616/107 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857765 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3267 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 | No assets on OS |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3268 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 19 | 19 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3266 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857765 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3267 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3266 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857765 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45858046 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3268 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/105 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3270 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/107 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856586 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3270 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856586 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3271 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3272 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235.8842 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | No jobs for the OS all NS | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3270 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856586 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3272 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | No jobs for the OS all NS | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3271 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | No jobs for the offside assets on NS | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3272 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | No jobs for the OS all NS | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3269 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 13/10: No time to complete |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856439 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3272 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | No jobs for the OS all NS | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure Amey 45110 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3273 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure | Lane 1 Closure | N/A |  |  | ILM Annual Network Wide | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3274 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 99.1431 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7180 | 7180 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Sept, Oct) | 0 | 0 | 52036699 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3275 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3276 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3277 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3278 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3279 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 27.9004 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 582 | 582 | 0 | 1 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/105 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3281 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/107 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3281 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 9 | 9 | 0 | 1 |  |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 34 | 34 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3281 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 15 | 15 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3281 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 16 | 16 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3280 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3282 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3283 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3284 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3285 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.46002 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 22.21 | 22.21 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862224 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3285 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.5399 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 170.91 | 170.91 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862224 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3286 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.5789 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 124.51 | 124.51 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862224 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3287 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 39.0689 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 943.13 | 943.13 | 0 | 1 |  | N |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3288 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 27.4783 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 663.33 | 663.33 | 0 | 1 |  | N |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.9405 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 103 | 103 | 0 | 1 |  |  |  | 4405A616/105 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3290 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 230 | 230 | 0 | 1 |  |  |  | 4405A616/107 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3290 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6208 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 337 | 337 | 0 | 1 |  |  |  | 4405A616/109 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 88.2426 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3091 | 3091 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.4772 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 367 | 367 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3290 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9062 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 347 | 347 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.3679 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 153 | 153 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3290 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.5971 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 126 | 126 | 0 | 1 |  |  |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.0555 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 72 | 72 | 0 | 1 |  |  |  | 4405A616/40 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3289 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7619 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 412 | 412 | 0 | 1 |  |  |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3291 | VRS - Check all Road Restraint System - ILM | 0.73133 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 56.84 | 56.84 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3292 | VRS - Check all Road Restraint System - ILM | 0.28834 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 22.41 | 22.41 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3293 | VRS - Check all Road Restraint System - ILM | 0.099329 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 7.72 | 7.72 | 0 | 1 |  |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3293 | VRS - Check all Road Restraint System - ILM | 0.91081 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 70.79 | 70.79 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3292 | VRS - Check all Road Restraint System - ILM | 3.6481 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 283.54 | 283.54 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3291 | VRS - Check all Road Restraint System - ILM | 4.5476 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 353.45 | 353.45 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3293 | VRS - Check all Road Restraint System - ILM | 0.68025 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 52.87 | 52.87 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3292 | VRS - Check all Road Restraint System - ILM | 8.4263 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 654.91 | 654.91 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3291 | VRS - Check all Road Restraint System - ILM | 1.0674 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 82.96 | 82.96 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3292 | VRS - Check all Road Restraint System - ILM | 1.7341 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 134.78 | 134.78 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3291 | VRS - Check all Road Restraint System - ILM | 2.0286 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 157.67 | 157.67 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3292 | VRS - Check all Road Restraint System - ILM | 0.53035 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 41.22 | 41.22 | 0 | 1 |  |  |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45861372 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3294 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857885 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3295 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 | No gullies on OS |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3296 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | EB | 52 | 0 | 52 | 0 | 13/10: no time |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857884 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3296 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 | 0 | 0 | 0 | 13/10: no time |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857884 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3297 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 16 | 16 | 0 | 1 | No gullies on OS |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3295 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 | No gullies on OS |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3294 | Gullies - Emptying / clear covers | 154.3969 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857885 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3295 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | No gullies on OS |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3294 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857885 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3296 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: no time |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857884 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3297 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | No gullies on OS |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3295 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 | No gullies on OS |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3294 | Gullies - Emptying / clear covers | 324.2336 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | WB | 46 | 42 | 4 | 0.91304 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | 45857885 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3295 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | No gullies on OS |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3298 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.1146 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 167 | 167 | 0 | 1 | No jobs for OS assets |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3300 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 | No catchpits on the OS |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3301 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: no time |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856409 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3301 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 | 0 | 0 | 0 | 13/10: no time |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856409 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3302 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 1 | 1 | 0 | 1 | No catchpits on the OS |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278.7722 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3300 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235.8842 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 | No catchpits on the OS |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3301 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 13/10: no time |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856409 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3300 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 | No catchpits on the OS |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3299 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 | 45856403 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3300 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 | No catchpits on the OS |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure Amey 45110 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3303 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-16 | 2024-1 | 2024-01-17 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys |  | 2 |  | 2 | 0 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | N/A |  |  | ILM Annual Network Wide | 0 | 0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3304 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 31.7037 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2296 | 2296 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Sept, Oct) | 0 | 0 | 52036732 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3306 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3306 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 27 | 27 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3306 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 17 | 17 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 38 | 38 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 41 | 41 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3305 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3307 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3307 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 14 | 14 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3308 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65.9159 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 11 | 11 | 0 | 1 |  |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3308 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 197.7477 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 33 | 33 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3307 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3307 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 119.8471 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3307 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 149.8089 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3309 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 12.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 303.37 | 303.37 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862983 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.0237 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 211 | 211 | 0 | 1 |  |  |  | 4405A616/101 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.9666 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 209 | 209 | 0 | 1 |  |  |  | 4405A616/103 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3311 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.283 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 115 | 115 | 0 | 1 |  |  |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3311 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 230 | 230 | 0 | 1 |  |  |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 54.0703 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1894 | 1894 | 0 | 1 |  |  |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.8777 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 346 | 346 | 0 | 1 |  |  |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3311 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.4772 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 367 | 367 | 0 | 1 |  |  |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 62.6348 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2194 | 2194 | 0 | 1 |  |  |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.3516 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 853 | 853 | 0 | 1 |  |  |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3310 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.6542 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 128 | 128 | 0 | 1 |  |  |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE81 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3312 | VRS - Check all Road Restraint System - ILM | 0.29992 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 23.31 | 23.31 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45860146
YNE81 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3313 | VRS - Check all Road Restraint System - ILM | 0.52469 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 40.78 | 40.78 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45860146
YNE81 Closure 1 EB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3313 | VRS - Check all Road Restraint System - ILM | 0.091609 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 7.12 | 7.12 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45860146
YNE81 Closure 1 WB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3312 | VRS - Check all Road Restraint System - ILM | 7.7722 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 604.07 | 604.07 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45860146
YNE81 Closure 1 WB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3314 | VRS - Check all Road Restraint System - ILM | 5.1165 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 397.66 | 397.66 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45860146
YNE81 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3315 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45857811
YNE81 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3316 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE81 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3317 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45858333
YNE81 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3318 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE81 Closure 1 EB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3317 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45858333
YNE81 Closure 1 EB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3318 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 2 | 2 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE81 Closure 1 WB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3315 | Gullies - Emptying / clear covers | 277.9145 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 36 | 36 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45857811
YNE81 Closure 1 WB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3316 | Gullies - Emptying / clear covers | 216.1557 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 28 | 28 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE81 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3319 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45856670
YNE81 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3320 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45857011
YNE81 Closure 1 EB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3320 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278.7722 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 13 | 13 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45857011
YNE81 Closure 1 EB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3321 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 1 | 1 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE81 Closure 1 WB NS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3319 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 428.8804 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45856670
YNE81 Closure 1 WB OS Enviroflow 45110 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3322 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 450.3244 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 21 | 21 | 0 | 1 | No jobs in confirm all NS |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE81 Closure Amey 45110 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3323 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 126dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE81 Closure 1 WB NS CGS 45110 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3324 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 13.3526 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 967 | 967 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Sept, Oct) |  |  | 52036775
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3325 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3326 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3327 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3328 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3329 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 25.072 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 523 | 523 | 0 | 1 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3330 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45862022
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3331 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 21 | 21 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45842512
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3331 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 11 | 11 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45842512
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3330 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 208.534 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 87 | 87 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45862022
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3332 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 113.8548 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 19 | 19 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 52036819
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3333 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 149.8089 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 52036822
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3334 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039364
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3335 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039365
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3335 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039365
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3334 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52039364
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3336 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.0604 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 244.32 | 244.32 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 45862987
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3337 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.6261 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 223.35 | 223.35 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 45862051
YNE81 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3337 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.63421 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 30.62 | 30.62 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 45862051
YNE81 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3336 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.0097 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 193.59 | 193.59 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 45862987
YNE81 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3338 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 90.8063 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 2192.08 | 2192.08 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | 3 time per year (Apr - Sep)
YNE81 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3339 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.3051 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 396 | 396 | 0 | 1 |  |  |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45901707
YNE81 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.9968 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | EB | 385.2 | 385.2 | 0 | 1 |  |  |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45901707
YNE81 Closure 1 EB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5375 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 229 | 229 | 0 | 1 |  |  |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45901707
YNE81 Closure 1 WB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3339 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 105.6513 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 3700.8 | 3700.8 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep) |  |  | 45901707
YNE81 Closure 1 WB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3341 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 64.7606 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | WB | 938 | 938 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept) |  |  | 52036823
YNE82 Closure 1 NB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3342 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | NB | 112.29 |  | 112.29 | 0 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3343 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 43dys | NB | 174.54 |  | 174.54 | 0 | 23/10 - not complete will be completed next week by internal resource |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45859454 |  |  | Day Shift
YNE82 Closure 1 NB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3342 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | NB | 73.06 |  | 73.06 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3343 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 43dys | NB | 242.79 |  | 242.79 | 0 | 23/10 - not complete will be completed next week by internal resource |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45859454 |  |  | Day Shift
YNE82 Closure 1 SB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3344 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | SB | 30.14 |  | 30.14 | 0 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3345 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 43dys | SB | 215.96 |  | 215.96 | 0 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45859454 |  |  | Day Shift
YNE82 Closure 1 NB NS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3342 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | CW | 431.44 |  | 431.44 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Bettamix 45110 VRS - Check all Road Restraint System - ILM | 3343 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 43dys | CW | 228.47 |  | 228.47 | 0 | 23/10 - not complete will be completed next week by internal resource |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45859454 |  |  | Day Shift
YNE82 Closure 1 NB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3346 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | NB | 57 | 1 | 56 | 0.017544 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3347 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45857072 |  |  | Day Shift
YNE82 Closure 1 NB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3346 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | NB | 0 |  | 0 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3347 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | NB | 0 |  | 0 | 0 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45857072 |  |  | Day Shift
YNE82 Closure 1 SB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3348 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | SB | 61 | 7 | 54 | 0.11475 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3349 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45857072 |  |  | Day Shift
YNE82 Closure 1 NB NS Enviroflow 45110 Gullies - Emptying / clear covers | 3346 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 |  | 0 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS Enviroflow 45110 Gullies - Emptying / clear covers | 3347 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys | CW | 0 |  | 0 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45857072 |  |  | Day Shift
YNE82 Closure 1 NB OS CGS 45110 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3350 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.5335 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 43dys | CW | 184 | 184 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45861955 |  |  | Day Shift
YNE82 Closure 1 NB NS Enviroflow 45110 G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 3351 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 0 | 4.3.3.3 | A40012 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-08 | 2024-1 | 2024-01-08 | 2023-07-03 | 2023-08-31 | 2024-01-31 |  | 43dys | CW | 1 |  | 1 | 0 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years | 0 | 0 | No jobs rasied | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure Amey 45110 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3352 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 3 | 3 | 0 | 1 |  |  |  |  | YNE82: A61 | YNE82 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE82 Closure Amey 45110 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3353 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 3 | 3 | 0 | 1 |  |  |  |  | YNE82: A61 | YNE82 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3354 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3355 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE82 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3356 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3357 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-08-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE82Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3358 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 27.6128 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys |  | 576 | 576 | 0 | 1 |  |  |  |  | YNE82: A61 | YNE82Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3359 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 117.4502 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 49 | 49 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3359 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 32 | 32 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3360 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3359 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 119.8471 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 50 | 50 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3361 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 425.4573 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 71 | 71 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3361 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 113.8548 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 19 | 19 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3361 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 41.9465 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 7 | 7 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3362 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3363 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3362 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 4 | 4 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3364 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 44.0664 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 2127.54 | 2127.54 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3364 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 24.0267 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 1160.02 | 1160.02 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3364 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.852 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 427.38 | 427.38 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3365 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.8746 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 1712 | 1712 | 0 | 1 |  |  |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3365 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8157 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 554 | 554 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3366 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8443 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | SB | 555 | 555 | 0 | 1 |  |  |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45110 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3365 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.8712 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 626 | 626 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3367 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 66.6976 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | NB | 742.03 | 742.03 | 0 | 1 |  |  |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE82 Closure 1 NB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3368 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 48.3979 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-08-31 | Complete |  | 43dys | CW | 701 | 701 | 0 | 1 |  |  |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE83NE83 M18 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3369 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 3748 | 0 | 3748 | 0 |  | Y |  |  | YNE83: M18 Link - J1 | YNE83NE83 M18 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3370 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3371 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Missed intervention |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3372 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Missed intervention |  |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3373 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3373 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3373 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3373 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 16 | 0 | 16 | 0 |  | Y |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 23 | 0 | 23 | 0 |  | Y |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 14 | 0 | 14 | 0 |  | Y |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3374 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3375 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 12.23 | 0 | 12.23 | 0 |  | Y |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3375 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 28.02 | 0 | 28.02 | 0 |  | Y |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3375 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 53.86 | 0 | 53.86 | 0 |  | Y |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3375 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 50.5 | 0 | 50.5 | 0 |  | Y |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 81.3 | 0 | 81.3 | 0 |  | Y |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 11.03 | 0 | 11.03 | 0 |  | Y |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 12.74 | 0 | 12.74 | 0 |  | Y |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 39.71 | 0 | 39.71 | 0 |  | Y |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 50.84 | 0 | 50.84 | 0 |  | Y |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3376 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 6.5 | 0 | 6.5 | 0 |  | Y |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3377 | Sweeping - Paved non-running areas - Full Sweep 01 | 115.8048 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 15548 | 15548 | 0 | 1 |  | Y |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3378 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 724 | 0 | 724 | 0 |  | Y |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3378 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 590 | 0 | 590 | 0 |  | Y |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3379 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 995 | 0 | 995 | 0 |  | Y |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3378 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1017 | 0 | 1017 | 0 |  | Y |  | 4400M18/176 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3378 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 666 | 0 | 666 | 0 |  | Y |  | 4400M18/177 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3379 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 347 | 0 | 347 | 0 |  | Y |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3379 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 695 | 0 | 695 | 0 |  | Y |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3379 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 478 | 0 | 478 | 0 |  | Y |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3380 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 4687 | 0 | 4687 | 0 |  | Y |  |  | YNE84: M18 J1-2 | YNE84 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3381 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | missed or complete? |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3382 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3383 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3384 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/119 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3385 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3386 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 11 | 0 | 11 | 0 |  | Y |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 14 | 0 | 14 | 0 |  | Y |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  |  |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3386 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 11 | 0 | 11 | 0 |  | Y |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 5 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | CW | 5 | 0 | 5 | 0 |  | Y |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 5 CW NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.14623 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 7.06 | 7.06 | 0 | 1 |  |  |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.6164 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 29.76 | 29.76 | 0 | 1 |  |  |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3392 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 9.31 | 0 | 9.31 | 0 |  | Y |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3393 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 21.87 | 0 | 21.87 | 0 |  | Y |  | 4400M18/130 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3393 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 35.26 | 0 | 35.26 | 0 |  | Y |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3394 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.21479 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 10.37 | 10.37 | 0 | 1 |  |  |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3395 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 21.76 | 0 | 21.76 | 0 |  | Y |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 16 | 0 | 16 | 0 |  | Y |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 76.75 | 0 | 76.75 | 0 |  | Y |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 3397 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 1001 | 0 | 1001 | 0 |  | Y |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3398 | Sweeping - Paved non-running areas - Full Sweep 01 | 501.0718 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 74749 | 67274.1 | 7474.9 | 0.9 | 08/09/2023: 90% complete 700m sb ns to do, J1 slips to do, 2.3k centres to do |  |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3399 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 526 | 0 | 526 | 0 |  | Y |  | 4400M18/149 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3399 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 136 | 0 | 136 | 0 |  | Y |  | 4400M18/150 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3400 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 563 | 0 | 563 | 1 |  | Y |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3401 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 665 | 0 | 665 | 0 |  | Y |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 646 | 0 | 646 | 0 |  | Y |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 285 | 0 | 285 | 0 |  | Y |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 855 | 0 | 855 | 0 |  | Y |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 293 | 0 | 293 | 0 |  | Y |  | 4400M18/292 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3403 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 1519 | 0 | 1519 | 0 |  | Y |  |  | YNE85: M18 J2-3 | YNE85Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3404 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3405 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3406 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037122
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 12 | 0 | 12 | 0 |  | Y |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3407 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 24.5 | 0 | 24.5 | 0 |  | Y |  | 4400M18/115 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3407 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 38.94 | 0 | 38.94 | 0 |  | Y |  | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3407 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 46.51 | 0 | 46.51 | 0 |  | Y |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7.57 | 0 | 7.57 | 0 |  | Y |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 11.32 | 0 | 11.32 | 0 |  | Y |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3398 | Sweeping - Paved non-running areas - Full Sweep 01 | 46.9033 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 6297.25 | 6297.25 | 0 | 1 |  |  |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3399 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 477 | 0 | 477 | 0 |  | Y |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3399 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 575 | 0 | 575 | 0 |  | Y |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 716 | 0 | 716 | 0 |  | Y |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 603 | 0 | 603 | 0 |  | Y |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3408 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 508.2991 | 0 | 508.2991 | 0 |  | Y |  |  | YNE86: M18 J3-4 | YNE86 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3409 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3410 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3411 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3412 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3412 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3413 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3413 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3414 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3414 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3415 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3416 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 21.78 | 0 | 21.78 | 0 |  | Y |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3417 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 21 | 0 | 21 | 0 |  | Y |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3416 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 23.42 | 0 | 23.42 | 0 |  | Y |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3418 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 168.22 | 0 | 168.22 | 0 |  | Y |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3419 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 48.29 | 0 | 48.29 | 0 |  | Y |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3420 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 508 | 0 | 508 | 0 |  | Y |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45110 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 3421 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2902 | 0 | 2902 | 0 |  | Y |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3422 | Sweeping - Paved non-running areas - Full Sweep 01 | 43.672 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 5863.4167 | 5863.4167 | 0 | 1 |  |  |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3423 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 696 | 0 | 696 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 & 2 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3424 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 357 | 0 | 357 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3425 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 482 | 0 | 482 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/250 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3426 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 1115 | 0 | 1115 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3427 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 3326 | 0 | 3326 | 0 |  | Y |  |  | YNE87: M18 J4-5 | YNE87Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3428 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037098
YNE87 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3429 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3430 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037098
YNE86 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3415 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3415 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3432 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 10.88 | 0 | 10.88 | 0 |  | Y |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3432 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 29.18 | 0 | 29.18 | 0 |  | Y |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3433 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 30.0743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 726 | 726 | 0 | 1 |  |  |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3434 | Sweeping - Paved non-running areas - Full Sweep 01 | 102.2751 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 13731.5 | 13731.5 | 0 | 1 | 18/8: 2000M18/101 | Y |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3435 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 371 | 0 | 371 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3435 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 657 | 0 | 657 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/143 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3435 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1266 | 0 | 1266 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3435 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 122 | 0 | 122 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/160 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3435 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 589 | 0 | 589 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/162 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3426 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 716 | 0 | 716 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3436 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 195 | 0 | 195 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/253 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3436 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 333 | 0 | 333 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3436 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 546 | 0 | 546 | 0 | M18 rescheduled for August to allow A628 cyclic to be brought forward to share planned full closures | Y |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3437 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 1849 | 0 | 1849 | 0 |  | Y |  |  | YNE88: M18 J5-6 | YNE88 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3438 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3439 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Missed? |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3440 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3441 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3441 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3441 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3441 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3441 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 13 | 0 | 13 | 0 |  | Y |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3443 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 22.15 | 0 | 22.15 | 0 |  | Y |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3444 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 55.72 | 0 | 55.72 | 0 |  | Y |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3443 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 28.91 | 0 | 28.91 | 0 |  | Y |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3443 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 22.67 | 0 | 22.67 | 0 |  | Y |  | 2000M18/147 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3445 | Sweeping - Paved non-running areas - Full Sweep 01 | 28.5248 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 7659.5 | 3829.75 | 3829.75 | 0.5 | 17/8: NB nearside complete, most of centres done NB and SB |  |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3446 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 478 | 0 | 478 | 0 |  | Y |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3447 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 231 | 0 | 231 | 0 |  | Y |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3447 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 270 | 0 | 270 | 0 |  | Y |  | 2000M18/124 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3447 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 585 | 0 | 585 | 0 |  | Y |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3446 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 505 | 0 | 505 | 0 |  | Y |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3447 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 621 | 0 | 621 | 0 |  | Y |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 286/3 | 282/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3448 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys |  | 3680 | 0 | 3680 | 0 |  | Y |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 1 SB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3449 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3450 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 1 SB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3451 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3452 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3452 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3452 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3453 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  |  |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3453 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  |  |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3453 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  |  |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3454 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 8 | 0 | 8 | 0 |  | Y |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3455 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 109.56 | 0 | 109.56 | 0 |  | Y |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3456 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.1838 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 491.68 | 491.68 | 0 | 1 |  |  |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3456 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.10791 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 5.21 | 5.21 | 0 | 1 |  |  |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 SB NS CGS 45110 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 3457 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 67 | 0 | 67 | 0 |  | Y |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45110 Sweeping - Paved non-running areas - Full Sweep 01 | 3458 | Sweeping - Paved non-running areas - Full Sweep 01 | 57.0905 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 7665 | 7665 | 0 | 1 | Faulty sweepers |  |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3459 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 604 | 0 | 604 | 0 |  | Y |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3460 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | SB | 469 | 0 | 469 | 0 |  | Y |  | 2000M18/150 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3461 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 42.5637 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-03 | 2023-07-03 | 2023-08-31 | 2023-10-31 |  | 21dys | NB | 3253 | 3253 | 0 | 1 |  | Y |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | Days | No |  | 2 times per year (ILM Certain Sections) | 291/3 | 293/0M18 M62 155/9 EB | 52037441 | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS Amey 45110 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3462 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | NB | 1481 | 0 | 1481 | 0 |  | Y |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3463 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 222.5321 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 4642 | 4642 | 0 | 1 |  | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3464 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3465 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3466 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3467 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3467 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3467 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3467 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3468 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3467 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3469 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.0623 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 99.57 | 99.57 | 0 | 1 | 0 |  |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3470 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.6342 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 78.9 | 78.9 | 0 | 1 |  | N |  | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3469 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.98135 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 47.38 | 47.38 | 0 | 1 |  |  |  | 2000A180/113 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3469 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9171 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 140.84 | 140.84 | 0 | 1 |  |  |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3471 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9511 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 142.48 | 142.48 | 0 | 1 |  | N |  | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3472 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.4668 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 167.38 | 167.38 | 0 | 1 |  | N |  | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3470 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.4755 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 119.52 | 119.52 | 0 | 1 |  | N |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3470 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.1433 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 200.04 | 200.04 | 0 | 1 |  | N |  | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3470 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1178 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 150.53 | 150.53 | 0 | 1 |  | N |  | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3472 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.5484 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 219.6 | 219.6 | 0 | 1 |  | N |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3472 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.5025 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 217.38 | 217.38 | 0 | 1 |  | N |  | 2000A180/909 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3473 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 44.283 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1069 | 1069 | 0 | 1 |  | N |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3473 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 20.2981 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 490 | 490 | 0 | 1 |  | N |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3474 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 31.2342 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 754 | 754 | 0 | 1 |  | N |  | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3475 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 23.6535 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 571 | 571 | 0 | 1 |  | N |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3475 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 11.6403 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 281 | 281 | 0 | 1 |  | N |  | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3475 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.1142 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 389 | 389 | 0 | 1 |  | N |  | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3476 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 9.4448 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 228 | 228 | 0 | 1 |  | N |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE97 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3477 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 136.9613 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 2857 | 2857 | 0 | 1 |  | N |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3478 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3479 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3480 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3481 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 2000A180/145 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3482 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3481 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3482 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3483 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 320.15 | 0 | 320.15 | 0 |  | Y |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 282.41 | 0 | 282.41 | 0 |  | Y |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3483 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 166.96 | 0 | 166.96 | 0 |  | Y |  | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 155.64 | 0 | 155.64 | 0 |  | Y |  | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3485 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 247 | 0 | 247 | 0 |  | Y |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3486 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 204 | 0 | 204 | 0 |  | Y |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3486 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 457 | 0 | 457 | 0 |  | Y |  | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3486 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1119 | 0 | 1119 | 0 |  | Y |  | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE98 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3487 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 109.78 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 2290 | 2290 | 0 | 1 |  | N |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3488 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3489 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3490 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3491 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3491 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3492 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3492 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3491 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3493 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 368.14 | 0 | 368.14 | 0 |  | Y |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3494 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 185.51 | 0 | 185.51 | 0 |  | Y |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3493 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 135.14 | 0 | 135.14 | 0 |  | Y |  | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3494 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 127.92 | 0 | 127.92 | 0 |  | Y |  | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3495 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1169 | 0 | 1169 | 0 |  | Y |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3496 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 442 | 0 | 442 | 0 |  | Y |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE99 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3497 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 56.1364 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 1171 | 1171 | 0 | 1 |  | N |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3498 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3499 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB OS CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3500 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3501 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A180/183 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3501 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 | Check jobs are closed |  |  | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3502 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 | Check jobs are closed |  |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3503 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.2833 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 158.52 | 158.52 | 0 | 1 |  | N |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.47556 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 22.96 | 22.96 | 0 | 1 |  |  |  | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3504 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.7251 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 276.41 | 276.41 | 0 | 1 |  |  |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3505 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 101.8219 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 2458 | 2458 | 0 | 1 |  |  |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep)
YNE100 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3506 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 39.6454 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 827 | 827 | 0 | 1 |  | N |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3506 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3506 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3506 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3507 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3509 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 13.1316 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 634 | 634 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3510 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 51 | 51 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW OS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3511 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1085 | 1085 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW OS | Lane 2 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3510 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 654 | 654 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3512 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 591.2298 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 6577.6 | 6577.6 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3513 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 55.9926 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys |  | 1168 | 1168 | 0 | 1 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3513 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3513 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3513 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-07-03 | 2023-07-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3514 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3514 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 3514 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.1657 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  |  |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.60066 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 |  |  |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.5898 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 463 | 463 | 0 | 1 |  |  |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.55923 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 27 | 27 | 0 | 1 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure 1 CW NS CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3516 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.57995 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 28 | 28 | 0 | 1 |  |  |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 25.9112 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1251 | 1251 | 0 | 1 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.4797 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 168 | 168 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3515 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.39353 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  |  |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 6653.51 | 6653.51 | 0 | 1 |  |  |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 351.65 | 351.65 | 0 | 1 |  |  |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 233.14 | 233.14 | 0 | 1 |  |  |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 389.64 | 389.64 | 0 | 1 |  |  |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | EB | 2302.85 | 2302.85 | 0 | 1 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure 1 CW NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3518 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | CW | 1819 | 1819 | 0 | 1 |  |  |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 9183.24 | 9183.24 | 0 | 1 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 3359.14 | 3359.14 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 869.31 | 869.31 | 0 | 1 |  |  |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 119.67 | 119.67 | 0 | 1 |  |  |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3517 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 1790.7 | 1790.7 | 0 | 1 |  |  |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 3 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 996.5353 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 11086.74 | 11086.74 | 0 | 1 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 222.664 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2477.2 | 2477.2 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 207.0958 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 2304 | 2304 | 0 | 1 |  |  |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45110 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 3519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 468.5003 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | WB | 5212.2 | 5212.2 | 0 | 1 |  |  |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3520 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 15.0976 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 364.46 | 364.46 | 0 | 1 |  |  |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3520 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 17.6639 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | NB | 426.41 | 426.41 | 0 | 1 |  |  |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3521 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 10.1325 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 244.6 | 244.6 | 0 | 1 |  |  |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45110 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 3521 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2.8314 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-07-03 | 2023-07-31 | Complete |  | 21dys | SB | 68.35 | 68.35 | 0 | 1 |  |  |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE1 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3522 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE2 Closure 1 WB NS Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3523 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE3 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3524 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 & 2 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE5 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3525 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE5: M62 J26-27 | YNE5 Closure | Lane 1 & 2 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE7 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3526 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE12 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3527 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE12 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3527 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 3 | No |  | 2 times per year |  |  | On ServiceNow
YNE19 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3528 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE26 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3529 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 1357 | 1357 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3529 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 3468 | 3468 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3529 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 2575 | 2575 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3530 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 462 | 462 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct) |  |  | 45854434
YNE27 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3531 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 329 | 329 | 0 | 1 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3531 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 1346 | 1346 | 0 | 1 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3532 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 199 | 199 | 0 | 1 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3533 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 7727 | 7727 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3533 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 2585 | 2585 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3534 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 8327 | 8327 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 4 | No |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3535 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 438 | 438 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3535 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 3851 | 3851 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3535 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 5971 | 5971 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3536 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 6695 | 6695 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3536 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 401 | 401 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3536 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 1105 | 1105 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3537 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3538 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  | 0 |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037353
YNE30 Closure 1 SB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3539 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  | 0 |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037353
YNE30 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3540 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3541 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 81.9754 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys |  | 1710 | 1710 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3542 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 3 |  | 3 | 0 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3542 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 2 |  | 2 | 0 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 3 |  | 3 | 0 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 5 |  | 5 | 0 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 2 |  | 2 | 0 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 3 |  | 3 | 0 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 2 |  | 2 | 0 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3543 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 4 |  | 4 | 0 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3544 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 39.18 |  | 39.18 | 0 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45139 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 3545 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Missed intervention | Missed intervention | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | WB | 1047 |  | 1047 | 0 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 3546 | Sweeping - Paved non-running areas - Full Sweep 02 | 52.6235 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 7065.25 | 7065.25 | 0 | 1 |  | N |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | 52037347
YNE30 Closure 1 NB OS Amey 45139 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 3547 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 15.7719 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 658 | 658 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually |  |  | 52037342
YNE30 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 3548 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 15.7719 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 658 | 658 | 0 | 1 |  | N |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037343
YNE30 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3549 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.5011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 344 | 344 | 0 | 1 |  | N |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 4 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3549 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 22.6099 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 1728 | 1728 | 0 | 1 |  | N |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3549 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.8693 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 525 | 525 | 0 | 1 |  | N |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3550 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3.6636 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 280 | 280 | 0 | 1 |  | N |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3549 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 29.5447 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | WB | 2258 | 2258 | 0 | 1 |  | N |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3549 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 15.3481 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | WB | 1173 | 1173 | 0 | 1 |  | N |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3550 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 12.6003 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 963 | 963 | 0 | 1 |  | N |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3550 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.6806 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 587 | 587 | 0 | 1 |  | N |  | 4700M606/21 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE30 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3550 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3.5721 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 273 | 273 | 0 | 1 |  | N |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038352
YNE31 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3551 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3552 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3553 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3554 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3555 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 9 |  | 9 | 0 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3555 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 4 |  | 4 | 0 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3555 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 2 |  | 2 | 0 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3556 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 25.16 |  | 25.16 | 0 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3556 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 72.17 |  | 72.17 | 0 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3557 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | NB | 29.61 |  | 29.61 | 0 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 02 | 3558 | Sweeping - Paved non-running areas - Full Sweep 02 | 34.893 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 4684.75 | 4684.75 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | 52037350
YNE31 Closure 1 NB OS Amey 45139 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 3559 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 14.5854 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 608.5 | 608.5 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually |  |  | 52037332
YNE31 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 3560 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 14.5854 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 608.5 | 608.5 | 0 | 1 |  | N |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037340
YNE31 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3561 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.0525 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 539 | 539 | 0 | 1 |  | N |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038788
YNE31 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3561 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.7702 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 441 | 441 | 0 | 1 |  | N |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 4 times per year (ILM Certain Sections) |  |  | 52038788
YNE31 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3562 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.3646 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 410 | 410 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 52038788
YNE88 Closure 1 SB NS Amey 45139 Electrical Testing - Network cabling and electrical components | 3563 | Electrical Testing - Network cabling and electrical components | 38.3511 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | Every 6 years | 286/3 | 282/5 | 52037276 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB OS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3564 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 14 | 14 | 0 | 1 |  | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45871660
YNE90 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3565 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 34 | 34 | 0 | 1 |  | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB OS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3566 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45871660
YNE90 Closure 1 WB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3567 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 43dys | WB | 31 | 13 | 18 | 0.41935 | 21/8: only area missed with assets in was J1 Entry nearside | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB OS Amey 45139 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3568 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 31.3758 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 406.43 | 406.43 | 0 | 1 | No v-channel in this location and no jobs rasied | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE90 Closure Amey 45139 Electrical Testing - Network cabling and electrical components | 3569 | Electrical Testing - Network cabling and electrical components | 230.1065 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 21dys |  | 12 | 12 | 0 | 1 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE90 Closure 1 WB NS Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3570 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 79.0991 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Completed | Completed | Completed | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 43dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3571 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE90 Closure 1 WB NS Amey 45139 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3572 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3573 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3574 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE90: M180 Ings - J1 | YNE90 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3575 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3576 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3577 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 0 | N/A |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3578 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 0 | N/A |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3579 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 54.9379 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1146 | 1146 | 0 | 1 | 0 | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 | 0 | N |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3581 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 | 0 | N |  | 2000M180/102 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3581 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 9 | 9 | 0 | 1 | 0 | N |  | 2000M180/103 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 | 0 | N |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3581 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 136.6257 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 57 | 57 | 0 | 1 | 0 | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3581 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 19 | 19 | 0 | 1 | 0 | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 27 | 27 | 0 | 1 | 0 | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3581 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107.8624 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 45 | 45 | 0 | 1 | 0 | N |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 | 0 | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 | 0 | N |  | 2000M180/198 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3580 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 | 0 | N |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3582 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 | 0 | N |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3583 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65.9159 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 11 | 11 | 0 | 1 | 0 | N |  | 2000M180/102 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3583 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 185.763 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 31 | 31 | 0 | 1 | 0 | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3583 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 | 0 | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3582 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3583 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3582 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3584 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3584 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3585 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 10 | 10 | 0 | 1 |  | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3585 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3584 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3585 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 | 0 | N |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3584 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 | 0 | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3586 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.25062 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 12.1 | 12.1 | 0 | 1 | 0 | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.9984 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 70 | 70 | 0 | 1 |  | N |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3588 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.1689 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 111 | 111 | 0 | 1 |  | N |  | 2000M180/102 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3588 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.7562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 657 | 657 | 0 | 1 |  | N |  | 2000M180/103 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.5849 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 651 | 651 | 0 | 1 |  | N |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3588 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.7554 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 692 | 692 | 0 | 1 |  | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3588 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4413 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 681 | 681 | 0 | 1 |  | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.7284 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 621 | 621 | 0 | 1 |  | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3588 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2146 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 603 | 603 | 0 | 1 |  | N |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.4405 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 716 | 716 | 0 | 1 |  | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.1314 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 495 | 495 | 0 | 1 |  | N |  | 2000M180/198 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3587 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.1109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 144 | 144 | 0 | 1 |  | N |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3589 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 218.4663 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2430.5 | 2430.5 | 0 | 1 |  | N |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3589 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 89.8925 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1000.08 | 1000.08 | 0 | 1 |  | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3589 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 23.4457 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 260.84 | 260.84 | 0 | 1 |  | N |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3590 | Sweeping - Paved non-running areas - Full Sweep 01 | 30.5191 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 4097.5 | 4097.5 | 0 | 1 |  | N |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0.91591 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 70 | 70 | 0 | 1 |  | N |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.4524 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 111 | 111 | 0 | 1 |  | N |  | 2000M180/102 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.5965 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 657 | 657 | 0 | 1 |  | N |  | 2000M180/103 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3593 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 40.3132 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3081 | 3081 | 0 | 1 |  | N |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.0544 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | CW | 692 | 692 | 0 | 1 |  | N |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3592 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.9105 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 681 | 681 | 0 | 1 |  | N |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3593 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.2099 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1621 | 1621 | 0 | 1 |  | N |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3594 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.8899 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 603 | 603 | 0 | 1 |  | N |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.3685 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 716 | 716 | 0 | 1 |  | N |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3591 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.4768 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 495 | 495 | 0 | 1 |  | N |  | 2000M180/198 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3593 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.2992 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 405 | 405 | 0 | 1 |  | N |  | 2000M180/199 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE91 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3595 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 2/3 | 10/5 | 45871315 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB OS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3596 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys | EB | 0 |  | 0 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE91 Closure 2 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3597 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 223.8756 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 29 | 29 | 0 | 1 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 2/3 | 10/5 | 45871315 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3598 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 79.0991 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE91: M180 J1-2 | YNE91 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE91 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3599 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 14 | 14 | 0 | 1 |  | N |  |  | YNE91: M180 J1-2 | YNE91 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE91 Closure Amey 45139 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3600 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 392.9414 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE91: M180 J1-2 | YNE91 Closure | Lane 1 Closure | 2 |  |  | Every 6 years |  |  | On ServiceNow
YNE90 Closure 1 WB NS Amey 45139 CCTV PTZ Cameras - Clean camera lens | 3601 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 43dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE91: M180 J1-2 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 CCTV PTZ Cameras - Check camera functionality | 3602 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 43dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE91: M180 J1-2 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS Amey 45139 CCTV PTZ Cameras - Check data and power supplies | 3603 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2023-12-31 |  | 43dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE91: M180 J1-2 | YNE90 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually | 2/7 | 0/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3604 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3605 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3606 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3607 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3608 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 19.3194 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys |  | 4303 | 403 | 3900 | 0.093656 |  | N |  |  | YNE91: M180 J1-2 | YNE91 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3609 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 3 |  | 3 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | No jobs raised
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 3 |  | 3 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 6 |  | 6 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 19 |  | 19 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 29 |  | 29 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3612 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 24 |  | 24 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3613 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 22 |  | 22 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3612 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 19 |  | 19 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 15 |  | 15 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3613 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 15 |  | 15 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/119 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3612 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 20 |  | 20 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3613 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 12 |  | 12 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 4 |  | 4 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 6 |  | 6 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 20 |  | 20 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 14 |  | 14 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3610 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 13 |  | 13 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/128 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45871314 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 6 |  | 6 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/130 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3611 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 19 |  | 19 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/131 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 6 |  | 6 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 2 |  | 2 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3616 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 2 |  | 2 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819244
YNE91 Closure 2 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3617 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3616 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819244
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819244
YNE91 Closure 2 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3617 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 2 |  | 2 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3614 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 | 45819207 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3615 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1 |  | 1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819244
YNE91 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3618 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 23.22 |  | 23.22 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818673
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 365 |  | 365 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 355 |  | 355 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1098 |  | 1098 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1800 |  | 1800 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3621 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1816 |  | 1816 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3622 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1445 |  | 1445 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3621 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1450 |  | 1450 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 959 |  | 959 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3622 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1268 |  | 1268 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/119 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3621 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1268 |  | 1268 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3622 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Check what was done - not fully complete | Check what was done - not fully complete | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 906 |  | 906 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 904 |  | 904 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 463 |  | 463 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1809 |  | 1809 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1809 |  | 1809 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3619 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | Intervention missed | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 466 |  | 466 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/128 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Apr - Sep) | 2/3 | 10/5 | 45872500 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 594 |  | 594 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/130 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3620 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 587 |  | 587 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/131 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872500
YNE91 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3623 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1430.29 |  | 1430.29 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3624 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1189.22 |  | 1189.22 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 2 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3625 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1287.1 |  | 1287.1 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3623 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1604.09 |  | 1604.09 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3623 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 3210.94 |  | 3210.94 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3624 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 85.01 |  | 85.01 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3623 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 3016.11 |  | 3016.11 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3623 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1354.48 |  | 1354.48 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/130 | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3626 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-30 | N/A | Removed following GC-898 | 43dys | EB | 1421 |  | 1421 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 2/3 | 10/5 | 52037260 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3627 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-30 | N/A | Removed following GC-898 | 43dys | EB | 2645 |  | 2645 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | Days | No |  | Annually (Sept, Oct) | 2/3 | 10/5 | 52037263 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3626 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-30 | N/A | Removed following GC-898 | 43dys | EB | 2234 |  | 2234 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Sept, Oct) | 2/3 | 10/5 | 52037262 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3626 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-30 | N/A | Removed following GC-898 | 43dys | EB | 1614 |  | 1614 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | Days | No |  | Annually (Sept, Oct) | 2/3 | 10/5 | 52037261 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3628 | Sweeping - Paved non-running areas - Full Sweep 01 | 529.0167 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 71026 | 71026 | 0 | 1 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 3629 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 8556 |  | 8556 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 52037223 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3630 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 365 |  | 365 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3631 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.3558 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 1785 | 1785 | 0 | 1 |  | N |  | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3630 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 2287 |  | 2287 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3630 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1800 |  | 1800 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3632 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 40.6011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 3103 | 3103 | 0 | 1 |  | N |  | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3633 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1445 |  | 1445 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3632 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.9725 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 1450 | 1450 | 0 | 1 |  | N |  | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3631 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 33.5355 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 2563 | 2563 | 0 | 1 |  | N |  | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3633 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1268 |  | 1268 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/119 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3632 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.5911 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 1268 | 1268 | 0 | 1 |  | N |  | 2000M180/120 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3633 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 906 |  | 906 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3631 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 53.8425 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 4115 | 4115 | 0 | 1 |  | N |  | 2000M180/122 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3630 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 548 |  | 548 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/123 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3630 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-08-01 | 2023-09-30 | 2023-10-31 |  | 43dys | EB | 1809 |  | 1809 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure |  | No |  | Annually | 2/3 | 10/5 | 45819703 | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3631 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 63.1325 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 4825 | 4825 | 0 | 1 |  | N |  | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3634 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.0974 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 466 | 466 | 0 | 1 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/128 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3631 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.4885 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 1948 | 1948 | 0 | 1 |  | N |  | 2000M180/130 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819703
YNE91 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3635 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 589 |  | 589 | 0 |  | Y | Works planned 31st July and cancelled due to severe weather. Unable to access OS since this time due to permanent TM now in place which clashes. NS scheduled for October. | 2000M180/131 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819703
YNE92 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3636 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 609.8679 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 46 | 79 | -33 | 1.7174 |  | N |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE92 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3636 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 787.4244 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 102 | 102 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE92 Closure 1 EB OS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3637 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 | 1/8: Not complete | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE92 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3636 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 12 | 22 | -10 | 1.8333 |  | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE92 Closure Amey 45139 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 3638 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE92 Closure Amey 45139 BC - Lamps (LED) for Road Lighting | 3639 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE92 Closure Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3640 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 105.4655 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE92 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3641 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE92 Closure 1 EB NS Amey 45139 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3642 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-30 |  | 43dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE92 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3643 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 13 | 13 | 0 | 1 |  | N |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3644 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3645 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 & 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3646 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3647 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3648 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 124.8807 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 2605 | 2605 | 0 | 1 | 1/8: Not complete | N |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 18 | 18 | 0 | 1 |  | N |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/133 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 26 | 26 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 32 | 32 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 24 | 24 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 24 | 24 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 23 | 23 | 0 | 1 |  | N |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3650 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870043
YNE92 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3649 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 19 | 19 | 0 | 1 | 1/8: Not complete | N |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3652 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 | 1/8: Not complete: 3 x comms/ tech cabininets, 1 x weather station , 1 x comms mast access/ steps cleared within area 11/5 to 16/2 | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3652 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | 1/8: Not complete: 3 x comms/ tech cabininets, 1 x weather station , 1 x comms mast access/ steps cleared within area 11/5 to 16/2 | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3652 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 | 1/8: Not complete: 3 x comms/ tech cabininets, 1 x weather station , 1 x comms mast access/ steps cleared within area 11/5 to 16/2 | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3652 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | 1/8: Not complete: 3 x comms/ tech cabininets, 1 x weather station , 1 x comms mast access/ steps cleared within area 11/5 to 16/2 | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3653 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819213
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3652 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 | 1/8: Not complete: 3 x comms/ tech cabininets, 1 x weather station , 1 x comms mast access/ steps cleared within area 11/5 to 16/2 | N |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3654 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.50331 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 24.3 | 24.3 | 0 | 1 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3654 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.35832 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 17.3 | 17.3 | 0 | 1 |  | N |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3655 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.5961 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 28.78 | 28.78 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818503
YNE92 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3655 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.33057 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 15.96 | 15.96 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818503
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.6452 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 513 | 513 | 0 | 1 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1273 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 670 | 670 | 0 | 1 | 1/9: 12/0--13/9completed | N |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.642 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 653 | 653 | 0 | 1 |  | N |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6175 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 477 | 477 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.4707 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 647 | 647 | 0 | 1 |  | N |  | 2000M180/133 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5295 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1805 | 1805 | 0 | 1 |  | N |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.8436 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1816 | 1816 | 0 | 1 |  | N |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7888 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 483 | 483 | 0 | 1 | 1/9: 12/0--13/9completed | N |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 44.3925 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1555 | 1555 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.023 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1472 | 1472 | 0 | 1 |  | N |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2146 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 603 | 603 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.0572 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1228 | 1228 | 0 | 1 |  | N |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 558 | 558 | 0 | 1 |  | N |  | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9585 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 559 | 559 | 0 | 1 | 1/8: Not complete - 40% done | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.5425 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1245 | 1245 | 0 | 1 |  | N |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.2105 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 778 | 778 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 52033134
YNE92 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3658 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.1265 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 705 | 705 | 0 | 1 |  | N |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.1518 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 846 | 846 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE92 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3659 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 188.6226 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2098.48 | 2098.48 | 0 | 1 |  | N |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 195.088 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2170.41 | 2170.41 | 0 | 1 |  | N |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3659 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 259.1772 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2883.42 | 2883.42 | 0 | 1 |  | N |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3659 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 50.8248 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 565.44 | 565.44 | 0 | 1 |  | N |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3659 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 199.5481 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2220.03 | 2220.03 | 0 | 1 |  | N |  | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 111.012 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1235.04 | 1235.04 | 0 | 1 |  | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4.079 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 45.38 | 45.38 | 0 | 1 |  | N |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 98.3534 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1094.21 | 1094.21 | 0 | 1 |  | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3659 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2.1519 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 23.94 | 23.94 | 0 | 1 |  | N |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 2 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 43.4757 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 483.68 | 483.68 | 0 | 1 | Complete | N |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3662 | Sweeping - Paved non-running areas - Full Sweep 01 | 443.5038 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 59545 | 59545 | 0 | 1 | 1/8: EB complete | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | 52038750
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 3663 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 844.7783 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 17622 | 17622 | 0 | 1 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.7123 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 513 | 513 | 0 | 1 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 36.2178 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2768 | 2768 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.5442 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 653 | 653 | 0 | 1 |  | N |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.2413 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 477 | 477 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.4656 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 647 | 647 | 0 | 1 |  | N |  | 2000M180/133 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 52.0238 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3976 | 3976 | 0 | 1 |  | N |  | 2000M180/134 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 61.497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4700 | 4700 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.7256 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1049 | 1049 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.3463 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1555 | 1555 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 48.3078 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3692 | 3692 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/140 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.0492 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1838 | 1838 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.6565 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1273 | 1273 | 0 | 1 | 1/8: Not complete - 40% done | N |  | 2000M180/142 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 558 | 558 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3664 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.6286 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1653 | 1653 | 0 | 1 |  | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3665 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.6042 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1269 | 1269 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037301
YNE92 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.1797 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 778 | 778 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE92 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5443 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1188 | 1188 | 0 | 1 |  | N |  | 2000M180/187 | YNE92: M180 J2-3 | YNE92 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | Annually
YNE92 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.0695 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 846 | 846 | 0 | 1 | 1/8: Not complete: 2m swathe cut / barrier strimmed from 11/5 to 16/2, 3.5 K left to do | N |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE93 Closure Amey 45139 BC - Lamps (LED) for Illuminated Signs and Bollards | 3669 | BC - Lamps (LED) for Illuminated Signs and Bollards | 224.7133 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 21dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | 2 |  |  | Every 2 years
YNE93 Closure 1 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3670 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 10 | 8 | 2 | 1 | 3/8: complete only 6 jobs | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 & 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE93 Closure Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3671 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 105.4655 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE93 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3672 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 41dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3673 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  | 0 |  | 0 | 0 |  | N/A |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037278
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3674 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  | 0 |  | 0 | 0 | Not complete | N/A |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037278
YNE93 Closure 1 EB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3675 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3676 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 | VC: 60% completed | N/A |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3677 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 216.6356 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 4519 | 4519 | 0 | 1 |  | N |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 28 | 8 | 20 | 0.28571 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3679 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 4 | 1 | 3 | 0.25 | 28/9: not complete. Rain canelled closure. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 24 | 6 | 18 | 0.25 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3680 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 34 | 34 | 0 | 1 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE93 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 20 | 5 | 15 | 0.25 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/151 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 3 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3681 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 16 | 7 | 9 | 0.4375 | 28/9: not complete. Rain canelled closure. 1/9: Not complete actuals based on confirm jobs. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 3 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3682 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 46 | 24 | 22 | 0.52174 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 3 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3681 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 25 | 8 | 17 | 0.32 | 28/9: not complete. Rain canelled closure. 1/9: Not complete actuals based on confirm jobs. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/155 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 3 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3682 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 21 | 7 | 14 | 0.33333 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3683 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 |  | N |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872478
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3679 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 12 | 7 | 5 | 0.58333 | 28/9: not complete. Rain canelled closure. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/160 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3683 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/161 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872478
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3679 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 15 | 12 | 3 | 0.8 | 28/9: not complete. Rain canelled closure. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3683 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872478
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3679 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 4 | 1 | 3 | 0.25 | 28/9: not complete. Rain canelled closure. 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/165 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45870874
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3683 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 | 3-4/8: Not complete - actuals based on jobs closed in Confirm. 150 of the 105 jobs left are for marker posts | N |  | 2000M180/167 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3683 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 24 | 24 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872478
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3684 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3685 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3686 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45819323
YNE93 Closure 2 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3687 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819323
YNE93 Closure 2 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3688 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 2 | -1 | 2 |  | N |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 3 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3689 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 3 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3689 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3690 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 2 | -1 | 2 |  | N |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3686 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3690 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819229
YNE93 Closure 3 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3691 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.12075 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 5.83 | 5.83 | 0 | 1 |  | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3692 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.2384 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 11.51 | 11.51 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818518
YNE93 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3693 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.4047 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1030 | 1030 | 0 | 1 |  | N |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3694 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.8752 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 451 | 451 | 0 | 1 | 28/9: complete | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3693 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1802 |  | 1802 | 0 | 3-4/8: not complete | N |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7579 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1813 | 1813 | 0 | 1 | 3-4/8: not complete | N |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872573
YNE93 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3693 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1804 |  | 1804 | 0 | 3-4/8: not complete | N |  | 2000M180/151 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 3 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1808 | 0 | 1808 | 0 | 28/9: not complete rain cancelled closure 00:30. 1/9: Not complete. 3-4/8: not complete | N |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 3 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3697 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1812 |  | 1812 | 0 | 3-4/8: not complete | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 3 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1814 | 0 | 1814 | 0 | 28/9: not complete rain cancelled closure 00:30. 1/9: Not complete. 3-4/8: not complete | N |  | 2000M180/155 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 3 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3697 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1809 |  | 1809 | 0 | 3-4/8: not complete | N |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3698 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5866 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1807 | 1807 | 0 | 1 |  | N |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3694 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.9625 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 384 | 384 | 0 | 1 | 28/9: complete | N |  | 2000M180/160 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3698 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.8801 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 241 | 241 | 0 | 1 |  | N |  | 2000M180/161 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3694 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6746 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 479 | 479 | 0 | 1 |  | N |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3698 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.1281 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 635 | 635 | 0 | 1 |  | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE93 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3694 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0735 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 528 | 528 | 0 | 1 | 28/9: complete | N |  | 2000M180/165 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3698 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4413 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 681 | 681 | 0 | 1 |  | N |  | 2000M180/167 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3698 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.9953 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1436 | 1436 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872525
YNE93 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3699 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 172.2302 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1916.11 | 1916.11 | 0 | 1 |  | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 2 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3700 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 174.1322 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1937.27 | 1937.27 | 0 | 1 |  | N |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 3 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3701 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 107.5514 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1196.54 | 1196.54 | 0 | 1 |  | N |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3699 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 35.0337 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 389.76 | 389.76 | 0 | 1 |  | N |  | 2000M180/165 | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3702 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 93.3477 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1038.52 | 1038.52 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3703 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 1.657 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-09 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 120 | 120 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) |  |  | 12013842
YNE94 Closure 1 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3704 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 1.8917 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-09 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 137 | 137 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000M180/160 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) |  |  | 12013841
YNE93 Closure 1 WB NS CGS 45139 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 3705 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | WB | 1367 | 0 | 1367 | 0 | 29/9: not completed | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037273
YNE93 Closure 2 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3706 | Sweeping - Paved non-running areas - Full Sweep 01 | 11.1089 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Complete | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | First intervention missed due to access | 43dys | EB | 6214.5 | 1491.48 | 4723.02 | 0.24 | 3-4/8: Not completed approx 24% done - centres acros 6 sections and one slip NS and OS. Not complete - C/R swept from J3 19/1 to 28/6 heavy silted in places against concrete wall, 1.5 K short of J4, J3 EB Entry swept nearside & offside , 1 sweeper load removed in total , no sweeping done nearside HS | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | 52037272
YNE93 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 3707 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 432.8878 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 9030 | 9030 | 0 | 1 | nearside HS verge just large debris removed | N |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually
YNE93 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3708 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.477 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1030 | 1030 | 0 | 1 |  | N |  | 2000M180/146 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3709 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 30.9709 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 2367 | 2367 | 0 | 1 |  | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | Days |  | Days | Annually |  |  | 45819747
YNE93 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3708 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5782 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1802 | 1802 | 0 | 1 |  | N |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3710 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 49.0798 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3751 | 3751 | 0 | 1 | Centres only | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819747
YNE93 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3708 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6044 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1804 | 1804 | 0 | 1 |  | N |  | 2000M180/151 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 3 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3711 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 39.3188 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 3005 | 3005 | 0 | 1 |  | N |  | 2000M180/152 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 3 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3712 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.709 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1812 | 1812 | 0 | 1 |  | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 3 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3711 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.7352 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | WB | 1814 | 1814 | 0 | 1 |  | N |  | 2000M180/155 | YNE93: M180 J3-4 | YNE93 Closure 3 WB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 3 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3712 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6698 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1809 | 1809 | 0 | 1 |  | N |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3713 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6436 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1807 | 1807 | 0 | 1 |  | N |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819747
YNE93 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3709 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.0244 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 384 | 384 | 0 | 1 |  | N |  | 2000M180/160 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3713 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.1534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 241 | 241 | 0 | 1 |  | N |  | 2000M180/161 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819747
YNE93 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 479 |  | 479 | 0 | 28/9: not complete. Rain canelled closure. 1/9: Not complete | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE93 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.3086 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 635 | 635 | 0 | 1 |  | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819747
YNE93 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3709 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.0115 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 918 | 918 | 0 | 1 |  | N |  | 2000M180/165 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819747
YNE93 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3713 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.9105 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 681 | 681 | 0 | 1 |  | N |  | 2000M180/167 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819747
YNE93 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3713 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.3709 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2474 | 2474 | 0 | 1 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819747
YNE94 Closure 2 WB OS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3716 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 10 | 10 | 0 | 1 | 8/8: Marked as complete on night report quants from confirm jobs | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE94 Closure 2 WB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3717 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 964.9808 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 127 | 125 | 2 | 1 | 8/8: Marked as complete on night report quants from confirm jobs | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE94 Closure 3 EB NS Enviroflow 45139 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3718 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 277.9145 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 34 | 36 | -2 | 1.0588 |  | N |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE94 Closure Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3719 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 237.2973 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 9 | 9 | 0 | 1 |  | N |  |  | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE94 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3720 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 18 | 18 | 0 | 1 |  | N |  |  | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE94 Closure 3 EB NS Amey 45139 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 3721 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 31.9592 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | Days |  | Days | 2 times per year |  |  | 45777054 and 45777817
YNE94 Closure 2 EB NS Amey 45139 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3722 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 785.8827 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Every 6 years |  |  | 45777596, 45779898, 45791537
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3723 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3724 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 | Complete job open with no evidence - can we get some 52037177 | N/A |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3725 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 0 | N/A |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3726 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | No assets | 43dys |  | 0 |  | 0 | 0 | 0 | N/A |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037177
YNE94 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3727 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 229.0997 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 4779 | 4779 | 0 | 1 | 8/8: Complete job open with no evidence - can we get some 52037177 | N |  |  | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3728 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 8 | 7 | 1 | 0.875 | 7-8/8: not complete | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3729 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3728 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 9 | 1 | 8 | 0.11111 | 7-8/8: not complete | N |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3728 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 8 | 1 | 7 | 0.125 | 7-8/8: not complete | N |  | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3729 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3729 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3730 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 26 | 26 | 0 | 1 | 7-8/8: not complete | N |  | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 34 | 34 | 0 | 1 |  | N |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 20 | 20 | 0 | 1 | 7-8/8: not complete | N |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 2 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure 2 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 28 | 28 | 0 | 1 | 7-8/8: not complete | N |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 3 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3733 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 23 | 23 | 0 | 1 | 7-8/8: not complete | N |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure 3 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3734 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 29 | 2 | 27 | 0.068966 | 18/10 cancelled high winds. 7-8/8: not complete | N |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE94 Closure 3 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3733 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 26 | 26 | 0 | 1 | 7-8/8: not complete | N |  | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure 3 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3734 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 27 | 7 | 20 | 0.25926 | 18/10 cancelled high winds. 7-8/8: not complete | N |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872381
YNE94 Closure 4 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3735 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3728 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 14 | 12 | 2 | 0.85714 | 7-8/8: not complete | N |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3729 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45873115
YNE94 Closure 4 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2000M180/192 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 WB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3735 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 EB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/196 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3737 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 | Complete | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3738 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 | Complete | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3737 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 359.5413 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 60 | 60 | 0 | 1 | Complete | N |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3737 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 EB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3739 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/196 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 WB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3740 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/197 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3741 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 6 | 1 | 5 | 0.16667 |  | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3742 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 2 | -1 | 2 |  | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3741 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 3 | 1 | 2 | 0.33333 |  | N |  | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3743 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1 | 0 | 1 | 0 |  | N |  | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3744 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819330
YNE94 Closure 2 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3745 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3745 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 3 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3746 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 3 | 1 | 2 | 0.33333 | 18/10 cancelled high winds. 7-8/8: not complete | N |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819272
YNE94 Closure 3 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3746 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 5 | 0 | 5 | 0 | 18/10 cancelled high winds. 7-8/8: not complete | N |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819272
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3741 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3742 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3747 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3748 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.16466 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 31.44 | 7.95 | 23.49 | 0.25286 | 7-8/8: not complete | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3749 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.4159 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 20.08 | 20.08 | 0 | 1 |  | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3748 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.0886 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 197.4 | 197.4 | 0 | 1 |  | N |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3749 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.85314 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 41.19 | 41.19 | 0 | 1 |  | N |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818644
YNE94 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3750 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.9332 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 418 | 418 | 0 | 1 |  | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3751 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.1615 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 426 | 426 | 0 | 1 |  | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3750 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2464 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 464 | 464 | 0 | 1 |  | N |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3750 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.5041 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 438 | 438 | 0 | 1 |  | N |  | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3751 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3891 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 469 | 469 | 0 | 1 |  | N |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3751 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.5041 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 438 | 438 | 0 | 1 |  | N |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872652
YNE94 Closure CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3752 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5295 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1805 | 1805 | 0 | 1 | 7-8/8: Not complete | N |  | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3753 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.815 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1815 | 1815 | 0 | 1 |  | N |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872652
YNE94 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3754 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1814 | 1814 | 0 | 1 | 7-8/8: Not complete | N |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 2 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3753 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7579 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1813 | 1813 | 0 | 1 |  | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872652
YNE94 Closure 2 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3754 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.501 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1804 | 1804 | 0 | 1 | 7-8/8: Not complete | N |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 3 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.6723 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1810 | 1810 | 0 | 1 | 7-8/8: Not complete | N |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872652
YNE94 Closure 3 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-09-29 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | EB | 1810 | 0 | 1810 | 0 | 18/10 cancelled high winds. 7-8/8: not complete | N |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45874204
YNE94 Closure 3 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.501 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1804 | 1804 | 0 | 1 | 7-8/8: Not complete | N |  | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) |  |  | 45872652
YNE94 Closure 3 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3756 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.545 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1140 | 1140 | 0 | 1 |  | N |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3757 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.691 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1005 | 1005 | 0 | 1 |  | N |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3750 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.9617 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 419 | 419 | 0 | 1 |  | N |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 1 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3751 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.987 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 560 | 560 | 0 | 1 |  | N |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3758 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7888 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 483 | 483 | 0 | 1 |  | N |  | 2000M180/192 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3757 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.3573 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 608 | 608 | 0 | 1 |  | N |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 EB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3758 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.341 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 82 | 82 | 0 | 1 |  | N |  | 2000M180/196 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 4 WB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3757 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.341 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 82 | 82 | 0 | 1 |  | N |  | 2000M180/197 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE94 Closure 2 EB NS CGS 45139 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3759 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 24.3439 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-09 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1763 | 1763 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) |  |  | 12013840
YNE94 Closure 1 EB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3760 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 10.9085 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 121.36 | 121.36 | 0 | 1 |  | N |  | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3761 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 182.2156 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2027.2 | 2027.2 | 0 | 1 |  | N |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3761 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 178.39 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1984.64 | 1984.64 | 0 | 1 |  | N |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3762 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 616.1748 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 6855.12 | 6855.12 | 0 | 1 |  | N |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3762 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 339.3037 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3774.85 | 3774.85 | 0 | 1 |  | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 3 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3763 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 273.077 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3038.06 | 3038.06 | 0 | 1 |  | N |  | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 3 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3763 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 168.4757 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1874.34 | 1874.34 | 0 | 1 |  | N |  | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3764 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 205.9435 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2291.18 | 2291.18 | 0 | 1 |  | N |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3764 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 70.0512 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 779.34 | 779.34 | 0 | 1 |  | N |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3764 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 164.625 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1831.5 | 1831.5 | 0 | 1 |  | N |  | 2000M180/197 | YNE94: M180 J4-5 | YNE94 Closure 4 WB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3765 | Sweeping - Paved non-running areas - Full Sweep 01 | 36.844 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 4946.6875 | 4946.6875 | 0 | 1 | 7/8: 13 out of 44 sections completed - full slips and centres on mainline approx 29.5%. 8/8: sweeper off road | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | 52037164
YNE94 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 3766 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 708.68 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 14783 | 14783 | 0 | 1 |  | N |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually
YNE94 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3767 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.4693 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 418 | 418 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819769
YNE94 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3768 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.574 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 426 | 426 | 0 | 1 |  | N |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE94 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3769 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.6544 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 585 | 585 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/169 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819769
YNE94 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3769 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.731 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 438 | 438 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819769
YNE94 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3770 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.6588 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2496 | 2496 | 0 | 1 |  | N |  | 2000M180/171 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037172
YNE94 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3770 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 31.7036 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 2423 | 2423 | 0 | 1 |  | N |  | 2000M180/172 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037172
YNE94 Closure Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3771 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6174 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1805 | 1805 | 0 | 1 |  | N |  | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3772 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 113.4423 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 8670 | 8670 | 0 | 1 |  | N |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037172
YNE94 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3773 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.7352 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1814 | 1814 | 0 | 1 |  | N |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 2 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3772 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 73.1029 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 5587 | 5587 | 0 | 1 |  | N |  | 2000M180/177 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 52037172
YNE94 Closure 2 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3773 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6044 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 1804 | 1804 | 0 | 1 |  | N |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 3 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3774 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 63.4335 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 4848 | 4848 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/180 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819763
YNE94 Closure 3 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3775 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6829 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1810 | 1810 | 0 | 1 |  | N |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 52037173
YNE94 Closure 3 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3774 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 48.1246 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3678 | 3678 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/183 | YNE94: M180 J4-5 | YNE94 Closure 3 WB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | 45819763
YNE94 Closure 3 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3775 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9163 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-30 | 2023-08-01 | 2023-09-29 | 2023-11-30 |  | 43dys | EB | 1140 | 1140 | 0 | 1 |  | N |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 52037173
YNE94 Closure 4 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3776 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 43.1264 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 3296 | 3296 | 0 | 1 |  | N |  | 2000M180/186 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 1 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3767 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.4824 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 419 | 419 | 0 | 1 |  | Y | TM Cancellations due to strong winds as per severe weather alert (Storm Edna) | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819769
YNE94 Closure 1 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3768 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3273 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 560 | 560 | 0 | 1 |  | N |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE94 Closure 4 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3777 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.3198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 483 | 483 | 0 | 1 |  | N |  | 2000M180/192 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 4 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3776 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.1481 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1387 | 1387 | 0 | 1 |  | N |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 4 EB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3777 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.0729 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | EB | 82 | 82 | 0 | 1 |  | N |  | 2000M180/196 | YNE94: M180 J4-5 | YNE94 Closure 4 EB NS | Lane 1 Closure | 2 | No |  | Annually
YNE94 Closure 4 WB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3776 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.0306 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys | WB | 1913 | 1913 | 0 | 1 |  | N |  | 2000M180/197 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 2 | No |  | Annually
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 33.3137 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 194.19 | 194.19 | 0 | 1 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB OS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 40.3765 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 235.36 | 235.36 | 0 | 1 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869857
YNE95 Closure 1 SB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3780 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 394.5699 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 4222.68 | 2300 | 1922.68 | 0.54468 |  | N |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 SB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3780 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 SB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3780 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 60.8513 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 354.71 | 354.71 | 0 | 1 |  | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB OS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 50.776 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 295.98 | 295.98 | 0 | 1 |  | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869857
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 18.9685 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 110.57 | 110.57 | 0 | 1 |  | N |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB OS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 18.7935 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 109.55 | 109.55 | 0 | 1 |  | N |  | 2000M181/133 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869857
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 30.5672 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 178.18 | 178.18 | 0 | 1 |  | N |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB OS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 30.5672 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 178.18 | 178.18 | 0 | 1 |  | N |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869857
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 210.8427 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 1229.03 | 1229.03 | 0 | 1 |  | N |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 SB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3780 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 77.7183 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 453.03 | 453.03 | 0 | 1 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB OS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 17.2376 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 100.48 | 100.48 | 0 | 1 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869857
YNE95 Closure 1 NB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3778 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 161.9315 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-28 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 943.92 | 943.92 | 0 | 1 |  | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 SB NS Bettamix 45139 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3780 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869887
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 1157.977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | NB | 233 | 150 | 83 | 0.64378 |  | N |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A |  | 22dys | SB | 286 |  | 286 | 0 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3783 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 2 | 2 | 0 | 1 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3783 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 1 | 1 | 0 | 1 |  | N |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | Days |  | Days | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3784 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 2 | 2 | 0 | 1 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45869035
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3783 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1 | 1 | 0 | 1 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3784 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1 | 1 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45869035
YNE95 Closure 1 NB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3781 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 |  | 0 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Gullies - Emptying / clear covers | 3783 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 2 | 2 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45869035
YNE95 Closure 1 SB NS Enviroflow 45139 Gullies - Emptying / clear covers | 3782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 |  | 0 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE95 Closure 1 NB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3785 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | NB | 51 |  | 51 | 0 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 SB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3786 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | SB | 396 |  | 396 | 0 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 NB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3785 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | NB | 68 |  | 68 | 0 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 SB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3786 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | SB | 1869 |  | 1869 | 0 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 NB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3785 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | NB | 786 |  | 786 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 SB OS CGS 45139 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3786 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Unable to complete within ADAMr timescales due to access | 22dys | SB | 537 |  | 537 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years (May - Sept) |  |  | 45868583
YNE95 Closure 1 NB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3787 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 NB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3788 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 3 | 3 | 0 | 1 | 0 on off side |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 SB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3789 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3790 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1 | 1 | 0 | 1 | 0 on off side |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 SB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3789 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3790 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 6 | 6 | 0 | 1 | 0 on off side |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 SB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3789 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3790 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 5 | 5 | 0 | 1 | 0 on off side |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 NB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3787 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 NB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3788 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 4 | 4 | 0 | 1 | 0 on off side |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 SB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3790 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 257.3282 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 12 | 12 | 0 | 1 | 0 on off side |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 NB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3788 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1 | 1 | 0 | 1 | 0 on off side |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 NB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3787 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 NB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3788 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 3 | 3 | 0 | 1 | 0 on off side |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure 1 SB NS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3789 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB | 0 | 0 | 0 | 0 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE95 Closure 1 SB OS Enviroflow 45139 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 3790 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 257.3282 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 12 | 12 | 0 | 1 | 0 on off side |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years |  |  | 45868321
YNE95 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3791 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys |  | 5 | 5 | 0 | 1 |  |  |  |  | YNE95: M181 | YNE95 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE95 Closure 1 NB NS Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3792 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 26.3664 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys |  | 1 | 1 | 0 | 1 | No assets | N |  |  | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | ILM Annual Network Wide |  |  | On ServiceNow
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3793 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3794 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3795 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037212
YNE95 Closure 1 SB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3796 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys |  | 0 |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037212
YNE95 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3797 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 94.3436 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys |  | 1968 | 1968 | 0 | 1 |  |  |  |  | YNE95: M181 | YNE95 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 2 | 2 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3799 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 20 | 20 | 0 | 1 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3799 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 18 | 18 | 0 | 1 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3799 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 12 | 12 | 0 | 1 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 8 | 8 | 0 | 1 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 2 | 2 | 0 | 1 |  |  |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 5 | 5 | 0 | 1 |  |  |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 21 | 21 | 0 | 1 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3799 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 22 | 22 | 0 | 1 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 15 | 15 | 0 | 1 |  |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3798 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 31 | 31 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3799 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 22 | 22 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3800 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 77.9006 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 13 | 13 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 3801 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 3 | 3 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3802 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1 | 1 | 0 | 1 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3802 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 8 | 8 | 0 | 1 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3802 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1 | 1 | 0 | 1 |  |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3802 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 7 | 7 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3803 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.51097 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 24.67 | 24.67 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3804 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.35294 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 17.04 | 17.04 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.5628 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 370 | 370 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3806 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.8761 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 416 | 416 | 0 | 1 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3806 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.7252 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 761 | 761 | 0 | 1 |  |  |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3806 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7904 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 413 | 413 | 0 | 1 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.7325 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 446 | 446 | 0 | 1 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.8548 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 100 | 100 | 0 | 1 |  |  |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.8548 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 100 | 100 | 0 | 1 |  |  |  | 2000M181/133 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.1077 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 284 | 284 | 0 | 1 |  |  |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.97 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1295 | 1295 | 0 | 1 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3806 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.5605 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1701 | 1701 | 0 | 1 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9894 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 455 | 455 | 0 | 1 |  |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3805 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.828 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1255 | 1255 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 SB NS CGS 45139 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3806 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.0279 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1262 | 1262 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Apr - Sep)
YNE95 Closure 1 NB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3807 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 26.8443 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 298.65 | 298.65 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 SB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3808 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 87.8 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 976.8 | 976.8 | 0 | 1 |  |  |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 SB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3808 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 130.0937 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1447.33 | 1447.33 | 0 | 1 |  |  |  | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 SB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3808 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 93.5634 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 1040.92 | 1040.92 | 0 | 1 |  |  |  | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 NB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3807 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 221.3507 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 2462.59 | 2462.59 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 SB OS CGS 45139 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 3808 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 71.8471 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | SB | 799.32 | 799.32 | 0 | 1 |  |  |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45868304
YNE95 Closure 1 NB NS Amey 45139 Sweeping - Paved non-running areas - Full Sweep 01 | 3809 | Sweeping - Paved non-running areas - Full Sweep 01 | 242.2159 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 32520 | 32520 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 3810 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 511.6513 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 10673 | 10673 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 |  | Days | Annually
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.7535 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 669 | 669 | 0 | 1 |  |  |  | 2000M181/110 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3812 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.2266 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 1393 | 1393 | 0 | 1 |  | N |  | 2000M181/115 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819793
YNE95 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3813 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.9573 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-01 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 761 | 761 | 0 | 1 |  | N |  | 2000M181/120 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | 2 times per year (ILM Certain Sections) |  |  | 45819793
YNE95 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3812 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.3371 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 1860 | 1860 | 0 | 1 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M181/125 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819793
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.8357 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 446 | 446 | 0 | 1 |  |  |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3814 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1.3084 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 100 | 100 | 0 | 1 |  |  |  | 2000M181/132 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections)
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.3084 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 100 | 100 | 0 | 1 |  |  |  | 2000M181/133 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.716 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 284 | 284 | 0 | 1 |  |  |  | 2000M181/134 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.9444 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 1295 | 1295 | 0 | 1 |  |  |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3812 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 35.8776 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 2742 | 2742 | 0 | 1 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M181/140 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819793
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3814 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.9534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 455 | 455 | 0 | 1 |  |  |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections)
YNE95 Closure 1 NB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3811 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 48.6349 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | NB | 3717 | 3717 | 0 | 1 |  |  |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | Annually
YNE95 Closure 1 SB NS Amey 45139 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3812 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 26.9671 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-08 | 2023-08-01 | 2023-08-31 | 2023-11-30 |  | 22dys | SB | 2061 | 2061 | 0 | 1 |  | Y | Partially complete due to severe weather. Catch-up works cancelled due to unsafe conditions snow/fog. Works planned w/c 4th December | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually |  |  | 45819793
YNE96 Closure Vaisala 45139 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3815 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE96 Closure 1 EB NS Amey 45139 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3816 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 79.0991 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 4 | 3 | 1 | 0.75 |  | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | Annually |  |  | On ServiceNow
YNE96 Closure Amey 45139 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 3817 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 2 | No |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE96 Closure Amey 45139 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3818 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-08-01 | 2023-09-29 | Complete |  | 43dys |  | 10 | 10 | 0 | 1 |  | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 2 | No |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE100 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3819 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 51 | 51 | 0 | 1 |  |  |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3820 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 1085 | 1085 | 0 | 1 |  |  |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3819 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 654 | 654 | 0 | 1 |  |  |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 6653.51 | 6653.51 | 0 | 1 |  |  |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 351.65 | 351.65 | 0 | 1 |  |  |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 233.14 | 233.14 | 0 | 1 |  |  |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 389.64 | 389.64 | 0 | 1 |  |  |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | EB | 2302.85 | 2302.85 | 0 | 1 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure 1 CW NS CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3822 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | CW | 1819 | 1819 | 0 | 1 |  |  |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 9183.24 | 9183.24 | 0 | 1 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 3359.14 | 3359.14 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 869.31 | 869.31 | 0 | 1 |  |  |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 119.67 | 119.67 | 0 | 1 |  |  |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45139 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 3821 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 4 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-08-01 | 2023-08-31 | Complete |  | 22dys | WB | 1790.7 | 1790.7 | 0 | 1 |  |  |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 4 |  |  | 6 times per year (Mar - Oct)
YNE103 Closure 1 NB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3823 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 NB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3824 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | NB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3825 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB OS CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3826 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | No assets | 22dys | SB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3827 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 523 |  | 523 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | SB | 3 |  | 3 | 0 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | CW | 598.47 |  | 598.47 | 0 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | SB | 423.62 |  | 423.62 | 0 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | SB | 256.85 |  | 256.85 | 0 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | SB | 807.18 |  | 807.18 | 0 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | CW | 368.98 |  | 368.98 | 0 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | Days |  | Days | ILM 2 times per year (Apr - Sept)
YNE114 Closure 1 CW NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3831 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | CW | 11 |  | 11 | 0 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept)
YNE114 Closure 1 CW NS CGS 45139 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3832 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | CW | 1210.26 |  | 1210.26 | 0 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept)
YNE114 Closure CGS 45139 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3833 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-08-01 | 2023-08-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 1041 |  | 1041 | 0 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
N/A Amey 45139 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3834 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2017.0269 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 91 | 51 | 40 | 0.56044 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
N/A Amey 45139 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3835 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 9 |  | 9 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Every 6 years |  |  | On ServiceNow
N/A Amey 45139 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 3836 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 17 |  | 17 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | ILM Annual Network Wide |  |  | On ServiceNow
N/A Amey 45139 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 3837 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 17 |  | 17 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | ILM Annual Network Wide |  |  | On ServiceNow
N/A Amey 45139 CCTV Masts - Check mast breaking system | 3838 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 15 |  | 15 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | ILM Annual Network Wide |  |  | On ServiceNow
N/A Amey 45139 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 3839 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 6 |  | 6 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | 2 times per year |  |  | On ServiceNow
N/A Amey 45139 CCTV PTZ Cameras - Clean camera lens | 3840 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 16 |  | 16 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
N/A Amey 45139 CCTV PTZ Cameras - Check camera functionality | 3841 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 16 |  | 16 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
N/A Amey 45139 CCTV PTZ Cameras - Check data and power supplies | 3842 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-08-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 16 |  | 16 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
YNE1 Closure 2 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3843 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 223.0859 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-28 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | EB | 16156 | 16156 | 0 | 1 | 28/11 complete - this plot is also out of spec and would need plotting better on the mapping due to being on a rock face | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013865
YNE10 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3844 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 185.7853 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 4484.89 | 4484.89 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) |  |  | 45855164
YNE10 Closure 1 WB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 3845 | Sweeping - Paved non-running areas - Full Sweep 02 | 70.3968 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-11-22 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 4 |  |  | 2 times per year
YNE10 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3846 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.7872 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 748 | 748 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3847 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.2469 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3846 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.5272 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 346 | 346 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3847 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 62.5568 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 4781 | 4781 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3847 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 17.8995 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1368 | 1368 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3846 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 13.1891 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1008 | 1008 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3846 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.4114 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 490 | 490 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE10 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3847 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.4451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 569 | 569 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037834
YNE11 Closure 2 WB NS CGS 45170 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 3848 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2024-02-29 | N/A | Removed following GC-898 | 127dys | WB | 2827 |  | 2827 | 0 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE11 Closure 1 WB NS CGS 45170 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 3849 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2024-02-29 | N/A | Removed following GC-898 | 127dys | WB | 4003 |  | 4003 | 0 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE11 Closure 1 EB NS CGS 45170 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 3850 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2024-02-29 | N/A | Removed following GC-898 | 127dys | EB | 598 |  | 598 | 0 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE11 Closure 1 EB NS CGS 45170 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 3850 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2024-02-29 | N/A | Removed following GC-898 | 127dys | EB | 1637 |  | 1637 | 0 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE11 Closure 2 EB NS CGS 45170 Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 3851 | Shrubs (General) - Maintain habitat integrity, including removal of scrub encroachment | 0 | 4.8.13 | A40089 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2024-02-29 | N/A | Removed following GC-898 | 127dys | EB | 1817 |  | 1817 | 0 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 4 |  | Days | Every 3 years (Sept - Feb)
YNE11 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3852 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 168.6489 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys |  | 3518 | 3518 | 0 | 1 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3853 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3854 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037835
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3855 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3856 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  | N |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037835
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3858 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 13 | 13 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3858 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 0 | 0 | 0 | 0 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3859 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 1 | 1 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3858 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 0 | 0 | 0 | 0 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3858 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 0 | 0 | 0 | 0 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3858 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 0 | 0 | 0 | 0 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 6 | 6 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3860 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3860 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3857 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/596 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925766
YNE11 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3861 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.1035 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 246.4 | 246.4 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925792
YNE11 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3861 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.24192 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 11.68 | 11.68 | 0 | 1 |  | N |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925792
YNE11 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3862 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.14478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 6.99 | 6.99 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925792
YNE11 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3862 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.2945 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 110.78 | 110.78 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925792
YNE11 Closure 2 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3863 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 91.3967 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-25 | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 43dys | WB | 6619 | 6619 | 0 | 1 |  | N |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 3 | No | Nights | Annually (Sept, Oct) |  |  | 12013861
YNE11 Closure 2 WB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3864 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 43dys | EB | 13078 |  | 13078 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 3 | No | Nights | Annually (Sept, Oct) |  |  | 12013862
YNE11 Closure 1 EB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 3865 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | EB | 11286.25 |  | 11286.25 | 0 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | 2 times per year |  |  | 52037416
YNE11 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3866 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.5759 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 579 | 579 | 0 | 1 |  | N |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 3 | Yes - slips only | Days | 2 times per year (ILM Certain Sections) |  |  | 52037422
YNE11 Closure 1 WB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3866 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.0208 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 613 | 613 | 0 | 1 |  | N |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 3 | Yes - slips only | Days | 3 times per year (ILM Certain Sections) |  |  | 52037422
YNE11 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3867 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.0489 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 768 | 768 | 0 | 1 |  | N |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 3 | Yes - slips only | Days | 3 times per year (ILM Certain Sections) |  |  | 52037422
YNE11 Closure 1 EB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3867 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.6001 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 428 | 428 | 0 | 1 |  | N |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 3 | Yes - slips only | Days | 2 times per year (ILM Certain Sections) |  |  | 52037422
YNE12 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3868 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 291.3723 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys |  | 6078 | 6078 | 0 | 1 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3869 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3870 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3871 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3872 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3873 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3873 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3874 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 2 | 2 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3873 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3875 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 1 | 1 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3876 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 3 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3877 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 13 | 13 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 3 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3877 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3873 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 11 | 11 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3874 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 2 | 2 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3873 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 92.6889 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 21 | 21 | 0 | 1 |  | N |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45886463
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3878 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0205 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 49.27 | 49.27 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925787
YNE12 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3879 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.48881 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 23.6 | 23.6 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925787
YNE12 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3878 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.41508 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 20.04 | 20.04 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925787
YNE12 Closure 3 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3880 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.54246 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-01 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 26.19 | 26.19 | 0 | 1 |  | Y | Works ongoing for completion this week - several shifts lost due to severe weather | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45925787
YNE12 Closure 2 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3881 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 24.8452 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-08 | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 43dys | EB | 1799.3018 | 1799.3018 | 0 | 1 |  | N | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013859
YNE13 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3882 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.4655 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys |  | 2200 | 2200 | 0 | 1 |  | N |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3883 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3884 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3885 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3886 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3887 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832221
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3887 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 17 | 17 | 0 | 1 |  | N |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832221
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3887 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832221
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3887 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832221
YNE13 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3888 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832221
YNE13 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3889 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.5306 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 73.9 | 73.9 | 0 | 1 |  | N |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45833923
YNE13 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3890 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.57539 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 27.78 | 27.78 | 0 | 1 |  | N |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45833923
YNE14 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3891 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.5134 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys |  | 2201 | 2201 | 0 | 1 |  | N |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3892 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3893 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3894 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3895 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3896 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832328
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3896 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 |  | 1 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832328
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3896 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832328
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3896 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 |  | 2 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832328
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3896 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 7 |  | 7 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832328
YNE14 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3897 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 94.3 |  | 94.3 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835379
YNE14 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3898 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed - ouse bridge | Intervention missed - ouse bridge | 2023-10-25 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 181.72 |  | 181.72 | 0 |  | Y | Unable to access due to Ouse Bridge | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835379
YNE15 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 3899 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  | N |  | 2 | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | Days | No |  | 2 times per year |  |  | On ServiceNow
YNE15 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3900 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 285.5717 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys |  | 5957 | 5957 | 0 | 1 |  | N |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3901 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3902 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  | N |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3903 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3904 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  | N |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3905 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45818946
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3905 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45818946
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3905 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45818946
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3906 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818946 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3907 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.11102 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 5.36 | 5.36 | 0 | 1 |  | N |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45818489
YNE15 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3907 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.3865 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 115.22 | 115.22 | 0 | 1 |  | N |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45818489
YNE15 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3908 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 136.74 |  | 136.74 | 0 |  | N |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 172/6 | 168/2 | 45818679 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3909 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1707 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | EB | 56.52 | 56.52 | 0 | 1 |  | N |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 | 45818679 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3908 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Intervention missed | Intervention missed | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 43dys | WB | 56.94 |  | 56.94 | 0 |  | N |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | Days | No | Days | ILM 2 times per year (Apr - Sept) | 172/6 | 168/2 | 45818679 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 1 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3910 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 17.0808 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-26 | 2023-09-01 | 2023-10-31 | 2023-10-31 |  | 41dys | EB | 1237 | 1237 | 0 | 1 |  | N |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013856
YNE15 Closure 3 WB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3911 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 45.4567 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-28 | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 41dys | WB | 3292 | 3292 | 0 | 1 |  | N |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | Days | No | Nights | Annually (Sept, Oct) |  |  | 12013857
YNE15 Closure 2 WB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3912 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 69.6487 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-28 | 2023-09-01 | 2023-10-31 | 2023-11-30 |  | 41dys | WB | 5044 | 5044 | 0 | 1 |  | N |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | Days | No | Nights | Annually (Sept, Oct) | 172/6 | 168/2 | 12013858 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE16 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3913 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2814 |  | 2814 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3914 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure | Lane 1 Closure | 3 |  |  | Every 3 years
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3915 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3916 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3917 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037568
YNE16 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3918 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037568
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3919 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3920 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3919 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/407 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3920 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3920 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/412 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3920 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3920 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3921 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 165.97 |  | 165.97 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/401 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3921 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 141.67 |  | 141.67 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/404 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3922 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 26.98 |  | 26.98 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/405 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3922 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1156.05 |  | 1156.05 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3922 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 559.69 |  | 559.69 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/417 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3922 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 220.65 |  | 220.65 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3922 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 238.77 |  | 238.77 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3923 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 447.42 |  | 447.42 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/903 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 250.2 |  | 250.2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3921 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 195.33 |  | 195.33 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/907 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3921 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 302.65 |  | 302.65 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/908 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE16 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3925 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1372.37 |  | 1372.37 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3926 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 232.61 |  | 232.61 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3926 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1514.95 |  | 1514.95 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3925 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 876.87 |  | 876.87 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3925 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1068.05 |  | 1068.05 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3926 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 634.13 |  | 634.13 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3927 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2812 |  | 2812 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE17: A63 South Cave - Welton | YNE17 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3928 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3929 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3930 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037540
YNE17 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3931 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037540
YNE17 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3932 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/410 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3933 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3932 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/420 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3934 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/430 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3935 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/433 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3936 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 33.84 |  | 33.84 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3937 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 157.04 |  | 157.04 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3938 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 176.08 |  | 176.08 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE17 Closure 2 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3939 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2955.53 |  | 2955.53 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3939 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 515.12 |  | 515.12 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3939 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 731.03 |  | 731.03 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3940 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1455 |  | 1455 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE18: A63 Welton - Melton | YNE18 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3941 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3942 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036853
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3943 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3944 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036853
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3945 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3932 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3945 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3946 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3947 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 608.61 |  | 608.61 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3948 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 437.6 |  | 437.6 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3948 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 167.37 |  | 167.37 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/431 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE17 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3949 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2281.69 |  | 2281.69 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3947 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 932.81 |  | 932.81 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/607 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3948 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2330.38 |  | 2330.38 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3948 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 778.58 |  | 778.58 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3950 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 613.37 |  | 613.37 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3951 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1858.52 |  | 1858.52 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3952 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7375.37 |  | 7375.37 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3951 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 10480.38 |  | 10480.38 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3951 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 229.77 |  | 229.77 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE19 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3953 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1633 |  | 1633 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure Amey 45170 BC - Lamps (LED) for Illuminated Signs and Bollards | 3954 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure | Lane 1 Closure | 3 |  |  | Every 2 years
YNE19 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3955 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3956 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3957 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3958 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3959 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/432 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3945 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3946 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/441 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3959 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/446 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3945 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/605 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3960 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3946 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/620 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3959 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/628 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3947 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 220.39 |  | 220.39 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE19 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3961 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 428.67 |  | 428.67 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/609 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE18 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3950 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 304 |  | 304 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3962 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 73.0456 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 5290 | 5290 | 0 | 1 |  | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE19 Closure 1 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 3963 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 450 |  | 450 | 0 |  | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000A63/444 | YNE19: A63 Melton - WesternInt | YNE19 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | Annually (Sept, Oct)
YNE20 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3964 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2057 |  | 2057 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3965 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3966 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038171
YNE20 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3967 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038171
YNE20 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3968 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3969 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3970 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/447 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3969 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/448 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3969 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/451 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3970 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 |  | 5 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3969 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3970 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3971 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 80.24 |  | 80.24 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/443 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3971 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 52.49 |  | 52.49 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/453 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept) | 191/1 | 195/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consents from Alan Hosty for his Jct 37 to western works & Consent from Karl Hinds Major projects LA consents for diversion
YNE20 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3972 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 299.59 |  | 299.59 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/454 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE20 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3973 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 960.67 |  | 960.67 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3974 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 3 |  |  | Every 3 years
YNE23 Closure Amey 45170 BC - Lamps (LED) for Illuminated Signs and Bollards | 3975 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 3 |  |  | Every 2 years
YNE23 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3976 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE23 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3977 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3978 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3979 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3980 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3981 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3982 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 638 |  | 638 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE23: A63 Daltry St - Mytongate | YNE23 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3983 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3983 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/302 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3983 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3983 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3984 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3985 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5269.96 |  | 5269.96 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/301 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3985 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1408.52 |  | 1408.52 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3986 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1394.61 |  | 1394.61 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3986 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1640.23 |  | 1640.23 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/307 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3985 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 917.21 |  | 917.21 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3986 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 265.81 |  | 265.81 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE23 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3987 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3211.09 |  | 3211.09 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3988 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1579.72 |  | 1579.72 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3987 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2029.91 |  | 2029.91 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3988 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1091.46 |  | 1091.46 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 3988 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 566.02 |  | 566.02 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure Amey 45170 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 3989 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE24 Closure Amey 45170 BC - Lamps (LED) for Road Lighting | 3990 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE24 Closure Amey 45170 BC - Lamps (LED) for Illuminated Signs and Bollards | 3991 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | Every 2 years
YNE24 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3992 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE24 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3993 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE24 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3994 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3995 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3996 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 3997 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 3998 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 659 |  | 659 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3999 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/317 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 3999 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4000 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4001 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4002 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2320.12 |  | 2320.12 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4003 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1884.32 |  | 1884.32 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/351 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4003 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 531.72 |  | 531.72 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4004 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1824.44 |  | 1824.44 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4003 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 407.89 |  | 407.89 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4003 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 509.9 |  | 509.9 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE24 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4005 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 866.38 |  | 866.38 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4006 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 198.76 |  | 198.76 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4007 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 517.05 |  | 517.05 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4006 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 671.53 |  | 671.53 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4006 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 838.2 |  | 838.2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4006 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 977.47 |  | 977.47 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure Amey 45170 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 4008 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE25 Closure Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4009 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  |  | Every 6 years
YNE25 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4010 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE25 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4011 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE25 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4012 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4013 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4014 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4015 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4016 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 842 |  | 842 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4017 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4017 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4018 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4019 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1424.44 |  | 1424.44 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4020 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1285.7 |  | 1285.7 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1122.09 |  | 1122.09 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4020 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 939.16 |  | 939.16 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  | Days | ILM 2 times per year (Apr - Sept)
YNE25 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4022 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7638 |  | 7638 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4022 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3142 |  | 3142 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4022 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1338 |  | 1338 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4023 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 602 |  | 602 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4024 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 11496 |  | 11496 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4024 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1800 |  | 1800 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4024 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4509 |  | 4509 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4024 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3244 |  | 3244 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4023 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 153 |  | 153 | 0 |  | Y | Access denied due to Alan Hosty schemes - first available date outside of season and therefore these works will not be completed | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 3 |  | Days | 3 time per year (Apr - Sep)
YNE26 Closure Amey 45170 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 4025 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 0 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure | Lane 1 Closure | N/A |  |  | Annually
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4026 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4027 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4028 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | N/A |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038041
YNE26 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4029 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4030 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 21.4766 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 448 | 448 | 0 | 1 |  | N |  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4031 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4031 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4031 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4032 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.65492 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 31.62 | 31.62 | 0 | 1 |  | N |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4032 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 77.6931 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 3751.05 | 3751.05 | 0 | 1 |  | N |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4032 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 26.5305 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1280.9 | 1280.9 | 0 | 1 |  | N |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4033 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.6836 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 467.53 | 467.53 | 0 | 1 |  | N |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE26 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4034 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1357 | 1357 | 0 | 1 |  | N |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4034 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 3468 | 3468 | 0 | 1 |  | N |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4034 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 2575 | 2575 | 0 | 1 |  | N |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4035 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 462 | 462 | 0 | 1 |  | N |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4036 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | N/A |  |  | Every 3 years
YNE27 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4037 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE27 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4038 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE27 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4039 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4040 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4041 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4042 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4043 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 12.9914 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 271 | 271 | 0 | 1 |  | N |  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4044 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4044 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 91.9927 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 4441.44 | 4441.44 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.7847 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 424.13 | 424.13 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4046 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 28.6638 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1383.9 | 1383.9 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE27 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4047 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 329 | 329 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4047 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1346 | 1346 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4048 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 199 | 199 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4049 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 30.5162 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 442 | 442 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4050 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure | Lane 1 Closure | N/A |  |  | Every 3 years
YNE28 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4051 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4052 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4053 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4054 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4055 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 31.8314 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 664 | 664 | 0 | 1 |  | N |  |  | YNE28: A1033 Marfleet - Somerden | YNE28 Closure | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4056 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4057 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 203.1182 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 9806.62 | 9806.62 | 0 | 1 |  | N |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4057 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 14.1432 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 682.84 | 682.84 | 0 | 1 |  | N |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 25.2121 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1217.25 | 1217.25 | 0 | 1 |  | N |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 5 | No |  | ILM 2 times per year (Apr - Sept)
YNE28 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4059 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 7727 | 7727 | 0 | 1 |  | N |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4059 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 2585 | 2585 | 0 | 1 |  | N |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4060 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 8327 | 8327 | 0 | 1 |  | N |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 5 | No |  | 6 times per year (Mar - Oct)
YNE29 Closure Amey 45170 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 4061 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | N/A |  |  | Every 2 years
YNE29 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4062 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE29 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4063 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | N/A |  |  | Annually |  |  | On ServiceNow
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4064 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4065 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4066 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4067 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4068 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 33.4134 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 697 | 697 | 0 | 1 |  | N |  |  | YNE29: A1033 Somerden - Salt End | YNE29 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4069 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4069 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4069 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4070 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45894928
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4071 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 41.5778 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2007.39 | 2007.39 | 0 | 1 |  | N |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4071 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 52.9623 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2557.04 | 2557.04 | 0 | 1 |  | N |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4071 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.6186 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 319.55 | 319.55 | 0 | 1 |  | N |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE29 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4072 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.1547 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 248.87 | 248.87 | 0 | 1 |  | N |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886475
YNE29 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4072 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.2029 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 396.04 | 396.04 | 0 | 1 |  | N |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886475
YNE29 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4073 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 438 | 438 | 0 | 1 |  | N |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4073 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 3851 | 3851 | 0 | 1 |  | N |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4073 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 5971 | 5971 | 0 | 1 |  | N |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4074 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 6695 | 6695 | 0 | 1 |  | N |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct) |  |  | 45894928
YNE29 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4074 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct) |  |  | 45894928
YNE29 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4074 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1105 | 1105 | 0 | 1 |  | N |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct) |  |  | 45894928
YNE29 Closure 1 WB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4075 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 245.1652 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 3551 | 3551 | 0 | 1 |  | N |  | 2000A1033/307 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036975
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1006 |  | 1006 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4077 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 565 |  | 565 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 507 |  | 507 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4077 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1093 |  | 1093 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4077 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 1521 |  | 1521 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 552 |  | 552 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 883 |  | 883 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 914 |  | 914 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 473 |  | 473 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 464 |  | 464 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 457 |  | 457 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 416 |  | 416 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 603 |  | 603 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 648 |  | 648 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 554 |  | 554 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1625 |  | 1625 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4078 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 477 |  | 477 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/204 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 709 |  | 709 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 540 |  | 540 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4079 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 4894 |  | 4894 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4079 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 4330 |  | 4330 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1084 |  | 1084 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4079 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 569 |  | 569 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 3 | No | Days | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 4076 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 374 |  | 374 | 0 |  | Y | Unable to access as due to major projects closures on the M621, no share oppurtunities available in month however works completed in other sections of M621 | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 3 | No | Days | 6 times per year (ILM Certain Sections)
YNE45 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4080 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE54 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4081 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE57 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4082 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4083 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4084 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4085 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  |  |  | 0 | 1 |  | N/A |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4086 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  |  |  | 0 | 1 |  | N/A |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4087 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 189.694 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3957 | 3957 | 0 | 1 |  | N |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 180.964 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 41 | 41 | 0 | 1 |  | N |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 163.309 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 37 | 37 | 0 | 1 |  | N |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 269.2391 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 61 | 61 | 0 | 1 |  | N |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 79.4476 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 123.5852 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 28 | 28 | 0 | 1 |  | N |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 19 | 19 | 0 | 1 |  | N |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4088 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 19 | 19 | 0 | 1 |  | N |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.9803 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 143.89 | 143.89 | 0 | 1 |  | N |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1634 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 56.17 | 56.17 | 0 | 1 |  | N |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.3074 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 63.12 | 63.12 | 0 | 1 |  | N |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.7881 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 376.01 | 376.01 | 0 | 1 |  | N |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.4867 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 506.3 | 506.3 | 0 | 1 |  | N |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.84817 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 40.95 | 40.95 | 0 | 1 |  | N |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.2129 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 155.12 | 155.12 | 0 | 1 |  | N |  | 4400M1/426 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.4378 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 117.7 | 117.7 | 0 | 1 |  | N |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.61226 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 29.56 | 29.56 | 0 | 1 |  | N |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4089 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.29142 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14.07 | 14.07 | 0 | 1 |  | N |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1651 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 56.25 | 56.25 | 0 | 1 |  | N |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.3239 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 112.2 | 112.2 | 0 | 1 |  | N |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.0553 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 244.07 | 244.07 | 0 | 1 |  | N |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.9407 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 431.66 | 431.66 | 0 | 1 |  | N |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.23301 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11.25 | 11.25 | 0 | 1 |  | N |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.16984 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8.2 | 8.2 | 0 | 1 |  | N |  | 4400M1/936 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.849 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 40.99 | 40.99 | 0 | 1 |  | N |  | 4400M1/938 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.9608 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 94.67 | 94.67 | 0 | 1 |  | N |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.2506 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 253.5 | 253.5 | 0 | 1 |  | N |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0766 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 51.98 | 51.98 | 0 | 1 |  | N |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.3202 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 63.74 | 63.74 | 0 | 1 |  | N |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0447 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 98.72 | 98.72 | 0 | 1 |  | N |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4090 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2129 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 58.56 | 58.56 | 0 | 1 |  | N |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4091 | Sweeping - Paved non-running areas - Full Sweep 02 | 170.1097 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22839 | 22839 | 0 | 1 |  | N |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE61 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4092 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.9478 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 531 | 531 | 0 | 1 |  | N |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4092 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.0058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 459 | 459 | 0 | 1 |  | N |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4092 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 558 | 558 | 0 | 1 |  | N |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4092 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.1179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 544 | 544 | 0 | 1 |  | N |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4093 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.7198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 590 | 590 | 0 | 1 |  | N |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4093 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.888 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 450 | 450 | 0 | 1 |  | N |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4093 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.5366 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 576 | 576 | 0 | 1 |  | N |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4093 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.0058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 459 | 459 | 0 | 1 |  | N |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4094 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4095 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4096 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | N/A |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038087
YNE62 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4097 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | N/A |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038087
YNE62Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4098 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 72.7232 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1517 | 1517 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4099 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 105.9301 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 24 | 24 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4099 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4099 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 189.7915 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 43 | 43 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4100 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4101 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.5267 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 73.71 | 73.71 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4101 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.5277 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 170.32 | 170.32 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4101 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.7856 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 327.61 | 327.61 | 0 | 1 |  | N |  | 4400M1/432 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4101 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8759 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 90.57 | 90.57 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4101 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.3198 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15.44 | 15.44 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4102 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.55613 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 26.85 | 26.85 | 0 | 1 |  | N |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4102 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.7278 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 324.82 | 324.82 | 0 | 1 |  | N |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4102 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2788 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 61.74 | 61.74 | 0 | 1 |  | N |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4102 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.9902 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 144.37 | 144.37 | 0 | 1 |  | N |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4103 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 310.202 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4493 | 4493 | 0 | 1 |  | N |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4104 | Sweeping - Paved non-running areas - Full Sweep 02 | 48.9087 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE62 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4105 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.3106 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 788 | 788 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE62 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4106 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.5386 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 729 | 729 | 0 | 1 |  | N |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4107 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4108 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4109 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4110 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4111 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE63 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4112 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 134.1808 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2799 | 2799 | 0 | 1 |  | N |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 114.7576 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26 | 26 | 0 | 1 |  | N |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 198.619 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 45 | 45 | 0 | 1 |  | N |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/914 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 119.1714 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 27 | 27 | 0 | 1 |  | N |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 16 | 16 | 0 | 1 |  | N |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4115 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.576 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 124.37 | 124.37 | 0 | 1 |  | N |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4115 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.9352 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 93.43 | 93.43 | 0 | 1 |  | N |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4115 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0251 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 49.49 | 49.49 | 0 | 1 |  | N |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4115 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.326 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 64.02 | 64.02 | 0 | 1 |  | N |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.57 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 27.52 | 27.52 | 0 | 1 |  | N |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.4849 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 168.25 | 168.25 | 0 | 1 |  | N |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.6771 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 80.97 | 80.97 | 0 | 1 |  | N |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.80757 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 38.99 | 38.99 | 0 | 1 |  | N |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0238 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 97.71 | 97.71 | 0 | 1 |  | N |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4117 | Sweeping - Paved non-running areas - Full Sweep 02 | 87.3768 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11731.25 | 11731.25 | 0 | 1 |  | N |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE63 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4118 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.2509 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1242 | 1242 | 0 | 1 |  | N |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4119 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 19.5482 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1494 | 1494 | 0 | 1 |  | N |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4119 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 35.2103 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2691 | 2691 | 0 | 1 |  | N |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4120 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4121 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4122 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4123 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4124 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 118.0734 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2463 | 2463 | 0 | 1 |  | N |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 145.6539 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 33 | 33 | 0 | 1 |  | N |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 79.4476 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4125 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 207.4465 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 47 | 47 | 0 | 1 |  | N |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4126 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4126 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 |  | N |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4126 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 167.7227 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 38 | 38 | 0 | 1 |  | N |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.12759 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6.16 | 6.16 | 0 | 1 |  | N |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.5107 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 169.5 | 169.5 | 0 | 1 |  | N |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.38981 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18.82 | 18.82 | 0 | 1 |  | N |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.83202 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 40.17 | 40.17 | 0 | 1 |  | N |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.54287 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26.21 | 26.21 | 0 | 1 |  | N |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4127 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.3906 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 115.42 | 115.42 | 0 | 1 |  | N |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.82725 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 39.94 | 39.94 | 0 | 1 |  | N |  | 4400M1/902 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.4132 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 116.51 | 116.51 | 0 | 1 |  | N |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0329 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 49.87 | 49.87 | 0 | 1 |  | N |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.53624 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 25.89 | 25.89 | 0 | 1 |  | N |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4128 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.94241 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 45.5 | 45.5 | 0 | 1 |  | N |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4129 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 10.2181 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 148 | 148 | 0 | 1 |  | N |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4130 | Sweeping - Paved non-running areas - Full Sweep 02 | 76.8786 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 10321.75 | 10321.75 | 0 | 1 |  | N |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE64 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4131 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.3067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 482 | 482 | 0 | 1 |  | N |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4131 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 13.9611 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1067 | 1067 | 0 | 1 |  | N |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4132 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 21.851 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1670 | 1670 | 0 | 1 |  | N |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4132 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 30.5522 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2335 | 2335 | 0 | 1 |  | N |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE65 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4133 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4134 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4135 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4136 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4137 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 22.4354 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 468 | 468 | 0 | 1 |  | N |  |  | YNE65: M1 Tinsley | YNE65 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4138 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1543 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 55.73 | 55.73 | 0 | 1 |  | N |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4139 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4140 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4141 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4142 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4143 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 22.4354 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 468 | 468 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4144 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4144 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 251.5841 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 57 | 57 | 0 | 1 |  | N |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4145 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 207.4465 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 47 | 47 | 0 | 1 |  | N |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4145 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4144 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4144 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4144 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 154.4814 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 35 | 35 | 0 | 1 |  | N |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4146 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.5988 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 77.19 | 77.19 | 0 | 1 |  | N |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4146 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.1392 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 199.84 | 199.84 | 0 | 1 |  | N |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4147 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.2179 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 203.64 | 203.64 | 0 | 1 |  | N |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4147 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.204 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 58.13 | 58.13 | 0 | 1 |  | N |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4146 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.06483 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3.13 | 3.13 | 0 | 1 |  | N |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4146 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0777 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 52.03 | 52.03 | 0 | 1 |  | N |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4148 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.24979 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 12.06 | 12.06 | 0 | 1 |  | N |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4148 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.9078 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 92.11 | 92.11 | 0 | 1 |  | N |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4148 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.5984 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 125.45 | 125.45 | 0 | 1 |  | N |  | 4400M1/842 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4149 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.92398 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 44.61 | 44.61 | 0 | 1 |  | N |  | 4400M1/846 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4149 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.5756 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 27.79 | 27.79 | 0 | 1 |  | N |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 4150 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 176.5245 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3196 | 3196 | 0 | 1 |  | N |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4151 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 28.3069 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 410 | 410 | 0 | 1 |  | N |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4152 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 8.9754 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 130 | 130 | 0 | 1 |  | N |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4151 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 2.8997 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 42 | 42 | 0 | 1 |  | N |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4153 | Sweeping - Paved non-running areas - Full Sweep 02 | 39.5491 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5309.875 | 5309.875 | 0 | 1 |  | N |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE66 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4154 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2.1197 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 162 | 162 | 0 | 1 |  | N |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4154 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.6525 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 432 | 432 | 0 | 1 |  | N |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4154 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.0152 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 689 | 689 | 0 | 1 |  | N |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4155 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.0152 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 689 | 689 | 0 | 1 |  | N |  | 4400M1/881 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4155 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 15.8453 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1211 | 1211 | 0 | 1 |  | N |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4156 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4157 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4158 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4159 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4160 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 120.8059 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2520 | 2520 | 0 | 1 |  | N |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4161 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 132.4127 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 30 | 30 | 0 | 1 |  | N |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4161 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4162 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 158.8952 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 36 | 36 | 0 | 1 |  | N |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4162 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 251.5841 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 57 | 57 | 0 | 1 |  | N |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4163 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4163 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.55551 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26.82 | 26.82 | 0 | 1 |  | N |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.6821 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 81.21 | 81.21 | 0 | 1 |  | N |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4164 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0323 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 98.12 | 98.12 | 0 | 1 |  | N |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4165 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.21727 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10.49 | 10.49 | 0 | 1 |  | N |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4165 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8295 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 88.33 | 88.33 | 0 | 1 |  | N |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4166 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.814 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 39.3 | 39.3 | 0 | 1 |  | N |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4167 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.6621 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 321.65 | 321.65 | 0 | 1 |  | N |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4167 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2552 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 60.6 | 60.6 | 0 | 1 |  | N |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4166 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.59444 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 28.7 | 28.7 | 0 | 1 |  | N |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4166 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.022991 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1.11 | 1.11 | 0 | 1 |  | N |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 SB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4168 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 20.2291 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 293 | 293 | 0 | 1 |  | N |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4169 | Sweeping - Paved non-running areas - Full Sweep 02 | 33.0807 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4441.4286 | 4441.4286 | 0 | 1 |  | N |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE67 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4170 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.4376 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 492 | 492 | 0 | 1 |  | N |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4170 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.9182 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1293 | 1293 | 0 | 1 |  | N |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4171 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 21.2492 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1624 | 1624 | 0 | 1 |  | N |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4171 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.6021 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 581 | 581 | 0 | 1 |  | N |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4172 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4173 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4174 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4175 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4176 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 88.1116 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1838 | 1838 | 0 | 1 |  | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4177 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832589
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4178 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832589
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4178 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832589
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4178 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832589
YNE68 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4179 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.3575 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 17.26 | 17.26 | 0 | 1 |  | N |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45839625
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4180 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.20464 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9.88 | 9.88 | 0 | 1 |  | N |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45839625
YNE68 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4180 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.28707 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 13.86 | 13.86 | 0 | 1 |  | N |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45839625
YNE68 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4179 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1328 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 54.69 | 54.69 | 0 | 1 |  | N |  | 4400M1/830 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45839625
YNE67 Closure 2 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4181 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 46.1195 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | 2023-11-14 | 2023-11-13 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 3340 | 3340 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M1/260 | YNE68: M1 J35a-36 | YNE67 Closure 2 NB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013820
YNE68 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4182 | Sweeping - Paved non-running areas - Full Sweep 02 | 22.3459 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3000.1667 | 3000.1667 | 0 | 1 |  | N |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE68 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4183 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.2619 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 555 | 555 | 0 | 1 |  | N |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038014
YNE68 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4184 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.1497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 470 | 470 | 0 | 1 |  | N |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038014
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4185 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4186 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4187 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4188 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4189 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 161.6977 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3373 | 3373 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4190 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45832497 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4191 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/113 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45832497 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4191 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45832497 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 66.2063 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4192 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832497
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4194 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.37614 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 18.16 | 18.16 | 0 | 1 |  | N |  | 4400M1/110 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45838894 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4194 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45008 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 21.73 | 21.73 | 0 | 1 |  | N |  | 4400M1/111 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45838894 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4195 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.4343 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 69.25 | 69.25 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45838894 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4194 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.14871 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7.18 | 7.18 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 | 45838894 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.24254 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11.71 | 11.71 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45236 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21.84 | 21.84 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4197 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.72369 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 34.94 | 34.94 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4197 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.35066 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16.93 | 16.93 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.75248 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 36.33 | 36.33 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4197 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0932 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 52.78 | 52.78 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838894
YNE69 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4198 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 39.7677 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 576 | 576 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4199 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 147.9552 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | 2023-11-15 | 2023-11-14 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 10715 | 10715 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 284/5 | 275/3 | 12013818 and 12013819 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4200 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 53.4241 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-13 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 3869 | 3869 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013816
YNE69 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4200 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 34.9072 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-13 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 2528 | 2528 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013817
YNE69 Closure 2 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4201 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-18 | 2023-12 | 2023-12-19 | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6994 |  | 6994 | 0 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4202 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 14.5499 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1112 | 1112 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 284/5 | 275/3 | 52038018 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4203 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.288 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 557 | 557 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 284/5 | 275/3 | 52038018 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4204 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.5497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 577 | 577 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038018
YNE69 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4205 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 11.9723 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 915 | 915 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038018
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4206 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4207 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4208 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4209 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4210 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 162.0333 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3380 | 3380 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4211 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832474
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4212 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832474 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4213 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.26947 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13.01 | 13.01 | 0 | 1 |  | N |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838827
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4213 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.2005 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9.68 | 9.68 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838827
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4213 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.2647 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 12.78 | 12.78 | 0 | 1 |  | N |  | 4400M1/107 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838827
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4213 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.50248 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 24.26 | 24.26 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838827
YNE70 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4213 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.93723 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 45.25 | 45.25 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838827
YNE70 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4214 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2214 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 58.97 | 58.97 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45838827 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE69 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4199 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 80.212 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 5809 | 5809 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE69 Closure 1 SB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 284/5 | 275/3 | 12013814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4200 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 91.0101 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-13 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 6591 | 6591 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M1/263 | YNE70: M1 J37-38 | YNE69 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) |  |  | 12013815
YNE70 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4215 | Sweeping - Paved non-running areas - Full Sweep 02 | 104.139 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13981.75 | 13981.75 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE70 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4216 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.4058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 566 | 566 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037982
YNE70 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4216 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.604 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 734 | 734 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52037982
YNE70 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4217 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.232 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 782 | 782 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52037982 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4217 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.0581 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 463 | 463 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52037982 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4218 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4219 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4220 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4221 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4222 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 169.2721 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3531 | 3531 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4224 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832928
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4224 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45832928
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 88.2751 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4223 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45832928 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4225 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.24088 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11.63 | 11.63 | 0 | 1 |  | N |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838903
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4225 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.70422 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 34 | 34 | 0 | 1 |  | N |  | 4700M1/174 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838903
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4225 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8227 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 88 | 88 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838903
YNE71 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4225 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.51035 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 24.64 | 24.64 | 0 | 1 |  | N |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45838903
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4226 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.2048 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 58.17 | 58.17 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45838903 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4226 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.6777 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 81 | 81 | 0 | 1 |  | N |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45838903 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE70 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4227 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 853 |  | 853 | 0 | 10/11 Unmaintainable | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M1/11 | YNE71: M1 J38-39 | YNE70 Closure 1 NB NS | Lane 1 Closure |  | No | Days | Annually (Sept, Oct) | 288/2 | 294/8 | 12013813 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4227 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 64.8573 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-10 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 4697 | 4697 | 0 | 1 |  | N |  | 4700M1/9 | YNE71: M1 J38-39 | YNE70 Closure 1 NB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 288/2 | 294/8 | 12013812 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE71 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4228 | Sweeping - Paved non-running areas - Full Sweep 02 | 108.5894 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14579.25 | 14579.25 | 0 | 1 |  | N |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE71 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4229 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.9498 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 684 | 684 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038003 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4229 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 14.4322 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1103 | 1103 | 0 | 1 |  | N |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038003 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4230 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 11.2134 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 857 | 857 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038003
YNE71 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4230 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 10.0096 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 765 | 765 | 0 | 1 |  | N |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 4 times per year (ILM Certain Sections) |  |  | 52038003
YNE71 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4230 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.7722 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 594 | 594 | 0 | 1 |  | N |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 4 times per year (ILM Certain Sections) |  |  | 52038003
YNE71 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4230 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.3927 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 565 | 565 | 0 | 1 |  | N |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038003
YNE71 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4229 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.7218 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 743 | 743 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038003 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4229 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.3908 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 412 | 412 | 0 | 1 |  | N |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038003 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4231 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4232 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4233 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4234 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4235 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 115.9641 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2419 | 2419 | 0 | 1 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4236 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4236 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 150.0677 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 34 | 34 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4236 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 260.4116 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 59 | 59 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4236 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 119.1714 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 27 | 27 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4236 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 136.8264 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 31 | 31 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4237 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/734 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4237 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45835270 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4238 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.092998 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4.49 | 4.49 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4238 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.48425 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 23.38 | 23.38 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4238 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.75952 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 36.67 | 36.67 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4238 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8695 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 90.26 | 90.26 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4238 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.34051 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16.44 | 16.44 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4239 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.68164 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 32.91 | 32.91 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4239 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 17.1291 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 827 | 827 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4239 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.2701 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 109.6 | 109.6 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45843538 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4240 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 427 |  | 427 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure |  | No | Days | Annually (Sept, Oct) | 288/2 | 294/8 | 12013824 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4241 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-09-01 | 2023-09-29 | 2024-02-29 | Subject to share with scheme works and clash management | 21dys | NB | 10264.5 |  | 10264.5 | 0 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year | 288/2 | 294/8 | No job number emailed NH | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4242 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.8974 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038142 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4242 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.4506 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 493 | 493 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 | 52038142 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4243 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 11.8938 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 909 | 909 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038142 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4243 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 15.7275 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1202 | 1202 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038142 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE73 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4244 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 2 | No |  | 2 times per year |  |  | On ServiceNow
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4245 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4246 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4247 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4248 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4249 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 107.8624 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2250 | 2250 | 0 | 1 |  | N |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 233.929 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 53 | 53 | 0 | 1 |  | N |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 207.4465 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 47 | 47 | 0 | 1 |  | N |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 97.1026 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22 | 22 | 0 | 1 |  | N |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 163.309 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 37 | 37 | 0 | 1 |  | N |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4251 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4251 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4251 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4251 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45835275
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 127.4224 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6152 | 6152 | 0 | 1 |  | N |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.6479 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 224.4 | 224.4 | 0 | 1 |  | N |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.44345 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21.41 | 21.41 | 0 | 1 |  | N |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 38.2143 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1845 | 1845 | 0 | 1 |  | N |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4253 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.17419 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8.41 | 8.41 | 0 | 1 |  | N |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4253 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 11.862 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 572.7 | 572.7 | 0 | 1 |  | N |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4253 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.8529 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 89.46 | 89.46 | 0 | 1 |  | N |  | 4700M1/725 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4253 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5.1333 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 247.84 | 247.84 | 0 | 1 |  | N |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843622
YNE73 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4254 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-09-01 | 2023-09-29 | 2024-02-29 | Subject to share with scheme works and clash management | 21dys | NB | 11572.5 |  | 11572.5 | 0 |  | N |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE73 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4255 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.7142 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 666 | 666 | 0 | 1 |  | N |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038127
YNE73 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4255 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.8824 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 526 | 526 | 0 | 1 |  | N |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038127
YNE73 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4256 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 11.7237 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 896 | 896 | 0 | 1 |  | N |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038127
YNE73 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4256 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.1909 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 626 | 626 | 0 | 1 |  | N |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038127
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4257 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4258 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4259 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS | Lane 3 & 4 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4260 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 2 & 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4261 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 78.5238 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1638 | 1638 | 0 | 1 |  | N |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 & 2 Closure | 2 | No |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4262 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 136.8264 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 31 | 31 | 0 | 1 |  | N |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45829210
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4262 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45829210
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4262 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 167.7227 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 38 | 38 | 0 | 1 |  | N |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45829210
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4262 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 119.1714 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 27 | 27 | 0 | 1 |  | N |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45829210
YNE74 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4263 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45829210 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4263 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45829210 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4263 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45829210 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4263 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45829210 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4264 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.19615 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9.47 | 9.47 | 0 | 1 |  | N |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843689
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4264 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45153 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21.8 | 21.8 | 0 | 1 |  | N |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843689
YNE74 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4264 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.55592 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26.84 | 26.84 | 0 | 1 |  | N |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 2 | No | Days | ILM 2 times per year (Apr - Sept) |  |  | 45843689
YNE74 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4265 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 6773 |  | 6773 | 0 |  |  |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year
YNE74 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4266 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.1889 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 473 | 473 | 0 | 1 |  | N |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038133
YNE74 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4266 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.1497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 470 | 470 | 0 | 1 |  | N |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038133
YNE74 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4266 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2.015 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 154 | 154 | 0 | 1 |  | N |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038133
YNE74 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4266 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0.73273 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 56 | 56 | 0 | 1 |  | N |  | 4700M1/699 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) |  |  | 52038133
YNE74 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4267 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 0.61497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 47 | 47 | 0 | 1 |  | N |  | 4700M1/760 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038133 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4267 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.217 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 628 | 628 | 0 | 1 |  | N |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038133 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4267 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 1.9496 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 149 | 149 | 0 | 1 |  | N |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038133 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4267 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.2769 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 709 | 709 | 0 | 1 |  | N |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038133 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4267 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.8955 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 527 | 527 | 0 | 1 |  | N |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No | Days | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 52038133 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE76 Closure Amey 45170 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 4268 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | Every 2 years
YNE76 Closure Amey 45170 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 4269 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 0 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | Annually
YNE76 Closure Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4270 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | Every 6 years
YNE76 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4271 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | Every 3 years
YNE76 Closure Amey 45170 BC - Lamps (LED) for Road Lighting | 4272 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | Every 6 years
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4273 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4274 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4275 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4276 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4277 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 81.8316 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1707 | 1707 | 0 | 1 |  | N |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4278 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4278 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4278 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4278 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 37.908 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1830.21 | 1830.21 | 0 | 1 |  | N |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 58.9933 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2848.22 | 2848.22 | 0 | 1 |  | N |  | 1000A628/107 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 39.5517 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1909.57 | 1909.57 | 0 | 1 |  | N |  | 1000A628/109 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.0855 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 438.65 | 438.65 | 0 | 1 |  | N |  | 1000A628/113 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4280 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 7.1025 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 342.91 | 342.91 | 0 | 1 |  | N |  | 1000A628/115 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 30.7411 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1484.19 | 1484.19 | 0 | 1 |  | N |  | 1000A628/117 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 72.0693 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 3479.53 | 3479.53 | 0 | 1 |  | N |  | 1000A628/125 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4279 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 55.3235 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2671.04 | 2671.04 | 0 | 1 |  | N |  | 1000A628/141 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE76 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4281 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 16.7666 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 404.75 | 404.75 | 0 | 1 |  | N |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4282 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-10-31 | N/A | Removed following GC-898 | 43dys | EB | 1716 |  | 1716 | 0 |  | Y | Wildflower plots removed following receipt of GC-898 | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 0 | 0 | 52038172 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4283 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 20.9057 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-10-31 | Complete |  | 43dys | WB | 1514 | 1514 | 0 | 1 |  | N |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | Days | No | Days | Annually (Sept, Oct) | 0 | 0 | 52042423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4284 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4285 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4286 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4287 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4288 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 135.5711 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2828 | 2828 | 0 | 1 |  | N |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept)
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4289 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4289 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4290 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4290 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4291 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 43.5763 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2103.88 | 2103.88 | 0 | 1 |  | N |  | 1000A628/151 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4291 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 27.7229 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1338.47 | 1338.47 | 0 | 1 |  | N |  | 1000A628/157 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4291 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 23.7815 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1148.18 | 1148.18 | 0 | 1 |  | N |  | 1000A628/165 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4291 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.66777 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 32.24 | 32.24 | 0 | 1 |  | N |  | 1000A628/179 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4291 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0414 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 98.56 | 98.56 | 0 | 1 |  | N |  | 1000A628/189 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4292 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 6.8862 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 332.47 | 332.47 | 0 | 1 |  | N |  | 4405A628/12 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4292 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.6095 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 512.23 | 512.23 | 0 | 1 |  | N |  | 4405A628/23 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4292 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 8.8941 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 429.41 | 429.41 | 0 | 1 |  | N |  | 4405A628/5 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4292 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.3713 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 211.05 | 211.05 | 0 | 1 |  | N |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE77 Closure 1 WB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4293 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 7.8017 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 113 | 113 | 0 | 1 |  | N |  | 4405A628/60 | YNE77: A628 Crowden - Flouch | YNE77 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE78 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4294 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 22.3329 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 539.12 | 539.12 | 0 | 1 |  | N |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 28.0077 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 676.11 | 676.11 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 10.3164 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 249.04 | 249.04 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 55.348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1336.11 | 1336.11 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4294 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 2.0348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 49.12 | 49.12 | 0 | 1 |  | N |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 63.024 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1521.41 | 1521.41 | 0 | 1 | Unable to cut quadrant e/b at Deepcar due to area out of closure, unaware of other work areas. | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 300.8 |  | 300.8 | 0 |  | Y | Cancelled due to storm Babet | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 257.11 |  | 257.11 | 0 |  | Y | Cancelled due to storm Babet | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 666.23 |  | 666.23 | 0 |  | Y | Cancelled due to storm Babet | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4295 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 81.18 |  | 81.18 | 0 |  | Y | Cancelled due to storm Babet | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 3 | Yes | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862264 | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE79 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4296 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 39.0689 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 943.13 | 943.13 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45901293 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4297 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 27.4783 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 663.33 | 663.33 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45901293 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure Amey 45170 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 4298 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 0 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | 3 | No |  | Annually | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4299 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4300 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4301 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4302 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4303 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 36.098 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 753 | 753 | 0 | 1 |  | N |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | 3 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4304 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4305 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4305 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4305 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4305 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4305 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45901058 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4306 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0553 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 99.23 | 99.23 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862156 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4307 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.95525 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 46.12 | 46.12 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862090 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4307 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4.5401 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 219.2 | 219.2 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862090 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4306 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.2583 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 157.31 | 157.31 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862156 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4307 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.74813 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 36.12 | 36.12 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 45862090 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4308 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 12.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 303.37 | 303.37 | 0 | 1 |  | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) | 0 | 0 | 45862983 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4309 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 16.0866 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 233 | 233 | 0 | 1 | 13/10 nothing found | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 52037550 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4309 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 2.2784 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 33 | 33 | 0 | 1 | 13/10 nothing found | Y | Utilising full closure from scheme as unable to access under M&R TM in September | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | ILM 2 times per year (Apr - Sept) | 0 | 0 | 52037550 | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE81 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4310 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 90.8063 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2192.08 | 2192.08 | 0 | 1 |  |  |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 3 | No | Days | 3 time per year (Apr - Sep) |  |  | 45901695
YNE83 Closure 1 SB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4311 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 9.06 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 117.36 | 117.36 | 0 | 1 |  | N |  | 4400M18/131 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 & 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4312 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 5.0673 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 65.64 | 65.64 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4313 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4314 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV Masts - Check mast breaking system | 4315 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4316 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4317 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4318 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 52.7327 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 33 | 2 | 31 | 0.060606 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4319 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 23 |  | 23 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83NE83 M18 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4320 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 13 | 13 | 0 | 1 |  | N |  |  | YNE83: M18 Link - J1 | YNE83NE83 M18 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE83 Closure Infratec 45170 Remotely operated temporary traffic management signs - Change batteries | 4321 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 4 |  | 4 | 0 |  | Y | Way forward for ROTTMS yet to be confirmed |  | YNE83: M18 Link - J1 | YNE83 Closure | Lane 1 & 2 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE83 Closure Infratec 45170 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 4322 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 4 |  | 4 | 0 |  | Y | Way forward for ROTTMS yet to be confirmed |  | YNE83: M18 Link - J1 | YNE83 Closure | Lane 1 & 2 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE83 Closure Infratec 45170 Remotely operated temporary traffic management signs - Clean sign face | 4323 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 4 |  | 4 | 0 |  | Y | Way forward for ROTTMS yet to be confirmed |  | YNE83: M18 Link - J1 | YNE83 Closure | Lane 1 & 2 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE84 Closure 1 NB NS Amey 45170 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 4324 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 6 years | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 4325 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 4326 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 4327 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE84 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | Annually | 253/0 | 257/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4328 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB |  |  | 0 | 0 |  | N/A |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4329 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037555
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4330 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 |  | N/A |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4331 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037555
YNE83NE83 M18 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4332 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 179.6748 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3748 | 3748 | 0 | 1 |  | N |  |  | YNE83: M18 Link - J1 | YNE83NE83 M18 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4333 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/131 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 19 | 19 | 0 | 1 |  | N |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/133 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 18 | 18 | 0 | 1 |  | N |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 25 | 25 | 0 | 1 |  | N |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 21 | 21 | 0 | 1 |  | N |  | 4400M18/175 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/176 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 41 | 41 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 38 | 38 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4337 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4338 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 551.2967 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 92 | 92 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4338 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 101.5164 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 23 | 23 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.25331 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 12.23 | 12.23 | 0 | 1 |  | N |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.58036 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 28.02 | 28.02 | 0 | 1 |  | N |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1156 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 53.86 | 53.86 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.046 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 50.5 | 50.5 | 0 | 1 |  | N |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.6839 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 81.3 | 81.3 | 0 | 1 |  | N |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.22846 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11.03 | 11.03 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.26388 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12.74 | 12.74 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.82249 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 39.71 | 39.71 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.053 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 50.84 | 50.84 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.13463 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6.5 | 6.5 | 0 | 1 |  | N |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.5857 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 616 | 616 | 0 | 1 |  | N |  | 4400M18/131 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.2269 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1304 | 1304 | 0 | 1 |  | N |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6975 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 725 | 725 | 0 | 1 |  | N |  | 4400M18/133 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.9438 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1189 | 1189 | 0 | 1 |  | N |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6689 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 724 | 724 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.837 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 870 | 870 | 0 | 1 |  | N |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.8435 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 590 | 590 | 0 | 1 |  | N |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.9153 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1188 | 1188 | 0 | 1 |  | N |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.4055 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 995 | 995 | 0 | 1 |  | N |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 558 | 558 | 0 | 1 |  | N |  | 4400M18/175 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.0335 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1017 | 1017 | 0 | 1 |  | N |  | 4400M18/176 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.0131 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 666 | 666 | 0 | 1 |  | N |  | 4400M18/177 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9062 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 347 | 347 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.2391 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 779 | 779 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.6584 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1179 | 1179 | 0 | 1 |  | N |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9348 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 348 | 348 | 0 | 1 |  | N |  | 4400M18/204 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 50.6446 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1774 | 1774 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.788 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 518 | 518 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.5816 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 791 | 791 | 0 | 1 |  | N |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.841 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 695 | 695 | 0 | 1 |  | N |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6461 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 478 | 478 | 0 | 1 |  | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.2121 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 708 | 708 | 0 | 1 |  | N |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4345 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 26.6223 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1928 | 1928 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/154 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 & 2 Closure | Days |  | Days | Annually (Sept, Oct) | 269/2 | 264/0 | 12013854 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE83 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4346 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 18.7792 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-15 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 1360 | 1360 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 253/0 | 257/0 | 12013855 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4347 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 21.6534 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 240.9 | 240.9 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4347 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 451.5579 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5023.71 | 5023.71 | 0 | 1 |  | N |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4347 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 157.7712 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1755.25 | 1755.25 | 0 | 1 |  | N |  | 4400M18/204 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4347 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 448.3283 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4987.78 | 4987.78 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4347 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 175.5128 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1952.63 | 1952.63 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE83 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4348 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-26 | 2024-1 | 2024-01-27 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 15548 |  | 15548 | 0 |  | N |  |  | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.06 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 616 | 616 | 0 | 1 |  | N |  | 4400M18/131 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.0621 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1304 | 1304 | 0 | 1 |  | N |  | 4400M18/132 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.4862 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 725 | 725 | 0 | 1 |  | N |  | 4400M18/133 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5574 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1189 | 1189 | 0 | 1 |  | N |  | 4400M18/134 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4350 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.4731 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 724 | 724 | 0 | 1 |  | N |  | 4400M18/137 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.3835 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 870 | 870 | 0 | 1 |  | N |  | 4400M18/138 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4350 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.7198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 590 | 590 | 0 | 1 |  | N |  | 4400M18/154 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5443 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1188 | 1188 | 0 | 1 |  | N |  | 4400M18/171 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4351 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 13.019 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 995 | 995 | 0 | 1 |  | N |  | 4400M18/172 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4349 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 558 | 558 | 0 | 1 |  | N |  | 4400M18/175 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4350 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 13.3069 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1017 | 1017 | 0 | 1 |  | N |  | 4400M18/176 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4350 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.7142 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 666 | 666 | 0 | 1 |  | N |  | 4400M18/177 | YNE83: M18 Link - J1 | YNE83 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4351 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.5403 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 347 | 347 | 0 | 1 |  | N |  | 4400M18/201 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.3331 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1019 | 1019 | 0 | 1 |  | N |  | 4400M18/202 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 81.1629 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6203 | 6203 | 0 | 1 |  | N |  | 4400M18/203 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.5297 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2104 | 2104 | 0 | 1 |  | N |  | 4400M18/204 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 88.4771 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6762 | 6762 | 0 | 1 |  | N |  | 4400M18/205 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.3186 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2470 | 2470 | 0 | 1 |  | N |  | 4400M18/206 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.3498 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 791 | 791 | 0 | 1 |  | N |  | 4400M18/239 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4351 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.0937 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 695 | 695 | 0 | 1 | 0 | N |  | 4400M18/240 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4351 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.2544 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 478 | 478 | 0 | 1 | 0 | N |  | 4400M18/241 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE83 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.2638 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 708 | 708 | 0 | 1 | 0 | N |  | 4400M18/260 | YNE83: M18 Link - J1 | YNE83 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4353 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 15.2181 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 197.13 | 197.13 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE84 Closure 2 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4353 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 5.9443 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 77 | 77 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE84 Closure 2 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4353 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1.3533 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 17.53 | 17.53 | 0 | 1 |  | N |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE85 Closure 1 SB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4354 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4355 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | YNE85 Closure 1 SB NS | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 CCTV Masts - Check mast breaking system | 4356 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4357 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4358 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4359 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 18 |  | 18 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4360 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 15 |  | 15 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4361 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE84: M18 J1-2 | YNE84 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE85 Closure 1 SB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 4362 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 4363 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 4364 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4365 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4366 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4367 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | N/A |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037522
YNE84 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4368 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE84: M18 J1-2 | YNE84 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4369 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 224.6894 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 4687 | 4687 | 0 | 1 |  | N |  |  | YNE84: M18 J1-2 | YNE84 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4370 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4371 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4371 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4372 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4372 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4400M18/119 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4374 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13 | 13 | 0 | 1 |  | N |  | 4400M18/121 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4374 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/122 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4374 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9 | 9 | 0 | 1 |  | N |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4374 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4374 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/125 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4375 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4375 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4375 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 18 | 18 | 0 | 1 |  | N |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4376 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13 | 13 | 0 | 1 |  | N |  | 4400M18/129 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4376 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/130 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/149 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/150 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4376 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 17 | 17 | 0 | 1 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4377 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/207 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4377 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4378 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22 | 22 | 0 | 1 |  | N |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4378 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4378 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4378 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4379 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4379 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4379 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4379 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/217 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/218 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/219 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4377 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 5 CW NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4381 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 182.1676 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 76 | 76 | 0 | 1 |  | N |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 5 CW NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 23 | 23 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M18/292 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4382 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 3 | -1 | 1.5 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4383 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 173.7783 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 29 | 29 | 0 | 1 |  | N |  | 4400M18/207 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4383 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 29.9618 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 5 | -3 | 2.5 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4384 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/119 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4385 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4386 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4387 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4388 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4386 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 5 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 5 | 5 | 0 | 1 |  | N |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 5 CW NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.14623 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7.06 | 7.06 | 0 | 1 |  | N |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.6164 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 29.76 | 29.76 | 0 | 1 |  | N |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4392 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.19283 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9.31 | 9.31 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4393 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45298 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 21.87 | 21.87 | 0 | 1 |  | N |  | 4400M18/130 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4393 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.73032 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 35.26 | 35.26 | 0 | 1 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4394 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.21479 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10.37 | 10.37 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4395 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.4507 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21.76 | 21.76 | 0 | 1 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.3314 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.5897 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 76.75 | 76.75 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.8826 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 136 | 136 | 0 | 1 |  | N |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.5033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 473 | 473 | 0 | 1 |  | N |  | 4400M18/119 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.9111 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 137 | 137 | 0 | 1 |  | N |  | 4400M18/120 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4398 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.6086 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 862 | 862 | 0 | 1 |  | N |  | 4400M18/121 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4398 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.5816 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 791 | 791 | 0 | 1 |  | N |  | 4400M18/122 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4398 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.2081 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 883 | 883 | 0 | 1 |  | N |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4398 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.102 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 529 | 529 | 0 | 1 |  | N |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4398 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1624 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 391 | 391 | 0 | 1 |  | N |  | 4400M18/125 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4399 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.8736 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 521 | 521 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4399 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.8843 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1292 | 1292 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4399 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.713 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1286 | 1286 | 0 | 1 |  | N |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4400 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.1836 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 707 | 707 | 0 | 1 |  | N |  | 4400M18/129 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4400 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.3573 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 608 | 608 | 0 | 1 |  | N |  | 4400M18/130 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0164 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 526 | 526 | 0 | 1 |  | N |  | 4400M18/149 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.8826 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 136 | 136 | 0 | 1 |  | N |  | 4400M18/150 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4400 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.0727 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 563 | 563 | 0 | 1 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4401 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.8696 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 696 | 696 | 0 | 1 |  | N |  | 4400M18/207 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4401 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.0425 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 632 | 632 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4402 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.8558 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1291 | 1291 | 0 | 1 |  | N |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4402 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.7408 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1322 | 1322 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4402 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.1599 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 496 | 496 | 0 | 1 |  | N |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4402 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.5335 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 404 | 404 | 0 | 1 |  | N |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4403 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.6452 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 513 | 513 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4403 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.3223 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 887 | 887 | 0 | 1 |  | N |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4403 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.5246 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 789 | 789 | 0 | 1 |  | N |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4403 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.4397 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 751 | 751 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2211 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 323 | 323 | 0 | 1 |  | N |  | 4400M18/217 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.3622 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 398 | 398 | 0 | 1 |  | N |  | 4400M18/218 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.854 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 135 | 135 | 0 | 1 |  | N |  | 4400M18/219 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4401 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.9846 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 665 | 665 | 0 | 1 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.4422 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 646 | 646 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 5 CW NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4405 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.8679 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 766 | 766 | 0 | 1 |  | N |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 5 CW NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.1362 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 285 | 285 | 0 | 1 |  | N |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.4087 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 855 | 855 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.3646 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 293 | 293 | 0 | 1 |  | N |  | 4400M18/292 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4406 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 6.8295 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 75.98 | 75.98 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4407 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 189.2698 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2105.68 | 2105.68 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45883311
YNE84 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4408 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 183.269 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2038.92 | 2038.92 | 0 | 1 |  | N |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4408 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 385.4499 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4288.24 | 4288.24 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4408 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 36.5618 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 406.76 | 406.76 | 0 | 1 |  | N |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4408 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 131.3989 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1461.85 | 1461.85 | 0 | 1 |  | N |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4409 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 118.9803 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1323.69 | 1323.69 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4409 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 378.1278 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4206.78 | 4206.78 | 0 | 1 |  | N |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4409 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 198.5828 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2209.29 | 2209.29 | 0 | 1 |  | N |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4410 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 19.3253 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 215 | 215 | 0 | 1 |  | N |  | 4400M18/217 | YNE84: M18 J1-2 | YNE85 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4410 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 104.5987 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1163.69 | 1163.69 | 0 | 1 |  | N |  | 4400M18/218 | YNE84: M18 J1-2 | YNE85 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE84 Closure 3 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4411 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 12965 |  | 12965 | 0 |  | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/121 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | Days |  |  | Annually (Sept, Oct) | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4411 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 82.0071 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | 2023-11-18 | 2023-11-17 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 5939 | 5939 | 0 | 1 |  | N |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 264/5 | 260/6 | 12013851 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE107 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4412 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1561.5529 |  | 1561.5529 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/149 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013798
YNE84 Closure 2 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4413 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 65.0506 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-27 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 4711 | 4711 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 256/4 | 260/6 | 12013852 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4413 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 124.5867 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 9022.64 | 9022.64 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 256/4 | 260/6 | 12013806 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4413 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 171.3878 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 12412 | 12412 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 256/4 | 260/6 | 12013807 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4414 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 138.2342 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-04 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 10011 | 10011 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 260/0 | 264/8 | 12013808 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4414 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 369.1632 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-03 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 26735 | 26735 | 4751.23 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 260/0 | 264/8 | 12013850 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4414 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4.681 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-16 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 339 | 339 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 260/0 | 264/8 | 12013848 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4414 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 149.5984 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-16 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 10834 | 10834 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 260/0 | 264/8 | 12013849 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4415 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 30.9581 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-15 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 2242 | 2242 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 253/0 | 257/0 | 12013809 | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 3 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4411 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | CW | 3278.6 |  | 3278.6 | 0 | 17/11 Unmaintainable | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) | 264/5 | 260/6 | 12013846 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4416 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 13.0902 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 948 | 948 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 264/4 | 268/8 | 12013843 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4417 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 69.1102 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1001 | 1001 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4418 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 3397.6818 |  | 3397.6818 | 0 |  | N |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4419 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1348.7115 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 28134 | 28134 | 0 | 1 |  | N |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7795 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 136 | 136 | 0 | 1 |  | N |  | 4400M18/118 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.1889 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 473 | 473 | 0 | 1 |  | N |  | 4400M18/119 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7926 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 137 | 137 | 0 | 1 |  | N |  | 4400M18/120 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4421 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.2788 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 862 | 862 | 0 | 1 |  | N |  | 4400M18/121 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4421 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.3498 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 791 | 791 | 0 | 1 |  | N |  | 4400M18/122 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4421 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.5536 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 883 | 883 | 0 | 1 |  | N |  | 4400M18/123 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4421 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.9217 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 529 | 529 | 0 | 1 |  | N |  | 4400M18/124 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4421 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.116 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 391 | 391 | 0 | 1 |  | N |  | 4400M18/125 | YNE84: M18 J1-2 | YNE84 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 264/5 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4422 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.817 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 521 | 521 | 0 | 1 |  | N |  | 4400M18/126 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4422 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.8865 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1367 | 1367 | 0 | 1 |  | N |  | 4400M18/127 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4422 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.8266 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1286 | 1286 | 0 | 1 |  | N |  | 4400M18/128 | YNE84: M18 J1-2 | YNE84 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 261/2 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4423 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.2507 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 707 | 707 | 0 | 1 |  | N |  | 4400M18/129 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4423 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.9554 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 608 | 608 | 0 | 1 |  | N |  | 4400M18/130 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4424 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.8824 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 526 | 526 | 0 | 1 |  | N |  | 4400M18/149 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4424 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 1.7795 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 136 | 136 | 0 | 1 |  | N |  | 4400M18/150 | YNE84: M18 J1-2 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4425 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.3665 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 563 | 563 | 0 | 1 |  | N |  | 4400M18/153 | YNE84: M18 J1-2 | YNE84 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 257/6 | 253/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4426 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.1068 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 696 | 696 | 0 | 1 |  | N |  | 4400M18/207 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4426 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 35.8122 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2737 | 2737 | 0 | 1 |  | N |  | 4400M18/208 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE84 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4427 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 43.5712 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3330 | 3330 | 0 | 1 |  | N |  | 4400M18/209 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4427 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 73.4038 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5610 | 5610 | 0 | 1 |  | N |  | 4400M18/210 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4427 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.8153 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 903 | 903 | 0 | 1 |  | N |  | 4400M18/211 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4427 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.4156 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1866 | 1866 | 0 | 1 |  | N |  | 4400M18/212 | YNE84: M18 J1-2 | YNE84 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 256/4 | 260/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4428 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.0361 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1837 | 1837 | 0 | 1 |  | N |  | 4400M18/213 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4428 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 66.6522 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5094 | 5094 | 0 | 1 |  | N |  | 4400M18/214 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4428 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 39.2403 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2999 | 2999 | 0 | 1 |  | N |  | 4400M18/215 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4428 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.8264 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 751 | 751 | 0 | 1 |  | N |  | 4400M18/216 | YNE84: M18 J1-2 | YNE84 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually | 260/0 | 264/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.0394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 538 | 538 | 0 | 1 |  | N |  | 4400M18/217 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.4379 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1562 | 1562 | 0 | 1 |  | N |  | 4400M18/218 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7664 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 135 | 135 | 0 | 1 |  | N |  | 4400M18/219 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4430 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.7012 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 665 | 665 | 0 | 1 |  | N |  | 4400M18/242 | YNE84: M18 J1-2 | YNE84 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 253/0 | 257/0 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Andy Reddy's Consent, note Access needed in & out of recovery bays and access through any slip roads
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.4526 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 646 | 646 | 0 | 1 |  | N |  | 4400M18/245 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE84 Closure 5 CW NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4432 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.7291 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 766 | 766 | 0 | 1 |  | N |  | 4400M18/247 | YNE84: M18 J1-2 | YNE84 Closure 5 CW NS | Lane 1 Closure | 2 | No |  | Annually
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 11.1872 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 285 | 285 | 0 | 1 |  | N |  | 4400M18/290 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 & 2 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3.8337 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 855 | 855 | 0 | 1 |  | N |  | 4400M18/291 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM |  | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 293 | 293 | 0 | 1 |  | N |  | 4400M18/292 | YNE84: M18 J1-2 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4433 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 111 | 0 | 111 | 0 | 14/8: Picking up on next visit - guly cart went to M621 | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4433 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 | 0 | 0 | 0 | 14/8: Picking up on next visit - guly cart went to M621 | N |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4434 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 8 | 5 | 3 | 0.625 |  | N |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4360 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 8 |  | 8 | 0 |  | N |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4435 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE85: M18 J2-3 | YNE85 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4436 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4437 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4438 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Not mentioned on report - next visit? | N/A |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4439 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Needed? Only doing 1st September | N/A |  |  | YNE85: M18 J2-3 | YNE85 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4440 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 72.8191 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1519 | 1519 | 0 | 1 | Progress obtained from Confirm Jobs | N |  |  | YNE85: M18 J2-3 | YNE85Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4372 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | 14/8: No assets | N/A |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 22 | 22 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/115 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/117 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 23 | 23 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21 | 21 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/296 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/297 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4380 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 13 | 13 | 0 | 1 | 14/8: Progress obtained from Confirm Jobs | N |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4441 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 | 14/8: Not mentioned on night report - job at allocated to crew | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4442 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.50745 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 24.5 | 24.5 | 0 | 1 |  | N |  | 4400M18/115 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4442 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.80654 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 38.94 | 38.94 | 0 | 1 |  | N |  | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4442 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.96333 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 46.51 | 46.51 | 0 | 1 |  | N |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.15679 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7.57 | 7.57 | 0 | 1 |  | N |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4396 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.23446 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11.32 | 11.32 | 0 | 1 |  | N |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7594 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 517 | 517 | 0 | 1 |  | N |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.461 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1067 | 1067 | 0 | 1 |  | N |  | 4400M18/115 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.788 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 518 | 518 | 0 | 1 |  | N |  | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.7398 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 131 | 131 | 0 | 1 |  | N |  | 4400M18/117 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6175 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 477 | 477 | 0 | 1 |  | N |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4397 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4152 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 575 | 575 | 0 | 1 |  | N |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.7684 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 132 | 132 | 0 | 1 |  | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.3377 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 222 | 222 | 0 | 1 |  | N |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.7325 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 446 | 446 | 0 | 1 |  | N |  | 4400M18/294 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.6958 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 795 | 795 | 0 | 1 |  | N |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.9911 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 385 | 385 | 0 | 1 |  | N |  | 4400M18/296 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.1371 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 250 | 250 | 0 | 1 |  | N |  | 4400M18/297 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.4405 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 716 | 716 | 0 | 1 |  | N |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4404 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2146 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 603 | 603 | 0 | 1 |  | N |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4345 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 18.793 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1361 | 1361 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 269/2 | 264/0 | 12013845 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4345 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 25.0758 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-14 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1816 | 1816 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 269/2 | 264/0 | 12013796 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4416 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 789 |  | 789 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 & 2 Closure |  |  | Days | Annually (Sept, Oct) | 264/4 | 268/8 | 12013847 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4416 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 89 |  | 89 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 & 2 Closure |  |  | Days | Annually (Sept, Oct) | 264/4 | 268/8 | 12013811 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4418 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-31 | 2024-1 | 2024-02-01 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 6297.25 |  | 6297.25 | 0 |  |  |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4419 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 922.1516 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 19236 | 19236 | 0 | 1 | Complete | N |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.7647 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 517 | 517 | 0 | 1 |  | N |  | 4400M18/114 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.9611 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1067 | 1067 | 0 | 1 |  | N |  | 4400M18/115 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.7777 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 518 | 518 | 0 | 1 |  | N |  | 4400M18/116 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4420 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7141 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 131 | 131 | 0 | 1 |  | N |  | 4400M18/117 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4424 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.2413 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 477 | 477 | 0 | 1 |  | N |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4424 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.5236 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 575 | 575 | 0 | 1 |  | N |  | 4400M18/148 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 269/2 | 264/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7271 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 132 | 132 | 0 | 1 |  | N |  | 4400M18/220 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.9047 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 222 | 222 | 0 | 1 |  | N |  | 4400M18/293 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.8357 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 446 | 446 | 0 | 1 |  | N |  | 4400M18/294 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.4021 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 795 | 795 | 0 | 1 |  | N |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.0375 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 385 | 385 | 0 | 1 |  | N |  | 4400M18/296 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4429 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.2711 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 250 | 250 | 0 | 1 |  | N |  | 4400M18/297 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.3685 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 716 | 716 | 0 | 1 |  | N |  | 4400M18/298 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4431 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.8899 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 603 | 603 | 0 | 1 |  | N |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 264/4 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4443 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 1125.27 |  | 1125.27 | 0 |  |  |  | 4400M18/147 | YNE85: M18 J2-3 | YNE85 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 269/2 | 264/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4444 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 286.9 |  | 286.9 | 0 |  |  |  | 4400M18/295 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 264/4 | 268/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4444 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 896.03 |  | 896.03 | 0 | 0 |  |  | 4400M18/299 | YNE85: M18 J2-3 | YNE85 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 264/4 | 268/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4445 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 | 1/9: Tablet actually showing 13 gullies in work area, full of straw. | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE86 Closure 3 SB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4446 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys | SB | 106 | 0 | 106 | 0 |  | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4447 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 6.0794 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 78.75 | 78.75 | 0 | 1 | 17/8: not complete | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4448 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 77.8346 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1008.24 | 1008.24 | 0 | 1 | 30/8: not complete | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE86 Closure 1 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4448 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 80.6654 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1044.91 | 1044.91 | 0 | 1 | 30/8: not complete | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE86 Closure 1 NB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4449 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 27.617 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 357.74 | 357.74 | 0 | 1 | 30/8: not complete | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE86 Closure 3 NB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 47.5095 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 615.42 | 615.42 | 0 | 1 |  | N |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE86 Closure 3 SB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4451 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 281/4 | 277/3 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4452 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 281/4 | 277/3 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 CCTV Masts - Check mast breaking system | 4453 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 281/4 | 277/3 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4454 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 4 |  | 4 | 0 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 281/4 | 277/3 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4455 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 16 | 16 | 0 | 1 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE86 Closure 3 SB NS Amey 45170 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 4456 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Every 6 years | 281/4 | 277/3 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4457 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4458 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4459 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Check jobs are closed | N/A |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4460 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | check jobs are closed | N/A |  |  | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4461 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 203.5963 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 4247 | 4247 | 0 | 1 | check all jobs are closed | N |  |  | YNE86: M18 J3-4 | YNE86 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4462 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | 17/8: check all jobs are closed | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4463 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 | check all jobs are closed | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4464 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 24 | 24 | 0 | 1 | check all jobs are closed | N |  | 4400M18/108 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4464 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 24 | 24 | 0 | 1 | check all jobs are closed | N |  | 4400M18/109 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4465 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 25 | 25 | 0 | 1 | check all jobs are closed | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4465 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 27 | 27 | 0 | 1 | check jobs are closed | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4465 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 | check all jobs are closed | N |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4465 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 | check all jobs are closed | N |  | 4400M18/113 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4463 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 | check all jobs are closed | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4465 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9 | 9 | 0 | 1 | check all jobs are closed | N |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4466 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 | check all jobs are closed | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4466 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 | check all jobs are closed | N |  | 4400M18/225 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4466 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 30 | 30 | 0 | 1 | check all jobs are closed | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4466 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 | check jobs are closed | N |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4467 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 32 | 32 | 0 | 1 | check all jobs are closed | N |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4467 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 29 | 29 | 0 | 1 | check jobs are closed | N |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4468 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4466 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M18/250 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4468 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4469 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 | check all jobs are closed | N |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4469 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 | check all jobs are closed | N |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4470 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | check all jobs are closed | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4470 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 | check all jobs are closed | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4471 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | check all jobs are closed | N |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4471 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 | check all jobs are closed | N |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4472 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 | check all jobs are closed | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4473 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45112 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 21.78 | 21.78 | 0 | 1 | check all jobs are closed | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4474 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.43496 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 21 | 21 | 0 | 1 | check all jobs are closed | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4473 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.48508 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 23.42 | 23.42 | 0 | 1 | check all jobs are closed | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4475 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.4842 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 168.22 | 168.22 | 0 | 1 | check all jobs are closed | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4476 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0002 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 48.29 | 48.29 | 0 | 1 | check all jobs are closed | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4477 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 21.0438 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 508 | 508 | 0 | 1 | 0 | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4478 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.1828 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 742 | 742 | 0 | 1 | 0 | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4479 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.1935 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1513 | 1513 | 0 | 1 | 0 | N |  | 4400M18/108 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4479 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.4725 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1803 | 1803 | 0 | 1 | 0 | N |  | 4400M18/109 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4480 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5581 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1806 | 1806 | 0 | 1 | 0 | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4480 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5295 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1805 | 1805 | 0 | 1 | 0 | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4480 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.9617 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 419 | 419 | 0 | 1 | 0 | N |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4480 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.5049 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 403 | 403 | 0 | 1 | 0 | N |  | 4400M18/113 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4478 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.8696 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 696 | 696 | 0 | 1 | 0 | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4480 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.1917 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 357 | 357 | 0 | 1 | 0 | N |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4481 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.8165 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 519 | 519 | 0 | 1 | 0 | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4481 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.7929 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 308 | 308 | 0 | 1 | 0 | N |  | 4400M18/225 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4481 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.2726 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1796 | 1796 | 0 | 1 | 0 | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4481 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3297 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1798 | 1798 | 0 | 1 | 0 | N |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4482 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3868 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1800 | 1800 | 0 | 1 | 0 | N |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4482 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 45.877 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1607 | 1607 | 0 | 1 | 0 | N |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4483 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.6134 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 652 | 652 | 0 | 1 |  | N |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4481 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7602 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 482 | 482 | 0 | 1 |  | N |  | 4400M18/250 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4483 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.6134 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 607 | 652 | -45 | 1.0741 |  | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE85 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4416 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 135.4726 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-06 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 9811 | 9811 | 0 | 1 |  | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE85 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 264/4 | 268/8 | 12013828 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4484 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 15.9169 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 177.08 | 177.08 | 0 | 1 |  | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4485 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 99.0896 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1102.4 | 1102.4 | 0 | 1 |  | N |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE86 Closure 2 NB NS CGS 45170 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 4486 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 2 ILM | 160.286 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2902 | 2902 | 0 | 1 | 16/8: not copmpleted | N |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4487 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-02-05 | 2024-2 | 2024-02-06 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys | SB | 5863.4167 |  | 5863.4167 | 0 |  | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4488 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 832.5539 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 17367 | 17367 | 0 | 1 | 17/8: No litter pickers | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4489 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.7087 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 742 | 742 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/107 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4490 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 19.7968 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1513 | 1513 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/108 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4490 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5913 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1803 | 1803 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/109 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 277/7 | 273/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4491 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.9465 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1983 | 1983 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/110 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4491 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6174 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1805 | 1805 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4491 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.4824 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 419 | 419 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4491 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.273 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 403 | 403 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/113 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4492 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.1068 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 696 | 696 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/145 | YNE86: M18 J3-4 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4493 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.6712 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 357 | 357 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 273/6 | 268/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.7908 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 519 | 519 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/224 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.03 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 308 | 308 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/225 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.4997 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1796 | 1796 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 37.958 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2901 | 2901 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/227 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4495 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.552 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1800 | 1800 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4495 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.0267 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1607 | 1607 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 272/4 | 276/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.5311 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 652 | 652 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/230 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4497 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.3067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 482 | 482 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/250 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 268/4 | 272/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4498 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 14.5892 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1115 | 1115 | 0 | 1 | 15-17/8: No litter pickers | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4499 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 607.08 |  | 607.08 | 0 |  |  |  | 4400M18/108 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 277/7 | 273/2 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4499 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 1396.3 |  | 1396.3 | 0 |  |  |  | 4400M18/109 | YNE86: M18 J3-4 | YNE86 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 277/7 | 273/2 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4500 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 1823.69 |  | 1823.69 | 0 |  |  |  | 4400M18/111 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 273/6 | 268/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4500 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 399.68 |  | 399.68 | 0 |  |  |  | 4400M18/112 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 273/6 | 268/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4500 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 20.73 |  | 20.73 | 0 |  |  |  | 4400M18/146 | YNE86: M18 J3-4 | YNE86 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 273/6 | 268/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4501 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 364.38 |  | 364.38 | 0 |  |  |  | 4400M18/225 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 268/4 | 272/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4501 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1756.1 |  | 1756.1 | 0 |  |  |  | 4400M18/226 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 268/4 | 272/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4502 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1360.7 |  | 1360.7 | 0 |  |  |  | 4400M18/228 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 272/4 | 276/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4502 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1109.17 |  | 1109.17 | 0 |  |  |  | 4400M18/229 | YNE86: M18 J3-4 | YNE86 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 272/4 | 276/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4501 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 593.61 |  | 593.61 | 0 |  |  |  | 4400M18/250 | YNE86: M18 J3-4 | YNE86 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 268/4 | 272/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4503 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys | SB | 96 | 2 | 94 | 0.020833 |  | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 283/1 | 281/0 | 45879010 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4504 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | completed | 2023-09-01 | 2023-09-29 | 2023-11-30 | 120 | 21dys | SB | 18 | 18 | 0 | 1 |  | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45879307
YNE86 Closure 3 NB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 57.7715 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 748.35 | 748.35 | 0 | 1 |  | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE86 Closure 3 NB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4450 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 92.0978 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1193 | 1193 | 0 | 1 |  | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE87 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4505 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 623.88 |  | 623.88 | 0 |  |  |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/1 | 281/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4506 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 598.89 |  | 598.89 | 0 |  |  |  | 4400M18/104 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 281/4 | 277/3 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4506 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 1137.79 |  | 1137.79 | 0 |  |  |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 281/4 | 277/3 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4505 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 231.82 |  | 231.82 | 0 |  |  |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/1 | 281/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4505 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 952.81 |  | 952.81 | 0 |  |  |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 283/1 | 281/0 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4507 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1213.43 |  | 1213.43 | 0 |  |  |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 276/4 | 280/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4508 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 551.56 |  | 551.56 | 0 |  |  |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 280/4 | 283/4 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4508 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 624.24 |  | 624.24 | 0 |  |  |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 280/4 | 283/4 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4507 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 869.94 |  | 869.94 | 0 |  |  |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 276/4 | 280/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4508 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 226.05 |  | 226.05 | 0 |  |  |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 280/4 | 283/4 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4508 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 392.19 |  | 392.19 | 0 |  |  |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 280/4 | 283/4 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4509 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 280/4 | 283/4 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4510 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | No jobs
YNE87 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4511 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 9 | 9 | 0 | 1 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE87 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 4512 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 280/4 | 283/4 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 4513 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 280/4 | 283/4 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 4514 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 280/4 | 283/4 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4515 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE87 Closure Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4516 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE87 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4517 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE87 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4510 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 0 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N |  |  | YNE87: M18 J4-5 | YNE87 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4518 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4519 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4520 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | check jobs are closed | N/A |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4521 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4522 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 | check jobs are closed | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 | check jobs are closed | N |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13 | 13 | 0 | 1 | check jobs are closed | N |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 | check jobs are closed | N |  | 4400M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 | check jobs are closed | N |  | 4400M18/103 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4463 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 16 | 16 | 0 | 1 | check jobs are closed | N |  | 4400M18/104 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4463 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 30 | 30 | 0 | 1 | check jobs are closed | N |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4463 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 | check jobs are closed | N |  | 4400M18/106 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 | check jobs are closed | N |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 | check jobs are closed | N |  | 4400M18/143 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 | check jobs are closed | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 | check jobs are closed | N |  | 4400M18/160 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 | check jobs are closed | N |  | 4400M18/162 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4468 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | check jobs are closed | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4468 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 | check jobs are closed | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 | check jobs are closed | N |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 | check jobs are closed | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 | check jobs are closed | N |  | 4400M18/235 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22 | 22 | 0 | 1 | check jobs are closed | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4468 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 | check jobs are closed | N |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 | check jobs are closed | N |  | 4400M18/253 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 | check jobs are closed | N |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 | check jobs are closed | N |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | check jobs are closed | N |  | 4400M18/280 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4525 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 143.8165 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 24 | 24 | 0 | 1 |  | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4526 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4472 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4472 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4528 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.22535 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10.88 | 10.88 | 0 | 1 | 0 | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4528 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.60439 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 29.18 | 29.18 | 0 | 1 | 0 | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4529 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 30.0743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 726 | 726 | 0 | 1 | 0 | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 3 time per year (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8499 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 310 | 310 | 0 | 1 |  | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8785 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 311 | 311 | 0 | 1 | 0 | N |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.7807 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 833 | 833 | 0 | 1 |  | N |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4152 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 575 | 575 | 0 | 1 | 0 | N |  | 4400M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.0156 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 561 | 561 | 0 | 1 | 0 | N |  | 4400M18/103 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4478 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.3174 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1097 | 1097 | 0 | 1 |  | N |  | 4400M18/104 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4478 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1377 | 1377 | 0 | 1 |  | N |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4478 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 581 | 581 | 0 | 1 |  | N |  | 4400M18/106 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.5914 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 371 | 371 | 0 | 1 | 0 | N |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.7562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 657 | 657 | 0 | 1 | 0 | N |  | 4400M18/143 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.416 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 540 | 540 | 0 | 1 | 0 | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.4829 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 122 | 122 | 0 | 1 | 0 | N |  | 4400M18/160 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.8149 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 589 | 589 | 0 | 1 | 0 | N |  | 4400M18/162 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4764 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 402 | 402 | 0 | 1 | 0 | N |  | 4400M18/180 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4483 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 788 | 788 | 0 | 1 |  | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4483 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.6869 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1180 | 1180 | 0 | 1 |  | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.6877 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1145 | 1145 | 0 | 1 |  | N |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.531 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 509 | 509 | 0 | 1 |  | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.1004 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 599 | 599 | 0 | 1 |  | N |  | 4400M18/235 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.7505 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 902 | 902 | 0 | 1 |  | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4483 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.4405 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 716 | 716 | 0 | 1 |  | N |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.5669 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 195 | 195 | 0 | 1 |  | N |  | 4400M18/253 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.5066 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 333 | 333 | 0 | 1 |  | N |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5873 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 546 | 546 | 0 | 1 |  | N |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4530 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6787 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 304 | 304 | 0 | 1 |  | N |  | 4400M18/280 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4532 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 23.8735 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 265.6 | 265.6 | 0 | 1 |  | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 10.5301 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 117.15 | 117.15 | 0 | 1 |  |  |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 73.732 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 820.29 | 820.29 | 0 | 1 |  |  |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 113.8515 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1266.63 | 1266.63 | 0 | 1 |  |  |  | 4400M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 88.2791 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 982.13 | 982.13 | 0 | 1 |  |  |  | 4400M18/103 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 19.8386 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 220.71 | 220.71 | 0 | 1 |  |  |  | 4400M18/180 | YNE87: M18 J4-5 | YNE87 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4532 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 225.6239 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2510.13 | 2510.13 | 0 | 1 |  | N |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4532 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 108.6498 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1208.76 | 1208.76 | 0 | 1 |  | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE87 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4532 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 7.0138 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 78.03 | 78.03 | 0 | 1 |  | N |  | 4400M18/280 | YNE87: M18 J4-5 | YNE87 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45886198
YNE86 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4534 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 12.0132 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-11-09 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 870 | 870 | 0 | 1 |  | N | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400M18/234 | YNE87: M18 J4-5 | YNE86 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Annually (Sept, Oct) | 268/4 | 272/8 | 12013844 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4535 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-02-06 | 2024-2 | 2024-02-07 | 2023-09-01 | 2023-09-29 | 2024-02-29 |  | 21dys | NB | 13731.5 |  | 13731.5 | 0 |  | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4536 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1248.2317 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26038 | 26038 | 0 | 1 | 18/8: No litter pickers | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.5236 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 575 | 575 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 2000M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4538 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.6132 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 429 | 429 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 2000M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4538 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.6417 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1654 | 1654 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/101 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4538 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.1016 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1842 | 1842 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/102 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4538 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.1893 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1543 | 1543 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/103 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4489 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.3537 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1097 | 1097 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/104 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4489 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.0173 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1377 | 1377 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/105 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4489 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.6021 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 581 | 581 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/106 | YNE87: M18 J4-5 | YNE86 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 281/4 | 277/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4539 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.8543 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 371 | 371 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/142 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4539 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.5965 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 657 | 657 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/143 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4539 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.5649 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1266 | 1266 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4539 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 1.5963 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 122 | 122 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/160 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4539 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.7067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 589 | 589 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/162 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4538 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.1516 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 623 | 623 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/180 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.3106 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 788 | 788 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/231 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.4397 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1180 | 1180 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/232 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 47.8237 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3655 | 3655 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/233 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.66 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 509 | 509 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/234 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.8376 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 599 | 599 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/235 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.6213 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2111 | 2111 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/236 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE86 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4498 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.3685 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 716 | 716 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/252 | YNE87: M18 J4-5 | YNE86 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2.5515 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 195 | 195 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/253 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.3571 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 333 | 333 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/254 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.1441 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 546 | 546 | 0 | 1 | 17-18/8: No litter pickers | N |  | 4400M18/255 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 & 2 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4537 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.9983 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 382 | 382 | 0 | 1 | 4/9: CR picked. 17-18/8: No litter pickers | N |  | 4400M18/280 | YNE87: M18 J4-5 | YNE87 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 280/4 | 283/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4541 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 301.074 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 39 | 39 | 0 | 1 | 8/9: 51 completed in total ut jobs not closed? Check do forms | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 286/3 | 282/5 | 45879066 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4542 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45879157
YNE88 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4541 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 | 8/9: 51 completed in total ut jobs not closed? Check do forms | N |  | 2000M18/134 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 286/3 | 282/5 | 45879066 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4542 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 2000M18/134 | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 3 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45879157
YNE88 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4543 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 872.3427 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 113 | -106 | 16.1429 |  | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4544 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | 45877636
YNE88 Closure 1 SB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4545 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 11.9847 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 286/3 | 282/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4546 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 11.9847 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 286/3 | 282/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 CCTV Masts - Check mast breaking system | 4547 | CCTV Masts - Check mast breaking system | 63.9185 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 286/3 | 282/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4548 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 79.0991 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 6 | 3 | 0 | 0.5 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 286/3 | 282/5 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4549 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4550 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 45879066 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4551 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4550 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | check jobs are closed | N |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 45879066 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4552 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 | check jobs are closed | N/A |  |  | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4553 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 88.6389 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1849 | 1849 | 0 | 1 | check jobs are closed | N |  |  | YNE88: M18 J5-6 | YNE88 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4554 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 | check jobs are closed | N |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4554 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 167.786 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 | check jobs are closed | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 |  | N |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 |  | N |  | 2000M18/124 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 |  | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 2000M18/134 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 2000M18/136 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 15 | 15 | 0 | 1 |  | N |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 |  | N |  | 2000M18/142 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 2000M18/147 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4556 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 |  | N |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 45880008 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4555 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 |  | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4557 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 239.6942 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 40 | 40 | 0 | 1 |  | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4558 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 |  | N |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52037491 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4558 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 239.6942 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 40 | 40 | 0 | 1 |  | N |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52037491 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4559 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 | check jobs are closed | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4559 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 | check jobs are closed | N |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 52039420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4559 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | check jobs are closed | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4560 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 52039420 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4559 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 | check jobs are closed | N |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4559 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 13 | 13 | 0 | 1 | check jobs are closed | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4561 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.45878 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 22.15 | 22.15 | 0 | 1 |  | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 45828353 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4562 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.1541 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 55.72 | 55.72 | 0 | 1 | Complete | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4561 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.59879 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 28.91 | 28.91 | 0 | 1 |  | N |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 45828353 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4561 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.46955 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 22.67 | 22.67 | 0 | 1 | Complete | N |  | 2000M18/147 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 286/3 | 282/5 | 45828353 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5588 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 545 | 545 | 0 | 1 |  | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.8467 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 450 | 450 | 0 | 1 |  | N |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6461 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 478 | 478 | 0 | 1 |  | N |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5946 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 231 | 231 | 0 | 1 |  | N |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.708 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 270 | 270 | 0 | 1 |  | N |  | 2000M18/124 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.7007 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 585 | 585 | 0 | 1 |  | N |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.0433 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 597 | 597 | 0 | 1 |  | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.2986 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 676 | 676 | 0 | 1 |  | N |  | 2000M18/134 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.4169 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 505 | 505 | 0 | 1 |  | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.673 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 549 | 549 | 0 | 1 |  | N |  | 2000M18/136 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.7284 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 621 | 621 | 0 | 1 |  | N |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.2439 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 569 | 569 | 0 | 1 |  | N |  | 2000M18/142 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.0759 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 423 | 423 | 0 | 1 |  | N |  | 2000M18/147 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4564 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.5066 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 333 | 333 | 0 | 1 |  | N |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 286/3 | 282/5 | 52032956 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.2235 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 218 | 218 | 0 | 1 |  | N |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.5898 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 441 | 441 | 0 | 1 |  | N |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.3867 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 574 | 574 | 0 | 1 |  | N |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4563 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.527 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 684 | 684 | 0 | 1 |  | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 58.6106 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 652.06 | 652.06 | 0 | 1 |  | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4566 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 10.8321 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 120.51 | 120.51 | 0 | 1 |  | N |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 70.3488 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 782.65 | 782.65 | 0 | 1 |  | N |  | 2000M18/136 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 25.2749 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 281.19 | 281.19 | 0 | 1 |  | N |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 119.9942 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1334.97 | 1334.97 | 0 | 1 |  | N |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 207.2342 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2305.54 | 2305.54 | 0 | 1 |  | N |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4565 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 182.727 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2032.89 | 2032.89 | 0 | 1 |  | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE88 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4567 | Sweeping - Paved non-running areas - Full Sweep 02 | 57.0496 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7659.5 | 7659.5 | 0 | 1 |  | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4568 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 797.7983 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16642 | 16642 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.6621 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1197 | 1197 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/105 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.4712 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 571 | 571 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/108 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4571 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.2544 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 478 | 478 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4572 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3.0225 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 231 | 231 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4572 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 3.5328 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 270 | 270 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/124 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4572 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.6544 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 585 | 585 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.8114 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 597 | 597 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.8451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 676 | 676 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/134 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4571 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.6077 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 505 | 505 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Certain Sections) | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.4285 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1332 | 1332 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/136 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4572 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.1254 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 621 | 621 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Certain Sections) | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.4451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 569 | 569 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/142 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.5347 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 423 | 423 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/147 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4570 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.3571 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 333 | 333 | 0 | 1 | 8/9: No litter pickers | N |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 286/3 | 282/5 | 52037423 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.5291 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 499 | 499 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.238 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1776 | 1776 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 37.6832 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2880 | 2880 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4569 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 35.5505 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2717 | 2717 | 0 | 1 | 17/8: No litter pickers | N |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 282/8 | 288/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1068.11 |  | 1068.11 | 0 |  |  |  | 2000M18/115 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 655.36 |  | 655.36 | 0 |  |  |  | 2000M18/122 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 573.92 |  | 573.92 | 0 |  |  |  | 2000M18/126 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 30.39 |  | 30.39 | 0 |  |  |  | 2000M18/131 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 576.73 |  | 576.73 | 0 |  |  |  | 2000M18/135 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 657.36 |  | 657.36 | 0 |  |  |  | 2000M18/140 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 742.11 |  | 742.11 | 0 |  |  |  | 2000M18/142 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4574 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 547.22 |  | 547.22 | 0 |  |  |  | 2000M18/152 | YNE88: M18 J5-6 | YNE88 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 286/3 | 282/5 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 11.06 |  | 11.06 | 0 |  |  |  | 2000M18/157 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 600.55 |  | 600.55 | 0 |  |  |  | 2000M18/162 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 802.66 |  | 802.66 | 0 |  |  |  | 2000M18/167 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE88 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4573 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 278.54 |  | 278.54 | 0 |  |  |  | 2000M18/172 | YNE88: M18 J5-6 | YNE88 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 282/8 | 288/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4575 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys | SB | 121 | 3 | 118 | 0.024793 |  | N |  | 2000M18/137 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 291/3 | 285/8 | 45877638 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4576 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 | 26 gullys cleaned out in total | N |  | 2000M18/137 | YNE89: M18 J6-7 | YNE89 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE89 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4577 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 | 26 gullys cleaned out in total | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE89 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4578 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 424.5916 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys | NB | 108 | 55 | 53 | 0.50926 |  | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4579 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4580 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 CCTV Masts - Check mast breaking system | 4581 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 1 |  | 1 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4582 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 237.2973 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 10 | 9 | 0 | 0.9 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4583 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 197.7477 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 6 | 5 | 1 | 0.83333 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4584 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | 2 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE89 Closure 2 NB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 4585 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 4586 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 4587 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys |  | 2 |  | 2 | 0 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 291/3 | 293/0M18 M62 155/9 EB | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4588 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE89 Closure Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4589 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4590 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB |  |  | 0 | 0 |  | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4591 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB |  |  | 0 | 0 |  | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS | Lane 3 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4592 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 | Completed 1 - not sure which and jobs remain open | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4593 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 | Completed 1 - not sure which and jobs remain open | N/A |  |  | YNE89: M18 J6-7 | YNE89 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4594 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 176.415 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 3680 | 3680 | 0 | 1 |  | N |  |  | YNE89: M18 J6-7 | YNE89 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4595 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 | 11/8: Completed 1 - not sure which and jobs remain open | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4595 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 | 11/8: Completed 1 - not sure which and jobs remain open | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4596 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 | 0 | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 8 | 8 | 0 | 1 |  | N |  | 2000M18/137 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4596 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9 | 9 | 0 | 1 |  | N |  | 2000M18/150 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4596 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 32 | 32 | 0 | 1 |  | N |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4596 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 25 | 25 | 0 | 1 | 0 | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 | Complete - asset issue as all jobs closed yet quants don’t match | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 | Complete - asset issue as all jobs closed yet quants don’t match | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 |  | N |  | 2000M18/185 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 32 | 32 | 0 | 1 |  | N |  | 2000M18/186 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 34 | 34 | 0 | 1 |  | N |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4599 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 16 | 16 | 0 | 1 |  | N |  | 2000M18/188 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4599 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 12 | 12 | 0 | 1 |  | N |  | 2000M18/189 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 35 | 35 | 0 | 1 | Complete - asset issue as all jobs closed yet quants don’t match | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4599 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26 | 26 | 0 | 1 |  | N |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16 | 16 | 0 | 1 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4601 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 191.7554 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 32 | 32 | 0 | 1 |  | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4603 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4603 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4603 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4604 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4605 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.2692 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 109.56 | 109.56 | 0 | 1 |  | N |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4606 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 10.1838 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 491.68 | 491.68 | 0 | 1 | 0 | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4606 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.10791 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5.21 | 5.21 | 0 | 1 |  | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4607 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.7562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 657 | 657 | 0 | 1 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4608 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.5596 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 510 | 510 | 0 | 1 |  | N |  | 2000M18/137 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4607 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.6843 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 59 | 59 | 0 | 1 |  | N |  | 2000M18/138 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4607 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2431 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 604 | 604 | 0 | 1 |  | N |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4608 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3891 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 469 | 469 | 0 | 1 |  | N |  | 2000M18/150 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4607 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.5002 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1839 | 1839 | 0 | 1 |  | N |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4607 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.9047 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1643 | 1643 | 0 | 1 |  | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4609 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.4063 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 960 | 960 | 0 | 1 |  | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4609 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.5221 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 894 | 894 | 0 | 1 |  | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4608 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 2000M18/185 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4608 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.6437 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1809 | 1809 | 0 | 1 |  | N |  | 2000M18/186 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4608 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.3909 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1625 | 1625 | 0 | 1 |  | N |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4610 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.4055 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 995 | 995 | 0 | 1 |  | N |  | 2000M18/188 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4610 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.952 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 839 | 839 | 0 | 1 |  | N |  | 2000M18/189 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4609 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 55.4978 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1944 | 1944 | 0 | 1 |  | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4610 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.2799 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1481 | 1481 | 0 | 1 |  | N |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4611 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 14.0401 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 156.2 | 156.2 | 0 | 1 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4612 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 158.1919 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1759.93 | 1759.93 | 0 | 1 |  | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 2 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4612 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 117.6482 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1308.87 | 1308.87 | 0 | 1 |  | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE89 Closure 1 SB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4613 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4.6258 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 67 | 67 | 0 | 1 |  | N |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4614 | Sweeping - Paved non-running areas - Full Sweep 02 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-12 | 2023-12 | 2023-12-13 | 2023-09-01 | 2023-09-29 | 2023-12-31 |  | 21dys | NB | 7665 |  | 7665 | 0 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4615 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1748.7132 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 36478 | 36478 | 0 | 1 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4616 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.6377 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 813 | 813 | 0 | 1 |  | N |  | 2000M18/133 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.6731 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 510 | 510 | 0 | 1 |  | N |  | 2000M18/137 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4616 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0.77198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 59 | 59 | 0 | 1 |  | N |  | 2000M18/138 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4618 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.903 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 604 | 604 | 0 | 1 |  | N |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Certain Sections) | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4619 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.1366 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 469 | 469 | 0 | 1 | 11/8: No litter resource provided for this closure | N |  | 2000M18/150 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Certain Sections) | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4616 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.0623 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1839 | 1839 | 0 | 1 | 11/8: No litter resource provided for this closure | N |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4616 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.4978 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1643 | 1643 | 0 | 1 |  | N |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 154/7 | 154/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4620 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.5611 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 960 | 960 | 0 | 1 | 11/8: No litter resource provided for this closure | N |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4620 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 34.7262 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2654 | 2654 | 0 | 1 | 11/8: No litter resource provided for this closure | N |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.0094 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 2000M18/185 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6698 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1809 | 1809 | 0 | 1 |  | N |  | 2000M18/186 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.2622 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1625 | 1625 | 0 | 1 |  | N |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually | 291/3 | 285/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4621 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.019 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 995 | 995 | 0 | 1 |  | N |  | 2000M18/188 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4621 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.9779 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 839 | 839 | 0 | 1 |  | N |  | 2000M18/189 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4622 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 42.5637 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3253 | 3253 | 0 | 1 | 11/8: No litter resource provided for this closure | N |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 291/3 | 293/0M18 M62 155/9 EB |  | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4623 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 19.3781 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1481 | 1481 | 0 | 1 |  | N |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 153/0 | 155/7 291/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4624 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 276.06 |  | 276.06 | 0 |  |  |  | 2000M18/145 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 154/7 | 154/2 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4624 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 978.99 |  | 978.99 | 0 |  |  |  | 2000M18/155 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 154/7 | 154/2 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4624 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 1131.58 |  | 1131.58 | 0 |  |  |  | 2000M18/165 | YNE89: M18 J6-7 | YNE89 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 154/7 | 154/2 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4625 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 886.28 |  | 886.28 | 0 |  |  |  | 2000M18/175 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 291/3 | 293/0M18 M62 155/9 EB | No jobs | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4625 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 843.84 |  | 843.84 | 0 |  |  |  | 2000M18/176 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 291/3 | 293/0M18 M62 155/9 EB | No jobs | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4626 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 979.77 |  | 979.77 | 0 |  |  |  | 2000M18/186 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 291/3 | 285/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4626 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 780.54 |  | 780.54 | 0 |  |  |  | 2000M18/187 | YNE89: M18 J6-7 | YNE89 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 291/3 | 285/8 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4627 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 609.96 |  | 609.96 | 0 |  |  |  | 2000M18/189 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 153/0 | 155/7 291/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE89 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4625 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 2118.64 |  | 2118.64 | 0 |  |  |  | 2000M18/191 | YNE89: M18 J6-7 | YNE89 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 291/3 | 293/0M18 M62 155/9 EB | No jobs | 20:00 | 6:00 | Night Shift | Approved | Lane 1 NE Link
YNE89 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4627 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 2457.89 |  | 2457.89 | 0 |  |  |  | 2000M18/196 | YNE89: M18 J6-7 | YNE89 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 153/0 | 155/7 291/6 | No jobs | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4628 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-22 | 2024-1 | 2024-01-23 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 43dys |  | 16 |  | 16 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years | 44/4 | 49/0 | 52037832 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4629 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | EB | 327.87 |  | 327.87 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/132 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE96 Closure 1 EB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4629 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | EB | 111.89 |  | 111.89 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/139 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE96 Closure 1 WB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4630 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 14.0771 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 182.35 | 182.35 | 0 | 1 | 0 aset OS | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4631 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | WB | 391.35 | 0 | 391.35 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE96 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4632 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE96 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4633 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4634 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4635 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4636 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 | 0 | N/A |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4637 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 4642 |  | 4642 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/101 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000A180/102 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 17 |  | 17 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 9 |  | 9 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/113 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 26 |  | 26 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 34 | 34 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 28 |  | 28 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4640 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36 |  | 36 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4641 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 |  | 6 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/127 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4642 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 24 |  | 24 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4642 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36 |  | 36 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4642 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 13 |  | 13 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 10 |  | 10 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/132 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4640 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/133 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4641 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/135 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/139 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 |  | 5 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/151 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4639 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 19 | 0 | 19 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 106 |  | 106 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 106 |  | 106 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4638 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 23 |  | 23 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4642 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 29 |  | 29 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4642 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 19 |  | 19 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/909 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4643 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 8 |  | 8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/101 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4644 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 8 | 0 | 8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/102 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4645 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4645 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4645 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4645 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4646 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4645 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5 |  | 5 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4647 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 99.57 |  | 99.57 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4648 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 78.9 |  | 78.9 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4647 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 47.38 |  | 47.38 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/113 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4647 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 140.84 |  | 140.84 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4649 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 142.48 |  | 142.48 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4650 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 167.38 |  | 167.38 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4648 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 119.52 |  | 119.52 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4648 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 200.04 |  | 200.04 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4648 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 150.53 |  | 150.53 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4650 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 219.6 |  | 219.6 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4650 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 217.38 |  | 217.38 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/909 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4651 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1069 |  | 1069 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4651 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 490 |  | 490 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4652 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 754 |  | 754 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4653 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 571 |  | 571 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4653 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 281 |  | 281 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4653 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 389 |  | 389 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4654 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 228 |  | 228 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 583 |  | 583 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/101 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0449 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 527 | 527 | 0 | 1 |  | N |  | 2000A180/102 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1350 |  | 1350 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.8248 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1395 | 1395 | 0 | 1 |  | N |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 609 |  | 609 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/108 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.7872 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 553 | 553 | 0 | 1 |  | N |  | 2000A180/113 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1805 |  | 1805 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.1299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1791 | 1791 | 0 | 1 |  | N |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1796 |  | 1796 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/124 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1800 |  | 1800 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4658 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 439 |  | 439 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/127 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1782 |  | 1782 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1790 |  | 1790 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 653 |  | 653 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/131 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 320 |  | 320 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/132 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 444 |  | 444 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/133 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4658 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 83 |  | 83 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/135 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 419 |  | 419 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/139 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4657 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 646 |  | 646 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/151 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4656 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.9283 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 628 | 628 | 0 | 1 |  | N |  | 2000A180/153 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 666 |  | 666 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 684 |  | 684 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4655 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 680 |  | 680 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 655 |  | 655 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 688 |  | 688 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/909 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 44/4 | 49/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2.87 |  | 2.87 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/101 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 34.31 |  | 34.31 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/102 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4660 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1829.03 |  | 1829.03 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/105 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 40/7 | 45/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 623.68 |  | 623.68 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1801.26 |  | 1801.26 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 45/8 | 40/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 2 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4662 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 392.48 |  | 392.48 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4663 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 942.24 |  | 942.24 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/128 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 2 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4663 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2762.8 |  | 2762.8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/130 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4664 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 141.6934 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1576.38 | 1576.38 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/151 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE96 Closure 1 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4665 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | EB | 1076 |  | 1076 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2000A180/118 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013788
YNE96 Closure 1 WB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4666 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | WB | 293 |  | 293 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure |  |  | Days | Annually (Sept, Oct) |  |  | 12013787
YNE97 Closure 2 EB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4667 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | EB | 508.35 |  | 508.35 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE97 Closure 2 WB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4668 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | WB | 695.92 |  | 695.92 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/149 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route)
YNE97 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4669 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5 | 5 | 0 | 1 |  | N | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE97 Closure Amey 45170 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 4670 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 8 | 8 | 0 | 1 |  | N |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE97 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4671 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 20dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE97 Closure 2 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4672 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4673 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4674 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4675 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4676 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 136.9613 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2857 | 2857 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 14 |  | 14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/142 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 12 |  | 12 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/145 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/146 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/147 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 10 |  | 10 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/149 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 49 |  | 49 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 45 |  | 45 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 28 |  | 28 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 24 |  | 24 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 8 |  | 8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/160 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 7 |  | 7 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4677 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 10 |  | 10 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4678 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 14 |  | 14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4679 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 12 |  | 12 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4680 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4681 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/145 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4682 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4681 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4682 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4683 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 320.15 |  | 320.15 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4684 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 282.41 |  | 282.41 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4683 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 166.96 |  | 166.96 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4684 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 155.64 |  | 155.64 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4685 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 247 |  | 247 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4686 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 204 |  | 204 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4686 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 457 |  | 457 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4686 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1119 |  | 1119 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 909 |  | 909 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/141 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 484 |  | 484 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/142 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1127 |  | 1127 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/145 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1157 |  | 1157 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/146 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 445 |  | 445 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/147 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 806 |  | 806 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/149 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1800 |  | 1800 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1791 |  | 1791 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1506 |  | 1506 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1364 |  | 1364 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 527 |  | 527 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/160 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 667 |  | 667 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4687 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 491 |  | 491 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/163 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4688 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 643 |  | 643 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/171 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE97 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4689 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 84.6234 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 941.46 | 941.46 | 0 | 1 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/147 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4690 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 540.34 |  | 540.34 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4691 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 3926.45 |  | 3926.45 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4690 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1280.1 |  | 1280.1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4691 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 940.18 |  | 940.18 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4690 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 314.51 |  | 314.51 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/160 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4691 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 482.67 |  | 482.67 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE97 Closure 2 EB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4692 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 70.8086 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 5128 | 5128 | 0 | 1 |  | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 2000A180/155 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 3 |  |  | Annually (Sept, Oct)
Unsure on location Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4693 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 109 |  | 109 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE98: A180 Stallingborough - Great Coates | Unsure on location | Lane 1 Closure | 3 | Yes |  | Every 6 years |  |  | 52037850
YNE98 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4694 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5 | 5 | 0 | 1 |  | N | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE98 Closure Amey 45170 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 4695 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 6 | 6 | 0 | 1 |  | N | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE98: A180 Stallingborough - GreatCoates | YNE98 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE98 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4696 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE98: A180 Stallingborough - GreatCoates | YNE98 Closure | Lane 1 Closure | 3 |  |  | 2 times per year |  |  | On ServiceNow
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4697 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4698 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4699 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4700 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4701 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2290 |  | 2290 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/164 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 14 |  | 14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 |  | 6 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/168 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 35 |  | 35 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 45 |  | 45 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 14 |  | 14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/174 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 15 |  | 15 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/175 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 25 |  | 25 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 19 |  | 19 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 |  | 6 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/186 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4703 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/187 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 |  | 7 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/188 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4702 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 9 |  | 9 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/191 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4704 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 24 |  | 24 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/164 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4704 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 8 |  | 8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4705 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4704 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 14 |  | 14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/188 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4704 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/191 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4706 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4706 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4707 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4707 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4706 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4708 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 368.14 |  | 368.14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4709 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 185.51 |  | 185.51 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4708 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 135.14 |  | 135.14 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4709 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 127.92 |  | 127.92 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4710 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1169 |  | 1169 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4711 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 442 |  | 442 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 652 |  | 652 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/164 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 619 |  | 619 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/167 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 528 |  | 528 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/168 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1816 |  | 1816 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1935 |  | 1935 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 63 |  | 63 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/172 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 490 |  | 490 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/173 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 254 |  | 254 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/174 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 711 |  | 711 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/175 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 857 |  | 857 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 724 |  | 724 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 553 |  | 553 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/186 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4713 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 690 |  | 690 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/187 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 83 |  | 83 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/188 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4712 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 457 |  | 457 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/191 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE98 Closure 1 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4714 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 33.11 |  | 33.11 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/164 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4715 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 4013.74 |  | 4013.74 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/168 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4715 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2652.18 |  | 2652.18 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 EB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4714 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 369.2 |  | 369.2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/182 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4715 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1705.98 |  | 1705.98 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/184 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE98 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4715 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | Missed intervention | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1803.25 |  | 1803.25 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/187 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4716 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4717 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 CCTV Masts - Check mast breaking system | 4718 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure Amey 45170 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4719 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 5 | 5 | 0 | 1 |  | N | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE99 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4720 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 105.4655 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 1 | 4 | -3 | 4 |  | N |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure Amey 45170 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 4721 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 20dys |  | 1 | 1 | 0 | 1 |  | N | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 3 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4722 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 CCTV PTZ Cameras - Clean camera lens | 4723 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 CCTV PTZ Cameras - Check camera functionality | 4724 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 WB NS Amey 45170 CCTV PTZ Cameras - Check data and power supplies | 4725 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually |  |  | On ServiceNow
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4726 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4727 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4728 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4729 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4730 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1171 |  | 1171 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/178 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 15 |  | 15 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 20 |  | 20 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 |  | 6 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/189 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 13 |  | 13 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/190 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 9 |  | 9 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/192 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4731 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 37 |  | 37 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 35 |  | 35 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4732 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 49 |  | 49 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4733 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 8 |  | 8 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/178 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4733 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 38 |  | 38 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4733 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 | Check jobs are closed | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/192 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4733 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4 |  | 4 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4734 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 20 |  | 20 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4734 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 36 |  | 36 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4735 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4736 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/183 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4736 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4735 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 2 |  | 2 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4736 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4736 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 3 |  | 3 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4737 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 158.52 |  | 158.52 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4738 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 22.96 |  | 22.96 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4738 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 276.41 |  | 276.41 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 4739 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 2458 |  | 2458 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4740 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 100 |  | 100 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/178 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4740 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 301 |  | 301 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/180 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4741 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.3703 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 48 | 48 | 0 | 1 |  | N |  | 2000A180/183 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4741 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.2978 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 711 | 711 | 0 | 1 |  | N |  | 2000A180/185 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4741 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.6697 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 689 | 689 | 0 | 1 |  | N |  | 2000A180/189 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4740 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 550 |  | 550 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/190 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4740 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 435 |  | 435 | 0 | 0 | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/192 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4740 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1241 |  | 1241 | 0 |  | Y | Access denied due to Phil Taylors works - were access is available activities have been deffered; where this is outside the activity time constraints the works will not be completed. | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4741 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2318 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1094 | 1094 | 0 | 1 |  | N |  | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4741 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.2798 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 255 | 255 | 0 | 1 |  | N |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE99 Closure 1 WB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4742 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 375.3737 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | WB | 4176.14 | 4176.14 | 0 | 1 |  | N |  | 2000A180/193 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 WB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs raised emailed NH
YNE99 Closure 1 EB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4743 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 625.6713 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | EB | 911.78 | 911.78 | 0 | 1 | No Ditch assets on this route. LW confirmed 10/31/2023 |  |  | 2000A180/195 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | No jobs
YNE100 Closure Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4744 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 15.9129 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 206.13 | 206.13 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE100 Closure Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4744 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 66.8994 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 866.59 | 866.59 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 5 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE100 Closure Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4744 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 149.1443 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1931.96 | 1931.96 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 5 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE100 Closure Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4744 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 239.9815 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 3108.63 | 3108.63 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | 3 times per year (ILM Entire Route) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4745 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4745 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4745 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4745 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4746 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 39.6454 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 827 | 827 | 0 | 1 |  | N |  |  | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept) |  |  | No jobs
YNE100 Closure 1 CW NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4747 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 15 | 15 | 0 | 1 |  | N |  | 2000A160/201 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2000A160/205 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep) |  |  | No jobs
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep) |  |  | No jobs
YNE100 Closure 1 CW NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4747 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 21 | 21 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4748 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4749 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure 1 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4750 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4751 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 13.1316 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 634 | 634 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4752 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 51 | 51 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW OS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4753 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1085 | 1085 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW OS | Lane 2 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4752 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 654 | 654 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4754 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9894 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 455 | 455 | 0 | 1 |  | N |  | 2000A160/201 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.9976 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 105 | 105 | 0 | 1 |  | N |  | 2000A160/205 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.0817 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1404 | 1404 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure 1 CW NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4754 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.4511 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 261 | 261 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4755 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.7081 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1496 | 1496 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE100 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4756 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 591.2298 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 6577.6 | 6577.6 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4757 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4757 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  | N/A |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4757 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4757 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  | N/A |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4758 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 55.9926 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1168 | 1168 | 0 | 1 |  | N |  |  | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 25 | 25 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A160/225 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 41 | 41 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure 1 CW NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4760 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 18 | 18 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 25 | 25 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2000A160/317 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4761 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 701.1056 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 117 | 117 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4762 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4762 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4762 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.1657 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.60066 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 9.5898 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 463 | 463 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.55923 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 27 | 27 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure 1 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4764 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.57995 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 28 | 28 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 25.9112 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1251 | 1251 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 3.4797 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 168 | 168 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4763 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.39353 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 6653.51 | 6653.51 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 351.65 | 351.65 | 0 | 1 |  | N |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 233.14 | 233.14 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 389.64 | 389.64 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 2302.85 | 2302.85 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure 1 CW NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4766 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 1819 | 1819 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 9183.24 | 9183.24 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 3359.14 | 3359.14 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 869.31 | 869.31 | 0 | 1 |  | N |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 119.67 | 119.67 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 4765 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 5 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1790.7 | 1790.7 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5588 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 545 | 545 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.1942 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 252 | 252 | 0 | 1 |  | N |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.2251 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 148 | 148 | 0 | 1 |  | N |  | 2000A160/225 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.6843 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 59 | 59 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7904 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 413 | 413 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.8296 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | EB | 1185 | 1185 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure 1 CW NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4768 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.4234 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | CW | 225 | 225 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.8582 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 1186 | 1186 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5367 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 264 | 264 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.3083 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 256 | 256 | 0 | 1 |  | N |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.2219 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 288 | 288 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6493 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 338 | 338 | 0 | 1 |  | N |  | 2000A160/317 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4767 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.7301 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 551 | 551 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 5 |  |  | Annually (Apr - Sep)
YNE101 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4769 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 996.5353 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 11086.74 | 11086.74 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4769 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 222.664 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2477.2 | 2477.2 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4769 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 207.0958 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2304 | 2304 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE101 Closure CGS 45170 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 4769 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 468.5003 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 5212.2 | 5212.2 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 2 Closure | 5 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 94.6968 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 552 | 552 | 0 | 1 |  | N |  | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45909372 |  |  | Day Shift
YNE102 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 279.7 |  | 279.7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE102 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4772 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 84.31 |  | 84.31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/101 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE102 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4773 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 67.42 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 393 | 393 | 0 | 1 |  | N |  | 4700A162/103 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45909372 |  |  | Day Shift
YNE102 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4772 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 12.37 |  | 12.37 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/103 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE102 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4770 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 44.9672 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 262.12 | 262.12 | 0 | 1 |  | N |  | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45909372 |  |  | Day Shift
YNE102 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4771 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 12.6 |  | 12.6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE102 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4773 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 51.0762 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 297.73 | 297.73 | 0 | 1 |  | N |  | 4700A162/105 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45909372 |  |  | Day Shift
YNE102 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4772 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 102.52 |  | 102.52 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/105 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE102 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4773 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.3811 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-11-07 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 78 | 78 | 0 | 1 |  | N |  | 4700A162/211 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | Days |  |  | Every 2 years |  |  | 45909372 |  |  | Day Shift
YNE102 Closure Amey 45170 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 4774 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure | Lane 1 Closure | N/A |  |  | Every 6 years
YNE102 Closure Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4775 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure | Lane 1 Closure | N/A |  |  | Every 6 years
YNE102 Closure 1 SB NS CGS 45170 Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 4776 | Hedgerows (Habitat) - Maintain habitat integrity, including removal of undesirable species | 0 | 4.8.16 | A40092 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 95.1 |  | 95.1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/101 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 3 years | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4777 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE102 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4778 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4779 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE102 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4780 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4781 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 923 |  | 923 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE102: A162 Ferrybridge | YNE102 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/101 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/210 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/211 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4782 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/220 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4783 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/221 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4784 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 31 |  | 31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4785 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/221 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment | 4786 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/210 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4787 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 763 |  | 763 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4788 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 501 |  | 501 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/101 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4788 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 661 |  | 661 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/103 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4787 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 317 |  | 317 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4788 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 320 |  | 320 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/105 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4787 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1318 |  | 1318 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/210 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4788 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1084 |  | 1084 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/211 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4787 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 371 |  | 371 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/220 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4788 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 409 |  | 409 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/221 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | [5 empty] | Day Shift
YNE102 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4789 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 259.67 |  | 259.67 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/100 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4790 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2382.68 |  | 2382.68 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/103 | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4789 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 780.88 |  | 780.88 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A162/104 | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS Enviroflow 45170 Gullies - Emptying / clear covers | 4791 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 16 |  | 16 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE104 Closure 2 CW OS Enviroflow 45170 Gullies - Emptying / clear covers | 4792 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 22 |  | 22 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE104 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 4793 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45886122
YNE104 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 4794 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years |  |  | 45886122
YNE104 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 4795 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 | 0 | 2 | 0 | 06/09/2023 -TM Cancelled due to closurs not including rbts and so activities not being able to be completed | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years |  |  | 45886122
YNE104 Closure 3 CW NS Enviroflow 45170 Gullies - Emptying / clear covers | 4796 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 18 |  | 18 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE104 Closure 3 CW OS Enviroflow 45170 Gullies - Emptying / clear covers | 4797 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 16 |  | 16 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE104 Closure 2 CW OS CGS 45170 Filter drains - Edge Scrap, clear vegetation/weed/growth cut back to remove build up from edge of carriageway | 4798 | Filter drains - Edge Scrap, clear vegetation/weed/growth cut back to remove build up from edge of carriageway | 0 | 4.3.11.1 | A40019 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | TBC |  |  | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW OS | Lane 2 Closure | 2 |  |  | Every 5 years
YNE104 Closure 2 CW NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4799 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 3 |  | 3 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE104 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4800 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years |  |  | 45886117
YNE104 Closure 3 CW NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4801 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 1 |  | 1 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE104 Closure Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4802 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE104 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4803 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. | N/A |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037899
YNE104 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4804 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. | N/A |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037899
YNE104 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4805 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 | 06/09/2023 -TM Cancelled due to closurs not including rbts and so activities not being able to be completed | N/A |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037899
YNE104 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4806 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 | 06/09/2023 -TM Cancelled due to closurs not including rbts and so activities not being able to be completed | N/A |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037899
YNE104 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4807 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 831 |  | 831 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4808 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 17 |  | 17 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4809 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 22 | 0 | 22 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819000
YNE104 Closure 3 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4810 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 10 |  | 10 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4811 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 888.43 |  | 888.43 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4812 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1468.31 |  | 1468.31 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4812 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 23.26 |  | 23.26 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4813 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1452.29 |  | 1452.29 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 3 CW NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4814 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 590.5 |  | 590.5 | 0 |  | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4815 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 610 | 0 | 610 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037902
YNE104 Closure 1 SB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4816 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 136 | 0 | 136 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. | Y | Access denied due to Tinsley scheme - access not available in year therefore these works will not be completed | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037902
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4817 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 53.26 |  | 53.26 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4818 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 49.96 |  | 49.96 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 EB NS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4819 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15.18 |  | 15.18 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 WB NS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4820 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 490.01 |  | 490.01 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 WB OS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4821 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 119.7 |  | 119.7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4817 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 49.56 |  | 49.56 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4818 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 31.38 |  | 31.38 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4818 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 63.6 |  | 63.6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/4 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Check all Road Restraint System - ILM | 4817 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 222.8 |  | 222.8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4822 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 53.26 |  | 53.26 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4823 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 49.96 |  | 49.96 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4824 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15.18 |  | 15.18 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 WB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4825 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 490.01 |  | 490.01 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 WB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4826 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 105.49 |  | 105.49 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4822 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 49.56 |  | 49.56 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4823 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 17.77 |  | 17.77 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4823 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 63.6 |  | 63.6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/4 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4822 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 222.8 |  | 222.8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Enviroflow 45170 Gullies - Emptying / clear covers | 4827 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB OS Enviroflow 45170 Gullies - Emptying / clear covers | 4828 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB OS | Lane 2 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4829 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 WB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4830 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 | 23/8: complete | N |  | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4831 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4831 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM Every 2 years
YNE105 Closure 1 SB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4832 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4833 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4833 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/11 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4833 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 10 |  | 10 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4833 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 WB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4834 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 5 |  | 5 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/16 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 WB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4834 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 9 |  | 9 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4832 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4832 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/4 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4832 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 WB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 4834 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 0 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 |  | 6 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/7 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 4835 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 SB NS Amey 45170 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 4836 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 0 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Every 2 years
YNE105 Closure 1 EB NS Amey 45170 Bollards - Clean all illuminated and non-illuminated bollards | 4837 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually
YNE105 Closure 1 EB NS Amey 45170 Bollards - Clean all illuminated and non-illuminated bollards | 4837 | Bollards - Clean all illuminated and non-illuminated bollards | 0 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually
YNE105 Closure Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4838 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 69 |  | 69 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE105: A638 Redhouse | YNE105 Closure | Lane 1 Closure | 2 |  |  | Every 3 years
YNE105 Closure Amey 45170 Electrical Testing - Network cabling and electrical components | 4839 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE105: A638 Redhouse | YNE105 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4840 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4841 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 EB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4842 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 | 23/8: closure didn’t cover assets | N/A |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4843 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE105: A638 Redhouse | YNE105 Closure 1 WB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4844 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 459 |  | 459 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE105: A638 Redhouse | YNE105 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4845 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4846 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4846 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/11 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4846 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 11 |  | 11 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4846 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 11 |  | 11 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4847 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 8 |  | 8 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/16 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4847 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 9 |  | 9 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4845 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4845 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/4 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4845 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4847 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 6 |  | 6 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/7 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4848 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 204 |  | 204 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4849 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4850 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4850 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/12 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4851 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1 |  | 1 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4849 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 101.65 |  | 101.65 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 224.78 |  | 224.78 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/11 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 67.9 |  | 67.9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/12 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 462.66 |  | 462.66 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 675.35 |  | 675.35 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 WB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4853 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 119.73 |  | 119.73 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/16 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 EB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4852 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 58.31 |  | 58.31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/9 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE105 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4854 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 189 |  | 189 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/1 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 315 |  | 315 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/10 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 214 |  | 214 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/11 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 72 |  | 72 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/12 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 380 |  | 380 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/13 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 266 |  | 266 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/14 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4856 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 153 |  | 153 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/16 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4856 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1274 |  | 1274 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/2 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4854 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 113 |  | 113 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/3 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4854 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 126 |  | 126 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/4 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4854 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 454 |  | 454 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/5 | YNE105: A638 Redhouse | YNE105 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 WB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4856 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 236 |  | 236 | 0 | 23/8: closure didn’t cover assets | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/7 | YNE105: A638 Redhouse | YNE105 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE105 Closure 1 EB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4855 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 72 |  | 72 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A638/9 | YNE105: A638 Redhouse | YNE105 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4857 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 26 | 26 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE106 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4858 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 | 1/8: complete | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE106 Closure 2 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4859 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 285.6343 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 37 | 37 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4860 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 | 2/8: complete | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route
YNE106 Closure 2 NB NS Enviroflow 45170 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 4861 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 181.5708 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 147 | 147 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) | 4/2 | 8/7 | 52031354 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB OS Enviroflow 45170 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 4862 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 228.5075 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 185 | 185 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB OS | Lane 2 Closure | 2 |  |  | 2 times per year (ILM Certain Sections) |  |  | 52031354
YNE106 Closure 1 SB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4863 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 23.1595 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 300 | 300 | 0 | 1 |  | N |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE106 Closure Amey 45170 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 4864 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 11.9847 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE106 Closure Amey 45170 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 4865 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 11.9847 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE106 Closure Amey 45170 CCTV Masts - Check mast breaking system | 4866 | CCTV Masts - Check mast breaking system | 63.9185 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE106 Closure Vaisala 45170 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 4867 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | On ServiceNow
YNE106 Closure Amey 45170 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4868 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 79.0991 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE106 Closure Amey 45170 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 4869 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 785.8827 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Every 6 years |  |  | On ServiceNow
YNE106 Closure Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4870 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually |  |  | On ServiceNow
YNE106 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4871 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 4237.52 |  | 4237.52 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE106 Closure 2 NB NS CGS 45170 Woodland - Thin / coppice | 4872 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 17701.16 |  | 17701.16 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Woodland - Thin / coppice | 4873 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 3985.28 |  | 3985.28 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/45 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Woodland - Thin / coppice | 4873 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 3926.04 |  | 3926.04 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/46 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Woodland - Thin / coppice | 4873 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 9751.14 |  | 9751.14 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/47 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45170 Woodland - Thin / coppice | 4874 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 951.54 |  | 951.54 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Woodland - Thin / coppice | 4872 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 13564.27 |  | 13564.27 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4875 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 2321.96 |  | 2321.96 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE106 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4875 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 28152.84 |  | 28152.84 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/51 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE106 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4875 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 2006.05 |  | 2006.05 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years
YNE106 Closure 3 NB NS CGS 45170 Woodland - Thin / coppice | 4876 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 1307.12 |  | 1307.12 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Woodland - Thin / coppice | 4876 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 9396.16 |  | 9396.16 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4877 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4878 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4879 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4880 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4881 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 243.4814 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 5079 | 5079 | 0 | 1 |  | N |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4882 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4883 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4884 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/101 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4883 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4884 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 12 | 12 | 0 | 1 |  | N |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4883 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4885 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/3 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4885 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4886 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/44 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4886 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/45 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4886 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 20 | 20 | 0 | 1 |  | N |  | 4400A1M/46 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4886 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 22 | 22 | 0 | 1 |  | N |  | 4400A1M/47 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4887 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 19 | 19 | 0 | 1 |  | N |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4887 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4885 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 21 | 21 | 0 | 1 |  | N |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4884 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13 | 13 | 0 | 1 |  | N |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4884 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 17 | 17 | 0 | 1 |  | N |  | 4400A1M/51 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4883 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 28 | 28 | 0 | 1 |  | N |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4884 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 19 | 19 | 0 | 1 |  | N |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/8 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4889 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/100 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4890 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/100 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4891 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/3 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4891 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4890 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4892 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4892 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4893 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 1.0197 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 49.23 | 49.23 | 0 | 1 |  | N |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.70898 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 34.23 | 34.23 | 0 | 1 |  | N |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.24482 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11.82 | 11.82 | 0 | 1 |  | N |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.2595 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1130 | 1130 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.1648 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 286 | 286 | 0 | 1 |  | N |  | 4400A1M/100 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 4400A1M/101 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.3998 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1240 | 1240 | 0 | 1 |  | N |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.6151 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 582 | 582 | 0 | 1 |  | N |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.2155 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1794 | 1794 | 0 | 1 |  | N |  | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4897 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9919 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 350 | 350 | 0 | 1 |  | N |  | 4400A1M/3 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4897 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.3093 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1447 | 1447 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4898 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.3263 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 712 | 712 | 0 | 1 |  | N |  | 4400A1M/44 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4898 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.2342 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 989 | 989 | 0 | 1 |  | N |  | 4400A1M/45 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4898 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3012 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1797 | 1797 | 0 | 1 |  | N |  | 4400A1M/46 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4898 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3583 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1799 | 1799 | 0 | 1 |  | N |  | 4400A1M/47 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4899 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.3378 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1448 | 1448 | 0 | 1 |  | N |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4899 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.0204 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 351 | 351 | 0 | 1 |  | N |  | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4897 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.2155 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1794 | 1794 | 0 | 1 |  | N |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.4725 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1803 | 1803 | 0 | 1 |  | N |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.6306 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1143 | 1143 | 0 | 1 |  | N |  | 4400A1M/51 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2749 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 465 | 465 | 0 | 1 |  | N |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.6143 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 617 | 617 | 0 | 1 |  | N |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE106 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4900 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3297 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1798 | 1798 | 0 | 1 |  | N |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4900 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.545 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1140 | 1140 | 0 | 1 |  | N |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4900 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 558 | 558 | 0 | 1 |  | N |  | 4400A1M/8 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4901 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 0 | 0 | 0 | 0 | 10/3/2023: Removed from programme per Tim Haskell email as scheme completed | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Sept, Oct)
YNE107 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4412 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 2850.31 |  | 2850.31 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/44 | YNE106: A1M J34-35 | YNE107 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013789
YNE106 Closure 3 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4902 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-22 | 2024-1 | 2024-01-23 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 2651 |  | 2651 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 8/3 | 12/2 | 12013795 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4903 | Sweeping - Paved non-running areas - Full Sweep 02 | 52.0705 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6991 | 6991 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year
YNE106 Closure Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4904 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 769.2747 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16047 | 16047 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 2 |  |  | Annually
YNE106 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4905 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.7854 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1130 | 1130 | 0 | 1 |  | N |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4905 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.7422 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 286 | 286 | 0 | 1 |  | N |  | 4400A1M/100 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4906 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.0094 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 4400A1M/101 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4907 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.2247 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1240 | 1240 | 0 | 1 |  | N |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4908 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.6152 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 582 | 582 | 0 | 1 |  | N |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4905 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.4735 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1794 | 1794 | 0 | 1 |  | N |  | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4909 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.5796 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 350 | 350 | 0 | 1 |  | N |  | 4400A1M/3 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4909 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.9332 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1447 | 1447 | 0 | 1 |  | N |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4910 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.3161 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 712 | 712 | 0 | 1 |  | N |  | 4400A1M/44 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4910 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.9405 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 989 | 989 | 0 | 1 |  | N |  | 4400A1M/45 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4910 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5128 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1797 | 1797 | 0 | 1 |  | N |  | 4400A1M/46 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4910 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5389 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1799 | 1799 | 0 | 1 |  | N |  | 4400A1M/47 | YNE106: A1M J34-35 | YNE106 Closure 3 SB NS | Lane 1 Closure | 2 | No |  | Annually | 11/8 | 8/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4911 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.9463 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1448 | 1448 | 0 | 1 |  | N |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4911 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.5926 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 351 | 351 | 0 | 1 |  | N |  | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | 2 | No |  | Annually | 8/9 | 4/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4909 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.4735 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1794 | 1794 | 0 | 1 |  | N |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 2 | No |  | Annually | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4906 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5913 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1803 | 1803 | 0 | 1 |  | N |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4906 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9555 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1143 | 1143 | 0 | 1 |  | N |  | 4400A1M/51 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE106 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4907 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.0843 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 465 | 465 | 0 | 1 |  | N |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4908 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.0731 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 617 | 617 | 0 | 1 |  | N |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4912 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.5259 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1798 | 1798 | 0 | 1 |  | N |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4912 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9163 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1140 | 1140 | 0 | 1 |  | N |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4912 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 558 | 558 | 0 | 1 |  | N |  | 4400A1M/8 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 2 | No |  | Annually | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4913 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 907.54 |  | 907.54 | 0 |  |  |  | 4400A1M/2 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928143
YNE106 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4914 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 509.59 |  | 509.59 | 0 |  |  |  | 4400A1M/4 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 4/2 | 8/7 | 45928143 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4915 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 946.7 |  | 946.7 | 0 |  |  |  | 4400A1M/48 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 8/9 | 4/5 | 45928143 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4915 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 867.86 |  | 867.86 | 0 |  |  |  | 4400A1M/49 | YNE106: A1M J34-35 | YNE106 Closure 2 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 8/9 | 4/5 | 45928143 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4914 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | NB | 59.08 |  | 59.08 | 0 |  |  |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually | 4/2 | 8/7 | 45928143 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 SB NS Amey 45170 Ditches - Clean ditches by removing all material that could impair operation - ILM | 4916 | Ditches - Clean ditches by removing all material that could impair operation - ILM | 0 | 4.3.5 | A40014 |  | 0 | Amey | 0500 - Drainage & Service Ducts |  |  |  | 2023-09-01 | 2023-09-29 | N/A | Removed following updated instruction GC-928 | 21dys | SB | 59.49 |  | 59.49 | 0 |  |  |  | 4400A1M/50 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | Days | TBC | Days | ILM Annually |  |  | 45928143
YNE107 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4917 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | 4/8: No gullies present | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | No jobs
YNE107 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4918 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 301.074 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 39 | 39 | 0 | 1 |  | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route |  |  | No jobs
YNE107 Closure Amey 45170 BC - Lamps (LED) for Road Lighting | 4919 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 2 |  |  | Every 6 years |  |  | No jobs
YNE107 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4920 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 3067 |  | 3067 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years |  |  | No jobs
YNE107 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4921 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 5416.57 |  | 5416.57 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years |  |  | No jobs
YNE107 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4920 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 192.23 |  | 192.23 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years |  |  | No jobs
YNE107 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4921 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 1074.88 |  | 1074.88 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years |  |  | No jobs
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4922 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4923 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4924 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4925 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4926 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 80.0099 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 1669 | 1669 | 0 | 1 |  | N |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 27 | 27 | 0 | 1 |  | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4928 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/41 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4928 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 25 | 25 | 0 | 1 |  | N |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4928 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 7 | 7 | 0 | 1 |  | N |  | 4400A1M/43 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4928 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 25 | 25 | 0 | 1 |  | N |  | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4928 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/70 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4927 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4929 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4930 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4929 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4931 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4931 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4931 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4931 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4932 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.32291 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 15.59 | 15.59 | 0 | 1 |  | N |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4933 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.1336 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 103.01 | 103.01 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4932 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.53935 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 26.04 | 26.04 | 0 | 1 |  | N |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4933 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.63111 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 30.47 | 30.47 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.0222 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1507 | 1507 | 0 | 1 |  | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.5025 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 508 | 508 | 0 | 1 |  | N |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4935 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0449 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 527 | 527 | 0 | 1 |  | N |  | 4400A1M/41 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4935 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 44.4781 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1558 | 1558 | 0 | 1 |  | N |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4935 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.3288 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 607 | 607 | 0 | 1 |  | N |  | 4400A1M/43 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4935 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7309 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 516 | 516 | 0 | 1 |  | N |  | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.1028 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 494 | 494 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4935 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.0457 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 492 | 492 | 0 | 1 |  | N |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3606 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 468 | 468 | 0 | 1 |  | N |  | 4400A1M/70 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1053 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 389 | 389 | 0 | 1 |  | N |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4934 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep)
YNE107 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4936 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 275.752 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3067.82 | 3067.82 | 0 | 1 |  | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4936 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 200.2672 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2228.03 | 2228.03 | 0 | 1 |  | N |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4936 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 117.9332 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1312.04 | 1312.04 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4412 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 1553 |  | 1553 | 0 |  | Y | 20/9: We are not able to link the jobs to the plots. NH are aware and working on this. Working to identify daytime opportunities for wildflower. | 4400A1M/43 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Sept, Oct)
YNE107 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4412 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 1403 |  | 1403 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) |  |  | 12013797
YNE107 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4937 | Sweeping - Paved non-running areas - Full Sweep 02 | 51.577 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 6924.75 | 6924.75 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year |  |  | 52033905
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 4938 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 11.6611 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 486.5 | 486.5 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually
YNE107 Closure 1 NB OS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 4939 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 11.6611 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 486.5 | 486.5 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4940 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 781.3552 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16299 | 16299 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4941 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 59.8483 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4574 | 4574 | 0 | 1 | 4/8: OS completed | N |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4941 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 35.7991 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2736 | 2736 | 0 | 1 | 4/8: OS completed | N |  | 4400A1M/11 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE107 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4942 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.8955 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 527 | 527 | 0 | 1 |  | N |  | 4400A1M/41 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE107 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4942 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.3856 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1558 | 1558 | 0 | 1 |  | N |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE107 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4942 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.9423 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 607 | 607 | 0 | 1 |  | N |  | 4400A1M/43 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually
YNE107 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4943 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.7516 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 516 | 516 | 0 | 1 |  | N |  | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4944 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.4637 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 494 | 494 | 0 | 1 |  | N |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4943 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.4376 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 492 | 492 | 0 | 1 |  | N |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4944 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 6.1235 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 468 | 468 | 0 | 1 |  | N |  | 4400A1M/70 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4944 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5.0899 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 389 | 389 | 0 | 1 | not completed - for 2nd visit | N |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4941 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 26.0642 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1992 | 1992 | 0 | 1 |  | N |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually
YNE108 Closure 1 NB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4945 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1.4197 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18.39 | 18.39 | 0 | 1 |  | N |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 3 times per year (ILM Entire Route) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB OS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 4946 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 5.5135 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 71.42 | 71.42 | 0 | 1 |  | N |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | 3 times per year (ILM Entire Route)
YNE108 Closure Amey 45170 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 4947 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE108 Closure Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 4948 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE108 Closure Amey 45170 BC - Lamps (LED) for Road Lighting | 4949 | BC - Lamps (LED) for Road Lighting | 0 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 2 |  |  | Every 6 years
YNE108 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4950 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 2800 |  | 2800 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4950 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 8502.97 |  | 8502.97 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4950 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 7922.85 |  | 7922.85 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4951 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 15801.41 |  | 15801.41 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4951 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 738.2 |  | 738.2 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/39 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4950 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 529.74 |  | 529.74 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4951 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 1478.06 |  | 1478.06 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4952 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4953 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4954 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4955 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4956 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 135.4272 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 43dys |  | 2825 | 2825 | 0 | 1 |  | N |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4957 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/14 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/16 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400A1M/19 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/32 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/33 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 9 | 9 | 0 | 1 |  | N |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/35 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/36 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/38 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/39 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/40 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4960 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4960 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4961 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4962 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4962 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4962 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4962 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4962 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4963 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.49213 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 23.76 | 23.76 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4964 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 2.0313 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 98.07 | 98.07 | 0 | 1 |  | N |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4963 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.82767 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 39.96 | 39.96 | 0 | 1 |  | N |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.792 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 343 | 343 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6778 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 339 | 339 | 0 | 1 |  | N |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5946 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 231 | 231 | 0 | 1 |  | N |  | 4400A1M/14 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.9258 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 733 | 733 | 0 | 1 |  | N |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8499 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 310 | 310 | 0 | 1 |  | N |  | 4400A1M/16 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.1069 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 319 | 319 | 0 | 1 |  | N |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.8639 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 941 | 941 | 0 | 1 |  | N |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.6037 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1072 | 1072 | 0 | 1 |  | N |  | 4400A1M/19 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.3296 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 572 | 572 | 0 | 1 |  | N |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5009 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 578 | 578 | 0 | 1 |  | N |  | 4400A1M/32 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.2326 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1059 | 1059 | 0 | 1 |  | N |  | 4400A1M/33 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.6061 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 967 | 967 | 0 | 1 |  | N |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.4503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 296 | 296 | 0 | 1 |  | N |  | 4400A1M/35 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.9641 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 314 | 314 | 0 | 1 |  | N |  | 4400A1M/36 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.0971 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 739 | 739 | 0 | 1 |  | N |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5661 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 4400A1M/38 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.363 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 363 | 363 | 0 | 1 |  | N |  | 4400A1M/39 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.4209 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 330 | 330 | 0 | 1 |  | N |  | 4400A1M/40 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8214 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 309 | 309 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.9927 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 315 | 315 | 0 | 1 |  | N |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.9854 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 630 | 630 | 0 | 1 |  | N |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.0139 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 631 | 631 | 0 | 1 |  | N |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4965 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5302 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 544 | 544 | 0 | 1 |  | N |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4966 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.6159 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 547 | 547 | 0 | 1 |  | N |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 61.3189 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 682.19 | 682.19 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4.3145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 48 | 48 | 0 | 1 |  | N |  | 4400A1M/14 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 253.2474 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2817.45 | 2817.45 | 0 | 1 |  | N |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 99.3952 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1105.8 | 1105.8 | 0 | 1 |  | N |  | 4400A1M/16 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 93.9266 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1044.96 | 1044.96 | 0 | 1 |  | N |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 338.6412 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3767.48 | 3767.48 | 0 | 1 |  | N |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4967 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 205.0464 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2281.2 | 2281.2 | 0 | 1 |  | N |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4968 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 23.23 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 258.44 | 258.44 | 0 | 1 |  | N |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4968 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 31.7547 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 353.28 | 353.28 | 0 | 1 |  | N |  | 4400A1M/35 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4968 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 22.5432 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 250.8 | 250.8 | 0 | 1 |  | N |  | 4400A1M/36 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4968 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 9.4991 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 105.68 | 105.68 | 0 | 1 |  | N |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 4969 | Sweeping - Paved non-running areas - Full Sweep 02 | 86.9262 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-30 | Complete |  | 43dys | NB | 11670.75 | 11670.75 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 4970 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 118.4089 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4940 | 4940 | 0 | 1 | 7/8: No litter pickers | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB OS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 4971 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 118.4089 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4940 | 4940 | 0 | 1 | 7/8: No litter pickers | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 4972 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1156.9561 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 24134 | 24134 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.4116 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1025 | 1025 | 0 | 1 |  | N |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.4356 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 339 | 339 | 0 | 1 |  | N |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.6506 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 279 | 279 | 0 | 1 |  | N |  | 4400A1M/14 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 46.4498 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3550 | 3550 | 0 | 1 |  | N |  | 4400A1M/15 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.5145 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1415 | 1415 | 0 | 1 |  | N |  | 4400A1M/16 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.8472 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1364 | 1364 | 0 | 1 |  | N |  | 4400A1M/17 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 61.6147 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4709 | 4709 | 0 | 1 |  | N |  | 4400A1M/18 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.0265 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1072 | 1072 | 0 | 1 |  | N |  | 4400A1M/19 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4973 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 37.343 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2854 | 2854 | 0 | 1 |  | N |  | 4400A1M/20 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.5628 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 578 | 578 | 0 | 1 |  | N |  | 4400A1M/32 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.8564 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1059 | 1059 | 0 | 1 |  | N |  | 4400A1M/33 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.0285 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1225 | 1225 | 0 | 1 |  | N |  | 4400A1M/34 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.4918 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 649 | 649 | 0 | 1 |  | N |  | 4400A1M/35 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3927 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 565 | 565 | 0 | 1 |  | N |  | 4400A1M/36 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.0564 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 845 | 845 | 0 | 1 |  | N |  | 4400A1M/37 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.0094 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 230 | 230 | 0 | 1 |  | N |  | 4400A1M/38 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.7497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 363 | 363 | 0 | 1 |  | N |  | 4400A1M/39 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4974 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.3179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 330 | 330 | 0 | 1 |  | N |  | 4400A1M/40 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4975 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.0431 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 309 | 309 | 0 | 1 |  | N |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4976 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.1216 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 315 | 315 | 0 | 1 |  | N |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4975 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.2432 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 630 | 630 | 0 | 1 |  | N |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4976 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 8.2563 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 631 | 631 | 0 | 1 |  | N |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4975 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.1179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 544 | 544 | 0 | 1 |  | N |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 3 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4976 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 7.1572 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 547 | 547 | 0 | 1 |  | N |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 3 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4977 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4978 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 22 | 22 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4977 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4978 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually for ILM Sections Within the Route | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4979 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 29883.67 |  | 29883.67 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4979 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 6953.34 |  | 6953.34 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4980 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 9638.23 |  | 9638.23 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Woodland - Thin / coppice | 4979 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | NB | 3686.26 |  | 3686.26 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Woodland - Thin / coppice | 4980 | Woodland - Thin / coppice | 0 | 4.8.2 | A40071 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Removed following GC-898 | 21dys | SB | 2014.79 |  | 2014.79 | 0 |  | Y | Woodland removed from Service Plan pending update via CEMAR for sites to be attended in year. | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | Days |  | Days | Every 7 years | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4981 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4982 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4983 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 4984 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 4985 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 101.2948 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys |  | 2113 | 2113 | 0 | 1 |  | N |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept)
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4986 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400A1M/25 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/26 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4400A1M/28 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 13 | 13 | 0 | 1 |  | N |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 18 | 18 | 0 | 1 |  | N |  | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/31 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4400A1M/64 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4987 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4988 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 16 | 16 | 0 | 1 |  | N |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4989 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4990 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4990 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4990 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4990 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4991 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1 | 1 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 4992 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0.83036 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 40.09 | 40.09 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/25 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 401 | 401 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.1771 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 987 | 987 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2318 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1094 | 1094 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.3239 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 817 | 817 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.531 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 509 | 509 | 0 | 1 |  | N |  | 4400A1M/25 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.2529 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 184 | 184 | 0 | 1 |  | N |  | 4400A1M/26 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.589 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 476 | 476 | 0 | 1 |  | N |  | 4400A1M/27 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.9805 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 840 | 840 | 0 | 1 |  | N |  | 4400A1M/28 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.7456 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1112 | 1112 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.2056 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 988 | 988 | 0 | 1 |  | N |  | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.5914 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 371 | 371 | 0 | 1 | 31/7: Evidence captured on Do-forms only, completed 20/5--24/4. VRS only strimmed to 22/5. Jobs closed 52032690, 52032691 | N |  | 4400A1M/31 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.7056 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 375 | 375 | 0 | 1 |  | N |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.792 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 343 | 343 | 0 | 1 |  | N |  | 4400A1M/64 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4993 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.7252 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 761 | 761 | 0 | 1 |  | N |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4994 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.0279 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1262 | 1262 | 0 | 1 |  | N |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 |  |  | Annually (Apr - Sep) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4995 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 118.5156 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1318.52 | 1318.52 | 0 | 1 |  | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4995 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 349.1542 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3884.44 | 3884.44 | 0 | 1 |  | N |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4995 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 475.5294 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 5290.4 | 5290.4 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4996 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 57.8322 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 643.4 | 643.4 | 0 | 1 |  | N |  | 4400A1M/26 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4996 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 131.833 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1466.68 | 1466.68 | 0 | 1 |  | N |  | 4400A1M/27 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4996 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 29.5327 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 328.56 | 328.56 | 0 | 1 |  | N |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4997 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-24 | 2024-1 | 2024-01-25 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | NB | 2248 |  | 2248 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/22 | YNE109: A1M J37-38 | YNE108 Closure 1 NB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 14/7 | 20/4 | 12013794 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45170 Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 4998 | Wildflower Grasslands - Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 0 | 4.8.11 | A40087 |  | 0 | CGS | 3000 - Landscape and Ecology | 2024-01-25 | 2024-1 | 2024-01-26 | 2023-09-01 | 2023-09-29 | 2023-11-30 |  | 21dys | SB | 3178 |  | 3178 | 0 |  | Y | Issues with jobs and inability to plot onto a map delayed progress with Wildflower works - as reported in weekly report | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure |  |  | Nights | Annually (Sept, Oct) | 285/8 | 19/9 | 12013805 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45170 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 4999 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 2.8997 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 42 | 42 | 0 | 1 | No litter pickers | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Sweeping - Paved non-running areas - Full Sweep 02 | 5000 | Sweeping - Paved non-running areas - Full Sweep 02 | 65.0005 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8727 | 8727 | 0 | 1 |  | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | 2 times per year | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 5001 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 93.3729 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3895.5 | 3895.5 | 0 | 1 |  | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS Amey 45170 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 5002 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 93.3729 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 3895.5 | 3895.5 | 0 | 1 | No litter pickers | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 2 |  |  | Annually | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 5003 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 478.6214 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 9984 | 9984 | 0 | 1 | No litter pickers | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 |  |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5004 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.5053 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 1720 | 1720 | 0 | 1 |  | N |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5004 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 63.7475 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 4872 | 4872 | 0 | 1 |  | N |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5004 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 83.5443 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6385 | 6385 | 0 | 1 |  | N |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5004 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.69 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 817 | 817 | 0 | 1 |  | N |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5004 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.66 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 509 | 509 | 0 | 1 |  | N |  | 4400A1M/25 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | Annually | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.8208 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 827 | 827 | 0 | 1 |  | N |  | 4400A1M/26 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.4231 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1943 | 1943 | 0 | 1 |  | N |  | 4400A1M/27 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.9909 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 840 | 840 | 0 | 1 |  | N |  | 4400A1M/28 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.8416 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1440 | 1440 | 0 | 1 |  | N |  | 4400A1M/29 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.9274 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 988 | 988 | 0 | 1 |  | N |  | 4400A1M/30 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5005 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.8543 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 371 | 371 | 0 | 1 |  | N |  | 4400A1M/31 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | Annually | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5006 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.9067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 375 | 375 | 0 | 1 |  | N |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 3 times per year (ILM Certain Sections) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5007 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 4.488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 343 | 343 | 0 | 1 | only slips closed | N |  | 4400A1M/64 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 3 times per year (ILM Certain Sections) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5006 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 9.9573 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 761 | 761 | 0 | 1 | only slips closed | N |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45170 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5007 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 16.5126 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | SB | 1262 | 1262 | 0 | 1 | 0 | N |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 2 | No |  | 2 times per year (ILM Certain Sections) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 190.91 |  | 190.91 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 20.389 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 118.85 | 118.85 | 0 | 1 | 23/8: Awaiting evidence | N |  | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 99.82 |  | 99.82 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 376.65 |  | 376.65 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 107.49 |  | 107.49 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 151.12 |  | 151.12 | 0 | only slips closed | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 343.77 |  | 343.77 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 348.42 |  | 348.42 | 0 | only slips closed | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 324.08 |  | 324.08 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 310.94 |  | 310.94 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 155.69 |  | 155.69 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 249.42 |  | 249.42 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 75.42 |  | 75.42 | 0 | only slips closed | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 496.93 |  | 496.93 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 789.11 |  | 789.11 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5008 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 75.97 |  | 75.97 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 156.92 |  | 156.92 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 114.38 |  | 114.38 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 602.66 |  | 602.66 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5009 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 153.97 |  | 153.97 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/383 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 231.4 |  | 231.4 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 848.4 |  | 848.4 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 178.07 |  | 178.07 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 79.05 |  | 79.05 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 105.31 |  | 105.31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 21.75 |  | 21.75 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/633 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 165.35 |  | 165.35 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 71.9 |  | 71.9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 93.18 |  | 93.18 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 38.16 |  | 38.16 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/643 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 92.65 |  | 92.65 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 45.29 |  | 45.29 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 211.96 |  | 211.96 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 303.86 |  | 303.86 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 132.17 |  | 132.17 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 82.98 |  | 82.98 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 82.21 |  | 82.21 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/658 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 91.53 |  | 91.53 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 597.84 |  | 597.84 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 25.43 |  | 25.43 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 51.39 |  | 51.39 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 2.62 |  | 2.62 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 54.27 |  | 54.27 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5011 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 368.4 |  | 368.4 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 42.55 |  | 42.55 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5010 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 77.55 |  | 77.55 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/694 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 54 |  | 54 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 74 |  | 74 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 5014 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually for ILM Sections Within the Route | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 5015 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Annually for ILM Sections Within the Route
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 5014 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually for ILM Sections Within the Route | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5012 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5013 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 39 |  | 39 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 62 |  | 62 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5017 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5016 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/694 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE110 Closure 1 NB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5018 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 172 |  | 172 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 NB NS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5019 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | NB | 418 |  | 418 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5018 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 57 |  | 57 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 SB NS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5020 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | SB | 65 |  | 65 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5021 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 92 |  | 92 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 SB NS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5020 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | SB | 180 |  | 180 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years (May - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5021 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 242 |  | 242 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 SB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5021 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 197 |  | 197 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 SB OS CGS 45170 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5021 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 124 |  | 124 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years (May - Sept)
YNE110 Closure 1 SB NS Amey 45170 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 5022 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 83.86 |  | 83.86 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 times per year (ILM Entire Route) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 | 0 | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5024 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 8 | 8 | 0 | 1 | 23/8: Only 3 catchpts found | N |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5024 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | NB | 13 | 5 | 8 | 0.38462 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5024 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 NB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5024 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5023 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5025 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys | SB | 25 |  | 25 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5026 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5025 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5026 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5025 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5025 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5026 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5025 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5026 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE110 Closure 1 SB NS Amey 45170 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 5027 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 | No TM required |  | Every 2 years | 290/2 | 285/5 | 52037778 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45170 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5028 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 53 |  | 53 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years | 290/2 | 285/5 | 52037779 | 20:00 | 6:00 | Night Shift | Approved | 0
TBC Amey 45170 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5029 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | TBC | Lane 1 Closure | 3 | Yes on slips |  | Every 3 years |  |  | 52037776
YNE110 Closure 1 SB NS Amey 45170 BC - Lamps (LED) for Illuminated Signs and Bollards | 5030 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 | No TM required |  | Every 2 years | 290/2 | 285/5 | 52037777 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS Amey 45170 Electrical Testing - Network cabling and electrical components | 5031 | Electrical Testing - Network cabling and electrical components | 0 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | 2024-01-29 | 2024-1 | 2024-01-30 | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 | Yes |  | Every 6 years | 290/2 | 285/5 | 52037728 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5032 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB |  |  | 0 | 0 |  | N/A |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5033 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB |  |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5034 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 | 0 | N/A |  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5035 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB |  |  | 0 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 5036 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2813 |  | 2813 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 5037 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 3 |  | 3 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 17 | 17 | 0 | 1 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 12 |  | 12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 9 |  | 9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 9 |  | 9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 24 |  | 24 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 27 |  | 27 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5038 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 17 |  | 17 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 15 |  | 15 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/643 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/658 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 11 |  | 11 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 12 |  | 12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 9 |  | 9 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 12 |  | 12 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 11 |  | 11 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5039 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 37 |  | 37 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 12 |  | 12 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 4 |  | 4 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 2 |  | 2 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5040 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 18 |  | 18 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 12 |  | 12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5041 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5042 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5043 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5043 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 636.78 |  | 636.78 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 89.44 |  | 89.44 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/309 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 136.42 |  | 136.42 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 55.3 |  | 55.3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 348.12 |  | 348.12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 22.77 |  | 22.77 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 89.64 |  | 89.64 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5044 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 84.77 |  | 84.77 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 35.04 |  | 35.04 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 196.31 |  | 196.31 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 50.53 |  | 50.53 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 64.87 |  | 64.87 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 27.86 |  | 27.86 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 220.06 |  | 220.06 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 134.97 |  | 134.97 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 109.62 |  | 109.62 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1093.02 |  | 1093.02 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5045 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1336.02 |  | 1336.02 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5046 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 364.46 |  | 364.46 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5046 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 426.41 |  | 426.41 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5047 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 244.6 |  | 244.6 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 5047 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 3 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 68.35 |  | 68.35 | 0 | 0 | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 188 |  | 188 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.6102 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 792 | 792 | 0 | 1 |  | N |  | 4400A1/3 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1366 |  | 1366 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/305 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 342 |  | 342 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/309 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 841 |  | 841 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/312 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.3075 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-09-01 | 2023-09-29 | Complete |  | 21dys | NB | 291 | 291 | 0 | 1 |  | N |  | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 392 |  | 392 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 275 |  | 275 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 391 |  | 391 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/327 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 92 |  | 92 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 230 |  | 230 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 316 |  | 316 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 315 |  | 315 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 270 |  | 270 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 69 |  | 69 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 769 |  | 769 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 283 |  | 283 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 324 |  | 324 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/361 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 137 |  | 137 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 157 |  | 157 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 782 |  | 782 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 299 |  | 299 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/375 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5048 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 140 |  | 140 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/383 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 421 |  | 421 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/613 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 209 |  | 209 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/618 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 769 |  | 769 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/621 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 169 |  | 169 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/623 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 387 |  | 387 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/628 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 74 |  | 74 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/630 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 182 |  | 182 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/631 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 45 |  | 45 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/633 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 342 |  | 342 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/635 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 169 |  | 169 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/638 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 234 |  | 234 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/640 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 124 |  | 124 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/643 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 279 |  | 279 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/646 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 131 |  | 131 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/647 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 323 |  | 323 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/648 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 385 |  | 385 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/651 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 268 |  | 268 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/654 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 169 |  | 169 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/656 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 128 |  | 128 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/658 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 83 |  | 83 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/660 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 342 |  | 342 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/662 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 513 |  | 513 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 385 |  | 385 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 266 |  | 266 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/671 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 194 |  | 194 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/675 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 406 |  | 406 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/678 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 612 |  | 612 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/684 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 121 |  | 121 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/687 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5049 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 77 |  | 77 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/694 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 685.29 |  | 685.29 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4400A1/2 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1350.44 |  | 1350.44 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/315 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 2028.12 |  | 2028.12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/319 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 638.57 |  | 638.57 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/331 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1700.01 |  | 1700.01 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/334 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1790.99 |  | 1790.99 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/338 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1734.21 |  | 1734.21 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/342 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1317.58 |  | 1317.58 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/350 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 101.32 |  | 101.32 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/352 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 4579.61 |  | 4579.61 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/354 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1331.7 |  | 1331.7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/364 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1464.06 |  | 1464.06 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/369 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 3912.87 |  | 3912.87 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/372 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE110 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5050 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 276.67 |  | 276.67 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/383 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5051 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 90.8 |  | 90.8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5052 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 386.46 |  | 386.46 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5053 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 807.68 |  | 807.68 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5053 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 159.48 |  | 159.48 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB NS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5052 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 500.13 |  | 500.13 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5053 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 114.73 |  | 114.73 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB OS Bettamix 45170 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5054 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 679.09 |  | 679.09 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5055 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5055 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 6 |  | 6 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 5056 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 40 |  | 40 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually for ILM Sections Within the Route
YNE113 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 5057 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Annually for ILM Sections Within the Route
YNE113 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5055 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 21 |  | 21 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5058 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 10 |  | 10 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5059 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5060 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 NB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5059 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Gullies - Emptying / clear covers | 5055 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB OS Enviroflow 45170 Gullies - Emptying / clear covers | 5058 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 11 |  | 11 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5061 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5061 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE113 Closure 1 SB OS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5062 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/436 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM Every 2 years
YNE113 Closure 1 NB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5063 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | NB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE113 Closure 1 SB NS Enviroflow 45170 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 5061 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys | SB | 0 |  | 0 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM Every 2 years
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5064 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5065 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5066 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB OS CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 5067 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 2 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N/A |  |  | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure CGS 45170 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 5068 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1041 |  | 1041 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed |  | YNE113: A1 Darrington - A162 | YNE113 Closure | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 2 CW NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5070 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 7 |  | 7 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/425 | YNE113: A1 Darrington - A162 | YNE113 Closure 2 CW NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 12 |  | 12 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 8 |  | 8 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/433 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 2 |  | 2 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/436 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5071 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 20 |  | 20 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5071 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 3 |  | 3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5071 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 11 |  | 11 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 5069 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5072 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 4 |  | 4 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 5073 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 5 |  | 5 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5074 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 5075 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 2 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 1 |  | 1 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5076 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 77.59 |  | 77.59 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5076 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 628.32 |  | 628.32 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5077 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 418.82 |  | 418.82 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45170 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 5076 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 2-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 9.62 |  | 9.62 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 194 |  | 194 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/423 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 2 CW NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5079 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 86 |  | 86 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/425 | YNE113: A1 Darrington - A162 | YNE113 Closure 2 CW NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 704 |  | 704 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/428 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 535 |  | 535 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/430 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 58 |  | 58 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/433 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 374 |  | 374 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/436 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5080 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 802 |  | 802 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 1480 |  | 1480 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/850 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5080 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 210 |  | 210 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/851 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5080 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 982 |  | 982 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 SB NS CGS 45170 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 744 |  | 744 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB NS | Lane 1 Closure | 3 |  |  | Annually (Apr - Sep)
YNE113 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5081 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 2299.3 |  | 2299.3 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/585 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 NB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5081 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 732.27 |  | 732.27 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1/853 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 NB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
YNE113 Closure 1 SB OS CGS 45170 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5082 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-09-01 | 2023-09-29 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 3524.45 |  | 3524.45 | 0 |  | Y | Access denied due to Wentbridge scheme - access not available in year therefore these works will not be completed | 4700A1M/450 | YNE113: A1 Darrington - A162 | YNE113 Closure 1 SB OS | Lane 2 Closure | 3 |  |  | ILM 2 times per year (Apr - Sept)
N/A Amey 45170 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5083 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
N/A Amey 45170 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5084 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 21dys |  | 5 |  | 5 | 0 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
N/A Amey 45170 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5085 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2452.072 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-09-01 | 2023-09-29 | 2024-01-31 |  | 20dys |  | 138 | 93 | 45 | 0.67391 |  | N |  |  | DBFO 27 - technology assets only | N/A | N/A | N/A |  |  | Annually |  |  | On ServiceNow
YNE1 Closure 3 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5086 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 68.6209 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 210.48 | 400 | -189.52 | 1.9004 |  |  |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032145
YNE1 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5087 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 69.4323 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 899.4 | 899.4 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034402
YNE1 Closure 2 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5088 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 45.93 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 594.96 | 594.96 | 0 | 1 |  |  |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034402
YNE1 Closure 3 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5089 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 77.2996 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1001.31 | 1001.31 | 0 | 1 |  |  |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034402
YNE1 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5090 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 49.2001 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 637.32 | 637.32 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 52034402
YNE1 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5091 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 58.3356 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 649 | 649 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 & 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5091 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 69.8625 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 777.24 | 777.24 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 & 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5092 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 232.6844 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2588.68 | 2588.68 | 0 | 1 |  |  |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 3 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5092 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 322.7351 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 3590.52 | 3590.52 | 0 | 1 |  |  |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5093 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 140.4153 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1562.16 | 1562.16 | 0 | 1 |  |  |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5094 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 212.3847 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2362.84 | 2362.84 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5094 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 652.1091 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 7254.9 | 7254.9 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE1 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5094 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 202.7112 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2255.22 | 2255.22 | 0 | 1 | 18/9: cancelled heavy rain | N | 2 shifts cancelled then roadspace clash | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892453
YNE2 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5095 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 10.8644 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 63.33 | 63.33 | 0 | 1 |  |  |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52031821
YNE2 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5096 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 132.5962 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 1475.17 | 1475.17 | 0 | 1 |  |  |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892457
YNE2 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5096 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 9.2159 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 102.53 | 102.53 | 0 | 1 |  |  |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892457
YNE2 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5096 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 28.4307 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 316.3 | 316.3 | 0 | 1 |  |  |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892457
YNE2 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5096 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 245.1982 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 2727.9 | 2727.9 | 0 | 1 |  |  |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892457
YNE2 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5096 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 43.6483 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 485.6 | 485.6 | 0 | 1 |  |  |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45892457
YNE3 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5097 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-12-31 |  | 44dys | WB | 201.09 |  | 201.09 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS Enviroflow 45201 LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 5098 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 0 | 4.3.2.2 | A40008 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-12-31 |  | 44dys |  | 57.2 |  | 57.2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | Every 2 years | 100/4 | 95/9 | 45902936 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5099 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 323.8703 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 3603.15 | 3603.15 | 0 | 1 |  | Y | Clash Terry Barraclough | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 95/5 | 101/1 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5100 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 277.9039 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 3091.76 | 3091.76 | 0 | 1 |  | Y | Clash Terry Barraclough | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5100 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 70.933 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 789.15 | 789.15 | 0 | 1 |  | Y | Clash Terry Barraclough | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5101 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 56.9334 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 633.4 | 633.4 | 0 | 1 |  | Y | Clash Terry Barraclough | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5101 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 28.9215 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 321.76 | 321.76 | 0 | 1 |  | Y | Clash Terry Barraclough | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5102 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 522.13 |  | 522.13 | 0 |  | Y | Clash Terry Barraclough | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5102 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-10-02 | 2023-11-30 | N/A | Unable to complete within ADAMr timescales due to access | 44dys | WB | 3590.83 |  | 3590.83 | 0 |  | Y | Clash Terry Barraclough | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5103 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 23.9504 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | NB | 139.61 | 139.61 | 0 | 1 |  | N |  | 4700M606/5 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45909916
YNE4 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5103 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 62.445 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 364 | 364 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45909916
YNE4 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5103 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 41.3115 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 240.81 | 240.81 | 0 | 1 |  | N |  | 4700M62/612 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45909916
YNE4 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5103 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 109.1226 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 636.09 | 636.09 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years |  |  | 45909916
YNE4 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5104 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 62.0435 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 361.66 | 361.66 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years
YNE4 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5104 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 36.8717 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 214.93 | 214.93 | 0 | 1 |  | N |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years
YNE4 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5104 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 8.8349 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 51.5 | 51.5 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years
YNE4 Closure 1 WB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5104 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 48.9867 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 285.55 | 285.55 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45201 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 5105 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 90.1678 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 73 | 73 | 0 | 1 | No assets - job suspended | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | Every 2 years |  |  | 52032308
YNE4 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5106 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 28.5634 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 370 | 370 | 0 | 1 | 23/10 complete check jobs closed | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5106 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 24.7035 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 320 | 320 | 0 | 1 | 23/10 complete check jobs closed | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5106 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 31.2654 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 405 | 405 | 0 | 1 | 23/10 complete check jobs closed | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 EB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5106 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 14.6677 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | 2023-10-31 |  | 44dys | EB | 190 | 190 | 0 | 1 | 23/10 complete check jobs closed | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5107 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 3.8599 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 50 | 50 | 0 | 1 |  | N | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5107 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 18.6048 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 241 | 241 | 0 | 1 |  | N | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/925 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5107 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 29.7214 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 385 | 385 | 0 | 1 |  | N | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5107 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2.7019 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 35 | 35 | 0 | 1 |  | N | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 WB OS Amey 45201 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5107 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 35.5113 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | WB | 460 | 460 | 0 | 1 |  | N | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  | Nights | 3 times per year (ILM Entire Route) |  |  | 45877348
YNE4 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5108 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 38.2022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 425.01 | 425.01 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE4 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5108 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 73.3303 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 815.82 | 815.82 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE4 Closure 1 EB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5108 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 40.3181 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | EB | 448.55 | 448.55 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE4 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5109 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 81.0496 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 901.7 | 901.7 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE4 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5109 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 65.3493 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 727.03 | 727.03 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE4 Closure 1 WB OS CGS 45201 Grass & Vegetation - Grass cut the central reserve 2 - ILM | 5109 | Grass & Vegetation - Grass cut the central reserve 2 - ILM | 83.117 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-10-02 | 2023-11-30 | Complete |  | 44dys | WB | 924.7 | 924.7 | 0 | 1 |  | Y | Clash with Frank Firth Scheme - shares but restricted access | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 4 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45901769
YNE5 Closure 1 EB OS Bettamix 45201 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5110 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-10-02 | 2023-11-30 | 2023-11-30 | Subject to access via scheme shares | 44dys | EB | 471.43 |  | 471.43 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 4 |  | Nights | Every 2 years | 104/3 | 108/6 | 45915919 | 20:00 | 6:00 | Night Shift | Approved | 0